## 2211
خلاصه مالی صورتحساب خرید انواع کابل | [8 empty] | شماره پیش فاکتورها: 123409 و 213410
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ پیش فاکتور: 1401/05/19
فروشنده: شرکت توان الکترو سدید | [8 empty] | تاریخ تهیه گزارش: 1401/07/16
ردیف | کد کالا | شرح کالا (مطابق با پیش فاکتور) | واحد | مقدار | بهای واحد | مبلغ پیش فاکتور | مقدار رسید (MRS-SLD-9000-068) | درصد کالای دریافتی | مبلغ کالای دریافتی
1 | 6843333513 | کابل مس زره دار 70+150*3 N2XRY (کابل یزد) | متر | 233 | 21340000 | 4972220000 | 233 | 100% | 4972220000
2 | 6843333514 | کابل مس زره دار 95+185*3 N2XRY (کابل یزد) | متر | 18 | 27860000 | 501480000 | 25 | 138.9% | 696500000
3 | 6843330302 | کابل مس زره دار 2.5*3 N2XRY (کابل مغان) | متر | 1470 | 515000 | 757050000 | 1435 | 97.62% | 739025000
4 | 6843333508 | کابل مس زره دار 16+35*3 N2XRY (کابل مغان) | متر | 93 | 4700000 | 437100000 | 93 | 100% | 437100000
5 | 6843333510 | کابل مس زره دار 35+70*3 N2XRY-O (کابل یزد) | متر | 25 | 9837000 | 245925000 | 25 | 100% | 245925000
6 | 6843333511 | کابل مس زره دار 50+95*3 N2XRY (کابل یزد) | متر | 46 | 13356000 | 614376000 | 46 | 100% | 614376000
7 | 6843330405 | کابل مس 10*4 N2XRY (کابل مغان) | متر | 80 | 1930000 | 154400000 | 80 | 100% | 154400000
8 | 6843330402 | کابل مس 2.5*4 N2XY (کابل مغان) | متر | 250 | 446000 | 111500000 | 250 | 100% | 111500000
9 | 6843330403 | کابل مس 4*4 N2XY-J (کابل مغان) | متر | 20 | 688000 | 13760000 | 20 | 100% | 13760000
10 | 6843330404 | کابل مس 6*4 N2XY (کابل مغان) | متر | 50 | 1007000 | 50350000 | 50 | 100% | 50350000
11 | 6843330506 | کابل مس 16*5 N2XY-J (کابل مغان) | متر | 75 | 3120000 | 234000000 | 75 | 100% | 234000000
12 | 6843330502 | کابل مس 2.5*5 N2XY-J (کابل مغان) | متر | 45 | 554000 | 24930000 | 45 | 100% | 24930000
13 | 6843330507 | کابل مس 25*5 N2XY-J (کابل مغان) | متر | 85 | 5435000 | 461975000 | 85 | 100% | 461975000
14 | 6843330503 | کابل مس 4*5 N2XY-J (کابل مغان) | متر | 20 | 865000 | 17300000 | 20 | 100% | 17300000
15 | 6843330504 | کابل مس 6*5 N2XY-J (کابل مغان) | متر | 20 | 1264000 | 25280000 | 20 | 100% | 25280000
16 | 6843020106 | سیم افشان ارت نمره 16 (کابل یزد) | متر | 80 | 489000 | 39120000 | 80 | 100% | 39120000
17 | 6843020108 | سیم افشان ارت نمره 35*1 (کابل یزد) | متر | 25 | 1053500 | 26337500 | 25 | 100% | 26337500
18 | 6843020109 | سیم افشان ارت نمره 50 (کابل یزد) | متر | 50 | 1492000 | 74600000 | 50 | 100% | 74600000
19 | 6843020110 | سیم ارت نیمه افشان 70*1 (کابل یزد) | متر | 180 | 2251000 | 405180000 | 193 | 107.2% | 434443000
20 | 6843310302 | کابل مس 2.5*3 N2XY (کابل یزد) | متر | 1287 | 353800 | 455340600 | 1287 | 100% | 455340600
21 | 6843310302 | کابل مس 2.5*3 N2XY (کابل مغان) | متر | 658 | 353800 | 232800400 | 658 | 100% | 232800400
22 | 6843675034 | کابل افشان شیلد دار 1.5*3 سیمکان | متر | 600 | 251000 | 150600000 | 600 | 100% | 150600000
23 | 6843675033 | کابل افشان شیلد دار 1*3 سیمکان | متر | 150 | 198000 | 29700000 | 150 | 100% | 29700000
[6 empty] | 10035324500 |  |  | 10241582500
خلاصه محاسبات پرداخت صورت حساب: | [6 empty] | توضیحات:
ناخالص صورتحساب | [5 empty] | 10241582500 | میزان تلرانس ریالی کل در حدود 2 درصد مثبت و میزان تلرانس مقداری کل در حدود 2/7 درصد منفی می باشد.
مالیات و عوارض بر ارزش افزوده 9% | [5 empty] | 921742425
جمع مبلغ قابل پرداخت | [5 empty] | 11163324925
کسور:
پیش پرداخت (40%) | [5 empty] | 4015000000
جمع کسور | [5 empty] | 4015000000
خالص قابل پرداخت | [5 empty] | 7148324925

## Packing List Items
[16 empty] | 5545 |  |  |  |  | 5545
# | Opi No. | Date | Project Name | Packing List No. | Purchase Order | Vendor | Purchaser | Consignee | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843333513 | 0.6/1KV, N2XRY - 3.5C-150mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 107 |  |  |  |  | 107 | Meter |  |  | 3*150+70
2 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843333513 | 0.6/1KV, N2XRY - 3.5C-150mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 126 |  |  |  |  | 126 | Meter |  |  | 3*150+70
3 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843333514 | 0.6/1KV, N2XRY - 3.5C-185mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 25 |  |  |  |  | 25 | Meter |  |  | 3*185+95
4 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330302 | 0.6/1KV, N2XRY - 3C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 1021 |  |  |  |  | 1021 | Meter
5 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330302 | 0.6/1KV, N2XRY - 3C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 414 |  |  |  |  | 414 | Meter
6 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843333508 | 0.6/1KV CABLE, N2XRY - 3.5C-35mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 93 |  |  |  |  | 93 | Meter |  |  | 3*35+16
7 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843333510 | 0.6/1KV, N2XYRY - 3.5C-70mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 25 |  |  |  |  | 25 | Meter |  |  | 3*70+35
8 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843333511 | 0.6/1KV CABLE, N2XRY - 3.5C-95mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 46 |  |  |  |  | 46 | Meter |  |  | 3*95+50
9 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330405 | 0.6/1KV, N2XYRY - 4C-10mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 80 |  |  |  |  | 80 | Meter
10 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330402 | 0.6/1KV CABLE, N2XRY - 4C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 250 |  |  |  |  | 250 | Meter
11 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330403 | 0.6/1KV, N2XRY - 4C-4mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 20 |  |  |  |  | 20 | Meter
12 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330404 | 0.6/1KV, N2XRY - 4C-6mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 50 |  |  |  |  | 50 | Meter
13 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330506 | 0.6/1KV, N2XRY - 5C-16mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 75 |  |  |  |  | 75 | Meter
14 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330502 | 0.6/1KV, N2XRY - 5C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 45 |  |  |  |  | 45 | Meter
15 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330507 | 0.6/1KV, N2XRY - 5C-25mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 85 |  |  |  |  | 85 | Meter
16 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330503 | 0.6/1KV, N2XRY - 5C-4mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 20 |  |  |  |  | 20 | Meter
17 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843330504 | 0.6/1KV CABLE, N2XRY - 5C-6mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 20 |  |  |  |  | 20 | Meter
18 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843020106 | CU/PVC NY - 1C-16mm2 Earthing wire, Stranded copper (Class 2 of IEC 60228), PVC Insulation, Yellow/Green Color | 80 |  |  |  |  | 80 | Meter
19 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843020108 | CU/PVC NY - 1C-35mm2 Earthing wire, Stranded copper (Class 2 of IEC 60228), PVC Insulation, Yellow/Green Color | 25 |  |  |  |  | 25 | Meter
20 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843020109 | 0.6/1KV CABLE, NY - 1C-50mm2 PVC Insulation, Yellow/Green color outer sheath | 50 |  |  |  |  | 50 | Meter
21 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843020110 | CU/PVC NY - 1C-70mm2 Earthing wire, Stranded copper (Class 2 of IEC 60228), PVC Insulation, Yellow/Green Color | 193 |  |  |  |  | 193 | Meter
22 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843310302 | 0.6/1KV, N2XY - 3C-2.5mm2 XLPE Insulation, BLACK color outer sheath | 1287 |  |  |  |  | 1287 | Meter
23 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843310302 | 0.6/1KV, N2XY - 3C-2.5mm2 XLPE Insulation, BLACK color outer sheath | 658 |  |  |  |  | 658 | Meter
24 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843675034 | CU/ PVC/CUB/PVC(H05VC4V-F) / 3*1.5 | 600 |  |  |  |  | 600 | Meter
25 | OPI-SLD-9000-069 | 2022-09-19 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-067 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 67 |  | Main Item | - | 6843675033 | CU/ PVC/CUB/PVC(H05VC4V-F) / 3*1 | 150 |  |  |  |  | 150 | Meter