## Packing List Items
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-501-001 | Fire Water Hydrant For CDU | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
2 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-501-001 | Fire Water Hydrant For CDU | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
3 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-501-002 | Fire Water Hydrant For CDU | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
4 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-501-003 | Fire Water Hydrant For CDU | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
5 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-501-004 | Fire Water Hydrant For CDU | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
6 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-501-007 | Fire Water Hydrant For CDU | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
7 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-502-001 | Fire Water Hydrant For NHT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
8 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-502-002 | Fire Water Hydrant For NHT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
9 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-502-003 | Fire Water Hydrant For NHT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
10 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-502-004 | Fire Water Hydrant For NHT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
11 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-502-005 | Fire Water Hydrant For NHT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
12 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-502-006 | Fire Water Hydrant For NHT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
13 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-505-003 | Fire Water Hydrant For LPG/LPT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
14 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-505-004 | Fire Water Hydrant For LPG/LPT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
15 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-505-005 | Fire Water Hydrant For LPG/LPT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
16 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-505-006 | Fire Water Hydrant For LPG/LPT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
17 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-505-007 | Fire Water Hydrant For LPG/LPT | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
18 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-509-001 | Fire Water Hydrant For AMN/SWS | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
19 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-509-002 | Fire Water Hydrant For AMN/SWS | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
20 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-509-003 | Fire Water Hydrant For AMN/SWS | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
21 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-509-004 | Fire Water Hydrant For AMN/SWS | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
22 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-509-005 | Fire Water Hydrant For AMN/SWS | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
23 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-516-001 | Fire Water Hydrant For MDH | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
24 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-516-002 | Fire Water Hydrant For MDH | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
25 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-516-003 | Fire Water Hydrant For MDH | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
26 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-520-001 | Fire Water Hydrant For TNK | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
27 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-530-002 | Fire Water Hydrant For TNK | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
28 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-001 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
29 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-002 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
30 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-003 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
31 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-004 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
32 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-005 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
33 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-006 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
34 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-007 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
35 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-008 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
36 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-009 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
37 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-011 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
38 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-012 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
39 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-013 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
40 | OPI-SIS-044-001 | 2022-03-01 | SACR-PL-SIS-044-001 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 1 |  | Main Item | - | FH-545-017 | Fire Water Hydrant For Utility/Offsite | 1 |  |  |  |  | 1 | Piece |  |  |  | 194
41 | OPI-SIS-044-002 | 2022-03-01 | SACR-PL-SIS-044-002 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 2 |  | Main Item | - | Foam-AFFF-3% | Foam 3% AFFF | 16600 |  |  |  |  | 16600 | Liter |  |  |  | 194
42 | OPI-SIS-044-002 | 2022-03-01 | SACR-PL-SIS-044-002 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 2 |  | Main Item | - | Foam-AFFF-3% | Foam 3% AFFF | 100 |  |  |  |  | 100 | Liter |  |  |  | 194
43 | OPI-SIS-044-002 | 2022-03-01 | SACR-PL-SIS-044-002 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 2 |  | Main Item | - | Foam-AFFF-3% | Foam 3% AFFF | 40 |  |  |  |  | 40 | Liter |  |  |  | 194
44 | OPI-SIS-044-002 | 2022-03-01 | SACR-PL-SIS-044-002 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 2 |  | Main Item | - | Foam-AFFF-3% | Foam 3% AFFF | 20 |  |  |  |  | 20 | Liter |  |  |  | 194
45 | OPI-SIS-044-002 | 2022-03-01 | SACR-PL-SIS-044-002 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 2 |  | Main Item | - | Foam-AFFF-3% | Foam 3% AFFF | 20 |  |  |  |  | 20 | Liter |  |  |  | 194
46 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-501-001 | Foam Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100
47 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-501-002 | Foam Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100
48 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-501-003 | Foam Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100
49 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-501-004 | Foam Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100
50 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-501-005 | Foam Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100
51 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-502-001 | Foam Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100
52 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-502-002 | Foam Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100
53 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-502-003 | Foam Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100
54 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-502-004 | Foam Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100
55 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-516-001 | Foam Hose Box For MDH | 1 |  |  |  |  | 1 | Piece | 100
56 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-516-002 | Foam Hose Box For MDH | 1 |  |  |  |  | 1 | Piece | 100
57 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-516-003 | Foam Hose Box For MDH | 1 |  |  |  |  | 1 | Piece | 100
58 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-516-004 | Foam Hose Box For MDH | 1 |  |  |  |  | 1 | Piece | 100
59 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-001 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
60 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-002 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
61 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-003 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
62 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-004 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
63 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-005 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
64 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-006 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
65 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-007 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
66 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-008 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
67 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-009 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
68 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-545-001 | Foam Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100
69 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-010 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
70 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-011 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
71 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-012 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
72 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-013 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
73 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-014 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
74 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-015 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
75 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-016 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
76 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-017 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
77 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-018 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
78 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-019 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
79 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-020 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
80 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-021 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
81 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-022 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
82 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-023 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
83 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-025 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
84 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-027 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
85 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-028 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
86 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-029 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
87 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-030 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
88 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-031 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
89 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-032 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
90 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-001 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100
91 | OPI-SIS-044-003 | 2022-10-12 | SACR-PL-SIS-044-003 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 3 |  | Main Item | - | FHB-520-002 | Foam Hose Box For TNK | 1 |  |  |  |  | 1 | Piece
92 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-501-001 | Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
93 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-501-002 | Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
94 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-501-003 | Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
95 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-501-004 | Hose Box For CDU | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
96 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-001 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  | فاقدNAME PLATE | 194
97 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-001 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
98 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-002 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
99 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-003 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
100 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-004 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
101 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-005 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
102 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-006 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
103 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-505-007 | Hose Box For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
104 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-502-001 | Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
105 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-502-002 | Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
106 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-502-003 | Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
107 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-502-004 | Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
108 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-502-005 | Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
109 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-502-006 | Hose Box For NHT | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
110 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-516-001 | Hose Box For MDH | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
111 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-516-002 | Hose Box For MDH | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
112 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-516-003 | Hose Box For MDH | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
113 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-509-001 | Hose Box For AMN/SWS | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
114 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-509-002 | Hose Box For AMN/SWS | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
115 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-509-003 | Hose Box For AMN/SWS | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
116 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-509-004 | Hose Box For AMN/SWS | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
117 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-509-005 | Hose Box For AMN/SWS | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
118 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-509-006 | Hose Box For AMN/SWS | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
119 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-520-001 | Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
120 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-530-001 | Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
121 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-530-002 | Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
122 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-530-003 | Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
123 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-530-004 | Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
124 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-530-005 | Hose Box For TNK | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
125 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-001 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
126 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-002 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
127 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-003 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
128 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-004 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
129 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-005 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
130 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-006 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
131 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-007 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
132 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-008 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
133 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-009 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
134 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-011 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
135 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-012 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
136 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-013 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
137 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-017 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  |  | 194
138 | OPI-SIS-044-004 | 2022-10-12 | SACR-PL-SIS-044-004 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 4 |  | Main Item | - | HB-545-011 | Hose Box For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 100 |  | فاقدNAME PLATE | 194
139 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | MONITOR | Foam Monitor 2000 lpm Model VAJRA - 331, 80 NB Cast Bronze Waterway, Bronze Swivel Joint, Lever Operated (Catalogue No. HD210) With Brass Drain valve for Inlet connection: 4" Flanged as per ANSI B16.5 #150 RF) | 8 |  |  |  |  | 8 | Set | 380
140 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | NOZZLE | Hydro foam Nozzle for Monitor Model VARSHA-HF40U, Bronze, jet & fog, 3 inch BSP, | 8 |  |  |  |  | 8 | Set | 12
141 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | MONITOR | Foam Monitor 2000 lpm Model VAJRA - 331, 80 NB Cast Bronze Waterway, Bronze Swivel Joint, Lever Operated (Catalogue No. HD210) With Brass Drain valve for Inlet connection: 4" Flanged as per ANSI B16.5 #150 RF) | 8 |  |  |  |  | 8 | Set | 380
142 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | NOZZLE | Hydro foam Nozzle for Monitor Model VARSHA-HF40U, Bronze, jet & fog, 3 inch BSP, | 8 |  |  |  |  | 8 | Set | 12
143 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | MONITOR | Foam Monitor 2000 lpm Model VAJRA - 331, 80 NB Cast Bronze Waterway, Bronze Swivel Joint, Lever Operated (Catalogue No. HD210) With Brass Drain valve for Inlet connection: 4" Flanged as per ANSI B16.5 #150 RF) | 8 |  |  |  |  | 8 | Set | 380
144 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | NOZZLE | Hydro foam Nozzle for Monitor Model VARSHA-HF40U, Bronze, jet & fog, 3 inch BSP, | 8 |  |  |  |  | 8 | Set | 12
145 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | MONITOR | Foam Monitor 2000 lpm Model VAJRA - 331, 80 NB Cast Bronze Waterway, Bronze Swivel Joint, Lever Operated (Catalogue No. HD210) With Brass Drain valve for Inlet connection: 4" Flanged as per ANSI B16.5 #150 RF) | 8 |  |  |  |  | 8 | Set | 380
146 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | NOZZLE | Hydro foam Nozzle for Monitor Model VARSHA-HF40U, Bronze, jet & fog, 3 inch BSP, | 8 |  |  |  |  | 8 | Set | 12
147 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | MONITOR | Water Monitor 2000 lpm Model VAJRA - 331, 80 NB Cast Bronze Waterway, Bronze Swivel Joint, Lever Operated (Catalogue No. HD210) With Brass Drain valve for Inlet connection: 4" Flanged as per ANSI B16.5 #150 RF) | 8 |  |  |  |  | 8 | Set | 300
148 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | NOZZLE | Water Nozzle for Monitor Model VARSHA-40U, Bronze with SS internals , jet & fog 3inch BSP | 8 |  |  |  |  | 8 | Set | 44
149 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | MONITOR | Water Monitor 2000 lpm Model VAJRA - 331, 80 NB Cast Bronze Waterway, Bronze Swivel Joint, Lever Operated (Catalogue No. HD210) With Brass Drain valve for Inlet connection: 4" Flanged as per ANSI B16.5 #150 RF) | 3 |  |  |  |  | 3 | Set | 120
150 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Water Nozzle for Monitor Model VARSHA-40U, Bronze with SS internals , jet & fog 3inch BSP | 3 |  |  |  |  | 3 | Set | 9
151 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
152 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
153 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
154 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
155 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
156 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
157 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
158 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
159 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
160 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
161 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
162 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
163 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
164 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
165 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
166 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
167 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
168 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
169 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Foam Monitor 4000 lpm Model VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement with Hydro-foam Nozzle Model H4 -1000 GPM (3785 LPM @ 7 Bar) Inlet connection: 4" Flanged ASME B16. | 2 |  |  |  |  | 2 | Set | 144
170 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSHA | Water Monitor 4000 lpm VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement. UL LISTED with Water Nozzle H4 Flow 1000 GPM Inlet connection: 4" Flanged ASME B16.5 #150 RF | 2 |  |  |  |  | 2 | Set | 72
171 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | VARSH | Water Monitor 4000 lpm VARUN 443, 100NB size Monitor with Stainless Steel 304 waterway, hand wheel gear operated for vertical and horizontal movement. UL LISTED with Water Nozzle H4 Flow 1000 GPM Inlet connection: 4" Flanged ASME B16.5 #150 RF | 2 |  |  |  |  | 2 | Set | 140
172 | OPI-SIS-044-005 | 2022-10-12 | SACR-PL-SIS-044-005 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 5 |  | Sub Item | FH-509-001 | HAND WHEEL | Wheel for Monitor Model VARUN 443 (Commissioning Spare Part) | 1 |  |  |  |  | 1 | Set | 10
173 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-501-001 | Hydrant with Foam Monitor For CDU | 1 |  |  |  |  | 1 | Piece | 45
174 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-501-002 | Hydrant with Foam Monitor For CDU | 1 |  |  |  |  | 1 | Piece | 45
175 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-501-003 | Hydrant with Foam Monitor For CDU | 1 |  |  |  |  | 1 | Piece | 45
176 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-501-004 | Hydrant with Foam Monitor For CDU | 1 |  |  |  |  | 1 | Piece | 45
177 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-501-005 | Hydrant with Foam Monitor For CDU | 1 |  |  |  |  | 1 | Piece | 45
178 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-502-001 | Hydrant with Foam Monitor For NHT | 1 |  |  |  |  | 1 | Piece | 45
179 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-502-002 | Hydrant with Foam Monitor For NHT | 1 |  |  |  |  | 1 | Piece | 45
180 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-502-003 | Hydrant with Foam Monitor For NHT | 1 |  |  |  |  | 1 | Piece | 45
181 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-502-004 | Hydrant with Foam Monitor For NHT | 1 |  |  |  |  | 1 | Piece | 45
182 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-516-001 | Hydrant with Foam Monitor For MDH | 1 |  |  |  |  | 1 | Piece | 45
183 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-516-002 | Hydrant with Foam Monitor For MDH | 1 |  |  |  |  | 1 | Piece | 45
184 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-516-003 | Hydrant with Foam Monitor For MDH | 1 |  |  |  |  | 1 | Piece | 45
185 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-516-004 | Hydrant with Foam Monitor For MDH | 1 |  |  |  |  | 1 | Piece | 45
186 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-545-001 | Hydrant with Foam Monitor For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 45
187 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-001 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
188 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-002 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
189 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-003 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
190 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-004 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
191 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-005 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
192 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-006 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
193 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-007 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
194 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-008 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
195 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-009 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45 |  | رنگ پریدگی
196 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-010 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
197 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-011 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
198 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-012 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
199 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-013 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
200 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-014 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
201 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-015 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
202 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-016 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
203 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-017 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
204 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-018 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
205 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-019 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
206 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-020 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
207 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-021 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45 |  | رنگ پریدگی
208 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-022 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
209 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-023 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
210 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-025 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
211 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-027 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
212 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-028 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
213 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-029 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
214 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-030 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
215 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-031 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
216 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-520-032 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
217 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-530-001 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
218 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-530-006 | Hydrant with Foam Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
219 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-505-001 | Hydrant with Water Monitor For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 45
220 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-505-002 | Hydrant with Water Monitor For LPG/LPT | 1 |  |  |  |  | 1 | Piece | 45
221 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-509-001 | Hydrant with Water Monitor For Utility/Offsite | 1 |  |  |  |  | 1 | Piece | 45
222 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-530-002 | Hydrant with Water Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
223 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-530-003 | Hydrant with Water Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
224 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-530-004 | Hydrant with Water Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
225 | OPI-SIS-044-006 | 2022-10-12 | SACR-PL-SIS-044-007 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 7 |  | Main Item | - | FHM-530-005 | Hydrant with Water Monitor For TNK | 1 |  |  |  |  | 1 | Piece | 45
226 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B44-001 | 2458 | Indoor Hose Reel for Multi Porpuse Building,Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With Al | 1 |  |  |  |  | 1 | Set | 60
227 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B44-002 | 2458 | Indoor Hose Reel for Multi Porpuse Building, Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With A | 1 |  |  |  |  | 1 | Set | 60
228 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B44-003 | 2458 | Indoor Hose Reel for Multi Porpuse Building, Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With A | 1 |  |  |  |  | 1 | Set | 60
229 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B44-004 | 2458 | Indoor Hose Reel for Multi Porpuse Building,Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With Al | 1 |  |  |  |  | 1 | Set | 60
230 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B44-005 | 2458 | Indoor Hose Reel for Multi Porpuse Building, Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With A | 1 |  |  |  |  | 1 | Set | 60
231 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B27-001 | 2458 | Indoor Hose Reel for fire Station Building, Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With Al | 1 |  |  |  |  | 1 | Set | 60
232 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B42-001 | 2458 | Indoor Hose Reel for Warehouse Building, Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With Alumi | 1 |  |  |  |  | 1 | Set | 60
233 | OPI-SIS-044-007 | 2023-02-15 | SACR-PL-SIS-044-008 | ADISH-P-PO-GE-044 | SISICO | DDP Site | 8 |  | Sub Item | IHR-B42-002 | 2458 | Indoor Hose Reel for Warehouse Building, Cabinet Assembly THK1.5.M, 1 NOLatch Type Without Key Zamak, 2 NOHinge ZamaK, 6 NO Lug Plate C.S, 1NO 1.1/2" GlobeValve Angle Type Regulator Type Brass, 1 NOFire House 1"*25M Rigid Non Collapsible Rubber With Alumi | 1 |  |  |  |  | 1 | Set | 60