## خرید قراردادی و فاکتوری
خلاصه مالی خرید لوله و اتصالات طی پیش فاکتور | [8 empty] | شماره پیش فاکتور:SH-01-802
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ پیش فاکتور: 1400/04/18
فروشنده: شرکت بهبود ره پویان آریا گستر | [8 empty] | تاریخ تهیه گزارش: 1401/06/01
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (ریال) | مبلغ پیش فاکتور (ریال) | مقدار رسید شده | درصد کالای ارسالی | مبلغ کل (ریال) | فاکتور
1 | 7662811219 | A-105 N, 14, 150, WN, RF, XS, -, ASME B.16.5 | عدد | 1 | 130900000 | 130900000 | 1 | 100% | 130900000 | 36 | 35 | 4712400000
2 | 7662811705 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 160,0.75" | عدد | 4 | 5390000 | 21560000 | 4 | 100% | 21560000 | 4 | 0 | 21560000
3 | 7662710006 | Flange,A-105,Rating 150,Type SO,ASME B.16.5,Sch -,1" | عدد | 22 | 4389000 | 96558000 | 22 | 100% | 96558000 | 112 | 90 | 491568000
4 | 7662110006 | Flange,A-105,Rating 150,Type BL,ASME B.16.5,Sch -,1" | عدد | 6 | 4620000 | 27720000 | 6 | 100% | 27720000 | 30 | 24 | 138600000
5 | 7662831706 | Flange,A-105,Rating 300,Type WN,ASME B.16.5,Sch 160,1" | عدد | 2 | 8470000 | 16940000 | 2 | 100% | 16940000 | 54 | 52 | 457380000
6 | 7662811708 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 160,1.5" | عدد | 3 | 10010000 | 30030000 | 3 | 100% | 30030000 | 14 | 11 | 140140000
7 | 7662710008 | Flange,A-105,Rating 150,Type SO,ASME B.16.5,Sch -,1.5" | عدد | 34 | 4312000 | 146608000 | 34 | 100% | 146608000 | 10 | -24 | 43120000
8 | 7662110008 | Flange,A-105,Rating 150,Type BL,ASME B.16.5,Sch -,1.5" | عدد | 4 | 15400000 | 61600000 | 4 | 100% | 61600000 | 6 | 2 | 92400000
9 | 7662831709 | Flange,A-105,Rating 300,Type WN,ASME B.16.5,Sch 160,2" | عدد | 3 | 18480000 | 55440000 | 3 | 100% | 55440000 | 12 | 9 | 221760000
10 | 7662831309 | Flange,A-105,Rating 300,Type WN,ASME B.16.5,Sch 80,2" | عدد | 5 | 15400000 | 77000000 | 5 | 100% | 77000000
11 | 7662710009 | Flange,A-105,Rating 150,Type SO,ASME B.16.5,Sch -,2" | عدد | 371 | 4928000 | 1828288000 | 371 | 100% | 1828288000
12 | 7662110009 | Flange,A-105,Rating 150,Type BL,ASME B.16.5,Sch -,2" | عدد | 32 | 6930000 | 221760000 | 32 | 100% | 221760000
13 | 7662710010 | Flange,A-105,Rating 150,Type SO,ASME B.16.5,Sch -,2.5" | عدد | 9 | 6930000 | 62370000 | 9 | 100% | 62370000
14 | 7662710011 | Flange,A-105,Rating 150,Type SO,ASME B.16.5,Sch -,3" | عدد | 44 | 8162000 | 359128000 | 44 | 100% | 359128000
15 | 7662831311 | A-105 N, 3, 300, WN, RF, 80, -, ASME B.16.5 | عدد | 1 | 33880000 | 33880000 | 1 | 100% | 33880000
16 | 7662810911 | A-105 N, 3, 150, WN, RF, 40, -, ASME B.16.5 | عدد | 3 | 13090000 | 39270000 | 3 | 100% | 39270000
17 | 7662811711 | A-105 N, 3, 150, WN, RF, 160, -, ASME B.16.5 | عدد | 2 | 20020000 | 40040000 | 2 | 100% | 40040000
18 | 7662710013 | Flange,A-105,Rating 150,Type SO,ASME B.16.5,Sch -,4" | عدد | 95 | 10010000 | 950950000 | 95 | 100% | 950950000
19 | 7662811313 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 80,4" | عدد | 4 | 23100000 | 92400000 | 4 | 100% | 92400000
20 | 7662810915 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 40,6" | عدد | 8 | 24640000 | 197120000 | 8 | 100% | 197120000
21 | 7662110015 | A-105 N, 6, 150, BL, RF, -, -, ASME B.16.5 | عدد | 2 | 26180000 | 52360000 | 2 | 100% | 52360000
22 | 7662710015 | Flange,A-105,Rating 150,Type SO,ASME B.16.5,Sch -,6" | عدد | 28 | 20020000 | 560560000 | 28 | 100% | 560560000
23 | 7662810916 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 40,8" | عدد | 7 | 38500000 | 269500000 | 7 | 100% | 269500000
24 | 7662110016 | Flange,A-105,Rating 150,Type BL,ASME B.16.5,Sch -,8" | عدد | 2 | 53900000 | 107800000 | 2 | 100% | 107800000
25 | 7662811316 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 80,8" | عدد | 5 | 52360000 | 261800000 | 5 | 100% | 261800000
26 | 7662810917 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 40,10" | عدد | 15 | 53900000 | 808500000 | 15 | 100% | 808500000
27 | 7662811017 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch 60,10" | عدد | 1 | 80080000 | 80080000 | 1 | 100% | 80080000
28 | 7662810818 | A-105 N, 12, 150, WN, RF, STD, -, ASME B.16.5 | عدد | 2 | 100100000 | 200200000 | 2 | 100% | 200200000 | 10 | 8 | 1001000000
29 | 7662812619 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch t13,14" | عدد | 1 | 130900000 | 130900000 | 1 | 100% | 130900000 | 10 | 9 | 1309000000
30 | 7662812720 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch t15,16" | عدد | 1 | 192500000 | 192500000 | 1 | 100% | 192500000 |  | -1 | 0
31 | 7662812520 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch t10,16" | عدد | 2 | 138600000 | 277200000 | 2 | 100% | 277200000 | 3 | 1 | 415800000
32 | 7662813224 | A-105 N, 24, 150, WN, RF, t24, -, ASME B.16.5 | عدد | 1 | 308000000 | 308000000 | 1 | 100% | 308000000 | 8 | 7 | 2464000000
33 | 7662110024 | A-105 N, 24, 150, BL, RF, -, -, ASME B.16.5 | عدد | 2 | 308000000 | 616000000 | 2 | 100% | 616000000 | 2 | 0 | 616000000
34 | 7662812424 | A-105 N, 24, 150, WN, RF, t8, -, ASME B.16.5 | عدد | 2 | 308000000 | 616000000 | 2 | 100% | 616000000 | 4 | 2 | 1232000000
35 | 7662812524 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch t10,24" | عدد | 2 | 308000000 | 616000000 | 2 | 100% | 616000000 | 53 | 51 | 16324000000
36 | 7662812324 | Flange,A-105,Rating 150,Type WN,ASME B.16.5,Sch t7,24" | عدد | 1 | 308000000 | 308000000 | 1 | 100% | 308000000 | 6 | 5 | 1848000000
37 | 7662812327 | Flange,A-105,Rating 150,Type WN,ASME B.16.47 SERIES "A",Sch t7,30" | عدد | 2 | 462000000 | 924000000 | 2 | 100% | 924000000 | 4 | 2 | 1848000000
38 | 7662812627 | A-105 N, 30, 150, WN, RF, t13, -, ASME B.16.47 SERIES "A" | عدد | 1 | 462000000 | 462000000 | 1 | 100% | 462000000 | 465 | 464 | 214830000000
39 | 7662812827 | A-105 N, 30, 150, WN, RF, t16, -, ASME B.16.47 SERIES "A" | عدد | 1 | 592900000 | 592900000 | 1 | 100% | 592900000 | 97 | 96 | 57511300000
40 | 7662813430 | A-105 N, 36, 150, WN, RF, t28, -, ASME B.16.47 SERIES "A" | عدد | 1 | 693000000 | 693000000 | 1 | 100% | 693000000 | 12 | 11 | 8316000000
41 | 7662110030 | A-105 N, 36, 150, BL, RF, -, -, ASME B.16.47 SERIES "A" | عدد | 1 | 693000000 | 693000000 | 1 | 100% | 693000000
42 | 7413240909 | Pipe,ASME B.36.10,A-106 B,Sch 40,2" | عدد | 258 | 5605600 | 1446244800 | 258 | 100% | 1446244800
43 | 7413211313 | Pipe,ASME B.36.10,A-53,Sch 80,4" | عدد | 306 | 22522500 | 6891885000 | 306 | 100% | 6891885000
44 | 7413241306 | Pipe,ASME B.36.10,A-106 B,Sch 80,1" | عدد | 30 | 3503500 | 105105000 | 30 | 100% | 105105000
45 | 7413210806 | PIPE A53 , 1 STD ASME B36.10 | عدد | 90 | 2502500 | 225225000 | 84 | 93.33% | 210210000
46 | 7413211306 | Pipe,ASME B.36.10,A-53,Sch 80,1" | عدد | 6 | 3503500 | 21021000 | 12 | 200% | 42042000
47 | 7413241711 | PIPE A106 B , 3,160 ASME B36.10 | عدد | 126 | 21521500 | 2711709000 | 125.9 | 99.92% | 2709556850
48 | 7630091523 | A-234 WPB, 6, Tee, Equal Tee, Butt Welded, 40, ASME B.16.9 | عدد | 38 | 24640000 | 936320000 | 38 | 100% | 936320000
49 | 7630090900 | Tee,Butt Welded,ASME B.16.9,A-234 WPB,Equal Tee,Sch 40, 2" | عدد | 3 | 5390000 | 16170000 | 3 | 100% | 16170000
50 | 7631091309 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 40, 4",2" | عدد | 27 | 3696000 | 99792000 | 27 | 100% | 99792000
51 | 7632401713 | Elbow,Butt Welded,ASME B.16.9,A-234 WPB,90-LR,Sch 160, 4" | عدد | 1 | 16632000 | 16632000 | 1 | 100% | 16632000
52 | 7631091108 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 40, 3",1.5" | عدد | 2 | 1848000 | 3696000 | 2 | 100% | 3696000
53 | 7605282004 | Half Coupling,Socket Welded,A-105,Sch NPT 3000#, 0.5" | عدد | 582 | 394240 | 229447680 | 582 | 100% | 229447680
54 | 7632381713 | A-234 WPB, 4, Elbow, 45-LR, Butt Welded, 160, ASME B.16.9 | عدد | 2 | 8316000 | 16632000 | 2 | 100% | 16632000
55 | 7631130906 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 80, 2",1" | عدد | 10 | 1108800 | 11088000 | 10 | 100% | 11088000
56 | 7630181305 | CAP,Butt Welded,A-234 WPB,Sch 80, 0.75" | عدد | 6 | 770000 | 4620000 | 6 | 100% | 4620000
57 | 7630741306 | Return,Butt Welded,A-234 WPB,180-LR,Sch 80, 1" | عدد | 64 | 4389000 | 280896000 | 64 | 100% | 280896000
58 | 7631131109 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 80, 3",2" | عدد | 8 | 2772000 | 22176000 | 8 | 100% | 22176000
59 | 7631131511 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 80, 6",3" | عدد | 5 | 11088000 | 55440000 | 5 | 100% | 55440000
60 | 7632401306 | A-234 WPB, 1, Elbow, 90-LR, Butt Welded, 80, ASME B.16.9 | عدد | 4 | 554400 | 2217600 | 4 | 100% | 2217600
61 | 7631091109 | A-234 WPB, 3x2, Reducer, Concentric, Butt Welded, 40, ASME B.16.9 | عدد | 5 | 1848000 | 9240000 | 5 | 100% | 9240000
62 | 7631090908 | A-234 WPB, 2x1.5, Reducer, Concentric, Butt Welded, 40, ASME B.16.9 | عدد | 2 | 924000 | 1848000 | 2 | 100% | 1848000
63 | 7630081110 | A-234 WPB, 3x2.5, Tee, Reduced Tee, Butt Welded, STD, ASME B.16.9 | عدد | 3 | 10780000 | 32340000 | 3 | 100% | 32340000
64 | 7632401711 | A-234 WPB, 3, Elbow, 90-LR, Butt Welded, 160, ASME B.16.9 | عدد | 46 | 13090000 | 602140000 | 46 | 100% | 602140000
|  | جمع کل اقلام خریداری شده |  |  |  | 27001747080 |  |  | 27005600930
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (ریال) | توضیحات:
جمع کل کالای ارسالی | [5 empty] | 27005600930 | کلیه اقلام به غیر از ردیف های 45 و 46 جدول فوق مطابق با پیش فاکتور رسید انبار شده است. در خصوص کسری و اضافه دو ردیف مذکور، با توجه به کم اهمیت بودن اثر ریالی آن و مطابقت صورتحسابهای دریافتی با اقلام ارسالی، پرداخت مبلغ محاسبه شده مورد تایید می باشد.
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 2430504083.7
جمع کل صورتحسابها (شامل مالیات و عوارض) | [5 empty] | 29436105013.7
کسر می شود پرداختهای قبلی بابت تستهای آزمایشگاهی | [5 empty] | -280275000
خالص قابل پرداخت | [5 empty] | 29155830013.7

## SH-01-832
# | Opi No. | Date | Project Name | Packing List No. | Purchase Order | Vendor | Purchaser | Consignee | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
106 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662811219 | A-105 N, 14, 150, WN, RF, XS, -, ASME B.16.5 | 1 |  |  |  |  | 1 | Piece |  |  | SCH80
107 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662811705 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 160,0.75" | 4 |  |  |  |  | 4 | Piece
108 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662710006 | Flange,A-105,Rating 150,Type SO,Facing RF,ASME B.16.5,Sch -,1" | 22 |  |  |  |  | 22 | Piece
109 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662110006 | Flange,A-105,Rating 150,Type BL,Facing RF,ASME B.16.5,Sch -,1" | 6 |  |  |  |  | 6 | Piece
110 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662831706 | Flange,A-105,Rating 300,Type WN,Facing RF,ASME B.16.5,Sch 160,1" | 2 |  |  |  |  | 2 | Piece
111 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662811708 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 160,1.5" | 3 |  |  |  |  | 3 | Piece
112 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662710008 | Flange,A-105,Rating 150,Type SO,Facing RF,ASME B.16.5,Sch -,1.5" | 34 |  |  |  |  | 34 | Piece
113 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662110008 | Flange,A-105,Rating 150,Type BL,Facing RF,ASME B.16.5,Sch -,1.5" | 4 |  |  |  |  | 4 | Piece
103 | OPI-SLD-9000-013 | 2022-04-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-013 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 13 |  | Main Item | - | 7662831709 | Flange,A-105,Rating 300,Type WN,Facing RF,ASME B.16.5,Sch 160,2" | 3 |  |  |  |  | 3 | Piece
115 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662831309 | Flange,A-105,Rating 300,Type WN,Facing RF,ASME B.16.5,Sch 80,2" | 5 |  |  |  |  | 5 | Piece
116 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662710009 | Flange,A-105,Rating 150,Type SO,Facing RF,ASME B.16.5,Sch -,2" | 371 |  |  |  |  | 371 | Piece
117 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662110009 | Flange,A-105,Rating 150,Type BL,Facing RF,ASME B.16.5,Sch -,2" | 32 |  |  |  |  | 32 | Piece
118 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662710010 | Flange,A-105,Rating 150,Type SO,Facing RF,ASME B.16.5,Sch -,2.5" | 9 |  |  |  |  | 9 | Piece
119 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662710011 | Flange,A-105,Rating 150,Type SO,Facing RF,ASME B.16.5,Sch -,3" | 44 |  |  |  |  | 44 | Piece
120 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662831311 | A-105 N, 3, 300, WN, RF, 80, -, ASME B.16.5 | 1 |  |  |  |  | 1 | Piece
121 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662810911 | A-105 N, 3, 150, WN, RF, 40, -, ASME B.16.5 | 3 |  |  |  |  | 3 | Piece
122 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662811711 | A-105 N, 3, 150, WN, RF, 160, -, ASME B.16.5 | 2 |  |  |  |  | 2 | Piece
123 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662710013 | Flange,A-105,Rating 150,Type SO,Facing RF,ASME B.16.5,Sch -,4" | 95 |  |  |  |  | 95 | Piece
124 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662811313 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 80,4" | 4 |  |  |  |  | 4 | Piece
125 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662810915 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 40,6" | 8 |  |  |  |  | 8 | Piece
126 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662110015 | A-105 N, 6, 150, BL, RF, -, -, ASME B.16.5 | 2 |  |  |  |  | 2 | Piece
127 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662710015 | Flange,A-105,Rating 150,Type SO,Facing RF,ASME B.16.5,Sch -,6" | 28 |  |  |  |  | 28 | Piece
128 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662810916 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 40,8" | 7 |  |  |  |  | 7 | Piece
129 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662110016 | Flange,A-105,Rating 150,Type BL,Facing RF,ASME B.16.5,Sch -,8" | 2 |  |  |  |  | 2 | Piece
130 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662811316 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 80,8" | 5 |  |  |  |  | 5 | Piece
131 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662810917 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 40,10" | 15 |  |  |  |  | 15 | Piece
132 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662811017 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch 60,10" | 1 |  |  |  |  | 1 | Piece |  |  | SCH80
133 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662810818 | A-105 N, 12, 150, WN, RF, STD, -, ASME B.16.5 | 2 |  |  |  |  | 2 | Piece
134 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812619 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch t13,14" | 1 |  |  |  |  | 1 | Piece |  |  | SCH80
135 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812720 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch t15,16" | 1 |  |  |  |  | 1 | Piece |  |  | SCH80
136 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812520 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch t10,16" | 2 |  |  |  |  | 2 | Piece |  |  | SCH40
137 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662813224 | A-105 N, 24, 150, WN, RF, t24, -, ASME B.16.5 | 1 |  |  |  |  | 1 | Piece |  |  | SCH60
138 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662110024 | A-105 N, 24, 150, BL, RF, -, -, ASME B.16.5 | 2 |  |  |  |  | 2 | Piece
139 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812424 | A-105 N, 24, 150, WN, RF, t8, -, ASME B.16.5 | 2 |  |  |  |  | 2 | Piece
140 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812524 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch t10,24" | 2 |  |  |  |  | 2 | Piece
141 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812324 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.5,Sch t7,24" | 1 |  |  |  |  | 1 | Piece
142 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812327 | Flange,A-105,Rating 150,Type WN,Facing RF,ASME B.16.47 SERIES "A",Sch t7,30" | 2 |  |  |  |  | 2 | Piece |  |  | SCH STD
143 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812627 | A-105 N, 30, 150, WN, RF, t13, -, ASME B.16.47 SERIES "A" | 1 |  |  |  |  | 1 | Piece |  |  | SCH XS
144 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662812827 | A-105 N, 30, 150, WN, RF, t16, -, ASME B.16.47 SERIES "A" | 1 |  |  |  |  | 1 | Piece |  |  | SCH 30
145 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662813430 | A-105 N, 36, 150, WN, RF, t28, -, ASME B.16.47 SERIES "A" | 1 |  |  |  |  | 1 | Piece
146 | OPI-SLD-9000-045 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-045 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 45 |  | Main Item | - | 7662110030 | A-105 N, 36, 150, BL, RF, -, -, ASME B.16.47 SERIES "A" | 1 |  |  |  |  | 1 | Piece
105 | OPI-SLD-9000-046 | 2022-08-14 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-044 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 44 |  | Main Item | - | 7413240909 | Pipe,ASME B.36.10,A-106 B,Sch 40,2" | 258 |  |  |  |  | 258 | Meter
164 | OPI-SLD-9000-046 | 2022-08-14 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-044 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 44 |  | Main Item | - | 7413211313 | Pipe,ASME B.36.10,A-53,Sch 80,4" | 306 |  |  |  |  | 306 | Meter
165 | OPI-SLD-9000-046 | 2022-08-14 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-044 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 44 |  | Main Item | - | 7413241306 | Pipe,ASME B.36.10,A-106 B,Sch 80,1" | 30 |  |  |  |  | 30 | Meter
166 | OPI-SLD-9000-046 | 2022-08-14 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-044 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 44 |  | Main Item | - | 7413210806 | PIPE A53 , 1 STD ASME B36.10 | 90 | 6 |  |  |  | 84 | Piece |  | Advise Vendor of Overage/Shortage
167 | OPI-SLD-9000-046 | 2022-08-14 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-044 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 44 |  | Main Item | - | 7413211306 | Pipe,ASME B.36.10,A-53,Sch 80,1" | 6 |  | 6 |  |  | 12 | Meter |  | Advise Vendor of Overage/Shortage | SCH160دریافت شده است
168 | OPI-SLD-9000-046 | 2022-08-14 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-044 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 44 |  | Main Item | - | 7413241711 | PIPE A106 B , 3,160 ASME B36.10 | 126 | 0.1 |  |  |  | 125.9 | Meter |  | Advise Vendor of Overage/Shortage
147 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7630091523 | A-234 WPB, 6, Tee, Equal Tee, Butt Welded, 40, ASME B.16.9 | 38 |  |  |  |  | 38 | Piece
148 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7630090900 | Tee,Butt Welded,ASME B.16.9,A-234 WPB,Equal Tee,Sch 40, 2" | 3 |  |  |  |  | 3 | Piece
149 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7631091309 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 40, 4",2" | 27 |  |  |  |  | 27 | Piece
150 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7632401713 | Elbow,Butt Welded,ASME B.16.9,A-234 WPB,90-LR,Sch 160, 4" | 1 |  |  |  |  | 1 | Piece
151 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7631091108 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 40, 3",1.5" | 2 |  |  |  |  | 2 | Piece
152 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7605282004 | Half Coupling,Socket Welded,A-105,Sch NPT 3000#, 0.5" | 582 |  |  |  |  | 582 | Piece
153 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7632381713 | A-234 WPB, 4, Elbow, 45-LR, Butt Welded, 160, ASME B.16.9 | 2 |  |  |  |  | 2 | Piece
154 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7631130906 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 80, 2",1" | 10 |  |  |  |  | 10 | Piece
155 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7630181305 | CAP,Butt Welded,A-234 WPB,Sch 80, 0.75" | 6 |  |  |  |  | 6 | Piece
156 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7630741306 | Return,Butt Welded,A-234 WPB,180-LR,Sch 80, 1" | 64 |  |  |  |  | 64 | Piece
157 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7631131109 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 80, 3",2" | 8 |  |  |  |  | 8 | Piece
158 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7631131511 | Reducer,Butt Welded,ASME B.16.9,A-234 WPB,Concentric,Sch 80, 6",3" | 5 |  |  |  |  | 5 | Piece |  |  | متریال رسیدهSCH40میباشد
159 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7632401306 | A-234 WPB, 1, Elbow, 90-LR, Butt Welded, 80, ASME B.16.9 | 4 |  |  |  |  | 4 | Piece
160 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7631091109 | A-234 WPB, 3x2, Reducer, Concentric, Butt Welded, 40, ASME B.16.9 | 5 |  |  |  |  | 5 | Piece
161 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7631090908 | A-234 WPB, 2x1.5, Reducer, Concentric, Butt Welded, 40, ASME B.16.9 | 2 |  |  |  |  | 2 | Piece
162 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7630081110 | A-234 WPB, 3x2.5, Tee, Reduced Tee, Butt Welded, STD, ASME B.16.9 | 3 |  |  |  |  | 3 | Piece
163 | OPI-SLD-9000-044 | 2022-08-13 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9000-046 | ADISH-P-PO-GE-9000 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 46 |  | Main Item | - | 7632401711 | A-234 WPB, 3, Elbow, 90-LR, Butt Welded, 160, ASME B.16.9 | 46 |  |  |  |  | 46 | Piece