## Packing List Items
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Sub Item | PK-026-01 | 1 | External cabinets with control unit of Sanitary Package | 4 |  |  |  |  | 4 | Set | 20
2 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Sub Item | PK-026-01 | 2 | Stand for External cabinets with control unit of Sanitary Package | 4 |  |  |  |  | 4 | Set | 2
3 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Sub Item | PK-026-01 | 3 | Stainless Steel Multistage submersible centrifugal electric pump Model No.: IDROGO 40/15 | 2 |  |  |  |  | 2 | Piece | 18.3
4 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Sub Item | PK-026-01 | 4 | Stainless Steel SUBMERSIBLE SUMP PUMP Model No.; Best 2 | 1 |  |  |  |  | 1 | Piece | 12
5 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Sub Item | PK-026-01 | 5 | Stainless Steel UV. Module Model No. 12GPM | 1 |  |  |  |  | 1 | Piece | 5
6 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Sub Item | PK-026-01 | 6 | Hose size 1/2" . Lenght; 50meter | 4 |  |  |  |  | 4 | Roll | 6 |  | هر رول 50 متر
7 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Sub Item | PK-026-01 | 7 | Hose size 3/4" . Lenght; 50meter | 2 |  |  |  |  | 2 | Roll | 6 |  | هر رول 50 متر
8 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Spare Part | PK-026-01 | 8 | Step Motor Valve for SPARE PARTS | 4 |  |  |  |  | 4 | Piece | 0.05
9 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Spare Part | PK-026-01 | 9 | Diffuser Disk Aeration DIM. 33mm for SPARE PARTS | 3 |  |  |  |  | 3 | Piece | 1.2
10 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Spare Part | PK-026-01 | 10 | UV. Lamp for SPARE PARTS | 1 |  |  |  |  | 1 | Piece | 0.2
11 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Spare Part | PK-026-01 | 11 | Air Compressore Model No. LAM-200 for SPARE PARTS | 1 |  |  |  |  | 1 | Piece | 12.3
12 | OPI-TAHKIM DIA-102-002 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-002 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 2 |  | Sub Item | PK-026-01 | 12 | Grease Trap Underground Polyethene Tank of Sanitary Package | 1 |  |  |  |  | 1 | Set | 850 |  | PK-526-01-TK-V01
13 | OPI-TAHKIM DIA-102-003 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-003 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 3 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (Tank A) | Sub Item | PK-026-01 | 13 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (tank A) | 1 |  |  |  |  | 1 | Set | 1200 |  | PK-526-01-TK-01A
14 | OPI-TAHKIM DIA-102-003 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-003 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 3 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (Tank A) | Sub Item | PK-026-01 | 14 | Charging Mechanism Air Lift Pumping (Installed inside the tank-item 1) | 2 |  |  |  |  | 2 | Set | 5 |  | کلیه متعلقات در داخل مخزن نصب میباشند
15 | OPI-TAHKIM DIA-102-003 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-003 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 3 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (Tank A) | Sub Item | PK-026-01 | 15 | Discharge Mechanism Air Lift Pumping (Installed inside the tank-item 1) | 2 |  |  |  |  | 2 | Set | 5 |  | کلیه متعلقات در داخل مخزن نصب میباشند
16 | OPI-TAHKIM DIA-102-003 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-003 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 3 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (Tank A) | Sub Item | PK-026-01 | 16 | Sludge Return Mechanism Air Lift Pumping (Installed inside the tank-item 1) | 2 |  |  |  |  | 2 | Set | 5 |  | کلیه متعلقات در داخل مخزن نصب میباشند
17 | OPI-TAHKIM DIA-102-003 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-003 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 3 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (Tank A) | Sub Item | PK-026-01 | 17 | Nr. 3 Air Disc Diffuser with stainless steel Pipe and Connections (Installed inside the tank-item 1) | 2 |  |  |  |  | 2 | Set | 20 |  | کلیه متعلقات در داخل مخزن نصب میباشند
18 | OPI-TAHKIM DIA-102-004 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-004 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 4 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (B) | Sub Item | PK-026-01 | 18 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (tank B) | 1 |  |  |  |  | 1 | Set | 1200 |  | PK-526-01-TK-01B
19 | OPI-TAHKIM DIA-102-004 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-004 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 4 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (B) | Sub Item | PK-026-01 | 19 | Charging Mechanism Air Lift Pumping (Installed inside the tank-item 1) | 2 |  |  |  |  | 2 | Set | 5 |  | کلیه متعلقات در داخل مخزن نصب میباشند
20 | OPI-TAHKIM DIA-102-004 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-004 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 4 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (B) | Sub Item | PK-026-01 | 20 | Discharge Mechanism Air Lift Pumping (Installed inside the tank-item 1) | 2 |  |  |  |  | 2 | Set | 5 |  | کلیه متعلقات در داخل مخزن نصب میباشند
21 | OPI-TAHKIM DIA-102-004 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-004 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 4 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (B) | Sub Item | PK-026-01 | 21 | Sludge Return Mechanism Air Lift Pumping (Installed inside the tank-item 1) | 2 |  |  |  |  | 2 | Set | 5 |  | کلیه متعلقات در داخل مخزن نصب میباشند
22 | OPI-TAHKIM DIA-102-004 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-004 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 4 | Primary and Reactor Underground Polyethene Tank of Sanitary Package (B) | Sub Item | PK-026-01 | 22 | Nr. 3 Air Disc Diffuser with stainless steel Pipe and Connections (Installed inside the tankitem 1) | 2 |  |  |  |  | 2 | Set | 20 |  | کلیه متعلقات در داخل مخزن نصب میباشند
23 | OPI-TAHKIM DIA-102-005 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-005 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 5 | UV. Chamber and Storage Underground Polyethene Tank of Sanitary Package | Sub Item | PK-026-01 | 23 | UV. Chamber and Storage Underground Polyethene Tank of Sanitary Package | 1 |  |  |  |  | 1 | Set | 1100 |  | PK-526-01-TK-02A-ضرب خوردگی بر روی بدنه مخزن مشاهده گردید
24 | OPI-TAHKIM DIA-102-001 | 2023-01-01 | SACR-PL-TAHKIM DIA-102-001 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 1 | Equipment of Sanitary Sewage Treatment Package | Spare Part | PK-026-01 | 12 | AIR FILTER FOR AIR COMPRESSORE |  |  | 2 |  |  | 2 | Set |  | Advise Vendor of Overage/Shortage
25 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 24 | Push Fit Polypropylene Pipe Ø110 mm (Length: 3m). Mfr: Poliran | 5 |  |  |  |  | 5 | Piece
26 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 25 | Push Fit Polypropylene Elbow Ø110mm, ∠45º. Mfr: Poliran | 18 |  |  |  |  | 18 | Piece
27 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 26 | Push Fit Polypropylene Coupling Ø110mm. Mfr: Poliran | 6 |  |  |  |  | 6 | Piece
28 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 27 | UPVC Pipe Ø110 mm (Length: 6m). Mfr: Polymer Golpayegan | 11 |  |  |  |  | 11 | Piece
29 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 28 | UPVC Elbow Ø110mm, ∠45º. Mfr: Polymer Golpayegan | 32 |  |  |  |  | 32 | Piece
30 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 29 | UPVC Coupling Ø110mm. Mfr: Polymer Golpayegan | 30 |  |  |  |  | 30 | Piece
31 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 30 | UPVC Tee Ø110mm, ∠90º. Mfr: Polymer Golpayegan | 2 |  |  |  |  | 2 | Piece
32 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 31 | UPVC Elbow Ø110mm, ∠90º. Mfr: Polymer Golpayegan | 10 |  |  |  |  | 10 | Piece
33 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 32 | End Cap Ø110mm. Mfr: Polymer Golpayegan | 10 |  |  |  |  | 10 | Piece
34 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 33 | PVC Adhesive. Mfr: Razi | 40 |  |  |  |  | 40 | Piece
35 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 34 | Polyethylene Pipe Ø50 mm. Mfr: Poliran | 50 |  |  |  |  | 50 | Meter
36 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 35 | Polyethylene Elbow Ø50mm, ∠90º. Mfr: Poliran | 13 |  |  |  |  | 13 | Piece
37 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 36 | Polyethylene Reducer (Female-size: 50*1-1/2"). Mfr: Poliran | 5 |  |  |  |  | 5 | Piece
38 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 37 | Polyethylene Reducer (male-size: 50*1-1/2"). Mfr: Poliran | 1 |  |  |  |  | 1 | Piece
39 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 38 | Stainless Steel 316 Reducer (male-size: 1"*1-1/2"). | 3 |  |  |  |  | 3 | Piece
40 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 39 | Stainless Steel 316 Reducer (size: 1-1/2"-1-1/4"). | 2 |  |  |  |  | 2 | Piece
41 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 40 | Polyethylene Reducer (male-size: 2"*50). Mfr: Poliran | 8 |  |  |  |  | 8 | Piece
42 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 41 | Stainless Steel 316 Nipple (male-size: 2"). | 2 |  |  |  |  | 2 | Piece
43 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 42 | Polyethylene Elbow (Female-size: 50*1-1/2"). Mfr: Poliran | 2 |  |  |  |  | 2 | Piece
44 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 43 | Stainless Steel 316 Reducer (male-size: 2"*1-1/2") | 2 |  |  |  |  | 2 | Piece
45 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 44 | UPVC Check Valve (size: 2"). Mfr: Pimtaş | 3 |  |  |  |  | 3 | Piece
46 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 45 | UPVC Ball Valve (size: 2"). Mfr: Pimtaş | 2 |  |  |  |  | 2 | Piece
47 | OPI-TAHKIM DIA-102-006 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-006 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 6 |  | Sub Item | PK-026-01 | 46 | UPVC Tee Ø50mm. Mfr: Polymer Golpayegan | 1 |  |  |  |  | 1 | Piece
48 | OPI-TAHKIM DIA-102-007 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-007 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 7 |  | Sub Item | PK-026-01 | 48 | MCC Panel for Sanitary Package | 1 |  |  |  |  | 1 | Piece | 80
49 | OPI-TAHKIM DIA-102-007 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-007 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 7 |  | Spare Part | PK-026-01 | 49 | Signaling Lamp for each color (Green, Red, Yellow) | 3 |  |  |  |  | 3 | Piece
50 | OPI-TAHKIM DIA-102-007 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-007 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 7 |  | Spare Part | PK-026-01 | 50 | MCB 16A/2P, 6KA | 1 |  |  |  |  | 1 | Piece
51 | OPI-TAHKIM DIA-102-007 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-007 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 7 |  | Spare Part | PK-026-01 | 51 | RCBO 16A/2P, 6KA, 30mA | 1 |  |  |  |  | 1 | Piece
52 | OPI-TAHKIM DIA-102-007 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-007 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 7 |  | Spare Part | PK-026-01 | 52 | Contactor 4KW, 230VAC | 1 |  |  |  |  | 1 | Piece
53 | OPI-TAHKIM DIA-102-007 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-007 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 7 |  | Spare Part | PK-026-01 | 53 | 2A Fast Acting Glass Fuse | 2 |  |  |  |  | 2 | Piece
54 | OPI-TAHKIM DIA-102-007 | 2023-02-06 | SACR-PL-TAHKIM DIA-102-007 | ADSH-P-PO-GE-102 | TAHKIM DIAMS | DDP Site | 7 |  | Sub Item | PK-026-01 | 54 | Plug-2Pins for Socket Installed on MCC Panel | 1 |  |  |  |  | 1 | Piece