## شرکت پالایش میعانات گازی آدیش
سفارش خرید Ejectors with all necessary raw materials شماره قرارداد ADSH-P-PO-GH-088
| مبلغ فاکتور یورو | نرخ ریال در روز پرداخت محاسبه بر اساس نرخ خرید اسکناس در سامانه سنا | تاریخ واریزی | مبلغ خالص فاکتور ریال | مبلغ ارزش افزوده -ریال
50 درصد پیش پرداخت | 23655 | 288779 | 1401/04/06 | 6831067245 | 614796052
50 درصد قسط تحویل تجهیز | 23655 | 427867 | 1402/01/07 | 10121193885 | 910907450
قطعات یدکی | 2600 | 427867 | 1402/01/07 | 1112454200 | 100120878
مبلغ کل قرارداد | 49910 |  |  | 18064715330 | 1625824380
توضیحات : با توجه به واریز یورو به حساب خارجی و صدور فاکتور رسمی ریالی برای قرارداد فوق طبق توافق(تبدیل نرخ یورو به ریال بر اساس خرید اسکناس در سامانه سنا تاریخ 1402/01/07 ) در نظر گرفته شده است

## محاسبات قراردادی
خلاصه مالی خرید Ejector | [8 empty] | شماره قرارداد: ADSH-P-P0-GE-088 | [6 empty] | 1 | bulk | New | 170.00 Pieces
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ شروع قرارداد: 1401/03/31 | [6 empty] | 2 | bulk | New | 1,200.00 Pieces
فروشنده: کارا صنعت تدبیر پایا | [8 empty] | تاریخ تهیه گزارش: 1402/01/07 | [6 empty] | 3 | bulk | New | 28.00 Pieces
[16 empty] | 4 | bulk | New | 60.00 Pieces
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده | درصد کالای دریافتی | مبلغ کل (یورو) | فاکتور | [5 empty] | 5 | bulk | New | 120.00 Pieces
1 | EJ-501-01 | Hydrocarbon Closed Drain Ejector | Set | 1 | 6500 | 6500 | 1 | 100% | 6500 | 36 | 35 | 234000 | 2 | 1401/11/06 |  | 6 | bulk | New | 140.00 Pieces
2 | EJ-502-02 | Hydrocarbon Closed Drain Ejector | Set | 1 | 6700 | 6700 | 1 | 100% | 6700
3 | EJ-509-01 | Sour Water Closed Drain Sump Ejector | Set | 1 | 6700 | 6700 | 1 | 100% | 6700
4 | EJ-517-01 | Amine Closed Drain Ejector | Set | 1 | 11500 | 11500 | 1 | 100% | 11500
5 | EJ-501-01 | Gasket Spiral Wound 1"150# | Piece | 2 | 7.5 | 15 | 2 | 100% | 15
6 | EJ-517-01 | Gasket Spiral Wound 1"150# | Piece | 2 | 7.5 | 15 | 2 | 100% | 15
7 | EJ-502-02 | Gasket Spiral Wound 1"150# | Piece | 2 | 7.5 | 15 | 2 | 100% | 15
8 | EJ-509-01 | Gasket Spiral Wound 1"150# | Piece | 2 | 7.5 | 15 | 2 | 100% | 15
9 | EJ-501-01 | Gasket Spiral Wound 11/2"300# | Piece | 1 | 12.5 | 12.5 | 1 | 100% | 12.5
10 | EJ-517-01 | Gasket Spiral Wound 11/2"300# | Piece | 1 | 12.5 | 12.5 | 1 | 100% | 12.5
11 | EJ-502-02 | Gasket Spiral Wound 11/2"300# | Piece | 1 | 12.5 | 12.5 | 1 | 100% | 12.5
12 | EJ-509-01 | Gasket Spiral Wound 11/2"300# | Piece | 1 | 12.5 | 12.5 | 1 | 100% | 12.5
13 | EJ-501-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
14 | EJ-501-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
15 | EJ-517-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
16 | EJ-517-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
17 | EJ-502-02 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
18 | EJ-502-02 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
19 | EJ-509-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
20 | EJ-509-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
21 | EJ-501-01 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
22 | EJ-502-02 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
23 | EJ-509-01 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55 | 4 | 2 | 110 | 2 | 1401/11/06 |  | 7 | bulk | New | 30.00 Pieces
24 | EJ-517-01 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
25 | EJ-501-01 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
26 | EJ-502-02 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
27 | EJ-509-01 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
28 | EJ-517-01 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
29 | EJ-501-01 | KLINGRITE C-4400 | Piece | 2 | 30 | 60 | 0 | 0% | 0
30 | EJ-502-02 | KLINGRITE C-4400 | Piece | 2 | 30 | 60 | 0 | 0% | 0
31 | EJ-509-01 | KLINGRITE C-4400 | Piece | 2 | 30 | 60 | 0 | 0% | 0
32 | EJ-517-01 | KLINGRITE C-4400 | Piece | 2 | 30 | 60 | 0 | 0% | 0
33 | EJ-501-01 | Gasket Spiral Wound 1"150# | Piece | 4 | 7.5 | 30 | 4 | 100% | 30
34 | EJ-502-02 | Gasket Spiral Wound 1"150# | Piece | 4 | 7.5 | 30 | 4 | 100% | 30
35 | EJ-509-01 | Gasket Spiral Wound 1"150# | Piece | 4 | 7.5 | 30 | 4 | 100% | 30
36 | EJ-517-01 | Gasket Spiral Wound 1"150# | Piece | 4 | 7.5 | 30 | 4 | 100% | 30
37 | EJ-501-01 | Gasket Spiral Wound 11/2"300# | Piece | 2 | 12.5 | 25 | 2 | 100% | 25
38 | EJ-502-02 | Gasket Spiral Wound 11/2"300# | Piece | 2 | 12.5 | 25 | 2 | 100% | 25
39 | EJ-509-01 | Gasket Spiral Wound 11/2"300# | Piece | 2 | 12.5 | 25 | 2 | 100% | 25
40 | EJ-517-01 | Gasket Spiral Wound 11/2"300# | Piece | 2 | 12.5 | 25 | 2 | 100% | 25
41 | EJ-501-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 4 | 27.5 | 110 | 4 | 100% | 110
42 | EJ-502-02 | Bolt & Nuts 1/2"(M14) x70 | Set | 4 | 27.5 | 110 | 4 | 100% | 110
43 | EJ-509-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 4 | 27.5 | 110 | 4 | 100% | 110
44 | EJ-517-01 | Bolt & Nuts 1/2"(M14) x70 | Set | 4 | 27.5 | 110 | 4 | 100% | 110
45 | EJ-501-01 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
46 | EJ-502-02 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
47 | EJ-509-01 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
48 | EJ-517-01 | Bolt & Nuts 1/2"(M14) x80 | Set | 2 | 27.5 | 55 | 2 | 100% | 55
49 | EJ-501-01 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
50 | EJ-502-02 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
51 | EJ-509-01 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
52 | EJ-517-01 | Bolt & Nuts 3/4"(M20) x110 | Set | 2 | 85 | 170 | 2 | 100% | 170
53 | EJ-502-01 | Evacuation Ejector | Set | 1 | 6500 | 6500 | 1 | 100% | 6500
54 | EJ-502-01 | Gasket Spiral Wound 2"300# | Piece | 1 | 15 | 15 | 1 | 100% | 15
55 | EJ-502-01 | Gasket Spiral Wound 4"300# | Piece | 2 | 40 | 80 | 2 | 100% | 80
56 | EJ-502-01 | Bolt & Nuts 5/8"(M16) x80 | Set | 4 | 30 | 120 | 4 | 100% | 120
57 | EJ-502-01 | Bolt & Nuts 3/4"(M20) x130 | Set | 2 | 85 | 170 | 2 | 100% | 170
58 | EJ-502-01 | Gasket KLINGRITE C-4400 | Piece | 2 | 35 | 70 | 0 | 0% | 0
59 | EJ-502-01 | Gasket Spiral Wound 2"300# | Piece | 2 | 15 | 30 | 2 | 100% | 30
60 | EJ-502-01 | Gasket Spiral Wound 4"300# | Piece | 2 | 20 | 40 | 2 | 100% | 40
61 | EJ-502-01 | Bolt & Nuts 5/8"(M16) x80 | Set | 4 | 30 | 120 | 4 | 100% | 120
62 | EJ-502-01 | Bolt & Nuts 3/4"(M20) x130 | Set | 2 | 85 | 170 | 2 | 100% | 170
63 | EJ-502-01 | SI-502-01 | Set | 1 | 5395 | 5395 | 1 | 100% | 5395
64 | EJ-502-01 | Gasket Spiral Wound 1"300# | Piece | 1 | 10 | 10 | 1 | 100% | 10
65 | EJ-502-01 | Gasket Spiral Wound 4"300# | Piece | 2 | 40 | 80 | 2 | 100% | 80
66 | EJ-502-01 | Bolt & Nuts 5/8"(M16) x90 | Set | 2 | 30 | 60 | 2 | 100% | 60
67 | EJ-502-01 | Bolt & Nuts 3/4"(M20) x130 | Set | 2 | 85 | 170 | 2 | 100% | 170
68 | EJ-502-01 | Gasket Spiral Wound 1"300# | Piece | 2 | 10 | 20 | 2 | 100% | 20
69 | EJ-502-01 | Gasket Spiral Wound 4"300# | Piece | 4 | 20 | 80 | 4 | 100% | 80
70 | EJ-502-01 | Bolt & Nuts 5/8"(M16) x90 | Set | 2 | 30 | 60 | 2 | 100% | 60
71 | EJ-502-01 | Bolt & Nuts 3/4"(M20) x130 | Set | 2 | 85 | 170 | 2 | 100% | 170
72 |  | Freit Charge |  | 1 | 900 | 900 | 1 | 100% | 900
73 |  | Packing |  | 1 | 1000 | 1000 | 1 | 100% | 1000
[6 empty] | 49910 |  |  | 49600
6889510142
خلاصه مالی خرید Ejector | [8 empty] | شماره قرارداد: ADSH-P-P0-GE-088 | [6 empty] | 1 | bulk | New | 170.00 Pieces
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ شروع قرارداد: 1401/03/31 | [6 empty] | 2 | bulk | New | 1,200.00 Pieces
فروشنده: کارا صنعت تدبیر پایا | [8 empty] | تاریخ تهیه گزارش: 1402/01/07 | [6 empty] | 3 | bulk | New | 28.00 Pieces
[16 empty] | 4 | bulk | New | 60.00 Pieces
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده | درصد کالای دریافتی | مبلغ کل (یورو) | فاکتور | [5 empty] | 5 | bulk | New | 120.00 Pieces
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات: | [7 empty] | 6889510142
6889510142
جمع کالای دریافتی | [5 empty] | 49910 | کلیه کالاهای موضوع قرارداد باید از زمان پرداخت پیش پرداخت ظرف 120 روز تقویمی تحویل گردد.تاریخ پرداخت پیش پرداخت 1401/03/31 میباشد-تاریخ تحویل 4 ماه پس از پرداخت پیش پرداخت 1401/07/31 میباشد ولیکن کالا طی MRS-KST-088-001 درمورخ 1401/12/23 به انبار رسید شده است.8 تیکه از ساب آیتم و اسپر مجموعا 310 یورو کسری در ارسال میباشد که از صورتحساب کسر گردید.طبق استعلام صورت گرفته از واحد برنامه ریزی تاخیرات فروشنده بیش از 4 ماه میباشد و مربوط به مراحل ساخت میباشد و به عهده فروشنده است.
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 4491.9
جمع صورتحساب | [5 empty] | 54401.9
کسور:
استهلاک پیش پرداخت (25%) | [5 empty] | -23655
سپرده حسن انجام کار (5%) | [5 empty] | 0
جرائم تاخیر 10% مبلغ قرارداد | [5 empty] | -4991
جمع کسور | [5 empty] | -28646
خالص قابل پرداخت | [5 empty] | 25755.9
خلاصه محاسبات پرداخت صورت حساب 1 : | [5 empty] | (یورو) |  | (ریالی)
جمع کالای دریافتی | [5 empty] | 49600 |  | 18273152465.1376
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 4464 |  | 1644583721.8624
جمع صورتحساب | [5 empty] | 54064 |  | 19917736187
کسور: | [12 empty] | 6788599210
استهلاک پیش پرداخت (50%) | [5 empty] | -23655 | 286982 | -6788559210 |  |  |  |  | 40000
سپرده حسن انجام کار (10%) | [5 empty] | 0 | 0 | 0 |  |  |  |  | -286983.691
جرائم تاخیر 10% مبلغ قرارداد-منتظر اعلام نظر واحد برنامه ریزی | [5 empty] | -4991 | 431753 | -2154879223 |  |  |  |  | -1.691
جمع کسور | [5 empty] | -28646 |  | -8943438433
خالص قابل پرداخت | [5 empty] | 25418 | 431753 | 10974297754
توضیحات در خصوص نرخ های تسعیر: | [5 empty] | 30409
1- محاسبه مبلغ خالص قابل پرداخت با نرخ تسعیر فروش اسکناس در سامانه سنا در تاریخ 1402/01/07 لحاظ شده است ولیکن MRS & PI (1401/12/23) تحویل سایت شده است.
2- در محاسبه نرخ تسعیر جهت استهلاک پیش پرداخت ، عینا از نرخ تسعیر پرداخت های انجام شده در همان تاریخ استفاده شده است. پیش پرداخت به شرح ذیل انجام شده است:
[5 empty] | تاریخ | مبلغ ارزی | نرخ تسعیر | معادل ریالی
پیش پرداخت (50%) |  |  |  |  | 1401/03/31 | 23655 | 286982 | 6788559210
استهلاک پیش پرداخت (50%) |  |  |  |  | 1402/01/07 | -23655 | 286982 | -6788559210
[6 empty] | 0 |  | 0

## ریز کالا
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Main Item | EJ-501-01 | EJ-501-01 | Hydrocarbon Closed Drain Ejector | 1 |  |  |  |  | 1 | Set | 10.8 |  |  | 6500 | 6500
2 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Main Item | EJ-502-02 | EJ-502-02 | Hydrocarbon Closed Drain Ejector | 1 |  |  |  |  | 1 | Set | 10.8 |  |  | 6700 | 6700
3 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Main Item | EJ-509-01 | EJ-509-01 | Sour Water Closed Drain Sump Ejector | 1 |  |  |  |  | 1 | Set | 10.8 |  |  | 6700 | 6700
4 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Main Item | EJ-517-01 | EJ-517-01 | Amine Closed Drain Ejector | 1 |  |  |  |  | 1 | Set | 10.8 |  |  | 11500 | 11500
5 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-501-01 | 1 | Gasket Spiral Wound 1"150# | 2 |  |  |  |  | 2 | Piece | 0.1 |  |  | 7.5 | 15
6 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-517-01 | 1 | Gasket Spiral Wound 1"150# | 2 |  |  |  |  | 2 | Piece | 0.1 |  |  | 7.5 | 15
7 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-02 | 1 | Gasket Spiral Wound 1"150# | 2 |  |  |  |  | 2 | Piece | 0.1 |  |  | 7.5 | 15
8 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-509-01 | 1 | Gasket Spiral Wound 1"150# | 2 |  |  |  |  | 2 | Piece | 0.1 |  |  | 7.5 | 15
9 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-501-01 | 2 | Gasket Spiral Wound 11/2"300# | 1 |  |  |  |  | 1 | Piece | 0.09 |  |  | 12.5 | 12.5
10 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-517-01 | 2 | Gasket Spiral Wound 11/2"300# | 1 |  |  |  |  | 1 | Piece | 0.09 |  |  | 12.5 | 12.5
11 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-02 | 2 | Gasket Spiral Wound 11/2"300# | 1 |  |  |  |  | 1 | Piece | 0.09 |  |  | 12.5 | 12.5
12 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-509-01 | 2 | Gasket Spiral Wound 11/2"300# | 1 |  |  |  |  | 1 | Piece | 0.09 |  |  | 12.5 | 12.5
13 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-501-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
14 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-501-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
15 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-517-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
16 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-517-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
17 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-02 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
18 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-02 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
19 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-509-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
20 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-509-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | 2 |  |  |  |  | 2 | Set | 0.24 |  |  | 27.5 | 55
21 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-501-01 | 4 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
22 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-02 | 4 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
23 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-509-01 | 4 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
24 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-517-01 | 4 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
25 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-501-01 | 5 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
26 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-02 | 5 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
27 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-509-01 | 5 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
28 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-517-01 | 5 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
29 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-501-01 | 6 | KLINGRITE C-4400 | 2 | 2 |  |  |  | 0 | Piece | 0.05 | Advise Vendor of Overage/Shortage |  | 30 | 0 | 60
30 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-02 | 6 | KLINGRITE C-4400 | 2 | 2 |  |  |  | 0 | Piece | 0.05 | Advise Vendor of Overage/Shortage |  | 30 | 0 | 60
31 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-509-01 | 6 | KLINGRITE C-4400 | 2 | 2 |  |  |  | 0 | Piece | 0.05 | Advise Vendor of Overage/Shortage |  | 30 | 0 | 60
32 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-517-01 | 6 | KLINGRITE C-4400 | 2 | 2 |  |  |  | 0 | Piece | 0.05 | Advise Vendor of Overage/Shortage |  | 30 | 0 | 60
33 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-501-01 | 7 | Gasket Spiral Wound 1"150# | 4 |  |  |  |  | 4 | Piece | 0.2 |  |  | 7.5 | 30
34 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-02 | 7 | Gasket Spiral Wound 1"150# | 4 |  |  |  |  | 4 | Piece | 0.2 |  |  | 7.5 | 30
35 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-509-01 | 7 | Gasket Spiral Wound 1"150# | 4 |  |  |  |  | 4 | Piece | 0.2 |  |  | 7.5 | 30
36 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-517-01 | 7 | Gasket Spiral Wound 1"150# | 4 |  |  |  |  | 4 | Piece | 0.2 |  |  | 7.5 | 30
37 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-501-01 | 8 | Gasket Spiral Wound 11/2"300# | 2 |  |  |  |  | 2 | Piece | 0.18 |  |  | 12.5 | 25
38 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-02 | 8 | Gasket Spiral Wound 11/2"300# | 2 |  |  |  |  | 2 | Piece | 0.18 |  |  | 12.5 | 25
39 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-509-01 | 8 | Gasket Spiral Wound 11/2"300# | 2 |  |  |  |  | 2 | Piece | 0.18 |  |  | 12.5 | 25
40 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-517-01 | 8 | Gasket Spiral Wound 11/2"300# | 2 |  |  |  |  | 2 | Piece | 0.18 |  |  | 12.5 | 25
41 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-501-01 | 9 | Bolt & Nuts 1/2"(M14) x70 | 4 |  |  |  |  | 4 | Set | 0.48 |  |  | 27.5 | 110
42 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-02 | 9 | Bolt & Nuts 1/2"(M14) x70 | 4 |  |  |  |  | 4 | Set | 0.48 |  |  | 27.5 | 110
43 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-509-01 | 9 | Bolt & Nuts 1/2"(M14) x70 | 4 |  |  |  |  | 4 | Set | 0.48 |  |  | 27.5 | 110
44 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-517-01 | 9 | Bolt & Nuts 1/2"(M14) x70 | 4 |  |  |  |  | 4 | Set | 0.48 |  |  | 27.5 | 110
45 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-501-01 | 10 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
46 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-02 | 10 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
47 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-509-01 | 10 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
48 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-517-01 | 10 | Bolt & Nuts 1/2"(M14) x80 | 2 |  |  |  |  | 2 | Set | 0.28 |  |  | 27.5 | 55
49 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-501-01 | 11 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
50 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-02 | 11 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
51 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-509-01 | 11 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
52 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-517-01 | 11 | Bolt & Nuts 3/4"(M20) x110 | 2 |  |  |  |  | 2 | Set | 0.75 |  |  | 85 | 170
53 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Main Item | EJ-502-01 | EJ-502-01 | Evacuation Ejector | 1 |  |  |  |  | 1 | Set | 50.5 |  |  | 6500 | 6500
54 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 12 | Gasket Spiral Wound 2"300# | 1 |  |  |  |  | 1 | Piece | 0.2 |  |  | 15 | 15
55 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 13 | Gasket Spiral Wound 4"300# | 2 |  |  |  |  | 2 | Piece | 0.52 |  |  | 40 | 80
56 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 14 | Bolt & Nuts 5/8"(M16) x80 | 4 |  |  |  |  | 4 | Set | 0.75 |  |  | 30 | 120
57 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 15 | Bolt & Nuts 3/4"(M20) x130 | 2 |  |  |  |  | 2 | Set | 0.875 |  |  | 85 | 170
58 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 16 | Gasket KLINGRITE C-4400 | 2 | 2 |  |  |  | 0 | Piece | 0.05 | Advise Vendor of Overage/Shortage |  | 35 | 0 | 70
59 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 17 | Gasket Spiral Wound 2"300# | 2 |  |  |  |  | 2 | Piece | 0.4 |  |  | 15 | 30
60 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 18 | Gasket Spiral Wound 4"300# | 2 |  |  |  |  | 2 | Piece | 0.52 |  |  | 20 | 40
61 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 19 | Bolt & Nuts 5/8"(M16) x80 | 4 |  |  |  |  | 4 | Set | 0.75 |  |  | 30 | 120
62 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 20 | Bolt & Nuts 3/4"(M20) x130 | 2 |  |  |  |  | 2 | Set | 0.875 |  |  | 85 | 170
63 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Sub Item | EJ-502-01 | 21 | SI-502-01 | 1 |  |  |  |  | 1 | Set | 86.7 |  |  | 5395 | 5395
64 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 22 | Gasket Spiral Wound 1"300# | 1 |  |  |  |  | 1 | Piece | 0.15 |  |  | 10 | 10
65 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 23 | Gasket Spiral Wound 4"300# | 2 |  |  |  |  | 2 | Piece | 0.52 |  |  | 40 | 80
66 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 24 | Bolt & Nuts 5/8"(M16) x90 | 2 |  |  |  |  | 2 | Set | 0.33 |  |  | 30 | 60
67 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Commissioning Spare Part | EJ-502-01 | 25 | Bolt & Nuts 3/4"(M20) x130 | 2 |  |  |  |  | 2 | Set | 0.875 |  |  | 85 | 170
68 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 22 | Gasket Spiral Wound 1"300# | 2 |  |  |  |  | 2 | Piece | 0.3 |  |  | 10 | 20
69 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 23 | Gasket Spiral Wound 4"300# | 4 |  |  |  |  | 4 | Piece | 1.04 |  |  | 20 | 80
70 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 24 | Bolt & Nuts 5/8"(M16) x90 | 2 |  |  |  |  | 2 | Set | 0.33 |  |  | 30 | 60
71 | OPI-KST-088-001 | 2023-03-14 | SACR-PL-KST-088-001 | ADSH-P-PO-GE-088 | KARA SANAT TADBIR PAYA | KANGAN | 001 |  | Spare Part | EJ-502-01 | 25 | Bolt & Nuts 3/4"(M20) x130 | 2 |  |  |  |  | 2 | Set | 0.875 |  |  | 85 | 170
900
1000
[24 empty] | 49600 | 310 | 0
-49910
-310
42100
900
1000
3310

## opi
Package No. 1: Wooden Box, 101cm x 81cm x 50cm, 90 Kg (70 Kg)
# | Group | Mark No. | Description | Size | PL Quantity | Unit | Shortage | Overage | Damage | Incorrect | Accepted | Action Code | Remark
1 | Main Item | EJ-501-01 | Hydrocarbon Closed Drain Ejector | - | 1 | Set | - | - | - | - | 1
2 | Main Item | EJ-502-02 | Hydrocarbon Closed Drain Ejector | - | 1 | Set | - | - | - | - | 1
3 | Main Item | EJ-509-01 | Sour Water Closed Drain Sump Ejector | - | 1 | Set | - | - | - | - | 1
4 | Main Item | EJ-517-01 | Amine Closed Drain Ejector | - | 1 | Set | - | - | - | - | 1
5 | Commissioning Spare Part of EJ-501-01 | 1 | Gasket Spiral Wound 1"150# | - | 2 | Piece | - | - | - | - | 2
6 | Commissioning Spare Part of EJ-517-01 | 1 | Gasket Spiral Wound 1"150# | - | 2 | Piece | - | - | - | - | 2
7 | Commissioning Spare Part of EJ-502-02 | 1 | Gasket Spiral Wound 1"150# | - | 2 | Piece | - | - | - | - | 2
8 | Commissioning Spare Part of EJ-509-01 | 1 | Gasket Spiral Wound 1"150# | - | 2 | Piece | - | - | - | - | 2
9 | Commissioning Spare Part of EJ-501-01 | 2 | Gasket Spiral Wound 11/2"300# | - | 1 | Piece | - | - | - | - | 1
10 | Commissioning Spare Part of EJ-517-01 | 2 | Gasket Spiral Wound 11/2"300# | - | 1 | Piece | - | - | - | - | 1
11 | Commissioning Spare Part of EJ-502-02 | 2 | Gasket Spiral Wound 11/2"300# | - | 1 | Piece | - | - | - | - | 1
12 | Commissioning Spare Part of EJ-509-01 | 2 | Gasket Spiral Wound 11/2"300# | - | 1 | Piece | - | - | - | - | 1
13 | Commissioning Spare Part of EJ-501-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
14 | Commissioning Spare Part of EJ-501-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
15 | Commissioning Spare Part of EJ-517-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
16 | Commissioning Spare Part of EJ-517-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
17 | Commissioning Spare Part of EJ-502-02 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
18 | Commissioning Spare Part of EJ-502-02 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
19 | Commissioning Spare Part of EJ-509-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
20 | Commissioning Spare Part of EJ-509-01 | 3 | Bolt & Nuts 1/2"(M14) x70 | - | 2 | Set | - | - | - | - | 2
21 | Commissioning Spare Part of EJ-501-01 | 4 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
22 | Commissioning Spare Part of EJ-502-02 | 4 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
23 | Commissioning Spare Part of EJ-509-01 | 4 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
24 | Commissioning Spare Part of EJ-517-01 | 4 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
25 | Commissioning Spare Part of EJ-501-01 | 5 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
26 | Commissioning Spare Part of EJ-502-02 | 5 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
27 | Commissioning Spare Part of EJ-509-01 | 5 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
28 | Commissioning Spare Part of EJ-517-01 | 5 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
Package No. 2: Wooden Box, 33cm x 33cm x 10cm, 4 Kg (2.5 Kg)
# | Group | Mark No. | Description | Size | PL Quantity | Unit | Shortage | Overage | Damage | Incorrect | Accepted | Action Code | Remark
1 | Spare Part of EJ-501-01 | 6 | KLINGRITE C-4400 | - | 2 | Piece | 2 | - | - | - | 0 | Advise Vendor of Overage/Shortage
2 | Spare Part of EJ-502-02 | 6 | KLINGRITE C-4400 | - | 2 | Piece | 2 | - | - | - | 0 | Advise Vendor of Overage/Shortage
3 | Spare Part of EJ-509-01 | 6 | KLINGRITE C-4400 | - | 2 | Piece | 2 | - | - | - | 0 | Advise Vendor of Overage/Shortage
4 | Spare Part of EJ-517-01 | 6 | KLINGRITE C-4400 | - | 2 | Piece | 2 | - | - | - | 0 | Advise Vendor of Overage/Shortage
5 | Spare Part of EJ-501-01 | 7 | Gasket Spiral Wound 1"150# | - | 4 | Piece | - | - | - | - | 4
6 | Spare Part of EJ-502-02 | 7 | Gasket Spiral Wound 1"150# | - | 4 | Piece | - | - | - | - | 4
7 | Spare Part of EJ-509-01 | 7 | Gasket Spiral Wound 1"150# | - | 4 | Piece | - | - | - | - | 4
8 | Spare Part of EJ-517-01 | 7 | Gasket Spiral Wound 1"150# | - | 4 | Piece | - | - | - | - | 4
9 | Spare Part of EJ-501-01 | 8 | Gasket Spiral Wound 11/2"300# | - | 2 | Piece | - | - | - | - | 2
10 | Spare Part of EJ-502-02 | 8 | Gasket Spiral Wound 11/2"300# | - | 2 | Piece | - | - | - | - | 2
11 | Spare Part of EJ-509-01 | 8 | Gasket Spiral Wound 11/2"300# | - | 2 | Piece | - | - | - | - | 2
12 | Spare Part of EJ-517-01 | 8 | Gasket Spiral Wound 11/2"300# | - | 2 | Piece | - | - | - | - | 2
13 | Spare Part of EJ-501-01 | 9 | Bolt & Nuts 1/2"(M14) x70 | - | 4 | Set | - | - | - | - | 4
14 | Spare Part of EJ-502-02 | 9 | Bolt & Nuts 1/2"(M14) x70 | - | 4 | Set | - | - | - | - | 4
15 | Spare Part of EJ-509-01 | 9 | Bolt & Nuts 1/2"(M14) x70 | - | 4 | Set | - | - | - | - | 4
16 | Spare Part of EJ-517-01 | 9 | Bolt & Nuts 1/2"(M14) x70 | - | 4 | Set | - | - | - | - | 4
17 | Spare Part of EJ-501-01 | 10 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
18 | Spare Part of EJ-502-02 | 10 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
19 | Spare Part of EJ-509-01 | 10 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
20 | Spare Part of EJ-517-01 | 10 | Bolt & Nuts 1/2"(M14) x80 | - | 2 | Set | - | - | - | - | 2
21 | Spare Part of EJ-501-01 | 11 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
22 | Spare Part of EJ-502-02 | 11 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
23 | Spare Part of EJ-509-01 | 11 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
24 | Spare Part of EJ-517-01 | 11 | Bolt & Nuts 3/4"(M20) x110 | - | 2 | Set | - | - | - | - | 2
Package No. 3: Wooden Box, 177cm x 44cm x 60cm, 100 Kg (75 Kg)
# | Group | Mark No. | Description | Size | PL Quantity | Unit | Shortage | Overage | Damage | Incorrect | Accepted | Action Code | Remark
1 | Main Item | EJ-502-01 | Evacuation Ejector | - | 1 | Set | - | - | - | - | 1
2 | Commissioning Spare Part of EJ-502-01 | 12 | Gasket Spiral Wound 2"300# | - | 1 | Piece | - | - | - | - | 1
3 | Commissioning Spare Part of EJ-502-01 | 13 | Gasket Spiral Wound 4"300# | - | 2 | Piece | - | - | - | - | 2
4 | Commissioning Spare Part of EJ-502-01 | 14 | Bolt & Nuts 5/8"(M16) x80 | - | 4 | Set | - | - | - | - | 4
5 | Commissioning Spare Part of EJ-502-01 | 15 | Bolt & Nuts 3/4"(M20) x130 | - | 2 | Set | - | - | - | - | 2
Package No. 4: Wooden Box, 38cm x 30cm x 10cm, 3 Kg (1.8 Kg)
# | Group | Mark No. | Description | Size | PL Quantity | Unit | Shortage | Overage | Damage | Incorrect | Accepted | Action Code | Remark
1 | Spare Part of EJ-502-01 | 16 | Gasket KLINGRITE C-4400 | - | 2 | Piece | 2 | - | - | - | 0 | Advise Vendor of Overage/Shortage
2 | Spare Part of EJ-502-01 | 17 | Gasket Spiral Wound 2"300# | - | 2 | Piece | - | - | - | - | 2
3 | Spare Part of EJ-502-01 | 18 | Gasket Spiral Wound 4"300# | - | 2 | Piece | - | - | - | - | 2
4 | Spare Part of EJ-502-01 | 19 | Bolt & Nuts 5/8"(M16) x80 | - | 4 | Set | - | - | - | - | 4
5 | Spare Part of EJ-502-01 | 20 | Bolt & Nuts 3/4"(M20) x130 | - | 2 | Set | - | - | - | - | 2
Package No. 5: Wooden Box, 38cm x 30cm x 10cm, 3 Kg (1.8 Kg)
# | Group | Mark No. | Description | Size | PL Quantity | Unit | Shortage | Overage | Damage | Incorrect | Accepted | Action Code | Remark
1 | Sub Item of EJ-502-01 | 21 | SI-502-01 | - | 1 | Set | - | - | - | - | 1
2 | Commissioning Spare Part of EJ-502-01 | 22 | Gasket Spiral Wound 1"300# | - | 1 | Piece | - | - | - | - | 1
3 | Commissioning Spare Part of EJ-502-01 | 23 | Gasket Spiral Wound 4"300# | - | 2 | Piece | - | - | - | - | 2
4 | Commissioning Spare Part of EJ-502-01 | 24 | Bolt & Nuts 5/8"(M16) x90 | - | 2 | Set | - | - | - | - | 2
5 | Commissioning Spare Part of EJ-502-01 | 25 | Bolt & Nuts 3/4"(M20) x130 | - | 2 | Set | - | - | - | - | 2
Package No. 6: Wooden Box, 18cm x 18cm x 7cm, 1 Kg (0.5 Kg)
# | Group | Mark No. | Description | Size | PL Quantity | Unit | Shortage | Overage | Damage | Incorrect | Accepted | Action Code | Remark
1 | Spare Part of EJ-502-01 | 22 | Gasket Spiral Wound 1"300# | - | 2 | Piece | - | - | - | - | 2
2 | Spare Part of EJ-502-01 | 23 | Gasket Spiral Wound 4"300# | - | 4 | Piece | - | - | - | - | 4
3 | Spare Part of EJ-502-01 | 24 | Bolt & Nuts 5/8"(M16) x90 | - | 2 | Set | - | - | - | - | 2
4 | Spare Part of EJ-502-01 | 25 | Bolt & Nuts 3/4"(M20) x130 | - | 2 | Set | - | - | - | - | 2