## کنترل قرارداد (1)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [8 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [8 empty] | تاریخ تهیه گزارش: 1401/06/28
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده | درصد کالای دریافتی | مبلغ کل (یورو) | فاکتور
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0% | 0 | 36 | 36 | 38.772
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 100% | 33.176 | 4 | -18 | 6.032
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 100% | 3.4455 | 112 | 110.5 | 257.264
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 100% | 1790.142 | 30 | -1528 | 34.47
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 100% | 211.0675 | 54 | -68.5 | 93.042
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 100% | 10.98 | 14 | 9.5 | 34.16
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0% | 0 | 10 | 10 | 11.92
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0% | 0 | 6 | 6 | 10.77
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 100% | 9.296 | 12 | 8.5 | 31.872
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0% | 0 | 10 | 10 | 15.08
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0% | 0 | 10 | 10 | 21.04
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0% | 0 |  | 0 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 5.475% | 173.69 | 3 | -107 | 4.737
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0% | 0 | 8 | 8 | 19.52
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 100% | 123.825 | 2 | -35.5 | 6.604
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0% | 0 | 4 | 4 | 16.94
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 49.12% | 1238.55 | 53 | -522 | 114.162
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 100% | 1914.863 | 6 | -614.5 | 18.516
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 0% | 0 | 4 | 4 | 16.296
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0% | 0 | 465 | 465 | 1160.64
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0% | 0 | 97 | 97 | 348.133
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0% | 0 | 12 | 12 | 56.844
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0% | 0 | 3 | 3 | 17.868
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 100% | 459.888
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0% | 0
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 | 6.315 | 306.2775 | 48.5 | 100% | 306.2775
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 100% | 2901.962
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 97.73% | 4227.76
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 | 6.315 | 808.32 | 0 | 0% | 0
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 | 15.892 | 2097.744 | 0 | 0% | 0
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0% | 0
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 178.5 | 7.751 | 1383.5535 | 84 | 47.06% | 651.084
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0% | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0% | 0
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 187 | 7.751 | 1449.437 | 0 | 0% | 0
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 0% | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0% | 0
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 102.5 | 9.329 | 956.2225 | 0 | 0% | 0
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 0% | 0
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 100% | 2944.944
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 241 | 9.329 | 2248.289 | 0 | 0% | 0
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 0% | 0
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 177.5 | 9.329 | 1655.8975 | 0 | 0% | 0
44 |  | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 0% | 0
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 0% | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 0% | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 0% | 0
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1007.6 | 17.508 | 17641.0608 | 0 | 0% | 0
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 0% | 0
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 0% | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 0% | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 0% | 0
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 0% | 0
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 17.508 | 4025.0892 | 0 | 0% | 0
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 0% | 0
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 | 11.313 | 66402.7848 | 5869.6 | 100% | 66402.7848
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 100% | 104183.6796
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 100% | 40651.38
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0% | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 0% | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 0% | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 0% | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 0% | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 0% | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 0% | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 0% | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 0% | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 0% | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 0% | 0
70 | 4YYYYYE06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 0% | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 0% | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 100% | 26535
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 100% | 13000
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 100% | 5760
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 100% | 280
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 100% | 7920
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 100% | 4560
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 44.25% | 1911.6
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0% | 0
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 100% | 288
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 100% | 22260
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 100% | 1196.25
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 100% | 5498.75
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 100% | 1650
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 100% | 975
[6 empty] | 529403.5689 |  |  | 320073.3949
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 320073.3949 | کالاهای رسید شده با شماره مرجع MRS--JAY-098-001 الی MRS-JAY-098-009 در این مرحله صورتحساب شده است که تماما در بازه مجاز قرارداد به انبار رسید شده است لذا مشمول جریمه تاخیر نمی باشد.
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 28806.6055
جمع صورتحسابها | [5 empty] | 348880.0004
کسور:
استهلاک پیش پرداخت (30%) | [5 empty] | 96022.0185
جمع کسور | [5 empty] | 96022.0185
خالص قابل پرداخت | [5 empty] | 252857.982

## کنترل قرارداد (2)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [10 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [10 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [10 empty] | تاریخ تهیه گزارش: 1401/07/21
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | فاکتور
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0 | 0 | 0% | 0 | 36 | 36 | 38.772 |  |  |  | -298.8675
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 0 | 22 | 100% | 33.176 | 4 | -18 | 6.032 |  |  |  | 0
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 0 | 1.5 | 100% | 3.4455 | 112 | 110.5 | 257.264 |  |  |  | 0
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 0 | 1558 | 100% | 1790.142 | 30 | -1528 | 34.47 |  |  |  | 0
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 0 | 122.5 | 100% | 211.0675 | 54 | -68.5 | 93.042 |  |  |  | 0
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 0 | 4.5 | 100% | 10.98 | 14 | 9.5 | 34.16 |  |  |  | 0
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0 | 0 | 0% | 0 | 10 | 10 | 11.92 |  |  |  | -1316.564
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0 | 0 | 0% | 0 | 6 | 6 | 10.77 |  |  |  | -580.6825
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 0 | 3.5 | 100% | 9.296 | 12 | 8.5 | 31.872 |  |  |  | 0
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0 | 0 | 0% | 0 | 10 | 10 | 15.08 |  |  |  | -2559.83
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0 | 0 | 0% | 0 | 10 | 10 | 21.04 |  |  |  | -275.624
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 |  |  |  | -4.4145
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 0 | 110 | 5.475% | 173.69 | 3 | -107 | 4.737 |  |  |  | -2998.521
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0 | 0 | 0% | 0 | 8 | 8 | 19.52 |  |  |  | -2332.64
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 0 | 37.5 | 100% | 123.825 | 2 | -35.5 | 6.604 |  |  |  | 0
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0 | 0 | 0% | 0 | 4 | 4 | 16.94 |  |  |  | -6.3525
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 0 | 575 | 49.12% | 1238.55 | 53 | -522 | 114.162 |  |  |  | -1282.707
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 0 | 620.5 | 100% | 1914.863 | 6 | -614.5 | 18.516 |  |  |  | 0
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 139 | 139 | 100% | 566.286 | 4 | 4 | 16.296 |  |  |  | 0
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0 | 0 | 0% | 0 | 465 | 465 | 1160.64 |  |  |  | -189.696
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0 | 0 | 0% | 0 | 97 | 97 | 348.133 |  |  |  | -3660.78
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0 | 0 | 0% | 0 | 12 | 12 | 56.844 |  |  |  | -632.3895
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0 | 0 | 0% | 0 | 3 | 3 | 17.868 |  |  |  | -407.986
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 0 | 132 | 100% | 459.888 | [6 empty] | 0
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -7219.96
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 | 6.315 | 306.2775 | 48.5 | 0 | 48.5 | 100% | 306.2775 | [6 empty] | 0
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 0 | 371 | 100% | 2901.962 | [6 empty] | 0
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 0 | 430 | 97.73% | 4227.76 | [6 empty] | -98.32
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 | 6.315 | 808.32 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -808.32
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 | 15.892 | 2097.744 | 0 | 132 | 132 | 100% | 2097.744 | [6 empty] | 0
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -43.39
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 178.5 | 7.751 | 1383.5535 | 84 | 0 | 84 | 47.06% | 651.084 | [6 empty] | -732.4695
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -3296.256
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -2749.614
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 187 | 7.751 | 1449.437 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -1449.437
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 223 | 223 | 100% | 3543.916 | [6 empty] | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -205.36
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 102.5 | 9.329 | 956.2225 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -956.2225
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 155 | 155 | 27.03% | 1746.385 | [6 empty] | -4715.2395
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 0 | 216 | 100% | 2944.944 | [6 empty] | 0
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 241 | 9.329 | 2248.289 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -2248.289
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 328 | 328 | 100% | 5212.576 | [6 empty] | 0
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 177.5 | 9.329 | 1655.8975 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -1655.8975
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 253 | 253 | 100% | 4225.1 | [6 empty] | 0
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 1.1 | 1.1 | 100% | 11.9768 | [6 empty] | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 5.5 | 5.5 | 100% | 42.9055 | [6 empty] | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 87.78 | 87.78 | 100% | 1394.9998 | [6 empty] | 0
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1007.6 | 17.508 | 17641.0608 | 0 | 1237.5 | 1237.5 | 122.8% | 21666.15 | [6 empty] | 4025.0892
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 1310.1 | 1310.1 | 100% | 23995.7916 | [6 empty] | 0
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 1243 | 1243 | 100% | 23771.132 | [6 empty] | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 403.7 | 403.7 | 100% | 8046.5484 | [6 empty] | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 822.8 | 822.8 | 100% | 17064.872 | [6 empty] | 2.3579e-12
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 11.88 | 11.88 | 100% | 255.9902 | [6 empty] | 0
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 17.508 | 4025.0892 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -4025.0892
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 229.9 | 229.9 | 100% | 4210.8484 | [6 empty] | -5.2057e-13
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 | 11.313 | 66402.7848 | 5869.601 | 0 | 5869.601 | 100% | 66402.7961 | [6 empty] | 0.011313
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 0 | 6906.9 | 100% | 104183.6796 | [6 empty] | 0
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 0 | 2156 | 100% | 40651.38 | [6 empty] | 0
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0 | 0 | 0% | 0 | [6 empty] | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 1.1 | 1.1 | 100% | 6.9751 | [6 empty] | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 20.9 | 20.9 | 100% | 145.255 | [6 empty] | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 8.8 | 8.8 | 100% | 84.7176 | [6 empty] | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 1.1 | 1.1 | 100% | 15.9104 | [6 empty] | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 2.2 | 2.2 | 100% | 26.4528 | [6 empty] | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 908.6 | 908.6 | 100% | 10078.1912 | [6 empty] | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 193.6 | 193.6 | 100% | 2831.5936 | [6 empty] | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 85.8 | 85.8 | 100% | 1812.3534 | [6 empty] | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 34.1 | 34.1 | 100% | 858.7744 | [6 empty] | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 38.5 | 38.5 | 100% | 1290.2505 | [6 empty] | 0
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 125.4 | 125.4 | 100% | 7028.9208 | [6 empty] | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 39.6 | 39.6 | 100% | 1769.328 | [6 empty] | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 0 | 43500 | 100% | 26535 | [6 empty] | 0
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 0 | 13000 | 100% | 13000 | [6 empty] | 0
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 0 | 72000 | 100% | 5760 | [6 empty] | 0
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 0 | 3500 | 100% | 280 | [6 empty] | 0
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 0 | 120000 | 100% | 7920 | [6 empty] | 0
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 0 | 80000 | 100% | 4560 | [6 empty] | 0
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 0 | 53100 | 44.25% | 1911.6 | [6 empty] | -2408.4
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0 | 0 | 0% | 0 | [6 empty] | -20394
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 0 | 3200 | 100% | 288 | [6 empty] | 0
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 0 | 106000 | 100% | 22260 | [6 empty] | 0
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 0 | 75 | 100% | 1196.25 | [6 empty] | 0
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 0 | 2075 | 100% | 5498.75 | [6 empty] | 0
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 0 | 550 | 100% | 1650 | [6 empty] | 0
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 0 | 750 | 100% | 975 | [6 empty] | 0
[6 empty] | 529403.5689 |  |  |  |  | 463875.3507 | [6 empty] | -65528.2182
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 463875.3507 | صورتحسابهای مرحله اول: MRS-JAY-098-009 الی MRS-JAY-098-001 صورتحسابهای مرحله دوم: MRS-JAY-098-018 الی MRS-JAY-098-010 تاریخ انعقاد قرارداد: 1401/04/22 تاریخ شروع قرارداد برابر با تاریخ ابلاغ قرارداد: 1401/04/26 تاریخ پیش پرداخت: 1401/05/09 مدت قرارداد: 60 روز تقویمی پیش از شروع قرارداد (تاخیر در پرداخت پیش پرداخت به مدت زمان تحویل اضافه می شود) سر رسید تاریخ تحویل (با توجه به توضیحات فوق): 1401/07/07 با توجه به استعلام اخذ شده از واحد برنامه ریزی، تاخیر در ارسال پارت دوم با هماهنگی خریدار و تحویل طی بازه های اعلامی توسط خریدار بوده است.
کسر می شود: کالای صورتحساب شده طی مراحل قبلی | [5 empty] | 320073.3949
جمع کالای دریافتی طی مرحله دوم | [5 empty] | 143801.9558
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 12942.18 | [8 empty] | 12942.176 | 12942.18 | 0.0039768
جمع صورتحسابهای مرحله دوم | [5 empty] | 156744.1358
کسور:
استهلاک پیش پرداخت (30%) | [5 empty] | 43140.5867
جمع کسور | [5 empty] | 43140.5867
خالص قابل پرداخت | [5 empty] | 113603.5491

## کنترل قرارداد (3&4)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [12 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [12 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [12 empty] | تاریخ تهیه گزارش: 1401/11/17
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | مقادیر رسید شده مرحله سوم | مقادیر رسید شده مرحله چهارم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | مازاد بر قرارداد و الحاقیه
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0 | 0 | 277.5 | 277.5 | 100% | 298.8675 | 0
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 0 | 0 | 0 | 22 | 100% | 33.176 | 0
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 0 | 0 | 0 | 1.5 | 100% | 3.4455 | 0
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 0 | 0 | 0 | 1558 | 100% | 1790.142 | 0
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 0 | 0 | 0 | 122.5 | 100% | 211.0675 | 0
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 0 | 0 | 0 | 4.5 | 100% | 10.98 | 0
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0 | 1104.5 | 0 | 1104.5 | 100% | 1316.564 | 0
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0 | 0 | 323.5 | 323.5 | 100% | 580.6825 | 0
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 0 | 0 | 0 | 3.5 | 100% | 9.296 | 0
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0 | 0 | 1697.5 | 1697.5 | 100% | 2559.83 | 0
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0 | 131 | 0 | 131 | 100% | 275.624 | 0
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0 | 0 | 1.5 | 1.5 | 100% | 4.4145 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 0 | 1782 | 117 | 2009 | 100% | 3172.211 | 0
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0 | 636 | 320 | 956 | 100% | 2332.64 | 0
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 0 | 0 | 0 | 37.5 | 100% | 123.825 | 0
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0 | 0 | 1.5 | 1.5 | 100% | 6.3525 | 0
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 0 | 96 | 499.5 | 1170.5 | 100% | 2521.257 | 0
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 0 | 0 | 0 | 620.5 | 100% | 1914.863 | 0
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 139 | 0 | 0 | 139 | 100% | 566.286 | 0
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0 | 76 | 0 | 76 | 100% | 189.696 | 0
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0 | 921 | 99 | 1020 | 100% | 3660.78 | 0
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0 | 45 | 88.5 | 133.5 | 100% | 632.3895 | 0
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0 | 0 | 68.5 | 68.5 | 100% | 407.986 | 0
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 0 | 0 | 0 | 132 | 100% | 459.888 | 0
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0 | 0 | 1479.5 | 1479.5 | 100% | 7219.96 | 0
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 | 6.315 | 306.2775 | 48.5 | 0 | 0 | 0 | 48.5 | 100% | 306.2775 | 0
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 0 | 0 | 0 | 371 | 100% | 2901.962 | 0
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 0 | 0 | 10 | 440 | 100% | 4326.08 | 0
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 | 6.315 | 808.32 | 0 | 0 | 128 | 0 | 128 | 100% | 808.32 | 0
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 | 15.892 | 2097.744 | 0 | 132 | 0 | 579 | 711 | 538.6% | 11299.212 | -9201.468
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0 | 10 | 0 | 10 | 100% | 43.39 | 0
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 365.5 | 7.751 | 2832.9905 | 84 | 0 | 138.5 | 143 | 365.5 | 100% | 2832.9905 | 0
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0 | 0 | 348 | 348 | 100% | 3296.256 | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0 | 0 | 238 | 238 | 100% | 2749.614 | 0
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 7.751 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 223 | 0 | 0 | 223 | 100% | 3543.916 | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0 | 0 | 40 | 40 | 100% | 205.36 | 0
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 521 | 9.329 | 4860.409 | 0 | 0 | 0 | 521 | 521 | 100% | 4860.409 | 0
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 155 | 0 | 418 | 573 | 99.91% | 6455.991 | 5.6335
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 0 | 0 | 0 | 216 | 100% | 2944.944 | 0
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 9.329 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 328 | 0 | 24 | 352 | 107.3% | 5593.984 | -381.408
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 9.329 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 253 | 0 | 0 | 253 | 100% | 4225.1 | 0
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 1.1 | 0 | 0 | 1.1 | 100% | 11.9768 | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 5.5 | 0 | 0 | 5.5 | 100% | 42.9055 | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 87.78 | 0 | 0 | 87.78 | 100% | 1394.9998 | 0
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1237.5 | 17.508 | 21666.15 | 0 | 1237.5 | 0 | 241.2 | 1478.7 | 119.5% | 25889.0796 | -4222.9296
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 1310.1 | 0 | 153.6 | 1463.7 | 111.7% | 26809.1292 | -2813.3376
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 1243 | 0 | 0 | 1243 | 100% | 23771.132 | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 403.7 | 0 | 0 | 403.7 | 100% | 8046.5484 | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 822.8 | 0 | 211 | 1033.8 | 125.6% | 21441.012 | -4376.14
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 11.88 | 0 | 0 | 11.88 | 100% | 255.9902 | 0
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 0 | 17.508 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 229.9 | 0 | 280.8 | 510.7 | 222.1% | 9353.9812 | -5143.1328
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 | 11.313 | 66402.7848 | 5869.601 | 0 | 0 | 0 | 5869.601 | 100% | 66402.7961 | -0.011313
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 0 | 0 | 0 | 6906.9 | 100% | 104183.6796 | 0
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 0 | 0 | 0 | 2156 | 100% | 40651.38 | 0
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 1.1 | 0 | 0 | 1.1 | 100% | 6.9751 | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 20.9 | 0 | 0 | 20.9 | 100% | 145.255 | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 8.8 | 0 | 0 | 8.8 | 100% | 84.7176 | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 1.1 | 0 | 0 | 1.1 | 100% | 15.9104 | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 2.2 | 0 | 0 | 2.2 | 100% | 26.4528 | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 908.6 | 0 | 0 | 908.6 | 100% | 10078.1912 | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 193.6 | 0 | 0 | 193.6 | 100% | 2831.5936 | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 85.8 | 0 | 0 | 85.8 | 100% | 1812.3534 | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 34.1 | 0 | 0 | 34.1 | 100% | 858.7744 | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 38.5 | 0 | 0 | 38.5 | 100% | 1290.2505 | 0
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 125.4 | 0 | 0 | 125.4 | 100% | 7028.9208 | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 39.6 | 0 | 0 | 39.6 | 100% | 1769.328 | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 0 | 0 | 0 | 43500 | 100% | 26535 | 0
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 0 | 0 | 0 | 13000 | 100% | 13000 | 0
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 0 | 0 | 0 | 72000 | 100% | 5760 | 0
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 0 | 0 | 0 | 3500 | 100% | 280 | 0
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 0 | 0 | 0 | 120000 | 100% | 7920 | 0
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 0 | 0 | 0 | 80000 | 100% | 4560 | 0
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 0 | 66900 | 0 | 120000 | 100% | 4320 | 0
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0 | 3090 | 750 | 3840 | 124.3% | 25344 | -4950
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 0 | 0 | 0 | 3200 | 100% | 288 | 0
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 0 | 0 | 0 | 106000 | 100% | 22260 | 0
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 0 | 0 | 0 | 75 | 100% | 1196.25 | 0
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 0 | 0 | 0 | 2075 | 100% | 5498.75 | 0
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 0 | 0 | 0 | 550 | 100% | 1650 | 0
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 0 | 0 | 0 | 750 | 100% | 975 | 0
[6 empty] | 529403.5689 | 517019.001 | 8042.96 | 75058 | 8931.1 |  |  | 560486.3627 | -31082.7938
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 560486.3627 | صورتحسابهای مرحله اول: MRS-JAY-098-001 الی MRS-JAY-098-009 صورتحسابهای مرحله دوم: MRS-JAY-098-010 الی MRS-JAY-098-018 صورتحسابهای مرحله سوم: MRS-JAY-098-019 الی MRS-JAY-098-025 صورتحسابهای مرحله چهارم: MRS-JAY-098-26 الی MRS-JAY-098-046 صورتحسابهای مرحله سوم به واحد مالی تحویل نشده است و محاسبات فوق با فرض عدم تسویه پارت سوم صورت گرفته است. تاریخ انعقاد قرارداد: 1401/04/22 تاریخ شروع قرارداد برابر با تاریخ ابلاغ قرارداد: 1401/04/26 تاریخ پیش پرداخت: 1401/05/09 مدت قرارداد: 60 روز تقویمی پیش از شروع قرارداد (تاخیر در پرداخت پیش پرداخت به مدت زمان تحویل اضافه می شود) سر رسید تاریخ تحویل (با توجه به توضیحات فوق): 1401/07/07 با توجه به استعلام اخذ شده از واحد برنامه ریزی، تاخیرها در ارسال اقلام با هماهنگی خریدار و تحویل طی بازه های اعلامی توسط خریدار بوده است. همچنین جمعا مبلغ 31.082/79 یورو بیشتر از سقف قرارداد کالا ارسال شده است که که مربوط به ردیف های هایلایت شده می باشد.لازم به توضیح است برخی مقادیر در مقادیر 80mm و 50mm و فی یکسان تهاتر گردید.ولیکن ردیفهای زرد رنگ از قرارداد و الحاقیه مازاد ارسال شده است.
کسر می شود: کالای صورتحساب شده طی مراحل قبلی | [5 empty] | 463875.3507
جمع کالای دریافتی طی مراحل سوم و چهارم | [5 empty] | 96611.012
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 8694.9911 | [8 empty] | 12942.176 | 12942.18 | 0.0039768
جمع کل باقیمانده | [5 empty] | 105306.0031
جمع صورتحسابهای مرحله سوم | [5 empty] | 34626.482
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 3116.3834 | [8 empty] | 12942.176 | 12942.18 | 0.0039768
کسور: | [5 empty] | 37742.8654
استهلاک پیش پرداخت (باقیمانده) | [5 empty] | -10387.9446
27354.9208
جمع صورتحسابهای مرحله چهارم | [5 empty] | 61984.53
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 5578.6077 | [8 empty] | 12942.176 | 12942.18 | 0.0039768
کسور: | [5 empty] | 67563.1377
استهلاک پیش پرداخت (باقیمانده) | [5 empty] | -9270.3854
جمع کسور | [5 empty] | 58292.7523
خالص قابل پرداخت (با فرض اینکه پارت سوم تسویه نشده است) | [5 empty] | 85647.6731

## کنترل قرارداد (5)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [13 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [13 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [13 empty] | تاریخ تهیه گزارش: 1402/02/19
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | مقادیر رسید شده مرحله سوم | مقادیر رسید شده مرحله چهارم | مقادیر رسید شده مرحله پنجم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | مازاد بر قرارداد و الحاقیه
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0 | 0 | 277.5 | 0 | 277.5 | 100% | 298.8675 | 0
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 0 | 0 | 0 | 0 | 22 | 100% | 33.176 | 0
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 100% | 3.4455 | 0
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 0 | 0 | 0 | 0 | 1558 | 100% | 1790.142 | 0
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 0 | 0 | 0 | 0 | 122.5 | 100% | 211.0675 | 0
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 0 | 0 | 0 | 0 | 4.5 | 100% | 10.98 | 0
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0 | 1104.5 | 0 | 3000 | 4104.5 | 371.6% | 4892.564 | -3576
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0 | 0 | 323.5 | 0 | 323.5 | 100% | 580.6825 | 0
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 0 | 0 | 0 | 0 | 3.5 | 100% | 9.296 | 0
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0 | 0 | 1697.5 | 0 | 1697.5 | 100% | 2559.83 | 0
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0 | 131 | 0 | 0 | 131 | 100% | 275.624 | 0
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0 | 0 | 1.5 | 0 | 1.5 | 100% | 4.4145 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 0 | 1782 | 117 | 0 | 2009 | 100% | 3172.211 | 0
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0 | 636 | 320 | 720 | 1676 | 175.3% | 4089.44 | -1756.8
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 100% | 123.825 | 0
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0 | 0 | 1.5 | 0 | 1.5 | 100% | 6.3525 | 0
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 0 | 96 | 499.5 | 0 | 1170.5 | 100% | 2521.257 | 0
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 0 | 0 | 0 | 0 | 620.5 | 100% | 1914.863 | 0
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 139 | 0 | 0 | 0 | 139 | 100% | 566.286 | 0
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0 | 76 | 0 | 0 | 76 | 100% | 189.696 | 0
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0 | 921 | 99 | 0 | 1020 | 100% | 3660.78 | 0
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0 | 45 | 88.5 | 0 | 133.5 | 100% | 632.3895 | 0
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0 | 0 | 68.5 | 0 | 68.5 | 100% | 407.986 | 0
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 0 | 0 | 0 | 0 | 132 | 100% | 459.888 | 0
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0 | 0 | 1479.5 | 0 | 1479.5 | 100% | 7219.96 | 0
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 | 6.315 | 306.2775 | 48.5 | 0 | 128 | 0 | 0 | 176.5 | 363.9% | 1114.5975 | -808.32
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 0 | 0 | 0 | 0 | 371 | 100% | 2901.962 | 0
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 0 | 0 | 10 | 0 | 440 | 100% | 4326.08 | 0
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 | 6.315 | 808.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 808.32
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 | 15.892 | 2097.744 | 0 | 132 | 0 | 579 | 0 | 711 | 538.6% | 11299.212 | -9201.468
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0 | 10 | 0 | 0 | 10 | 100% | 43.39 | 0
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 178.5 | 7.751 | 1383.5535 | 84 | 0 | 138.5 | 143 | 300 | 665.5 | 372.8% | 5158.2905 | -3774.737
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0 | 0 | 348 | 0 | 348 | 100% | 3296.256 | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0 | 0 | 238 | 0 | 238 | 100% | 2749.614 | 0
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 187 | 7.751 | 1449.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 1449.437
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 223 | 0 | 0 | 0 | 223 | 100% | 3543.916 | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0 | 0 | 40 | 0 | 40 | 100% | 205.36 | 0
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 102.5 | 9.329 | 956.2225 | 0 | 0 | 0 | 521 | 0 | 521 | 508.3% | 4860.409 | -3904.1865
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 155 | 0 | 418 | 0 | 573 | 99.91% | 6455.991 | 5.6335
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 0 | 0 | 0 | 0 | 216 | 100% | 2944.944 | 0
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 241 | 9.329 | 2248.289 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 2248.289
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 328 | 0 | 24 | 0 | 352 | 107.3% | 5593.984 | -381.408
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 177.5 | 9.329 | 1655.8975 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 1655.8975
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 253 | 0 | 0 | 700 | 953 | 376.7% | 15915.1 | -11690
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 1.1 | 0 | 0 | 0 | 1.1 | 100% | 11.9768 | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 5.5 | 0 | 0 | 0 | 5.5 | 100% | 42.9055 | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 87.78 | 0 | 0 | 0 | 87.78 | 100% | 1394.9998 | 0
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1007.6 | 17.508 | 17641.0608 | 0 | 1237.5 | 0 | 241.2 | 0 | 1478.7 | 146.8% | 25889.0796 | -8248.0188
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 1310.1 | 0 | 153.6 | 0 | 1463.7 | 111.7% | 26809.1292 | -2813.3376
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 1243 | 0 | 0 | 0 | 1243 | 100% | 23771.132 | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 403.7 | 0 | 0 | 0 | 403.7 | 100% | 8046.5484 | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 822.8 | 0 | 211 | 0 | 1033.8 | 125.6% | 21441.012 | -4376.14
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 11.88 | 0 | 0 | 0 | 11.88 | 100% | 255.9902 | 0
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 17.508 | 4025.0892 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 4025.0892
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 229.9 | 0 | 280.8 | 0 | 510.7 | 222.1% | 9353.9812 | -5143.1328
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 | 11.313 | 66402.7848 | 5869.6 | 0 | 0 | 0 | 0 | 5869.6 | 100% | 66402.7848 | 0
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 0 | 0 | 0 | 0 | 6906.9 | 100% | 104183.6796 | 0
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 0 | 0 | 0 | 0 | 2156 | 100% | 40651.38 | 0
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 1.1 | 0 | 0 | 0 | 1.1 | 100% | 6.9751 | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 20.9 | 0 | 0 | 0 | 20.9 | 100% | 145.255 | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 8.8 | 0 | 0 | 0 | 8.8 | 100% | 84.7176 | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 1.1 | 0 | 0 | 0 | 1.1 | 100% | 15.9104 | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 2.2 | 0 | 0 | 0 | 2.2 | 100% | 26.4528 | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 908.6 | 0 | 0 | 0 | 908.6 | 100% | 10078.1912 | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 193.6 | 0 | 0 | 0 | 193.6 | 100% | 2831.5936 | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 85.8 | 0 | 0 | 0 | 85.8 | 100% | 1812.3534 | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 34.1 | 0 | 0 | 0 | 34.1 | 100% | 858.7744 | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 38.5 | 0 | 0 | 0 | 38.5 | 100% | 1290.2505 | 0
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 125.4 | 0 | 0 | 0 | 125.4 | 100% | 7028.9208 | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 39.6 | 0 | 0 | 0 | 39.6 | 100% | 1769.328 | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 0 | 0 | 0 | 0 | 43500 | 100% | 26535 | 0
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 0 | 0 | 0 | 0 | 13000 | 100% | 13000 | 0
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 0 | 0 | 0 | 0 | 72000 | 100% | 5760 | 0
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 0 | 0 | 0 | 0 | 3500 | 100% | 280 | 0
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 0 | 0 | 0 | 0 | 120000 | 100% | 7920 | 0
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 0 | 0 | 0 | 0 | 80000 | 100% | 4560 | 0
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 0 | 66900 | 0 | 0 | 120000 | 100% | 4320 | 0
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0 | 3090 | 750 | 0 | 3840 | 124.3% | 25344 | -4950
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 0 | 0 | 0 | 0 | 3200 | 100% | 288 | 0
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 0 | 0 | 0 | 0 | 106000 | 100% | 22260 | 0
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 0 | 0 | 0 | 0 | 75 | 100% | 1196.25 | 0
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 0 | 0 | 0 | 0 | 2075 | 100% | 5498.75 | 0
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 0 | 0 | 0 | 0 | 550 | 100% | 1650 | 0
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 0 | 0 | 0 | 0 | 750 | 100% | 975 | 0
|  |  |  | 606812.96 |  | 529403.5689 | 517019 | 8042.96 | 75058 | 8931.1 | 4720 |  |  | 579834.4514 | -50430.8825
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 579834.4514 | صورتحسابهای مرحله اول: MRS-JAY-098-001 الی MRS-JAY-098-009 صورتحسابهای مرحله دوم: MRS-JAY-098-010 الی MRS-JAY-098-018 صورتحسابهای مرحله سوم: MRS-JAY-098-019 الی MRS-JAY-098-025 صورتحسابهای مرحله چهارم: MRS-JAY-098-26 الی MRS-JAY-098-046 صورتحسابهای مرحله پنجم: MRS-JAY-098-47وMRS-JAY-098-48 و MRS-JAY-098-051 و MRS-JAY-098-052 و MRS-JAY-098-054 و MRS-JAY-098-055 تاریخ انعقاد قرارداد: 1401/04/22 تاریخ شروع قرارداد برابر با تاریخ ابلاغ قرارداد: 1401/04/26 تاریخ پیش پرداخت: 1401/05/09 مدت قرارداد: 60 روز تقویمی پیش از شروع قرارداد (تاخیر در پرداخت پیش پرداخت به مدت زمان تحویل اضافه می شود) سر رسید تاریخ تحویل (با توجه به توضیحات فوق): 1401/07/07 با توجه به استعلام اخذ شده از واحد برنامه ریزی، تاخیرها در ارسال اقلام با هماهنگی خریدار و تحویل طی بازه های اعلامی توسط خریدار بوده است. همچنین جمعا مبلغ 60،624.90 یورو بیشتر از سقف قرارداد کالا ارسال شده است که که مربوط به ردیف های هایلایت شده می باشد. .
کسر می شود: کالای صورتحساب شده طی مراحل قبلی | [5 empty] | 560486.3627
جمع کالای دریافتی طی مرحله پنجم | [5 empty] | 19348.0887
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 1741.328 | [9 empty] | 12942.176 | 12942.18 | 0.0039768
جمع کل باقیمانده | [5 empty] | 21089.4167
جمع صورتحسابهای مرحله پنجم | [5 empty] | 19348.0987
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 1741.3289 | [9 empty] | 12942.176 | 12942.18 | 0.0039768
کسور: | [5 empty] | 21089.4276
استهلاک پیش پرداخت (باقیمانده) | [5 empty] | 0
خالص قابل پرداخت | [5 empty] | 21089.4276

## کنترل قرارداد (6)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [14 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [14 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [14 empty] | تاریخ تهیه گزارش: 1402/02/19
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | مقادیر رسید شده مرحله سوم | مقادیر رسید شده مرحله چهارم | مقادیر رسید شده مرحله پنجم | مقادیر رسید شده مرحله ششم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | مازاد بر قرارداد و الحاقیه
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0 | 0 | 277.5 | 0 | 0 | 277.5 | 100% | 298.8675 | 0
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 100% | 33.176 | 0
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 100% | 3.4455 | 0
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 0 | 0 | 0 | 0 | 0 | 1558 | 100% | 1790.142 | 0
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 0 | 0 | 0 | 0 | 0 | 122.5 | 100% | 211.0675 | 0
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 0 | 0 | 0 | 0 | 0 | 4.5 | 100% | 10.98 | 0
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0 | 1104.5 | 0 | 3000 | 0 | 4104.5 | 371.6% | 4892.564 | -3576 | 3576 | 0
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0 | 0 | 323.5 | 0 | 0 | 323.5 | 100% | 580.6825 | 0
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 0 | 0 | 0 | 0 | 0 | 3.5 | 100% | 9.296 | 0
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0 | 0 | 1697.5 | 0 | 0 | 1697.5 | 100% | 2559.83 | 0
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0 | 131 | 0 | 0 | 0 | 131 | 100% | 275.624 | 0
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 100% | 4.4145 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 0 | 1782 | 117 | 0 | 0 | 2009 | 100% | 3172.211 | 0
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0 | 636 | 320 | 720 | 0 | 1676 | 175.3% | 4089.44 | -1756.8 | 1756.8 | 0
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 0 | 0 | 0 | 0 | 0 | 37.5 | 100% | 123.825 | 0
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 100% | 6.3525 | 0
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 0 | 96 | 499.5 | 0 | 0 | 1170.5 | 100% | 2521.257 | 0
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 0 | 0 | 0 | 0 | 0 | 620.5 | 100% | 1914.863 | 0
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 139 | 0 | 0 | 0 | 0 | 139 | 100% | 566.286 | 0
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0 | 76 | 0 | 0 | 0 | 76 | 100% | 189.696 | 0
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0 | 921 | 99 | 0 | 0 | 1020 | 100% | 3660.78 | 0
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0 | 45 | 88.5 | 0 | 0 | 133.5 | 100% | 632.3895 | 0
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0 | 0 | 68.5 | 0 | 0 | 68.5 | 100% | 407.986 | 0
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 0 | 0 | 0 | 0 | 0 | 132 | 100% | 459.888 | 0
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0 | 0 | 1479.5 | 0 | 0 | 1479.5 | 100% | 7219.96 | 0
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 176.5 | 6.315 | 1114.5975 | 48.5 | 0 | 128 | 0 | 0 | 0 | 176.5 | 100% | 1114.5975 | 0
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 0 | 0 | 0 | 0 | 0 | 371 | 100% | 2901.962 | 0
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 0 | 0 | 10 | 0 | 0 | 440 | 100% | 4326.08 | 0
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 6.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 698.5 | 15.892 | 11100.562 | 0 | 132 | 0 | 579 | 0 | 0 | 711 | 101.8% | 11299.212 | -198.65 | 9201.468
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 100% | 43.39 | 0
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 651.5 | 7.751 | 5049.7765 | 84 | 0 | 138.5 | 143 | 300 | 0 | 665.5 | 102.1% | 5158.2905 | -108.514 | 2325.3 | 2216.786
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0 | 0 | 348 | 0 | 0 | 348 | 100% | 3296.256 | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0 | 0 | 238 | 0 | 0 | 238 | 100% | 2749.614 | 0
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 7.751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 223 | 0 | 0 | 0 | 0 | 223 | 100% | 3543.916 | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.504 | 5.134 | 17.9895 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 1142% | 205.36 | -187.3705
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 521 | 9.329 | 4860.409 | 0 | 0 | 0 | 521 | 0 | 0 | 521 | 100% | 4860.409 | 0
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 155 | 0 | 418.5 | 0 | 0 | 573.5 | 100% | 6461.6245 | 0
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 0 | 0 | 0 | 0 | 0 | 216 | 100% | 2944.944 | 0
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 9.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 | 15.892 | 5212.576 | 0 | 328 | 0 | 24 | 0 | 0 | 352 | 107.3% | 5593.984 | -381.408
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 9.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 253 | 0 | 0 | 700 | 0 | 953 | 376.7% | 15915.1 | -11690 | 11690 | 0
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 11.9768 | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 5.5 | 0 | 0 | 0 | 0 | 5.5 | 100% | 42.9055 | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 87.78 | 0 | 0 | 0 | 0 | 87.78 | 100% | 1394.9998 | 0
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1457.5 | 17.508 | 25517.91 | 0 | 1237.5 | 0 | 241.2 | 0 | 0 | 1478.7 | 101.5% | 25889.0796 | -371.1696
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 | 18.316 | 23995.7916 | 0 | 1310.1 | 0 | 153.6 | 0 | 0 | 1463.7 | 111.7% | 26809.1292 | -2813.3376
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 1243 | 0 | 0 | 0 | 0 | 1243 | 100% | 23771.132 | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 403.7 | 0 | 0 | 0 | 0 | 403.7 | 100% | 8046.5484 | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1033.8 | 20.74 | 21441.012 | 0 | 822.8 | 0 | 211 | 0 | 0 | 1033.8 | 100% | 21441.012 | -4.7157e-12
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 11.88 | 0 | 0 | 0 | 0 | 11.88 | 100% | 255.9902 | 0
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 0 | 17.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 342.1 | 18.316 | 6265.9036 | 0 | 229.9 | 0 | 280.8 | 0 | 0 | 510.7 | 149.3% | 9353.9812 | -3088.0776
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6198.5 | 11.313 | 70123.6305 | 5869.6 | 0 | 0 | 0 | 0 | 328.9 | 6198.5 | 100% | 70123.6305 | 0 | fls
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 7937.4 | 15.084 | 119727.7416 | 6906.9 | 0 | 0 | 0 | 0 | 1030.5 | 7937.4 | 100% | 119727.7416 | 0 | fls
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2281.4 | 18.855 | 43015.797 | 2156 | 0 | 0 | 0 | 0 | 125.4 | 2281.4 | 100% | 43015.797 | 0 | fls
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 6.9751 | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 20.9 | 0 | 0 | 0 | 0 | 20.9 | 100% | 145.255 | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 8.8 | 0 | 0 | 0 | 0 | 8.8 | 100% | 84.7176 | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 15.9104 | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 2.2 | 0 | 0 | 0 | 0 | 2.2 | 100% | 26.4528 | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 908.6 | 0 | 0 | 0 | 0 | 908.6 | 100% | 10078.1912 | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 193.6 | 0 | 0 | 0 | 0 | 193.6 | 100% | 2831.5936 | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 85.8 | 0 | 0 | 0 | 0 | 85.8 | 100% | 1812.3534 | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 34.1 | 0 | 0 | 0 | 0 | 34.1 | 100% | 858.7744 | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 38.5 | 0 | 0 | 0 | 0 | 38.5 | 100% | 1290.2505 | 0
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 125.4 | 0 | 0 | 0 | 0 | 125.4 | 100% | 7028.9208 | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 39.6 | 0 | 0 | 0 | 0 | 39.6 | 100% | 1769.328 | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 0 | 0 | 0 | 0 | 0 | 43500 | 100% | 26535 | 0
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 13000 | 100% | 13000 | 0
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 100% | 5760 | 0
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500 | 100% | 280 | 0
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 100% | 7920 | 0
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000 | 100% | 4560 | 0
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 0 | 66900 | 0 | 0 | 0 | 120000 | 100% | 4320 | 0
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3840 | 6.6 | 25344 | 0 | 0 | 3090 | 750 | 0 | 0 | 3840 | 100% | 25344 | 0
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 0 | 0 | 0 | 0 | 0 | 3200 | 100% | 288 | 0
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 0 | 0 | 0 | 0 | 0 | 106000 | 100% | 22260 | 0
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 100% | 1196.25 | 0
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 0 | 0 | 0 | 0 | 0 | 2075 | 100% | 5498.75 | 0
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 100% | 1650 | 0
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 100% | 975 | 0
|  |  |  | 610406.964 |  | 577298.0823 | 517019 | 8042.96 | 75058 | 8931.6 | 4720 | 1484.8 |  |  | 601469.4096 | -24171.3273
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 601469.4096 | صورتحسابهای مرحله اول: MRS-JAY-098-001 الی MRS-JAY-098-009 صورتحسابهای مرحله دوم: MRS-JAY-098-010 الی MRS-JAY-098-018 صورتحسابهای مرحله سوم: MRS-JAY-098-019 الی MRS-JAY-098-025 صورتحسابهای مرحله چهارم: MRS-JAY-098-26 الی MRS-JAY-098-046 صورتحسابهای مرحله پنجم: MRS-JAY-098-47وMRS-JAY-098-48 و MRS-JAY-098-051 و MRS-JAY-098-052 و MRS-JAY-098-054 و MRS-JAY-098-055 صورتحسابهای مرحله ششم: MRS-JAY-098-49وMRS-JAY-098-50 و MRS-JAY-098-053 و MRS-JAY-098-056 تاریخ انعقاد قرارداد: 1401/04/22 تاریخ شروع قرارداد برابر با تاریخ ابلاغ قرارداد: 1401/04/26 تاریخ پیش پرداخت: 1401/05/09 مدت قرارداد: 60 روز تقویمی پیش از شروع قرارداد (تاخیر در پرداخت پیش پرداخت به مدت زمان تحویل اضافه می شود) سر رسید تاریخ تحویل (با توجه به توضیحات فوق): 1401/07/07 با توجه به استعلام اخذ شده از واحد برنامه ریزی، تاخیرها در ارسال اقلام با هماهنگی خریدار و تحویل طی بازه های اعلامی توسط خریدار بوده است. همچنین جمعا مبلغ 72،067.18 یورو بیشتر از سقف قرارداد کالا ارسال شده است که که مربوط به ردیف های هایلایت شده می باشد. محموله 5 جزو درخواست واحد مهندسی میباشد که جمعا 19،349/44 یورو است و محموله 6 جزو درخواست عایق فلر جمعا 21،629/32 یورو الباقی معادل 31،088/42 یورو مازاد ارسال شده و MR ندارد.
کسر می شود: کالای صورتحساب شده طی مراحل قبلی | [5 empty] | 579834.4514
جمع کالای دریافتی طی مرحله ششم | [5 empty] | 21634.9582
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 1947.1462 | [11 empty] | 12942.176 | 12942.18 | 0.0039768
جمع کل باقیمانده | [5 empty] | 23582.1044
جمع صورتحسابهای مرحله ششم | [5 empty] | 21629.3282
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 1946.6395 | [11 empty] | 12942.176 | 12942.18 | 0.0039768
کسور: | [5 empty] | 23575.9677
استهلاک پیش پرداخت (باقیمانده) | [5 empty] | 0
خالص قابل پرداخت | [5 empty] | 23575.9677

## کنترل قرارداد (7)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [14 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [14 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [14 empty] | تاریخ تهیه گزارش: 1402/02/19
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | مقادیر رسید شده مرحله سوم | مقادیر رسید شده مرحله چهارم | مقادیر رسید شده مرحله پنجم-درخواست ضرورری | مقادیر رسید شده مرحله ششم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | مازاد بر قرارداد و الحاقیه
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 | 1.077 | 298.8675 | 0 | 0 | 0 | 277.5 | 0 | 0 | 277.5 | 100% | 298.8675 | 0
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 | 1.508 | 33.176 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 100% | 33.176 | 0
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.297 | 3.4455 | 1.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 100% | 3.4455 | 0
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 | 1.149 | 1790.142 | 1558 | 0 | 0 | 0 | 0 | 0 | 1558 | 100% | 1790.142 | 0
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 | 1.723 | 211.0675 | 122.5 | 0 | 0 | 0 | 0 | 68 | 122.5 | 100% | 211.0675 | 0
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 | 2.44 | 10.98 | 4.5 | 0 | 0 | 0 | 0 | 0 | 4.5 | 100% | 10.98 | 0
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 | 1.192 | 1316.564 | 0 | 0 | 1104.5 | 0 | 3000 | 994 | 4104.5 | 371.6% | 4892.564 | -3576 | 3576
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 | 1.795 | 580.6825 | 0 | 0 | 0 | 323.5 | 0 | 0 | 323.5 | 100% | 580.6825 | 0 | 720
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 | 2.656 | 9.296 | 3.5 | 0 | 0 | 0 | 0 | 0 | 3.5 | 100% | 9.296 | 0 | 300
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 | 1.508 | 2559.83 | 0 | 0 | 0 | 1697.5 | 0 | 0 | 1697.5 | 100% | 2559.83 | 0 | 700
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 | 2.104 | 275.624 | 0 | 0 | 131 | 0 | 0 | 0 | 131 | 100% | 275.624 | 0
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 2.943 | 4.4145 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 100% | 4.4145 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 | 1.579 | 3172.211 | 110 | 0 | 1782 | 117 | 0 | 1041 | 2009 | 100% | 3172.211 | 0
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 | 2.44 | 2332.64 | 0 | 0 | 636 | 320 | 720 | 287 | 1676 | 175.3% | 4089.44 | -1756.8 | 1756.8
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 | 3.302 | 123.825 | 37.5 | 0 | 0 | 0 | 0 | 0 | 37.5 | 100% | 123.825 | 0
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 | 4.235 | 6.3525 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 100% | 6.3525 | 0
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 | 2.154 | 2521.257 | 575 | 0 | 96 | 499.5 | 0 | 0 | 1170.5 | 100% | 2521.257 | 0
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 | 3.086 | 1914.863 | 620.5 | 0 | 0 | 0 | 0 | 0 | 620.5 | 100% | 1914.863 | 0
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 | 4.074 | 566.286 | 0 | 139 | 0 | 0 | 0 | 0 | 139 | 100% | 566.286 | 0
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 | 2.496 | 189.696 | 0 | 0 | 76 | 0 | 0 | 42 | 76 | 100% | 189.696 | 0
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 | 3.589 | 3660.78 | 0 | 0 | 921 | 99 | 0 | 461 | 1020 | 100% | 3660.78 | 0
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 | 4.737 | 632.3895 | 0 | 0 | 45 | 88.5 | 0 | 0 | 133.5 | 100% | 632.3895 | 0
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 | 5.956 | 407.986 | 0 | 0 | 0 | 68.5 | 0 | 0 | 68.5 | 100% | 407.986 | 0
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 | 3.484 | 459.888 | 132 | 0 | 0 | 0 | 0 | 0 | 132 | 100% | 459.888 | 0
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 | 4.88 | 7219.96 | 0 | 0 | 0 | 1479.5 | 0 | 195 | 1479.5 | 100% | 7219.96 | 0
26=29 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 176.5 | 6.315 | 1114.5975 | 48.5 | 0 | 128 | 0 | 0 | 0 | 176.5 | 100% | 1114.5975 | 0
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 | 7.822 | 2901.962 | 371 | 0 | 0 | 0 | 0 | 0 | 371 | 100% | 2901.962 | 0
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 | 9.832 | 4326.08 | 430 | 0 | 0 | 10 | 0 | 0 | 440 | 100% | 4326.08 | 0
29=26 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 6.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 711 | 15.892 | 11299.212 | 0 | 132 | 0 | 579 | 0 | 0 | 711 | 100% | 11299.212 | 0
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 | 4.339 | 43.39 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 100% | 43.39 | 0
32=35 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 365.5 | 7.751 | 2832.9905 | 84 | 0 | 138.5 | 143 | 300 | 0 | 665.5 | 182.1% | 5158.2905 | -2325.3 | 2325.3
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 | 9.472 | 3296.256 | 0 | 0 | 0 | 348 | 0 | 0 | 348 | 100% | 3296.256 | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 | 11.553 | 2749.614 | 0 | 0 | 0 | 238 | 0 | 0 | 238 | 100% | 2749.614 | 0
35=32 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 7.751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 | 15.892 | 3543.916 | 0 | 223 | 0 | 0 | 0 | 0 | 223 | 100% | 3543.916 | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 | 5.134 | 205.36 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 100% | 205.36 | 0
38=41=43 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 521 | 9.329 | 4860.409 | 0 | 0 | 0 | 521 | 0 | 0 | 521 | 100% | 4860.409 | 0
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 | 11.267 | 6461.6245 | 0 | 155 | 0 | 418.5 | 0 | 0 | 573.5 | 100% | 6461.6245 | 0
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 | 13.634 | 2944.944 | 216 | 0 | 0 | 0 | 0 | 0 | 216 | 100% | 2944.944 | 0
41=38 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 9.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 352 | 15.892 | 5593.984 | 0 | 328 | 0 | 24 | 0 | 0 | 352 | 100% | 5593.984 | 0
43=38 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 0 | 9.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 | 16.7 | 4225.1 | 0 | 253 | 0 | 0 | 700.08 | 0 | 953.08 | 376.7% | 15916.436 | -11691.336 | 11691.336
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 | 10.888 | 11.9768 | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 11.9768 | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 | 7.801 | 42.9055 | 0 | 5.5 | 0 | 0 | 0 | 0 | 5.5 | 100% | 42.9055 | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 | 15.892 | 1394.9998 | 0 | 87.78 | 0 | 0 | 0 | 0 | 87.78 | 100% | 1394.9998 | 0
48=54 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1237.5 | 17.508 | 21666.15 | 0 | 1237.5 | 0 | 241.2 | 0 | 0 | 1478.7 | 119.5% | 25889.0796 | -4222.9296
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1540.1 | 18.316 | 28208.4716 | 0 | 1310.1 | 0 | 153.6 | 0 | 0 | 1463.7 | 95.04% | 26809.1292 | 1399.3424
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 | 19.124 | 23771.132 | 0 | 1243 | 0 | 0 | 0 | 0 | 1243 | 100% | 23771.132 | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 | 19.932 | 8046.5484 | 0 | 403.7 | 0 | 0 | 0 | 0 | 403.7 | 100% | 8046.5484 | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 | 20.74 | 17064.872 | 0 | 822.8 | 0 | 211 | 0 | 0 | 1033.8 | 125.6% | 21441.012 | -4376.14
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 | 21.548 | 255.9902 | 0 | 11.88 | 0 | 0 | 0 | 0 | 11.88 | 100% | 255.9902 | 0
54=48 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 0 | 17.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 | 18.316 | 4210.8484 | 0 | 229.9 | 0 | 280.8 | 0 | 0 | 510.7 | 222.1% | 9353.9812 | -5143.1328
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.601 | 11.313 | 66402.7961 | 5869.601 | 0 | 0 | 0 | 0 | 328.9 | 6198.501 | 105.6% | 70123.6418 | -3720.8457
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 | 15.084 | 104183.6796 | 6906.9 | 0 | 0 | 0 | 0 | 1030.5 | 7937.4 | 114.9% | 119727.7416 | -15544.062
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 | 18.855 | 40651.38 | 2156 | 0 | 0 | 0 | 0 | 125.4 | 2281.4 | 105.8% | 43015.797 | -2364.417
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 | 6.341 | 6.9751 | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 6.9751 | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 | 6.95 | 145.255 | 0 | 20.9 | 0 | 0 | 0 | 0 | 20.9 | 100% | 145.255 | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 | 9.627 | 84.7176 | 0 | 8.8 | 0 | 0 | 0 | 0 | 8.8 | 100% | 84.7176 | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 | 14.464 | 15.9104 | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 15.9104 | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 | 12.024 | 26.4528 | 0 | 2.2 | 0 | 0 | 0 | 0 | 2.2 | 100% | 26.4528 | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 | 11.092 | 10078.1912 | 0 | 908.6 | 0 | 0 | 0 | 0 | 908.6 | 100% | 10078.1912 | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 | 14.626 | 2831.5936 | 0 | 193.6 | 0 | 0 | 0 | 0 | 193.6 | 100% | 2831.5936 | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 | 21.123 | 1812.3534 | 0 | 85.8 | 0 | 0 | 0 | 0 | 85.8 | 100% | 1812.3534 | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 | 25.184 | 858.7744 | 0 | 34.1 | 0 | 0 | 0 | 0 | 34.1 | 100% | 858.7744 | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 | 33.513 | 1290.2505 | 0 | 38.5 | 0 | 0 | 0 | 0 | 38.5 | 100% | 1290.2505 | 0
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 | 56.052 | 7028.9208 | 0 | 125.4 | 0 | 0 | 0 | 0 | 125.4 | 100% | 7028.9208 | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 | 44.68 | 1769.328 | 0 | 39.6 | 0 | 0 | 0 | 0 | 39.6 | 100% | 1769.328 | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 | 0.61 | 26535 | 43500 | 0 | 0 | 0 | 0 | 0 | 43500 | 100% | 26535 | 0
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 | 1 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 13000 | 100% | 13000 | 0
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 | 0.08 | 5760 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 100% | 5760 | 0
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 | 0.08 | 280 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500 | 100% | 280 | 0
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 | 0.066 | 7920 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 100% | 7920 | 0
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 | 0.057 | 4560 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000 | 100% | 4560 | 0
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 | 0.036 | 4320 | 53100 | 0 | 66900 | 0 | 0 | 0 | 120000 | 100% | 4320 | 0
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 | 6.6 | 20394 | 0 | 0 | 3090 | 750 | 0 | 0 | 3840 | 124.3% | 25344 | -4950
80 | ACCESSORY | کلیپس S | عدد | 3200 | 0.09 | 288 | 3200 | 0 | 0 | 0 | 0 | 0 | 3200 | 100% | 288 | 0
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 | 0.21 | 22260 | 106000 | 0 | 0 | 0 | 0 | 0 | 106000 | 100% | 22260 | 0
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 | 15.95 | 1196.25 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 100% | 1196.25 | 0
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 | 2.65 | 5498.75 | 2075 | 0 | 0 | 0 | 0 | 0 | 2075 | 100% | 5498.75 | 0
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 | 3 | 1650 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 100% | 1650 | 0
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 | 1.3 | 975 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 100% | 975 | 0
|  |  |  | 607645.961 |  | 543199.1362 | 517019.001 | 8042.96 | 75058 | 8931.6 | 4720.08 | 4572.8 |  |  | 601470.7569 | -58271.6207
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات:
جمع کالای دریافتی | [5 empty] | 601470.7569 | صورتحسابهای مرحله اول: MRS-JAY-098-001 الی MRS-JAY-098-009 صورتحسابهای مرحله دوم: MRS-JAY-098-010 الی MRS-JAY-098-018 صورتحسابهای مرحله سوم: MRS-JAY-098-019 الی MRS-JAY-098-025 صورتحسابهای مرحله چهارم: MRS-JAY-098-26 الی MRS-JAY-098-046 صورتحسابهای مرحله پنجم: MRS-JAY-098-47وMRS-JAY-098-48 و MRS-JAY-098-051 و MRS-JAY-098-052 و MRS-JAY-098-054 و MRS-JAY-098-055 صورتحسابهای مرحله ششم: MRS-JAY-098-49وMRS-JAY-098-50 و MRS-JAY-098-053 و MRS-JAY-098-056 تاریخ انعقاد قرارداد: 1401/04/22 تاریخ شروع قرارداد برابر با تاریخ ابلاغ قرارداد: 1401/04/26 تاریخ پیش پرداخت: 1401/05/09 مدت قرارداد: 60 روز تقویمی پیش از شروع قرارداد (تاخیر در پرداخت پیش پرداخت به مدت زمان تحویل اضافه می شود) سر رسید تاریخ تحویل (با توجه به توضیحات فوق): 1401/07/07 با توجه به استعلام اخذ شده از واحد برنامه ریزی، تاخیرها در ارسال اقلام با هماهنگی خریدار و تحویل طی بازه های اعلامی توسط خریدار بوده است. همچنین جمعا مبلغ 88،611.21 یورو بیشتر از سقف قرارداد کالا ارسال شده است که که مربوط به ردیف های هایلایت شده می باشد. .
کسر می شود: کالای صورتحساب شده طی مراحل قبلی | [5 empty] | 579834.4514
جمع کالای دریافتی طی مرحله ششم | [5 empty] | 21636.3055
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 1947.2675 | [11 empty] | 12942.176 | 12942.18 | 0.0039768
جمع کل باقیمانده | [5 empty] | 23583.573
جمع صورتحسابهای مرحله ششم | [5 empty] | 21636.3055
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 1947.2675 | [11 empty] | 12942.176 | 12942.18 | 0.0039768
کسور: | [5 empty] | 23583.573
استهلاک پیش پرداخت (باقیمانده) | [5 empty] | 0
خالص قابل پرداخت | [5 empty] | 23583.573

## Packing List Items
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-JAY-098-001 | 2022-08-30 | SACR-PL-JAY-098-001 | ADSH-P-PO-GE-098 | jahanayegh | 1 |  | Main Item | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 270 |  |  |  |  | 270 | Meter
2 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | 22 |  |  |  |  | 22 | Meter
3 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1.5 |  |  |  |  | 1.5 | Meter
4 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 3.5 |  |  |  |  | 3.5 | Meter
5 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 110 |  |  |  |  | 110 | Meter
6 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 132 |  |  |  |  | 132 | Meter
7 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 101 |  |  |  |  | 101 | Meter
8 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1558 |  |  |  |  | 1558 | Meter
9 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 122.5 |  |  |  |  | 122.5 | Meter
10 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 4.5 |  |  |  |  | 4.5 | Meter
11 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 37.5 |  |  |  |  | 37.5 | Meter
12 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 48.5 |  |  |  |  | 48.5 | Meter
13 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 84 |  |  |  |  | 84 | Meter
14 | OPI-JAY-098-005 | 2022-09-12 | SACR-PL-JAY-098-004 | ADSH-P-PO-GE-098 | jahanayegh | 4 |  | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 4448.7 |  |  |  |  | 4448.7 | Sq. Meter
15 | OPI-JAY-098-005 | 2022-09-12 | SACR-PL-JAY-098-004 | ADSH-P-PO-GE-098 | jahanayegh | 4 |  | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 1973.58 |  |  |  |  | 1973.58 | Sq. Meter
16 | OPI-JAY-098-004 | 2022-09-04 | SACR-PL-JAY-098-005 | ADSH-P-PO-GE-098 | jahanayegh | 5 |  | Main Item | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 180 |  |  |  |  | 180 | Meter |  |  | 180بسته 1متری
17 | OPI-JAY-098-006 | 2022-09-12 | SACR-PL-JAY-098-006 | ADSH-P-PO-GE-098 | jahanayegh | 6 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 225 |  |  |  |  | 225 | Meter
18 | OPI-JAY-098-006 | 2022-09-12 | SACR-PL-JAY-098-006 | ADSH-P-PO-GE-098 | jahanayegh | 6 |  | Main Item | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 36 |  |  |  |  | 36 | Meter
19 | OPI-JAY-098-007 | 2022-09-12 | SACR-PL-JAY-098-007 | ADSH-P-PO-GE-098 | jahanayegh | 7 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 205 |  |  |  |  | 205 | Meter
20 | OPI-JAY-098-007 | 2022-09-12 | SACR-PL-JAY-098-007 | ADSH-P-PO-GE-098 | jahanayegh | 7 |  | Main Item | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 204 |  |  |  |  | 204 | Meter
21 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Main Item | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 5869.6 |  |  |  |  | 5869.6 | Sq. Meter
22 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 2458.2 |  |  |  |  | 2458.2 | Sq. Meter
23 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 182.42 |  |  |  |  | 182.42 | Sq. Meter
24 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | تسمه استنلس استیل سایز 0/5 * 13 میلیمتر | 43500 |  |  |  |  | 43500 | Meter
25 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | تسمه استنلس استیل سایز 0/5*19 میلیمتر | 13000 |  |  |  |  | 13000 | Meter
26 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | بست استنلس استیل سایز 0/5*13 میلیمتر | 72000 |  |  |  |  | 72000 | Piece
27 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | بست استنلس استیل سایز 0/5*19میلیمتر | 3500 |  |  |  |  | 3500 | Piece
28 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 میلیمتر | 120000 |  |  |  |  | 120000 | Piece
29 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 میلیمتر | 80000 |  |  |  |  | 80000 | Piece
30 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | واشر نئو پرن | 53100 |  |  |  |  | 53100 | Piece
31 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | S کلیپس | 3200 |  |  |  |  | 3200 | Piece
32 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | سیم استنلس استیل به قطر 1 میلیمتر | 106000 |  |  |  |  | 106000 | Meter
33 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | نوار چسب نخ دار تقویت شده فیلامنت با عرض 50 میلی متر | 75 |  |  |  |  | 75 | Roll
34 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | 2075 |  |  |  |  | 2075 | Kg
35 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Joint Sealant Mastic JAP 81-84 | 550 |  |  |  |  | 550 | Kg
36 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Glass Cloth Mesh | 750 |  |  |  |  | 750 | Sq. Meter
37 | OPI-JAY-098-009 | 2022-09-12 | SACR-PL-JAY-098-009 | ADSH-P-PO-GE-098 | jahanayegh | 9 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 575 |  |  |  |  | 575 | Meter
38 | OPI-JAY-098-009 | 2022-09-12 | SACR-PL-JAY-098-009 | ADSH-P-PO-GE-098 | jahanayegh | 9 |  | Main Item | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 416.5 |  |  |  |  | 416.5 | Meter
39 | OPI-JAY-098-010 | 2022-09-20 | SACR-PL-JAY-098-010 | ADSH-P-PO-GE-098 | jahanayegh | 10 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 155 |  |  |  |  | 155 | Meter
40 | OPI-JAY-098-010 | 2022-09-20 | SACR-PL-JAY-098-010 | ADSH-P-PO-GE-098 | jahanayegh | 10 |  | Main Item | - | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 139 |  |  |  |  | 139 | Meter
41 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 87.78 |  |  |  |  | 87.78 | Sq. Meter
42 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 328 |  |  |  |  | 328 | Sq. Meter
43 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 223 |  |  |  |  | 223 | Sq. Meter
44 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 132 |  |  |  |  | 132 | Sq. Meter
45 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 240 |  |  |  |  | 240 | Sq. Meter
46 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 100.8 |  |  |  |  | 100.8 | Sq. Meter
47 | OPI-JAY-098-012 | 2022-10-31 | SACR-PL-JAY-098-012 | ADSH-P-PO-GE-098 | jahanayegh | 12 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 253 |  |  |  |  | 253 | Sq. Meter
48 | OPI-JAY-098-012 | 2022-10-31 | SACR-PL-JAY-098-012 | ADSH-P-PO-GE-098 | jahanayegh | 12 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 307.2 |  |  |  |  | 307.2 | Sq. Meter
49 | OPI-JAY-098-012 | 2022-10-31 | SACR-PL-JAY-098-012 | ADSH-P-PO-GE-098 | jahanayegh | 12 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 403.7 |  |  |  |  | 403.7 | Sq. Meter
50 | OPI-JAY-098-013 | 2022-11-07 | SACR-PL-JAY-098-013 | ADSH-P-PO-GE-098 | jahanayegh | 13 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 229.9 |  |  |  |  | 229.9 | Sq. Meter
51 | OPI-JAY-098-013 | 2022-11-07 | SACR-PL-JAY-098-013 | ADSH-P-PO-GE-098 | jahanayegh | 13 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 634.1 |  |  |  |  | 634.1 | Sq. Meter
52 | OPI-JAY-098-014 | 2022-11-07 | SACR-PL-JAY-098-014 | ADSH-P-PO-GE-098 | jahanayegh | 14 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 676.8 |  |  |  |  | 676.8 | Sq. Meter
53 | OPI-JAY-098-014 | 2022-11-07 | SACR-PL-JAY-098-014 | ADSH-P-PO-GE-098 | jahanayegh | 14 |  | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 187.2 |  |  |  |  | 187.2 | Sq. Meter
54 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | 1.1 |  |  |  |  | 1.1 | Meter
55 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | 20.9 |  |  |  |  | 20.9 | Meter
56 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | 1.1 |  |  |  |  | 1.1 | Meter
57 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | 5.5 |  |  |  |  | 5.5 | Meter
58 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 8.8 |  |  |  |  | 8.8 | Meter
59 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 1.1 |  |  |  |  | 1.1 | Meter
60 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 2.2 |  |  |  |  | 2.2 | Meter
61 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 908.6 |  |  |  |  | 908.6 | Meter
62 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | 193.6 |  |  |  |  | 193.6 | Meter
63 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 85.8 |  |  |  |  | 85.8 | Meter
64 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | 34.1 |  |  |  |  | 34.1 | Meter
65 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 38.5 |  |  |  |  | 38.5 | Meter
66 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYG06 | 6" , Thk. 60mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | 125.4 |  |  |  |  | 125.4 | Meter
67 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | 39.6 |  |  |  |  | 39.6 | Meter
68 | OPI-JAY-098-015 | 2022-11-07 | SACR-PL-JAY-098-016 | ADSH-P-PO-GE-098 | jahanayegh | 16 |  | Main Item | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 648 |  |  |  |  | 648 | Sq. Meter
69 | OPI-JAY-098-016 | 2022-11-07 | SACR-PL-JAY-098-017 | ADSH-P-PO-GE-098 | jahanayegh | 17 |  | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 648 |  |  |  |  | 648 | Sq. Meter
70 | OPI-JAY-098-016 | 2022-11-07 | SACR-PL-JAY-098-017 | ADSH-P-PO-GE-098 | jahanayegh | 17 |  | Main Item | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 174.84 |  |  |  |  | 174.84 | Sq. Meter
71 | OPI-JAY-098-017 | 2022-11-07 | SACR-PL-JAY-098-018 | ADSH-P-PO-GE-098 | jahanayegh | 18 |  | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 997.5 |  |  |  |  | 997.5 | Sq. Meter
72 | OPI-JAY-098-017 | 2022-11-07 | SACR-PL-JAY-098-018 | ADSH-P-PO-GE-098 | jahanayegh | 18 |  | Main Item | - | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 11.88 |  |  |  |  | 11.88 | Sq. Meter
73 | OPI-JAY-098-019 | 2022-11-13 | SACR-PL-JAY-098-019 | ADSH-P-PO-GE-098 | jahanayegh | 19 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 600 |  |  |  |  | 600 | Meter
74 | OPI-JAY-098-019 | 2022-11-13 | SACR-PL-JAY-098-019 | ADSH-P-PO-GE-098 | jahanayegh | 19 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 684 |  |  |  |  | 684 | Meter
75 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 504.5 |  |  |  |  | 504.5 | Meter
76 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 630 |  |  |  |  | 630 | Meter
77 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 96 |  |  |  |  | 96 | Meter
78 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 57 |  |  |  |  | 57 | Meter
79 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 45 |  |  |  |  | 45 | Meter
80 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 128 |  |  |  |  | 128 | Meter
81 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 131 |  |  |  |  | 131 | Meter
82 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 20 |  |  |  |  | 20 | Meter
83 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 10 |  |  |  |  | 10 | Meter
84 | OPI-JAY-098-022 | 2022-11-26 | SACR-PL-JAY-098-022 | ADSH-P-PO-GE-098 | jahanayegh | 22 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 540 |  |  |  |  | 540 | Meter
85 | OPI-JAY-098-023 | 2022-11-26 | SACR-PL-JAY-098-023 | ADSH-P-PO-GE-098 | jahanayegh | 23 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 84 |  |  |  |  | 84 | Meter
86 | OPI-JAY-098-023 | 2022-11-26 | SACR-PL-JAY-098-023 | ADSH-P-PO-GE-098 | jahanayegh | 23 |  | Sub Item | Insulation-Acc | ACCESSORY | ماستیک METAL SEALANT | 3090 |  |  |  |  | 3090 | Piece
87 | OPI-JAY-098-023 | 2022-11-26 | SACR-PL-JAY-098-023 | ADSH-P-PO-GE-098 | jahanayegh | 23 |  | Sub Item | Insulation-Acc | ACCESSORY | واشر نئوپرن | 66900 |  |  |  |  | 66900 | Piece
88 | OPI-JAY-098-024 | 2022-11-30 | SACR-PL-JAY-098-024 | ADSH-P-PO-GE-098 | jahanayegh | 24 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 252 |  |  |  |  | 252 | Meter
89 | OPI-JAY-098-024 | 2022-11-30 | SACR-PL-JAY-098-024 | ADSH-P-PO-GE-098 | jahanayegh | 24 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 381 |  |  |  |  | 381 | Meter
90 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 216 |  |  |  |  | 216 | Meter
91 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 636 |  |  |  |  | 636 | Meter
92 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 19 |  |  |  |  | 19 | Meter
93 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 34.5 |  |  |  |  | 34.5 | Meter
94 | OPI-JAY-098-026 | 2022-12-10 | SACR-PL-JAY-098-026 | ADSH-P-PO-GE-098 | jahanayegh | 26 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 354 |  |  |  |  | 354 | Meter |  |  | طبق مکاتبات صورت گرفته ضخامت 50ارسال گردیده است
95 | OPI-JAY-098-027 | 2022-12-13 | SACR-PL-JAY-098-027 | ADSH-P-PO-GE-098 | jahanayegh | 27 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 285 |  |  |  |  | 285 | Meter
96 | OPI-JAY-098-027 | 2022-12-13 | SACR-PL-JAY-098-027 | ADSH-P-PO-GE-098 | jahanayegh | 27 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 117 |  |  |  |  | 117 | Meter
97 | OPI-JAY-098-028 | 2022-12-14 | SACR-PL-JAY-098-028 | ADSH-P-PO-GE-098 | jahanayegh | 28 |  | Main Item | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 160 |  |  |  |  | 160 | Meter
98 | OPI-JAY-098-029 | 2022-12-20 | SACR-PL-JAY-098-029 | ADSH-P-PO-GE-098 | jahanayegh | 29 |  | Main Item | - | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 323.5 |  |  |  |  | 323.5 | Meter
99 | OPI-JAY-098-029 | 2022-12-20 | SACR-PL-JAY-098-029 | ADSH-P-PO-GE-098 | jahanayegh | 29 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 320 |  |  |  |  | 320 | Meter
100 | OPI-JAY-098-029 | 2022-12-20 | SACR-PL-JAY-098-029 | ADSH-P-PO-GE-098 | jahanayegh | 29 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 139.5 |  |  |  |  | 139.5 | Meter
101 | OPI-JAY-098-030 | 2022-12-20 | SACR-PL-JAY-098-030 | ADSH-P-PO-GE-098 | jahanayegh | 30 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 143 |  |  |  |  | 143 | Meter
102 | OPI-JAY-098-031 | 2022-12-20 | SACR-PL-JAY-098-031 | ADSH-P-PO-GE-098 | jahanayegh | 31 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 112 |  |  |  |  | 112 | Meter
103 | OPI-JAY-098-031 | 2022-12-20 | SACR-PL-JAY-098-031 | ADSH-P-PO-GE-098 | jahanayegh | 31 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 99 |  |  |  |  | 99 | Meter
104 | OPI-JAY-098-031 | 2022-12-20 | SACR-PL-JAY-098-031 | ADSH-P-PO-GE-098 | jahanayegh | 31 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 220.5 |  |  |  |  | 220.5 | Meter
105 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 516 |  |  |  |  | 516 | Meter
106 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 216 |  |  |  |  | 216 | Meter
107 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 102 |  |  |  |  | 102 | Meter
108 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | 277.5 |  |  |  |  | 277.5 | Meter
109 | OPI-JAY-098-033 | 2022-12-27 | SACR-PL-JAY-098-033 | ADSH-P-PO-GE-098 | jahanayegh | 33 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 139.5 |  |  |  |  | 139.5 | Meter
110 | OPI-JAY-098-033 | 2022-12-27 | SACR-PL-JAY-098-033 | ADSH-P-PO-GE-098 | jahanayegh | 33 |  | Main Item | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 540 |  |  |  |  | 540 | Meter
111 | OPI-JAY-098-033 | 2022-12-27 | SACR-PL-JAY-098-033 | ADSH-P-PO-GE-098 | jahanayegh | 33 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 171.5 |  |  |  |  | 171.5 | Meter
112 | OPI-JAY-098-034 | 2023-01-04 | SACR-PL-JAY-098-034 | ADSH-P-PO-GE-098 | jahanayegh | 34 |  | Main Item | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 146 |  |  |  |  | 146 | Meter
113 | OPI-JAY-098-034 | 2023-01-04 | SACR-PL-JAY-098-034 | ADSH-P-PO-GE-098 | jahanayegh | 34 |  | Main Item | - | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 40 |  |  |  |  | 40 | Meter
114 | OPI-JAY-098-034 | 2023-01-04 | SACR-PL-JAY-098-034 | ADSH-P-PO-GE-098 | jahanayegh | 34 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 29 |  |  |  |  | 29 | Meter
115 | OPI-JAY-098-035 | 2023-01-04 | SACR-PL-JAY-098-035 | ADSH-P-PO-GE-098 | jahanayegh | 35 | Iso Blanket Mineral Wool with Stainless Steel on One Side -FOR UNIT FLR | Main Item | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 211 |  |  |  |  | 211 | Sq. Meter
116 | OPI-JAY-098-036 | 2023-01-04 | SACR-PL-JAY-098-036 | ADSH-P-PO-GE-098 | jahanayegh | 36 |  | Main Item | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 100 |  |  |  |  | 100 | Meter
117 | OPI-JAY-098-036 | 2023-01-04 | SACR-PL-JAY-098-036 | ADSH-P-PO-GE-098 | jahanayegh | 36 |  | Main Item | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 78 |  |  |  |  | 78 | Meter
118 | OPI-JAY-098-036 | 2023-01-04 | SACR-PL-JAY-098-036 | ADSH-P-PO-GE-098 | jahanayegh | 36 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 37 |  |  |  |  | 37 | Meter
119 | OPI-JAY-098-037 | 2023-01-04 | SACR-PL-JAY-098-037 | ADSH-P-PO-GE-098 | jahanayegh | 37 |  | Main Item | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 641.5 |  |  |  |  | 641.5 | Meter
120 | OPI-JAY-098-037 | 2023-01-04 | SACR-PL-JAY-098-037 | ADSH-P-PO-GE-098 | jahanayegh | 37 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 189 |  |  |  |  | 189 | Meter
121 | OPI-JAY-098-038 | 2023-01-16 | SACR-PL-JAY-098-038 | ADSH-P-PO-GE-098 | jahanayegh | 38 |  | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 579 |  |  |  |  | 579 | Sq. Meter
122 | OPI-JAY-098-038 | 2023-01-16 | SACR-PL-JAY-098-038 | ADSH-P-PO-GE-098 | jahanayegh | 38 |  | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 223.2 |  |  |  |  | 223.2 | Sq. Meter
123 | OPI-JAY-098-038 | 2023-01-16 | SACR-PL-JAY-098-038 | ADSH-P-PO-GE-098 | jahanayegh | 38 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 153.6 |  |  |  |  | 153.6 | Sq. Meter
124 | OPI-JAY-098-039 | 2023-01-16 | SACR-PL-JAY-098-039 | ADSH-P-PO-GE-098 | jahanayegh | 39 |  | Main Item | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 102 |  |  |  |  | 102 | Meter
125 | OPI-JAY-098-039 | 2023-01-16 | SACR-PL-JAY-098-039 | ADSH-P-PO-GE-098 | jahanayegh | 39 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 14 |  |  |  |  | 14 | Meter
126 | OPI-JAY-098-039 | 2023-01-16 | SACR-PL-JAY-098-039 | ADSH-P-PO-GE-098 | jahanayegh | 39 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 39 |  |  |  |  | 39 | Meter
127 | OPI-JAY-098-040 | 2023-01-16 | SACR-PL-JAY-098-040 | ADSH-P-PO-GE-098 | jahanayegh | 40 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 86 |  |  |  |  | 86 | Meter
128 | OPI-JAY-098-040 | 2023-01-16 | SACR-PL-JAY-098-040 | ADSH-P-PO-GE-098 | jahanayegh | 40 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 77 |  |  |  |  | 77 | Meter
129 | OPI-JAY-098-041 | 2023-01-16 | SACR-PL-JAY-098-041 | ADSH-P-PO-GE-098 | jahanayegh | 41 |  | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 24 |  |  |  |  | 24 | Sq. Meter
130 | OPI-JAY-098-041 | 2023-01-16 | SACR-PL-JAY-098-041 | ADSH-P-PO-GE-098 | jahanayegh | 41 |  | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 18 |  |  |  |  | 18 | Sq. Meter
131 | OPI-JAY-098-041 | 2023-01-16 | SACR-PL-JAY-098-041 | ADSH-P-PO-GE-098 | jahanayegh | 41 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 280.8 |  |  |  |  | 280.8 | Sq. Meter
132 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1.5 |  |  |  |  | 1.5 | Meter
133 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1.5 |  |  |  |  | 1.5 | Meter
134 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 88.5 |  |  |  |  | 88.5 | Meter
135 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 50 |  |  |  |  | 50 | Meter
136 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Sub Item | Insulation-Acc | ACCESSORY | MASTIC METAL SEALANT | 750 |  |  |  |  | 750 | Piece
137 | OPI-JAY-098-043 | 2023-01-18 | SACR-PL-JAY-098-043 | ADSH-P-PO-GE-098 | jahanayegh | 43 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 170 |  |  |  |  | 170 | Meter
138 | OPI-JAY-098-044 | 2023-01-18 | SACR-PL-JAY-098-044 | ADSH-P-PO-GE-098 | jahanayegh | 44 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 120 |  |  |  |  | 120 | Meter
139 | OPI-JAY-098-044 | 2023-01-18 | SACR-PL-JAY-098-044 | ADSH-P-PO-GE-098 | jahanayegh | 44 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 40 |  |  |  |  | 40 | Meter
140 | OPI-JAY-098-045 | 2023-01-24 | SACR-PL-JAY-098-045 | ADSH-P-PO-GE-098 | jahanayegh | 45 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 150 |  |  |  |  | 150 | Meter
141 | OPI-JAY-098-045 | 2023-01-24 | SACR-PL-JAY-098-045 | ADSH-P-PO-GE-098 | jahanayegh | 45 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 29.5 |  |  |  |  | 29.5 | Meter
142 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 97 |  |  |  |  | 97 | Meter
143 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 50.5 |  |  |  |  | 50.5 | Meter
144 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 10 |  |  |  |  | 10 | Meter
145 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 68.5 |  |  |  |  | 68.5 | Meter
146 | OPI-JAY-098-047 | 2023-04-06 | SACR-PL-JAY-098-047 | ADSH-P-PO-GE-098 | jahanayegh | 47 |  | Main Item | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 348 |  |  |  |  | 348 | Sq. Meter |  |  |  | 1402/01/21
147 | OPI-JAY-098-048 | 2023-04-06 | SACR-PL-JAY-098-048 | ADSH-P-PO-GE-098 | jahanayegh | 48 | Mineral Wool Iso Blanket | Main Item | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 352.08 |  |  |  |  | 352.08 | Sq. Meter |  |  |  | 1402/01/21
148 | OPI-JAY-098-049 | 2023-04-06 | SACR-PL-JAY-098-049 | ADSH-P-PO-GE-098 | jahanayegh | 49 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 994 |  |  |  |  | 994 | Meter
149 | OPI-JAY-098-049 | 2023-04-06 | SACR-PL-JAY-098-049 | ADSH-P-PO-GE-098 | jahanayegh | 49 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 287 |  |  |  |  | 287 | Meter
150 | OPI-JAY-098-049 | 2023-04-06 | SACR-PL-JAY-098-049 | ADSH-P-PO-GE-098 | jahanayegh | 49 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 32 |  |  |  |  | 32 | Meter
151 | OPI-JAY-098-050 | 2023-04-09 | SACR-PL-JAY-098-050 | ADSH-P-PO-GE-098 | jahanayegh | 50 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 162 |  |  |  |  | 162 | Meter
152 | OPI-JAY-098-050 | 2023-04-09 | SACR-PL-JAY-098-050 | ADSH-P-PO-GE-098 | jahanayegh | 50 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 216 |  |  |  |  | 216 | Meter
153 | OPI-JAY-098-050 | 2023-04-09 | SACR-PL-JAY-098-050 | ADSH-P-PO-GE-098 | jahanayegh | 50 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 167 |  |  |  |  | 167 | Meter
154 | OPI-JAY-098-051 | 2023-04-13 | SACR-PL-JAY-098-051 | ADSH-P-PO-GE-098 | jahanayegh | 51 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 147 |  |  |  |  | 147 | Meter |  |  |  | 1402/01/21
155 | OPI-JAY-098-051 | 2023-04-13 | SACR-PL-JAY-098-051 | ADSH-P-PO-GE-098 | jahanayegh | 51 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 270 |  |  |  |  | 270 | Meter |  |  |  | 1402/01/21
156 | OPI-JAY-098-052 | 2023-04-13 | SACR-PL-JAY-098-052 | ADSH-P-PO-GE-098 | jahanayegh | 52 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 42 |  |  |  |  | 42 | Meter |  |  |  | 1402/01/21
157 | OPI-JAY-098-052 | 2023-04-13 | SACR-PL-JAY-098-052 | ADSH-P-PO-GE-098 | jahanayegh | 52 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 450 |  |  |  |  | 450 | Meter |  |  |  | 1402/01/21
158 | OPI-JAY-098-052 | 2023-04-13 | SACR-PL-JAY-098-052 | ADSH-P-PO-GE-098 | jahanayegh | 52 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 720 |  |  |  |  | 720 | Meter |  |  |  | 1402/01/21
159 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 68 |  |  |  |  | 68 | Meter
160 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 213 |  |  |  |  | 213 | Meter
161 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 28 |  |  |  |  | 28 | Meter
162 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 879 |  |  |  |  | 879 | Meter
163 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 42 |  |  |  |  | 42 | Meter
164 | OPI-JAY-098-055 | 2023-04-25 | SACR-PL-JAY-098-054 | ADSH-P-PO-GE-098 | jahanayegh | 54 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 111 |  |  |  |  | 111 | Meter |  |  |  | 1402/01/21
165 | OPI-JAY-098-055 | 2023-04-25 | SACR-PL-JAY-098-054 | ADSH-P-PO-GE-098 | jahanayegh | 54 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1080 |  |  |  |  | 1080 | Meter |  |  |  | 1402/01/21
166 | OPI-JAY-098-054 | 2023-04-24 | SACR-PL-JAY-098-055 | ADSH-P-PO-GE-098 | jahanayegh | 55 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1200 |  |  |  |  | 1200 | Meter |  |  |  | 1402/01/21
167 | OPI-JAY-098-056 | 2023-05-07 | SACR-PL-JAY-098-056 | ADSH-P-PO-GE-098 | jahanayegh | 56 | Metal Jacketing | Main Item | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 328.9 |  |  |  |  | 328.9 | Sq. Meter | 542.6
168 | OPI-JAY-098-056 | 2023-05-07 | SACR-PL-JAY-098-056 | ADSH-P-PO-GE-098 | jahanayegh | 56 | Metal Jacketing | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 1030.5 |  |  |  |  | 1030.5 | Sq. Meter | 2267
169 | OPI-JAY-098-056 | 2023-05-07 | SACR-PL-JAY-098-056 | ADSH-P-PO-GE-098 | jahanayegh | 56 | Metal Jacketing | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 125.4 |  |  |  |  | 125.4 | Sq. Meter | 345
[12 empty] | 618344.98 |  |  |  |  | 618344.98

## ریز آیتم ها
# | Identity | Category | Mark No. | Description | Unit | Supply | Packing List | Receipt | PI-1 | PI-2 | PI-3 | PI-4 | Total MRS | نرخ | قراداد اولیه | 30% | نرخ تسعیر | ریال پیش پرداخت | ریال صورتحساب
1 | Bulk | - | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 277.5 | - | - |  |  |  |  | 0 | 1.077 | 298.8675 | 89.6603 | 290271 | 26025770.4278 | 0
2 | Bulk | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 22 | 22 | 22 |  | 22 |  |  | 22 | 1.508 | 33.176 | 9.9528 | 290271 | 2889009.2088 | 33.176
3 | Bulk | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | 2 | 2 |  | 1.5 |  |  | 1.5 | 2.297 | 3.4455 | 1.0336 | 290271 | 300038.6191 | 3.4455
4 | Bulk | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1558 | 1558 | 1558 |  | 1558 |  |  | 1558 | 1.149 | 1790.142 | 537.0426 | 290271 | 155887892.5446 | 1790.142
5 | Bulk | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 122.5 | 123 | 123 |  | 122.5 |  |  | 122.5 | 1.723 | 211.0675 | 63.3203 | 290271 | 18380032.2878 | 211.0675
6 | Bulk | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 4.5 | 5 | 5 |  | 4.5 |  |  | 4.5 | 2.44 | 10.98 | 3.294 | 290271 | 956152.674 | 10.98
7 | Bulk | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1104.5 | - | - |  |  |  |  | 0 | 1.192 | 1316.564 | 394.9692 | 290271 | 114648104.6532 | 0
8 | Bulk | - | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 323.5 | - | - |  |  |  |  | 0 | 1.795 | 580.6825 | 174.2047 | 290271 | 50566586.9873 | 0
9 | Bulk | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 3.5 | 4 | 4 |  | 3.5 |  |  | 3.5 | 2.656 | 9.296 | 2.7888 | 290271 | 809507.7648 | 9.296
10 | Bulk | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1697.5 | - | - |  |  |  |  | 0 | 1.508 | 2559.83 | 767.949 | 290271 | 222913324.179 | 0
11 | Bulk | - | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 131 | - | - |  |  |  |  | 0 | 2.104 | 275.624 | 82.6872 | 290271 | 24001696.2312 | 0
12 | Bulk | - | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | - | - |  |  |  |  | 0 | 2.943 | 4.4145 | 1.3244 | 290271 | 384420.3989 | 0
13 | Bulk | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 2009 | 110 | 110 | 110 |  |  |  | 110 | 1.579 | 3172.211 | 951.6633 | 290271 | 276240257.7543 | 173.69
14 | Bulk | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 956 | - | - |  |  |  |  | 0 | 2.44 | 2332.64 | 699.792 | 290271 | 203129323.632 | 0
15 | Bulk | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 37.5 | 38 | 38 | 37.5 |  |  |  | 37.5 | 3.302 | 123.825 | 37.1475 | 290271 | 10782841.9725 | 123.825
16 | Bulk | - | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | - | - |  |  |  |  | 0 | 4.235 | 6.3525 | 1.9058 | 290271 | 553183.9583 | 0
17 | Bulk | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1170.5 | 575 | 575 |  |  | 575 |  | 575 | 2.154 | 2521.257 | 756.3771 | 290271 | 219554337.1941 | 1238.55
18 | Bulk | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 620.5 | 621 | 621 | 204 |  | 416.5 |  | 620.5 | 3.086 | 1914.863 | 574.4589 | 290271 | 166748759.3619 | 1914.863
19 | Bulk | - | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 139 | - | - |  |  |  |  | 0 | 4.074 | 566.286 | 169.8858 | 290271 | 49312921.0518 | 0
20 | Bulk | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 76 | - | - |  |  |  |  | 0 | 2.496 | 189.696 | 56.9088 | 290271 | 16518974.2848 | 0
21 | Bulk | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1020 | - | - |  |  |  |  | 0 | 3.589 | 3660.78 | 1098.234 | 290271 | 318785481.414 | 0
22 | Bulk | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 133.5 | - | - |  |  |  |  | 0 | 4.737 | 632.3895 | 189.7168 | 290271 | 55069299.7664 | 0
23 | Bulk | - | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 68.5 | - | - |  |  |  |  | 0 | 5.956 | 407.986 | 122.3958 | 290271 | 35527951.2618 | 0
24 | Bulk | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 132 | 132 | 132 | 132 |  |  |  | 132 | 3.484 | 459.888 | 137.9664 | 290271 | 40047644.8944 | 459.888
25 | Bulk | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1479.5 | - | - |  |  |  |  | 0 | 4.88 | 7219.96 | 2165.988 | 290271 | 628723502.748 | 0
26 | Bulk | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 48.5 | 49 | 49 | 48.5 |  |  |  | 48.5 | 6.315 | 306.2775 | 91.8833 | 290271 | 26671042.8608 | 306.2775
27 | Bulk | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 371 | 371 | 371 | 371 |  |  |  | 371 | 7.822 | 2901.962 | 870.5886 | 290271 | 252706623.5106 | 2901.962
28 | Bulk | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 440 | 430 | 430 | 430 |  |  |  | 430 | 9.832 | 4326.08 | 1297.824 | 290271 | 376720670.304 | 4227.76
29 | Bulk | - | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 128 | - | - |  |  |  |  | 0 | 6.315 | 808.32 | 242.496 | 290271 | 70389556.416 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 132 | [6 empty] | 0 | 15.892 | 2097.744 | 629.3232 | 290271 | 182674274.5872 | 0
30 | Bulk | - | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 10 | - | - |  |  |  |  | 0 | 4.339 | 43.39 | 13.017 | 290271 | 3778457.607 | 0
31 | Bulk | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 178.5 | 84 | 84 | 84 |  |  |  | 84 | 7.751 | 1383.5535 | 415.066 | 290271 | 120481637.3995 | 651.084
32 | Bulk | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 348 | - | - |  |  |  |  | 0 | 9.472 | 3296.256 | 988.8768 | 290271 | 287042257.6128 | 0
33 | Bulk | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 238 | - | - |  |  |  |  | 0 | 11.553 | 2749.614 | 824.8842 | 290271 | 239439961.6182 | 0
34 | Bulk | - | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 187 | - | - |  |  |  |  | 0 | 7.751 | 1449.437 | 434.8311 | 290271 | 126218858.2281 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 223 | [6 empty] | 0 | 15.892 | 3543.916 | 1063.1748 | 290271 | 308608812.3708 | 0
35 | Bulk | - | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 40 | - | - |  |  |  |  | 0 | 5.134 | 205.36 | 61.608 | 290271 | 17883015.768 | 0
36 | Bulk | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 102.5 | - | - |  |  |  |  | 0 | 9.329 | 956.2225 | 286.8668 | 290271 | 83269098.3893 | 0
37 | Bulk | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 573.5 | - | - |  |  |  |  | 0 | 11.267 | 6461.6245 | 1938.4873 | 290271 | 562686661.5718 | 0
38 | Bulk | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 216 | 216 | 216 | 216 |  |  |  | 216 | 13.634 | 2944.944 | 883.4832 | 290271 | 256449551.9472 | 2944.944
39 | Bulk | - | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 241 | - | - |  |  |  |  | 0 | 9.329 | 2248.289 | 674.4867 | 290271 | 195783928.8957 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 328 | [6 empty] | 0 | 15.892 | 5212.576 | 1563.7728 | 290271 | 453917894.4288 | 0
40 | Bulk | - | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 177.5 | - | - |  |  |  |  | 0 | 9.329 | 1655.8975 | 496.7692 | 290271 | 144197706.9667 | 0
|  |  |  | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 253 | [6 empty] | 0 | 16.7 | 4225.1 | 1267.53 | 290271 | 367927200.63 | 0
41 | Bulk | - | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | Meter | 1.1 | - | - |  |  |  |  | 0 | 10.888 | 11.9768 | 3.593 | 290271 | 1042955.3138 | 0
42 | Bulk | - | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 5.5 | - | - |  |  |  |  | 0 | 7.801 | 42.9055 | 12.8717 | 290271 | 3736266.7172 | 0
43 | Bulk | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 87.78 | - | - |  |  |  |  | 0 | 15.892 | 1394.9998 | 418.4999 | 290271 | 121478392.6005 | 0
44 | Bulk | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1007.6 | - | - |  |  |  |  | 0 | 17.508 | 17641.0608 | 5292.3182 | 290271 | 1536206507.843 | 0
45 | Bulk | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1310.1 | - | - |  |  |  |  | 0 | 18.316 | 23995.7916 | 7198.7375 | 290271 | 2089584727.0571 | 0
46 | Bulk | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1243 | - | - |  |  |  |  | 0 | 19.124 | 23771.132 | 7131.3396 | 290271 | 2070021077.0316 | 0
47 | Bulk | - | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 403.7 | - | - |  |  |  |  | 0 | 19.932 | 8046.5484 | 2413.9645 | 290271 | 700703895.1849 | 0
48 | Bulk | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 822.8 | - | - |  |  |  |  | 0 | 20.74 | 17064.872 | 5119.4616 | 290271 | 1486031238.0936 | 0
49 | Bulk | - | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 11.88 | - | - |  |  |  |  | 0 | 21.548 | 255.9902 | 76.7971 | 290271 | 22291962.8865 | 0
50 | Bulk | - | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 229.9 | - | - |  |  |  |  | 0 | 17.508 | 4025.0892 | 1207.5268 | 290271 | 350510000.152 | 0
|  |  | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 229.9 | [6 empty] | 0 | 18.316 | 4210.8484 | 1263.2545 | 290271 | 366686152.7749 | 0
51 | Bulk | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 5869.6 | 5870 | 5870 |  |  | 5869.6 |  | 5869.6 | 11.313 | 66402.7848 | 19920.8354 | 290271 | 5782440824.0042 | 66402.7848
52 | Bulk | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 6906.9 | 6907 | 6907 |  | 4448.7 | 2458.2 |  | 6906.9 | 15.084 | 104183.6796 | 31255.1039 | 290271 | 9072450258.3515 | 104183.6796
53 | Bulk | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 2156 | 2156 | 2156 |  | 1973.58 | 182.42 |  | 2156 | 18.855 | 40651.38 | 12195.414 | 290271 | 3539975017.194 | 40651.38
54 | Bulk | - | Insulation-Acc | Accessories for Insulation | Set | 1 | - | - |  |  |  |  | 0 |  | 0 | 0 | 290271 | 0 | 0
55 | Bulk | - | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | Meter | 1.1 | - | - |  |  |  |  | 0 | 6.341 | 6.9751 | 2.0925 | 290271 | 607400.7756 | 0
56 | Bulk | - | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | Meter | 20.9 | - | - |  |  |  |  | 0 | 6.95 | 145.255 | 43.5765 | 290271 | 12648994.2315 | 0
57 | Bulk | - | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 8.8 | - | - |  |  |  |  | 0 | 9.627 | 84.7176 | 25.4153 | 290271 | 7377318.7409 | 0
58 | Bulk | - | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 1.1 | - | - |  |  |  |  | 0 | 14.464 | 15.9104 | 4.7731 | 290271 | 1385498.3155 | 0
59 | Bulk | - | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 2.2 | - | - |  |  |  |  | 0 | 12.024 | 26.4528 | 7.9358 | 290271 | 2303544.2126 | 0
60 | Bulk | - | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 908.6 | - | - |  |  |  |  | 0 | 11.092 | 10078.1912 | 3023.4574 | 290271 | 877621991.3446 | 0
61 | Bulk | - | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 193.6 | - | - |  |  |  |  | 0 | 14.626 | 2831.5936 | 849.4781 | 290271 | 246578851.7597 | 0
62 | Bulk | - | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 85.8 | - | - |  |  |  |  | 0 | 21.123 | 1812.3534 | 543.706 | 290271 | 157822090.1314 | 0
63 | Bulk | - | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 34.1 | - | - |  |  |  |  | 0 | 25.184 | 858.7744 | 257.6323 | 290271 | 74783191.1587 | 0
64 | Bulk | - | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 38.5 | - | - |  |  |  |  | 0 | 33.513 | 1290.2505 | 387.0751 | 290271 | 112356690.8656 | 0
65 | Bulk | - | 4YYYYYE06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 125.4 | - | - |  |  |  |  | 0 | 56.052 | 7028.9208 | 2108.6762 | 290271 | 612087560.861 | 0
66 | Bulk | - | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 39.6 | - | - |  |  |  |  | 0 | 44.68 | 1769.328 | 530.7984 | 290271 | 154075382.3664 | 0
|  |  | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | Meter | 43500 | [5 empty] | 43500 | 43500 | 0.61 | 26535 | 7960.5 | 294059 | 2340856669.5 | 26535
|  |  | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | Meter | 13000 | [5 empty] | 13000 | 13000 | 1 | 13000 | 3900 | 294059 | 1146830100 | 13000
|  |  | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | pcs | 72000 | [5 empty] | 72000 | 72000 | 0.08 | 5760 | 1728 | 294059 | 508133952 | 5760
|  |  | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | pcs | 3500 | [5 empty] | 3500 | 3500 | 0.08 | 280 | 84 | 294059 | 24700956 | 280
|  |  | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | pcs | 120000 | [5 empty] | 120000 | 120000 | 0.066 | 7920 | 2376 | 294059 | 698684184 | 7920
|  |  | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | pcs | 80000 | [5 empty] | 80000 | 80000 | 0.057 | 4560 | 1368 | 294059 | 402272712 | 4560
|  |  | ACCESSORY | واشر لئوپرن | pcs | 120000 | [5 empty] | 53100 | 53100 | 0.036 | 4320 | 1296 | 294059 | 381100464 | 1911.6
|  |  | ACCESSORY | ماستیک METAL SEALANT | pcs | 3090 | [6 empty] | 0 | 6.6 | 20394 | 6118.2 | 294059 | 1799111773.8 | 0
|  |  | ACCESSORY | کلیپس S | pcs | 3200 | [5 empty] | 3200 | 3200 | 0.09 | 288 | 86.4 | 294059 | 25406697.6 | 288
|  |  | ACCESSORY | سیم استنلس استیل به قطر 1mm | Meter | 106000 | [5 empty] | 106000 | 106000 | 0.21 | 22260 | 6678 | 294059 | 1963726002 | 22260
|  |  | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | Roll | 75 | [5 empty] | 75 | 75 | 15.95 | 1196.25 | 358.875 | 294059 | 105530423.625 | 1196.25
|  |  | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | Kg | 2075 | [5 empty] | 2075 | 2075 | 2.65 | 5498.75 | 1649.625 | 294059 | 485087077.875 | 5498.75
|  |  | ACCESSORY | Joint Sealant Mastic JAP 81-84 | Kg | 550 | [5 empty] | 550 | 550 | 3 | 1650 | 495 | 294059 | 145559205 | 1650
|  |  | ACCESSORY | Glass Cloth Mesh | Kg | 750 | [5 empty] | 750 | 750 | 1.3 | 975 | 292.5 | 294059 | 86012257.5 | 975

## Sheet1
# | Identity | Category | Mark No. | Description | Unit | Supply | Packing List | Receipt
1 | Bulk | - | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 277 | 278 | 278 | 0
2 | Bulk | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 22 | 22 | 22 | 0
3 | Bulk | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1 | 2 | 2 | 0
4 | Bulk | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1558 | 1558 | 1558 | 0
5 | Bulk | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 122 | 191 | 191 | 0
6 | Bulk | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 4 | 5 | 5 | 0
7 | Bulk | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1104 | 5099 | 5099 | 0
8 | Bulk | - | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 323 | 324 | 324 | 0
9 | Bulk | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 3 | 4 | 4 | 0
10 | Bulk | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1697 | 1698 | 1698 | 0
11 | Bulk | - | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 131 | 131 | 131 | 0
12 | Bulk | - | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1 | 2 | 2 | 0
13 | Bulk | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 2009 | 3050 | 3050 | 0
14 | Bulk | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 956 | 1963 | 1963 | 0
15 | Bulk | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 37 | 38 | 38 | 0
16 | Bulk | - | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1 | 2 | 2 | 0
17 | Bulk | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1170 | 1171 | 1171 | 0
18 | Bulk | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 620 | 621 | 621 | 0
19 | Bulk | - | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 139 | 139 | 139 | 0
20 | Bulk | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 76 | 118 | 118 | 0
21 | Bulk | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1020 | 1481 | 1481 | 0
22 | Bulk | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 133 | 134 | 134 | 0
23 | Bulk | - | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 68 | 69 | 69 | 0
24 | Bulk | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 132 | 132 | 132 | 0
25 | Bulk | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1480 | 1675 | 1675 | 0
26 | Bulk | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 48 | 177 | 177 | 0
27 | Bulk | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 371 | 371 | 371 | 0
28 | Bulk | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 440 | 440 | 440 | 0
29 | Bulk | - | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 128 | - | - | #VALUE!
30 | Bulk | - | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 10 | 10 | 10 | 0
31 | Bulk | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 178 | 666 | 666 | 0
32 | Bulk | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 348 | 348 | 348 | 0
33 | Bulk | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 238 | 238 | 238 | 0
34 | Bulk | - | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 187 | - | - | #VALUE!
35 | Bulk | - | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 40 | 40 | 40 | 0
36 | Bulk | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 102 | 521 | 521 | 0
37 | Bulk | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 573 | 573 | 573 | 0
38 | Bulk | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 216 | 216 | 216 | 0
39 | Bulk | - | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 241 | - | - | #VALUE!
40 | Bulk | - | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 177 | - | - | #VALUE!
41 | Bulk | - | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | Meter | 1 | 1 | 1 | 0
42 | Bulk | - | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 6 | 6 | 6 | 0
43 | Bulk | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 88 | 1374 | 1374 | 0
44 | Bulk | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1 | 953 | 953 | 0
45 | Bulk | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1008 | 1479 | 1479 | 0
46 | Bulk | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1310 | 1975 | 1975 | 0
47 | Bulk | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1243 | 1243 | 1243 | 0
48 | Bulk | - | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 404 | 404 | 404 | 0
49 | Bulk | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 823 | 1034 | 1034 | 0
50 | Bulk | - | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 12 | 12 | 12 | 0
51 | Bulk | - | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 230 | - | - | #VALUE!
52 | Bulk | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 5870 | 6199 | 5870 | 329
53 | Bulk | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 6907 | 7937 | 6907 | 1030
54 | Bulk | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 2156 | 2281 | 2156 | 125
55 | Bulk | - | Insulation-Acc | Accessories for Insulation | Set | 1 | - | - | #VALUE!
56 | Bulk | - | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | Meter | 1 | 1 | 1 | 0
57 | Bulk | - | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | Meter | 21 | 21 | 21 | 0
58 | Bulk | - | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 9 | 9 | 9 | 0
59 | Bulk | - | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 1 | 1 | 1 | 0
60 | Bulk | - | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 2 | 2 | 2 | 0
61 | Bulk | - | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 909 | 909 | 909 | 0
62 | Bulk | - | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 194 | 194 | 194 | 0
63 | Bulk | - | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 86 | 86 | 86 | 0
64 | Bulk | - | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 34 | 34 | 34 | 0
65 | Bulk | - | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 39 | 39 | 39 | 0
66 | Bulk | - | 4YYYYYE06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 125 | - | - | #VALUE!
67 | Bulk | - | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 40 | 40 | 40 | 0
68 | Bulk | - | 4YYYYYG06 | 6" , Thk. 60mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | Meter | 1 | 125 | 125 | 0