## کنترل قرارداد
خلاصه مالی خرید ایستگاه تقلیل گاز متان | [8 empty] | شماره قرارداد: ADSH-P-P0-GE-074 | [5 empty] | 1 | bulk | New | 170.00 Pieces
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ شروع قرارداد: 1401/02/08 | [5 empty] | 2 | bulk | New | 1,200.00 Pieces
فروشنده: سیستم های صنعتی سامان | [8 empty] | تاریخ تهیه گزارش: 1402/01/16 | [5 empty] | 3 | bulk | New | 28.00 Pieces
[15 empty] | 4 | bulk | New | 60.00 Pieces
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده | درصد کالای دریافتی | مبلغ کل (یورو) | فاکتور |  |  |  |  | 5 | bulk | New | 120.00 Pieces
1 | PK-523-01 | Gas Pressure Reducing Station (GPRS PACKAGE) | SET | 1 | 0 | 0 | 0 | 0% | 0 | 36 | 36 | 0 |  |  | 6 | bulk | New | 140.00 Pieces
2 | IR79511505 | Q.SONIC PLUS 4" ANSI 600 | Piece | 1 | 35000 | 35000 | 1 | 100% | 35000 |  |  |  | 2
3 | 1511644 | CABINET FOR FLOW METER INCLODING FC1 | Piece | 1 | 35000 | 35000 | 1 | 100% | 35000 |  |  |  | 3
4 | F01/A | Cyclone Scrubber | Piece | 1 | 105000 | 105000 | 1 | 100% | 105000 |  |  |  | 1
5 | F01/B | Cyclone Scrubber | Piece | 1 | 105000 | 105000 | 1 | 100% | 105000 |  |  |  | 1
6 | F03/A | Dry Gas Filter | Piece | 1 | 58333.334 | 58333.334 | 1 | 100% | 58333.334 |  |  |  | 1
7 | F03/B | Dry Gas Filter | Piece | 1 | 58333.333 | 58333.333 | 1 | 100% | 58333.333 |  |  |  | 1
8 | F03/C | Dry Gas Filter | Piece | 1 | 58333.333 | 58333.333 | 1 | 100% | 58333.333 |  |  |  | 1
9 | F02/A | Gas Filter Separator | Piece | 1 | 58333.334 | 58333.334 | 1 | 100% | 58333.334 |  |  |  | 1
10 | F02/B | Gas Filter Separator | Piece | 1 | 58333.333 | 58333.333 | 1 | 100% | 58333.333 |  |  |  | 1
11 | F02/C | Gas Filter Separator | Piece | 1 | 58333.333 | 58333.333 | 1 | 100% | 58333.333 |  |  |  | 1
12 |  |  |  | 2 | 140000 | 280000 | 0 | 0% | 0
13 |  |  |  | 3 | 46666.667 | 140000.001 | 0 | 0% | 0
14 |  |  |  | 3 | 46666.667 | 140000.001 | 0 | 0% | 0
15 | IR79511581 | Q.SONIC PLUS 6" ANSI 300 | Piece | 1 | 35000 | 35000 | 1 | 100% | 35000 |  |  |  | 2
16 | IR79511521 | Q.SONIC PLUS 10" ANSI 300 | Piece | 1 | 35000 | 35000 | 1 | 100% | 35000 |  |  |  | 2
17 | 1511616 | CABINET FOR FLOW METER INCLODING FC1 | Piece | 1 | 35000 | 35000 | 1 | 100% | 35000 |  |  |  | 3
18 | 1511655 | CABINET FOR FLOW METER INCLODING FC1 | Piece | 1 | 35000 | 35000 | 1 | 100% | 35000 |  |  |  | 3
19 | C4000005395674 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
20 | C4000005404151 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
21 | C4000005395483 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
22 | C4000005404347 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
23 | C4000005395593 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 | 4 | 3 | 1942.24 | 4 |  | 7 | bulk | New | 30.00 Pieces
24 | C4000005404280 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
25 | C4000005395596 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
26 | C4000005395587 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
27 | C4000005395691 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
28 | C4000005395690 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
29 | C4000005395640 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
30 | C4000005404322 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
31 | C4000005404283 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
32 | C4000005404154 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
33 | C4000005404277 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
34 | C4000005404317 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | Piece | 1 | 485.56 | 485.56 | 1 | 100% | 485.56 |  |  |  | 4
35 |  |  |  | 1 | 27231.04 | 27231.04 | 0 | 0% | 0
36 |  |  |  | 1 | 35000 | 35000 | 0 | 0% | 0
[6 empty] | 1400000.002 |  |  | 777768.96
6889510142
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (یورو) | توضیحات: | [6 empty] | 6889510142
6889510142
جمع کالای دریافتی | [5 empty] | 1400000.002 | کلیه کالاهای موضوع قرارداد باید از زمان پرداخت پیش پرداخت ظرف 240 روز تقویمی تحویل گردد.تاریخ پرداخت پیش پرداخت 1401/02/31 میباشد و تاریخ تحویل 1401/09/07 میباشد. طی MRS-SAM-074-001 درمورخ 1401/09/07 به انبار رسید شده است.
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 0
جمع صورتحساب | [5 empty] | 1400000.002
کسور:
استهلاک پیش پرداخت (25%) | [5 empty] | 350000.0005
سپرده حسن انجام کار (5%) | [5 empty] | 0 | MRS-SAM-074-004 & MRS-SAM-074-002 & MRS-SAM-074-003.درمورخ 1401/10/18 به انبار رسید شده است
جرائم تاخیر 10% مبلغ قرارداد | [5 empty] | 0
جمع کسور | [5 empty] | 350000.0005
خالص قابل پرداخت | [5 empty] | 1750000.0025
خلاصه محاسبات پرداخت صورت حساب 1 : | [5 empty] | (یورو) |  | (ریالی)
جمع کالای دریافتی | [5 empty] | 560000 |  | 221771760000
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 0 |  | 0
جمع صورتحساب | [5 empty] | 560000 |  | 221771760000
کسور:
استهلاک پیش پرداخت (25%) | [5 empty] | -140000 | 270750 | -37905000000
سپرده حسن انجام کار (10%) | [5 empty] | -56000 | 437778 | -24515568000
جرائم تاخیر 10% مبلغ قرارداد | [5 empty] | 0 | 0 | 0
جمع کسور | [5 empty] | -196000 |  | -62420568000
خالص قابل پرداخت | [5 empty] | 364000 | 437778 | 159351192000
توضیحات در خصوص نرخ های تسعیر:
1- محاسبه مبلغ خالص قابل پرداخت با نرخ تسعیر فروش اسکناس در سامانه سنا در تاریخ 1402/01/15 لحاظ شده است ولیکن MRS & PI (1401/09/07) تحویل سایت شده است.
2- در محاسبه نرخ تسعیر جهت استهلاک پیش پرداخت ، عینا از نرخ تسعیر پرداخت های انجام شده در همان تاریخ استفاده شده است. پیش پرداخت به شرح ذیل انجام شده است:
[5 empty] | تاریخ | مبلغ ارزی | نرخ تسعیر | معادل ریالی
پیش پرداخت (25%) |  |  |  |  | 1401/2/08 | 350000.0005 | 270750 | 94762500135.3751
استهلاک پیش پرداخت (25%)-پارت1 |  |  |  |  | 1401/01/15 | -140000 | 270750 | -37905000000
[6 empty] | 210000.0005 |  | 56857500135.3751
خلاصه محاسبات پرداخت صورت حساب 2 : | [5 empty] | (یورو) |  | (ریالی)
جمع کالای دریافتی | [5 empty] | 217768.96 |  | 89946964584.96
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 0 |  | 0
جمع صورتحساب | [5 empty] | 217768.96 |  | 89946964584.96
کسور:
استهلاک پیش پرداخت (25%) | [5 empty] | -54442.24 | 270750 | -14740236480
سپرده حسن انجام کار (10%) | [5 empty] | -21776.896 | 460468 | -10027563747.328
جرائم تاخیر 10% مبلغ قرارداد | [5 empty] | 0 | 0 | 0
جمع کسور | [5 empty] | -76219.136 |  | -24767800227.328
خالص قابل پرداخت | [5 empty] | 141549.824 | 460468 | 65179164357.632
توضیحات در خصوص نرخ های تسعیر:
1- محاسبه مبلغ خالص قابل پرداخت با نرخ تسعیر فروش اسکناس در سامانه سنا در تاریخ 1402/02/06 لحاظ شده است ولیکن MRS & PI (1401/10/18) تحویل سایت شده است.
2- در محاسبه نرخ تسعیر جهت استهلاک پیش پرداخت ، عینا از نرخ تسعیر پرداخت های انجام شده در همان تاریخ استفاده شده است. پیش پرداخت به شرح ذیل انجام شده است:
[5 empty] | تاریخ | مبلغ ارزی | نرخ تسعیر | معادل ریالی
پیش پرداخت (25%) |  |  |  |  | 1401/2/08 | 350000.0005 | 270750 | 94762500135.3751
استهلاک پیش پرداخت (25%)-پارت1 |  |  |  |  | 1401/01/15 | -140000 | 270750 | -37905000000
استهلاک پیش پرداخت (25%)-پارت2.3.4 | [5 empty] | -54442.24 | 270750 | -14740236480
[6 empty] | 155557.7605 |  | 42117263655.3751

## Sheet1
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
6 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F03/A | Dry Gas Filter | 1 |  |  |  |  | 1 | Piece | 317 | 1 | 58333.334 | 1
7 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F03/B | Dry Gas Filter | 1 |  |  |  |  | 1 | Piece | 317 | 1 | 58333.333 | 1
8 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F03/C | Dry Gas Filter | 1 |  |  |  |  | 1 | Piece | 317 | 1 | 58333.333 | 1
3 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F02/A | Gas Filter Separator | 1 |  |  |  |  | 1 | Piece | 1296 | 2 | 58333.334 | 1
4 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F02/B | Gas Filter Separator | 1 |  |  |  |  | 1 | Piece | 1296 | 2 | 58333.333 | 1
5 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F02/C | Gas Filter Separator | 1 |  |  |  |  | 1 | Piece | 1296 | 2 | 58333.333 | 1
1 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F01/A | Cyclone Scrubber | 1 |  |  |  |  | 1 | Piece | 607 | 3 | 105000 | 1
2 | OPI-SAM-740-001 | 2022-11-28 | SACR-PL-SAM-740-001 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 1 | pressure vessel | Sub Item | PK-523-01 | F01/B | Cyclone Scrubber | 1 |  |  |  |  | 1 | Piece | 607 | 3 | 105000 | 1
9 | OPI-SAM-740-002 | 2023-01-08 | SACR-PL-SAM-740-002 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 2 |  | Sub Item | PK-523-01 | IR79511505 | Q.SONIC PLUS 4" ANSI 600 | 1 |  |  |  |  | 1 | Piece | 80 | 1 | 35000 | 2
10 | OPI-SAM-740-002 | 2023-01-08 | SACR-PL-SAM-740-002 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 2 |  | Sub Item | PK-523-01 | IR79511581 | Q.SONIC PLUS 6" ANSI 300 | 1 |  |  |  |  | 1 | Piece | 106 | 2 | 35000 | 2
11 | OPI-SAM-740-002 | 2023-01-08 | SACR-PL-SAM-740-002 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 2 |  | Sub Item | PK-523-01 | IR79511521 | Q.SONIC PLUS 10" ANSI 300 | 1 |  |  |  |  | 1 | Piece | 228 | 3 | 35000 | 2
12 | OPI-SAM-740-003 | 2023-01-08 | SACR-PL-SAM-740-003 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 3 | CABINET FOR FLOW METER INCLODING FC1 | Sub Item | PK-523-01 | 1511644 | CABINET FOR FLOW METER INCLODING FC1 | 1 |  |  |  |  | 1 | Piece | 112 | 1 | 35000 | 2
13 | OPI-SAM-740-003 | 2023-01-08 | SACR-PL-SAM-740-003 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 3 | CABINET FOR FLOW METER INCLODING FC1 | Sub Item | PK-523-01 | 1511616 | CABINET FOR FLOW METER INCLODING FC1 | 1 |  |  |  |  | 1 | Piece | 112 | 2 | 35000 | 2
14 | OPI-SAM-740-003 | 2023-01-08 | SACR-PL-SAM-740-003 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 3 | CABINET FOR FLOW METER INCLODING FC1 | Sub Item | PK-523-01 | 1511655 | CABINET FOR FLOW METER INCLODING FC1 | 1 |  |  |  |  | 1 | Piece | 112 | 3 | 35000 | 2
15 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395674 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 1 | 485.56 | 2
23 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404151 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | 1 |  |  |  |  | 1 | Piece | 2 | 1 | 485.56 | 2
16 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395483 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 2 | 485.56 | 2
24 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404347 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | 1 |  |  |  |  | 1 | Piece | 2 | 2 | 485.56 | 2
17 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395593 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 3 | 485.56 | 2
25 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404280 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | 1 |  |  |  |  | 1 | Piece | 2 | 3 | 485.56 | 2
18 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395596 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 4 | 485.56 | 2
19 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395587 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 4 | 485.56 | 2
20 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395691 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 4 | 485.56 | 2
21 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395690 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 4 | 485.56 | 2
22 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005395640 | HONEYWELL SMART TEM. TRANSMITTER STT 750 WITH CALIBRATION REPORT MANUAL CD & RTD SENSOR | 1 |  |  |  |  | 1 | Piece | 1 | 4 | 485.56 | 2
26 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404322 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS , 2WAY VEELOK MANIFOLD | 1 |  |  |  |  | 1 | Piece | 2 | 5 | 485.56 | 2
27 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404283 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | 1 |  |  |  |  | 1 | Piece | 1 | 5 | 485.56 | 2
28 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404154 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | 1 |  |  |  |  | 1 | Piece | 1 | 5 | 485.56 | 2
29 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404277 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | 1 |  |  |  |  | 1 | Piece | 1 | 5 | 485.56 | 2
30 | OPI-SAM-740-004 | 2023-01-08 | SACR-PL-SAM-740-004 | PO ADSH-P-PO-GE-074 | Saman Co | DDP Site | 4 |  | Sub Item | PK-523-01 | C4000005404317 | HONEYWELL SMART PRESSURE TRANSMITTER STA700, WITH CALIBRATION REPORT & CERTIFICATE OF CONFORMANCE, MANUAL CD , BRACKETS | 1 |  |  |  |  | 1 | Piece | 1 | 5 | 485.56 | 2
777768.96