## Packing List Items
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 130 |  | Sub Item | TK-520-04 | 1 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (G-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
2 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 131 |  | Sub Item | TK-520-04 | 2 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L1, T1-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
3 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 132 |  | Sub Item | TK-520-04 | 3 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L2-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
4 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 133 |  | Sub Item | TK-520-05 | 4 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (G-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
5 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 134 |  | Sub Item | TK-520-05 | 5 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L1 T1-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
6 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 135 |  | Sub Item | TK-520-05 | 6 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L2-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
7 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 136 |  | Sub Item | TK-520-07 | 7 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (G-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
8 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 137 |  | Sub Item | TK-520-07 | 8 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L1 T1-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
9 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 138 |  | Sub Item | TK-520-07 | 9 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L2-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
10 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 139 |  | Sub Item | TK-520-07 | 10 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (N-21) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
11 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 140 |  | Sub Item | TK-520-13 | 11 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L2-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
12 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 141 |  | Sub Item | TK-520-13 | 12 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L1, T1-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
13 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 142 |  | Sub Item | TK-520-13 | 13 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (N-20) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
14 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 143 |  | Sub Item | TK-520-15A | 14 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L1 T1-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
15 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 144 |  | Sub Item | TK-520-15A | 15 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L2-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
16 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 145 |  | Sub Item | TK-520-15A | 16 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (N-20) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
17 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 146 |  | Sub Item | TK-520-15B | 17 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L1 T1-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
18 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 147 |  | Sub Item | TK-520-15B | 18 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (L2-12) FOR GUIDE POLE | 4 |  |  |  |  | 4 | Piece | 11000000
19 | OPI-SAB-125-001 | 2023-05-10 | SACR-PL-SAB-125-001 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 148 |  | Sub Item | TK-520-15B | 19 | UCP SHAFT C.S SIZE Ø 30 BALL BEARING (N-20) FOR GUIDE POLE | 4 | 1 |  |  |  | 3 | Piece | 11000000 | Advise Vendor of Overage/Shortage
20 | OPI-SAB-125-003 | 2023-06-16 | SACR-PL-SAB-125-003 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 3 |  | Sub Item | TK-520-04 | TK-520-04-23 | SUPPORT PLATE A283-C 173*150*10 | 4 |  |  |  |  | 4 | Piece
21 | OPI-SAB-125-003 | 2023-06-16 | SACR-PL-SAB-125-003 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 3 |  | Sub Item | TK-520-05 | TK-520-05-24 | SUPPORT PLATE A283-C 173*150*10 | 4 |  |  |  |  | 4 | Piece
22 | OPI-SAB-125-003 | 2023-06-16 | SACR-PL-SAB-125-003 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 3 |  | Sub Item | TK-520-07 | TK-520-07-25 | SUPPORT PLATE A283-C 173*150*10 | 4 |  |  |  |  | 4 | Piece
23 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-07 | TK-520-07-6 | GUIDE SA-516 70N PL100*41*25 (Assembled item includes 4 items) | 28 |  |  |  |  | 28 | Piece
24 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-07 | TK-520-07-6 | GUIDE COPPER PL100*25*17 | 36 |  |  |  |  | 36 | Piece | 68400000
25 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-07 | TK-520-07-6 | BOLT&NUT M8 L:16 SA-193 B7 | 72 |  |  |  |  | 72 | Piece
26 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-07 | TK-520-07-6 | GUIDE SA-516 70N PL100*30*25 | 8 |  |  |  |  | 8 | Piece
27 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-13 | TK-520-13-4 | GUIDE SA-516 70N PL100*41*25 (Assembled item includes 3 items) | 28 |  |  |  |  | 28 | Piece
28 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-13 | TK-520-13-4 | GUIDE COPPER PL100*25*17 | 28 |  |  |  |  | 28 | Piece
29 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-13 | TK-520-13-4 | BOLT&NUT M8 L:16 SA-193 B7 | 56 |  |  |  |  | 56 | Piece
30 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-04 | TK-520-04-5 | GUIDE SA-516 70N PL100*41*25 (Assembled item includes 4 items) | 20 |  |  |  |  | 20 | Piece
31 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-04 | TK-520-04-5 | GUIDE COPPER PL100*25*17 | 28 |  |  |  |  | 28 | Piece
32 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-04 | TK-520-04-5 | BOLT&NUT M8 L:16 SA-193 B7 | 56 |  |  |  |  | 56 | Piece
33 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-04 | TK-520-04-5 | GUIDE SA-516 70N PL100*30*25 | 8 |  |  |  |  | 8 | Piece
34 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-05 | TK-520-05-5 | GUIDE SA-516 70N PL100*41*25 (Assembled item includes 4 items) | 20 |  |  |  |  | 20 | Piece
35 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-05 | TK-520-05-5 | GUIDE COPPER PL100*25*17 | 28 |  |  |  |  | 28 | Piece
36 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-05 | TK-520-05-5 | BOLT&NUT M8 L:16 SA-193 B7 | 56 |  |  |  |  | 56 | Piece
37 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-05 | TK-520-05-5 | GUIDE SA-516 70N PL100*30*25 | 8 |  |  |  |  | 8 | Piece
38 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15A | TK-520-15A-4 | GUIDE SA-516 70N PL100*41*25 (Assembled item includes 3 items) | 28 |  |  |  |  | 28 | Piece
39 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15A | TK-520-15A-4 | GUIDE COPPER PL100*25*17 | 28 |  |  |  |  | 28 | Piece
40 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15A | TK-520-15A-4 | BOLT&NUT M8 L:16 SA-193 B7 | 56 |  |  |  |  | 56 | Piece
41 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15B | TK-520-15B-4 | GUIDE SA-516 70N PL100*41*25 (Assembled item includes 3 items) | 28 |  |  |  |  | 28 | Piece
42 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15B | TK-520-15B-4 | GUIDE COPPER PL100*25*17 | 28 |  |  |  |  | 28 | Piece
43 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15B | TK-520-15B-4 | BOLT&NUT M8 L:16 SA-193 B7 | 56 |  |  |  |  | 56 | Piece
44 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-04 | TK-520-04-1 | ROLLER SUPPORT A36 800*10*10 THK8 | 2 |  |  |  |  | 2 | Piece | 55000000
45 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-04 | TK-520-04-2 | BOLT&NUT M16 L:40 SA-193 B7/SA-194-2H | 48 |  |  |  |  | 48 | Piece
46 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-05 | TK-520-05-3 | ROLLER SUPPORT A36 800*10*10 THK8 | 2 |  |  |  |  | 2 | Piece
47 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-05 | TK-520-05-4 | BOLT&NUT M16 L:40 SA-193 B7/SA-194-2H | 48 |  |  |  |  | 48 | Piece
48 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-06 | TK-520-06-5 | ROLLER SUPPORT A36 800*10*10 THK8 | 2 |  |  |  |  | 2 | Piece
49 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-07 | TK-520-07-6 | BOLT&NUT M16 L:40 SA-193 B7/SA-194-2H | 64 |  |  |  |  | 64 | Piece
50 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-13 | TK-520-13-7 | BOLT&NUT M16 L:40 SA-193 B7/SA-194-2H | 48 |  |  |  |  | 48 | Piece
51 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15A | TK-520-15A-8 | BOLT&NUT M16 L:40 SA-193 B7/SA-194-2H | 48 |  |  |  |  | 48 | Piece
52 | OPI-SAB-125-004 | 2023-06-16 | SACR-PL-SAB-125-004 | ADSH-P-PO-GE-125 | Saba Kara | DDP Site | 4 |  | Sub Item | TK-520-15B | TK-520-15B-9 | BOLT&NUT M16 L:40 SA-193 B7/SA-194-2H | 48 |  |  |  |  | 48 | Piece