## 1
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962165601 | 6962165601 | FLOOD LIGHT LIGHTING FIXTURE, With Metal Halide Lamp, Explosion Proof Type, IP65, Ex”de” IIB T3, 400W, 230V AC, 50Hz, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, double sealed on steel wire armored cable, Min. Luminaire flux: 50,000 lm, Structure Mounted "LD-45" | 8 |  |  |  |  | 8 | Set | 30
2 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962165601 | 6962165601 | FLOOD LIGHT LIGHTING FIXTURE, With Metal Halide Lamp, Explosion Proof Type, IP65, Ex”de” IIB T3, 400W, 230V AC, 50Hz, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, double sealed on steel wire armored cable, Min. Luminaire flux: 50,000 lm, Structure Mounted "LD-45" | 8 |  |  |  |  | 8 | Set | 30
3 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962165601 | 6962165601 | FLOOD LIGHT LIGHTING FIXTURE, With Metal Halide Lamp, Explosion Proof Type, IP65, Ex”de” IIB T3, 400W, 230V AC, 50Hz, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, double sealed on steel wire armored cable, Min. Luminaire flux: 50,000 lm, Structure Mounted "LD-45" | 8 |  |  |  |  | 8 | Set | 30
4 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962165601 | 6962165601 | FLOOD LIGHT LIGHTING FIXTURE, With Metal Halide Lamp, Explosion Proof Type, IP65, Ex”de” IIB T3, 400W, 230V AC, 50Hz, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, double sealed on steel wire armored cable, Min. Luminaire flux: 50,000 lm, Structure Mounted "LD-45" | 6 |  |  |  |  | 6 | Set | 30
5 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
6 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
7 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
8 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
9 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
10 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
11 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
12 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
13 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
14 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
15 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
16 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
17 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
18 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
19 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
20 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
21 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
22 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
23 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
24 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
25 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
26 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
27 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
28 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
29 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125601 | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
30 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
31 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
32 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
33 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
34 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
35 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
36 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
37 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
38 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
39 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
40 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
41 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
42 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
43 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
44 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
45 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
46 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
47 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
48 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
49 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
50 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
51 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
52 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
53 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
54 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962125701 | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | 1 |  |  |  |  | 1 | Set | 38
55 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
56 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
57 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
58 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
59 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
60 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
61 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
62 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
63 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
64 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 30 |  |  |  |  | 30 | Set | 12
65 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356601 | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | 15 |  |  |  |  | 15 | Set | 12
66 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962357601 | 6962357601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | 15 |  |  |  |  | 15 | Set | 12
67 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962357601 | 6962357601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | 30 |  |  |  |  | 30 | Set | 12
68 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962357601 | 6962357601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | 30 |  |  |  |  | 30 | Set | 12
69 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962357601 | 6962357601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | 5 |  |  |  |  | 5 | Set | 12
70 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 20 |  |  |  |  | 20 | Set | 12
71 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
72 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
73 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
74 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
75 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
76 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
77 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
78 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
79 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
80 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
81 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
82 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
83 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
84 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
85 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
86 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
87 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
88 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
89 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
90 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
91 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
92 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
93 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
94 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
95 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
96 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358601 | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
97 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962359601 | 6962359601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted "LD-08" | 30 |  |  |  |  | 30 | Set | 12
98 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962359601 | 6962359601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted "LD-08" | 30 |  |  |  |  | 30 | Set | 12
99 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962359601 | 6962359601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted "LD-08" | 30 |  |  |  |  | 30 | Set | 12
100 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962359601 | 6962359601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted "LD-08" | 10 |  |  |  |  | 10 | Set | 12
101 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962356701 | 6962356701 | LED Lighting Fixture, Exde IIC T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface Mounted (LD-01) | 10 |  |  |  |  | 10 | Set | 12
102 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962357701 | 6962357701 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | 5 |  |  |  |  | 5 | Set | 12
103 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358701 | 6962358701 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 7 |  |  |  |  | 7 | Set | 12
104 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962359701 | 6962359701 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted "LD-08" | 3 |  |  |  |  | 3 | Set | 12
105 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Main Item | 6962358701 | 6962358701 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 30 |  |  |  |  | 30 | Set | 12
106 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 1 | Ceiling Mounting Bracket C/WITH: :. S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962356601 | 630 |  |  |  |  | 630 | Piece
107 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 2 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm ) & S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962357601 | 160 |  |  |  |  | 160 | Piece
108 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 3 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm ) & S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962358601 | 1600 |  |  |  |  | 1600 | Piece
109 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 4 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm ) & S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962359601 | 200 |  |  |  |  | 200 | Piece
110 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 5 | Ceiling Mounting Bracket C/WITH: :. S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962356701 | 20 |  |  |  |  | 20 | Piece
111 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 6 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm ) & S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962357701 | 10 |  |  |  |  | 10 | Piece
112 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 7 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm ) & S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962358701 | 74 |  |  |  |  | 74 | Piece
113 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 8 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm ) & S.Steel Bolt M8 * 16 With Spring Washer M8 / Related to Adish Code: 6962359701 | 6 |  |  |  |  | 6 | Piece
114 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 9 | SEMC TYPE 700 Exd REDUCER-M25(M)*M20(F) C/WITH: Sealing Washer , Locknut / Related to Adish Code: 6962165601 | 30 |  |  |  |  | 30 | Piece
115 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 10 | SEMC Ex CABLE GLAND : 453 - A - 20mm C/WITH: Sealing Washer , Locknut / | 30 |  |  |  |  | 30 | Piece
116 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 11 | SEMC TYPE 800 Exd PLUG - M25 C/WITH: Sealing Washer , Locknut / | 30 |  |  |  |  | 30 | Piece
117 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 12 | SEMC Ex CABLE GLAND : 453 - A - 20mm C/WITH: Sealing Washer , Locknut / Related to Adish Code: 6962125601 | 25 |  |  |  |  | 25 | Piece
118 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 13 | SEMC TYPE 800 Exd PLUG - M20 C/WITH: Sealing Washer , Locknut / | 25 |  |  |  |  | 25 | Piece
119 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 14 | SEMC Ex CABLE GLAND : 453 - A - 20mm C/WITH: Sealing Washer , Locknut / Related to Adish Code: 6962125701 | 50 |  |  |  |  | 50 | Piece
120 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 15 | SEMC Ex CABLE GLAND : 453 - A - 20mm C/WITH: Sealing Washer , Locknut / Related to Adish Code: 6962356601 6962357601 6962358601 6962359601 | 2590 |  |  |  |  | 2590 | Piece
121 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 16 | SEMC Ex CABLE GLAND : 453 - A - 20mm C/WITH: Sealing Washer , Locknut / Related to Adish Code: 6962356611 6962357611 6962358611 6962359611 | 530 |  |  |  |  | 530 | Piece
122 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 17 | SEMC Ex CABLE GLAND : 453 - A - 20mm C/WITH: Sealing Washer , Locknut / Related to Adish Code: 6962356701 6962357701 6962358701 6962359701 | 110 |  |  |  |  | 110 | Piece
123 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 18 | SEMC Ex CABLE GLAND : 453 - A - 20mm C/WITH: Sealing Washer , Locknut / Related to Adish Code: 6962357711 6962358711 | 20 |  |  |  |  | 20 | Piece
124 | OPI-SEMC-103-001 | 2023-03-04 | SACR-PL-SEMC-103-001 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 1 |  | Sub Item | 6962-MISC | Sub Item 19 | S.Steel Bolt M12 * 45 With: Spring & Flat Washer & Nut M12 / Related to Adish Code: 6962125601 6962125701 | 150 |  |  |  |  | 150 | Piece

## ف 1
خلاصه مالی خرید روشنایی |  |  |  | شماره قرارداد: ADSH-P-PO-GE-103
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی |  |  |  | تاریخ قرارداد: 1401/06/13 | 1401/08/12
فروشنده: ماشین سازی شمال |  |  |  | تاریخ تهیه گزارش: 1401/12/27 | 50
|  | یورو | نرخ تسعیر (ریال) | معادل ریالی
جمع کالای دریافتی |  | 288910.5 |  | 114630136450.1697
مالیات و عوارض بر ارزش افزوده |  | 26001.945 |  | 10316712280.5153 | 396766.945
جمع صورتحساب |  | 314912.445 |  | 124946848730.685 | 396767
124946866065.315
کسور: |  |  |  |  | 17334.63
پیش پرداخت (25%) |  | -72227.625 | 291965 | -21087938533.125 | 25,548,068,864 | 1401/05/26
|  | -72227.625 |  | -21087938533.125
خالص قابل پرداخت |  | 242684.82 | 427958 | 103858910197.56
کسر می شود: علی الحساب مبلغ پرداخت شده بابت پکینگ لیست های 1 |  | -163567.4529 | 427958 | -70000000000
مانده پرداختنی بابت پکینگ 1 + 9% ارزش افزوده کل قرارداد |  | -79117.3671 | 427958 | -33858910197.56
توضیحات در خصوص نرخ های تسعیر:
1- محاسبه مبلغ خالص قابل پرداخت، با استفاده از نرخ تسعیر فروش اسکناس در سامانه سنا در تاریخ 1401/12/27 انجام شده است(مطابق با تاریخ تحویل نرخ 1401/12/13 به ارزش 475.794 ریال بود که بدلیل تاخیرات تحویل نرخ روز پرداخت با ارزش کمتر محاسبه شد).
2- با توجه به تاریخ پیش پرداخت مورخ 1401/06/13 و توافق قرارداد مبنی بر تحویل کالا در 50 روز تقویمی فروشنده 120 روز تاخیر در تحویل کالا دارد که با توجه ارسال الباقی کالاها در پارت بعدی جرائم غیر مجاز پس از اخد استعلام در تسویه نهایی محاسبه و کسر میگردد.
3- در محاسبه نرخ تسعیر جهت استهلاک پیش پرداخت، عینا از نرخ تسعیر پیش پرداخت ریالی استفاده شده است. پیش پرداخت به شرح ذیل پرداخت شده است:
| تاریخ | مبلغ ارزی | نرخ تسعیر | معادل ریالی
پیش پرداخت | 1401/06/13 | 87503.875 | 291965 | 25548068864.375
استهلاک پیش پرداخت کسر شده پارت 1 | 1401/12/27 | -72227.625 | 291965 | -21087938533.125
باقیمانده پیش پرداخت |  | 15276.25 |  | 4460130331.25

## 2
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
125 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962356611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery backup Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Surface mounted type "LD-01" | 30 |  |  |  |  | 30 | Set | 12 |  | فاقد گلند می باشد
126 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962356611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery backup Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Surface mounted type "LD-01" | 30 |  |  |  |  | 30 | Set | 12 |  | فاقد گلند می باشد
127 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962356611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery backup Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Surface mounted type "LD-01" | 20 |  |  |  |  | 20 | Set | 12 |  | فاقد گلند می باشد
128 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962357611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted type "LD-05" | 10 |  |  |  |  | 10 | Set | 12 |  | فاقد گلند می باشد
129 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962357611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted type "LD-05" | 5 |  |  |  |  | 5 | Set | 12 |  | فاقد گلند می باشد
130 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962358611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported type "LD-07" | 25 |  |  |  |  | 25 | Set | 12 |  | فاقد گلند می باشد
131 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962358611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported type "LD-07" | 30 |  |  |  |  | 30 | Set | 12 |  | فاقد گلند می باشد
132 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962358611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported type "LD-07" | 30 |  |  |  |  | 30 | Set | 12 |  | فاقد گلند می باشد
133 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962358611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported type "LD-07" | 30 |  |  |  |  | 30 | Set | 12 |  | فاقد گلند می باشد
134 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962358611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported type "LD-07" | 30 |  |  |  |  | 30 | Set | 12 |  | فاقد گلند می باشد
135 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962358611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported type "LD-07" | 20 |  |  |  |  | 20 | Set | 12 |  | فاقد گلند می باشد
136 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962359611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted bolts "LD-08" | 5 |  |  |  |  | 5 | Set | 12 |  | فاقد گلند می باشد
137 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962357711 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | 4 |  |  |  |  | 4 | Set | 12 |  | فاقد گلند می باشد
138 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Main Item | - | 6962358711 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | 6 |  |  |  |  | 6 | Set | 12 |  | فاقد گلند می باشد
139 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Sub Item | 6962-MISC | Sub Item 1 | Ceiling Mounting Bracket C/WITH: :. S.Steel Bolt M8 * 16 With Spring Washer M8 Related to Adish Code:6962356611 | 160 |  |  |  |  | 160 | Piece
140 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Sub Item | 6962-MISC | Sub Item 2 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm) & S.Steel Bolt M8 * 16 With Spring Washer M8 Related to Adish Code:6962357611 | 30 |  |  |  |  | 30 | Piece
141 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Sub Item | 6962-MISC | Sub Item 3 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm) & S.Steel Bolt M8 * 16 With Spring Washer M8 Related to Adish Code:6962358611 | 330 |  |  |  |  | 330 | Piece
142 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Sub Item | 6962-MISC | Sub Item 4 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm) & S.Steel Bolt M8 * 16 With Spring Washer M8 Related to Adish Code:6962359611 | 10 |  |  |  |  | 10 | Piece
143 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Sub Item | 6962-MISC | Sub Item 5 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm) & S.Steel Bolt M8 * 16 With Spring Washer M8 Related to Adish Code:6962357711 | 8 |  |  |  |  | 8 | Piece
144 | OPI-SEMC-103-002 | 2023-07-15 | SACR-PL-SEMC-103-002 | ADSH-P-PO-GE-103 | MACHINE SAZI SHOMAL | EX WORK | 2 |  | Sub Item | 6962-MISC | Sub Item 6 | PIPE CLAMP 2" C/With Bolt & Nut (Size: M8 x 25 mm) & S.Steel Bolt M8 * 16 With Spring Washer M8 Related to Adish Code:6962358711 | 12 |  |  |  |  | 12 | Piece

## ف 2 فاینال4
خلاصه مالی خرید روشنایی |  |  |  | شماره قرارداد: ADSH-P-PO-GE-103
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی |  |  |  | تاریخ قرارداد: 1401/06/13 | 1401/08/12
فروشنده: ماشین سازی شمال |  |  |  | تاریخ تهیه گزارش: 1402/05/17 | 50
|  | یورو | نرخ تسعیر (ریال) | معادل ریالی
جمع کالای دریافتی |  | 60500 |  | 18030536425 |  |  | 349410.5
|  | 605 |  | 180305364.25
مالیات و عوارض بر ارزش افزوده |  | 5445 |  | 1622748278.25 | 298025.3955 |  | 3179635.55
جمع صورتحساب |  | 66550 |  | 19833590067.5 | 298025.3955
19833590067.5
کسور: |  |  |  |  | 0
پیش پرداخت (25%) |  | -15276.25 | 291965 | -4460130331.25 | 25,548,068,864 | 1401/05/26
|  | -15276.25 |  | -4460130331.25
خالص قابل پرداخت |  | 51273.75 | 299831 | 15373459736.25
توضیحات در خصوص نرخ های تسعیر:
1- محاسبه مبلغ خالص قابل پرداخت، با استفاده از نرخ تسعیر فروش اسکناس در سامانه سنا در تاریخ 1402/05/17 انجام شده است(مطابق با تاریخ تحویل نرخ 1402/04/24 به ارزش 463/580 ریال بود که بدلیل تاخیرات تحویل نرخ روز پرداخت با ارزش کمتر محاسبه شد).کنسل گردید و بند 2 طبق دستور مدیریت و قرارداد در محاسبات در نظر گرفته شده است.
2- با توجه به تاریخ پیش پرداخت مورخ 1401/06/13 و توافق قرارداد مبنی بر تحویل کالا در 50 روز تقویمی فروشنده 120 روز تاخیر در تحویل کالا مرحله 1 و 237 روز تاخیر در تحویل کالا مرحله 2 دارد، که طبق اعلام نظر واحد برنامه ریزی تاریخ تحویل قراردادی روز 1401/08/29 بوده و کل کالا تحویل میشد که طبق قرارداد نرخ همان روز در محاسبات در نظر گرفته خواهد شد.نرخ مورخ 1401/08/29 سنا اسکناس 299/831 ریال در نظر گرفته شده است.
3- در محاسبه نرخ تسعیر جهت استهلاک پیش پرداخت، عینا از نرخ تسعیر پیش پرداخت ریالی استفاده شده است. پیش پرداخت به شرح ذیل پرداخت شده است:
| تاریخ | مبلغ ارزی | نرخ تسعیر | معادل ریالی
پیش پرداخت | 1401/06/13 | 87503.875 | 291965 | 25548068864.375
استهلاک پیش پرداخت کسر شده پارت 1 | 1401/12/27 | -72227.625 | 291965 | -21087938533.125
استهلاک پیش پرداخت کسر شده پارت 2 | 1402/05/17 | -15276.25 | 291965 | -4460130331.25
باقیمانده پیش پرداخت |  | 0 |  | 0

## کنسلی-فاینال2
خلاصه مالی خرید روشنایی |  |  |  | شماره قرارداد: ADSH-P-PO-GE-103
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی |  |  |  | تاریخ قرارداد: 1401/06/13 | 1401/08/12
فروشنده: ماشین سازی شمال |  |  |  | تاریخ تهیه گزارش: 1402/05/17 | 50
|  | یورو | نرخ تسعیر (ریال) | معادل ریالی
جمع کالای دریافتی |  | 60500 |  | 25253283137.5 |  |  | 349410.5
بسته بندی |  | 605 |  | 252532831.375
مالیات و عوارض بر ارزش افزوده |  | 5445 |  | 2272795482.375 | 417409.6386 |  | 3179635.55
جمع صورتحساب |  | 66550 |  | 27778611451.25 | 417409.6386
27778611451.25
کسور: |  |  |  |  | 0
پیش پرداخت (25%) |  | -15276.25 | 291965 | -4460130331.25 | 25,548,068,864 | 1401/05/26
|  | -15276.25 |  | -4460130331.25
4460130331.25
خالص قابل پرداخت |  | 51273.75 | 454784 | 23318481120
توضیحات در خصوص نرخ های تسعیر:
1- محاسبه مبلغ خالص قابل پرداخت، با استفاده از نرخ تسعیر فروش اسکناس در سامانه سنا در تاریخ 1402/05/17 انجام شده است(مطابق با تاریخ تحویل نرخ 1402/04/24 به ارزش 463/580 ریال بود که بدلیل تاخیرات تحویل نرخ روز پرداخت با ارزش کمتر محاسبه شد).
2- با توجه به تاریخ پیش پرداخت مورخ 1401/06/13 و توافق قرارداد مبنی بر تحویل کالا در 50 روز تقویمی فروشنده 120 روز تاخیر در تحویل کالا مرحله 1 و 237 روز تاخیر در تحویل کالا مرحله 2 داردکه مستلزم اخذ استعلام بابت جرائم غیر مجاز از واحد برنامه ریزی جهت محاسبه و کسر می باشد.
3- در محاسبه نرخ تسعیر جهت استهلاک پیش پرداخت، عینا از نرخ تسعیر پیش پرداخت ریالی استفاده شده است. پیش پرداخت به شرح ذیل پرداخت شده است:
| تاریخ | مبلغ ارزی | نرخ تسعیر | معادل ریالی
پیش پرداخت | 1401/06/13 | 87503.875 | 291965 | 25548068864.375
استهلاک پیش پرداخت کسر شده پارت 1 | 1401/12/27 | -72227.625 | 291965 | -21087938533.125
استهلاک پیش پرداخت کسر شده پارت 2 | 1402/05/17 | -15276.25 | 291965 | -4460130331.25
باقیمانده پیش پرداخت |  | 0 |  | 0

## Sheet2
# | Identity | Category | Mark No. | Description | Unit | Supply | Packing List | Receipt
1 | Bulk | - | 6962165601 | FLOOD LIGHT LIGHTING FIXTURE, With Metal Halide Lamp, Explosion Proof Type, IP65, Ex”de” IIB T3, 400W, 230V AC, 50Hz, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, double sealed on steel wire armored cable, Min. Luminaire flux: 50,000 lm, Structure Mounted "LD-45" | Set | 30 | 30 | 30 | 1 | 860 | 25800
2 | Bulk | - | 6962359701 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted "LD-08" | Set | 3 | 3 | 3 | 11 | 165 | 495
3 | Bulk | - | 6962125601 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIB T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | Set | 25 | 25 | 25 | 2 | 750 | 18750
4 | Bulk | - | 6962125701 | FLOOD LIGHTING FIXTURE, With LED Panel, Explosion Proof Type, IP65, Ex”de” IIC T3, 200W, 230VAC, 50Hz, Body: Copper Free Aluminum, Connection box to be provided for Cable entry, 2xM20 cable entries equipped with 1 cable glands and 1 stopping plug, double sealed for steel wire armored cable, Min. Luminaire flux: 26,000 lm, Structure Mounted "LD-45" | Set | 25 | 25 | 25 | 3 | 750 | 18750
5 | Bulk | - | 6962357601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | Set | 80 | 80 | 80 | 5 | 165 | 13200
6 | Bulk | - | 6962358601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | Set | 800 | 800 | 800 | 6 | 165 | 132000
7 | Bulk | - | 6962359601 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted "LD-08" | Set | 100 | 100 | 100 | 7 | 165 | 16500
8 | Bulk | - | 6962355611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Surface mounted type "LD-01" | Set | 80 | 0 | 0 |  |  | 0
9 | Bulk | - | 6962357611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted type "LD-05" | Set | 15 | 0 | 0 |  |  | 0
10 | Bulk | - | 6962358611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported type "LD-07" | Set | 165 | 0 | 0 |  |  | 0
11 | Bulk | - | 6962359611 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIB T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Stanchion mounted bolts "LD-08" | Set | 5 | 0 | 0 |  |  | 0
12 | Bulk | - | 6962357701 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | Set | 5 | 5 | 5 | 9 | 165 | 825
13 | Bulk | - | 6962358701 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | Set | 37 | 37 | 37 | 10 | 165 | 6105
14 | Bulk | - | 6962357711 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Bracket mounted "LD-05" | Set | 4 | 0 | 0 |  |  | 0
15 | Bulk | - | 6962358711 | LED LIGHTING FIXTURE, WITH LED PANEL, Explosion Proof Type, IP65, Ex”de” IIC T3, 40W, 230V AC, 50Hz, Battery back up Type (min. 90min), Enclosure material: Copper free aluminum, Connection box to be provided for Cable entry 2xM20 cable entries equipped with 2 cable glands, double sealed for steel wire armored cable, with earthing terminal, internal wiring, Min. Luminous flux: 4,600 lm, Handrail supported "LD-07" | Set | 6 | 0 | 0 |  |  | 0
16 | Bulk | - | 6962-MISC | Lighting Fixtures Misellanious Items | Set | 1 | 0 | 0 |  |  | 0
17 | Bulk | - | 6962356601 | LED Lighting Fixture, Exde IIB T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface mounted (LD-01) | Set | 315 | 315 | 315 | 4 | 165 | 51975
18 | Bulk | - | 6962356701 | LED Lighting Fixture, Exde IIC T3 type, IP65, With 40 W LED Panel, 230V AC, 50Hz, TYPE-1, Surface Mounted (LD-01) | Set | 10 | 10 | 10 | 8 | 165 | 1650
[10 empty] | 3680 | 286050
2860.5
288910.5