## کنترل قرارداد (6)
خلاصه مالی خرید عایق گرم و سرد و آلومینیوم | [14 empty] | شماره قرارداد: ADSH-P-PO-GE-098
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [14 empty] | تاریخ قرارداد: 1401/04/22
فروشنده: شرکت جهان عایق پارس | [14 empty] | تاریخ تهیه گزارش: 1402/02/19
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (یورو) | مبلغ قرارداد (یورو) | مقادیر رسید شده مرحله اول | مقادیر رسید شده مرحله دوم | مقادیر رسید شده مرحله سوم | مقادیر رسید شده مرحله چهارم | مقادیر رسید شده مرحله پنجم | مقادیر رسید شده مرحله ششم | جمع مقادیر رسید شده | درصد کالای دریافتی | مبلغ کالای دریافتی (یورو) | مازاد بر قرارداد و الحاقیه
1 | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 277.5 |  |  | 0 | 0 | 0 | 277.5 | 0 | 0 | 277.5 | 100% | 0 | 0
2 | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 22 |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 100% | 0 | 0
3 | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 100% | 0 | 0
4 | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1558 |  |  | 1558 | 0 | 0 | 0 | 0 | 0 | 1558 | 100% | 0 | 0
5 | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 122.5 |  |  | 122.5 | 0 | 0 | 0 | 0 | 68 | 190.5 | 155.5% | 0 | 0
6 | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 4.5 |  |  | 4.5 | 0 | 0 | 0 | 0 | 0 | 4.5 | 100% | 0 | 0
7 | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1104.5 |  |  | 0 | 0 | 1104.5 | 0 | 3000 | 994 | 5098.5 | 461.6% | 0 | 0
8 | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 323.5 |  |  | 0 | 0 | 0 | 323.5 | 0 | 0 | 323.5 | 100% | 0 | 0
9 | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 3.5 |  |  | 3.5 | 0 | 0 | 0 | 0 | 0 | 3.5 | 100% | 0 | 0
10 | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1697.5 |  |  | 0 | 0 | 0 | 1697.5 | 0 | 0 | 1697.5 | 100% | 0 | 0
11 | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 131 |  |  | 0 | 0 | 131 | 0 | 0 | 0 | 131 | 100% | 0 | 0
12 | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 |  |  | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 100% | 0 | 0
13 | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 2009 |  |  | 110 | 0 | 1782 | 117 | 0 | 1041 | 3050 | 151.8% | 0 | 0
14 | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 956 |  |  | 0 | 0 | 636 | 320 | 720 | 287 | 1963 | 205.3% | 0 | 0
15 | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 37.5 |  |  | 37.5 | 0 | 0 | 0 | 0 | 0 | 37.5 | 100% | 0 | 0
16 | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1.5 |  |  | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 100% | 0 | 0
17 | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1170.5 |  |  | 575 | 0 | 96 | 499.5 | 0 | 0 | 1170.5 | 100% | 0 | 0
18 | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 620.5 |  |  | 620.5 | 0 | 0 | 0 | 0 | 0 | 620.5 | 100% | 0 | 0
19 | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 139 |  |  | 0 | 139 | 0 | 0 | 0 | 0 | 139 | 100% | 0 | 0
20 | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 76 |  |  | 0 | 0 | 76 | 0 | 0 | 42 | 118 | 155.3% | 0 | 0
21 | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1020 |  |  | 0 | 0 | 921 | 99 | 0 | 461 | 1481 | 145.2% | 0 | 0
22 | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 133.5 |  |  | 0 | 0 | 45 | 88.5 | 0 | 0 | 133.5 | 100% | 0 | 0
23 | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 68.5 |  |  | 0 | 0 | 0 | 68.5 | 0 | 0 | 68.5 | 100% | 0 | 0
24 | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 132 |  |  | 132 | 0 | 0 | 0 | 0 | 0 | 132 | 100% | 0 | 0
25 | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 1479.5 |  |  | 0 | 0 | 0 | 1479.5 | 0 | 195 | 1674.5 | 113.2% | 0 | 0
26 | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 48.5 |  |  | 48.5 | 0 | 128 | 0 | 0 | 0 | 176.5 | 363.9% | 0 | 0
27 | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 371 |  |  | 371 | 0 | 0 | 0 | 0 | 0 | 371 | 100% | 0 | 0
28 | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 440 |  |  | 430 | 0 | 0 | 10 | 0 | 0 | 440 | 100% | 0 | 0
29 | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 128 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
30 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 132 |  |  | 0 | 132 | 0 | 579 | 0 | 0 | 711 | 538.6% | 0 | 0
31 | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 10 |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 100% | 0 | 0
32 | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 178.5 |  |  | 84 | 0 | 138.5 | 143 | 300 | 0 | 665.5 | 372.8% | 0 | 0
33 | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 348 |  |  | 0 | 0 | 0 | 348 | 0 | 0 | 348 | 100% | 0 | 0
34 | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 238 |  |  | 0 | 0 | 0 | 238 | 0 | 0 | 238 | 100% | 0 | 0
35 | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 187 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
36 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 223 |  |  | 0 | 223 | 0 | 0 | 0 | 0 | 223 | 100% | 0 | 0
37 | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 40 |  |  | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 100% | 0 | 0
38 | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 102.5 |  |  | 0 | 0 | 0 | 521 | 0 | 0 | 521 | 508.3% | 0 | 0
39 | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 573.5 |  |  | 0 | 155 | 0 | 418 | 0 | 0 | 573 | 99.91% | 0 | 0
40 | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 216 |  |  | 216 | 0 | 0 | 0 | 0 | 0 | 216 | 100% | 0 | 0
41 | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 241 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
42 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 328 |  |  | 0 | 328 | 0 | 24 | 0 | 0 | 352 | 107.3% | 0 | 0
43 | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | متر | 177.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
44 | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 253 |  |  | 0 | 253 | 0 | 0 | 700.08 | 0 | 953.08 | 376.7% | 0 | 0
45 | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | متر | 1.1 |  |  | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 0 | 0
46 | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 5.5 |  |  | 0 | 5.5 | 0 | 0 | 0 | 0 | 5.5 | 100% | 0 | 0
47 | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 87.78 |  |  | 0 | 87.78 | 0 | 0 | 0 | 0 | 87.78 | 100% | 0 | 0
48 | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1007.6 |  |  | 0 | 1237.5 | 0 | 241.2 | 0 | 0 | 1478.7 | 146.8% | 0 | 0
49 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1310.1 |  |  | 0 | 1310.1 | 0 | 153.6 | 0 | 0 | 1463.7 | 111.7% | 0 | 0
50 | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 1243 |  |  | 0 | 1243 | 0 | 0 | 0 | 0 | 1243 | 100% | 0 | 0
51 | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 403.7 |  |  | 0 | 403.7 | 0 | 0 | 0 | 0 | 403.7 | 100% | 0 | 0
52 | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 822.8 |  |  | 0 | 822.8 | 0 | 211 | 0 | 0 | 1033.8 | 125.6% | 0 | 0
53 | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 11.88 |  |  | 0 | 11.88 | 0 | 0 | 0 | 0 | 11.88 | 100% | 0 | 0
54 | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
55 | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | متر مربع | 229.9 |  |  | 0 | 229.9 | 0 | 280.8 | 0 | 0 | 510.7 | 222.1% | 0 | 0
56 | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 5869.6 |  |  | 5869.601 | 0 | 0 | 0 | 0 | 328.9 | 6198.501 | 105.6% | 0 | 0
57 | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 6906.9 |  |  | 6906.9 | 0 | 0 | 0 | 0 | 1030.5 | 7937.4 | 114.9% | 0 | 0
58 | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | متر مربع | 2156 |  |  | 2156 | 0 | 0 | 0 | 0 | 125.4 | 2281.4 | 105.8% | 0 | 0
59 | Insulation-Acc | Accessories for Insulation | ست | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
60 | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | متر | 1.1 |  |  | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 0 | 0
61 | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | متر | 20.9 |  |  | 0 | 20.9 | 0 | 0 | 0 | 0 | 20.9 | 100% | 0 | 0
62 | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 8.8 |  |  | 0 | 8.8 | 0 | 0 | 0 | 0 | 8.8 | 100% | 0 | 0
63 | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 1.1 |  |  | 0 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 100% | 0 | 0
64 | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 2.2 |  |  | 0 | 2.2 | 0 | 0 | 0 | 0 | 2.2 | 100% | 0 | 0
65 | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 908.6 |  |  | 0 | 908.6 | 0 | 0 | 0 | 0 | 908.6 | 100% | 0 | 0
66 | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 193.6 |  |  | 0 | 193.6 | 0 | 0 | 0 | 0 | 193.6 | 100% | 0 | 0
67 | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 85.8 |  |  | 0 | 85.8 | 0 | 0 | 0 | 0 | 85.8 | 100% | 0 | 0
68 | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | متر | 34.1 |  |  | 0 | 34.1 | 0 | 0 | 0 | 0 | 34.1 | 100% | 0 | 0
69 | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | متر | 38.5 |  |  | 0 | 38.5 | 0 | 0 | 0 | 0 | 38.5 | 100% | 0 | 0
70 | 4YYYYYG06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 125.4 |  |  | 0 | 125.4 | 0 | 0 | 0 | 0 | 125.4 | 100% | 0 | 0
71 | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | متر | 39.6 |  |  | 0 | 39.6 | 0 | 0 | 0 | 0 | 39.6 | 100% | 0 | 0
72 | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | متر | 43500 |  |  | 43500 | 0 | 0 | 0 | 0 | 0 | 43500 | 100% | 0 | 0
73 | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | متر | 13000 |  |  | 13000 | 0 | 0 | 0 | 0 | 0 | 13000 | 100% | 0 | 0
74 | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | عدد | 72000 |  |  | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 100% | 0 | 0
75 | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | عدد | 3500 |  |  | 3500 | 0 | 0 | 0 | 0 | 0 | 3500 | 100% | 0 | 0
76 | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | عدد | 120000 |  |  | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 100% | 0 | 0
77 | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | عدد | 80000 |  |  | 80000 | 0 | 0 | 0 | 0 | 0 | 80000 | 100% | 0 | 0
78 | ACCESSORY | واشر لئوپرن | عدد | 120000 |  |  | 53100 | 0 | 66900 | 0 | 0 | 0 | 120000 | 100% | 0 | 0
79 | ACCESSORY | ماستیک METAL SEALANT | عدد | 3090 |  |  | 0 | 0 | 3090 | 750 | 0 | 0 | 3840 | 124.3% | 0 | 0
80 | ACCESSORY | کلیپس S | عدد | 3200 |  |  | 3200 | 0 | 0 | 0 | 0 | 0 | 3200 | 100% | 0 | 0
81 | ACCESSORY | سیم استنلس استیل به قطر 1mm | متر | 106000 |  |  | 106000 | 0 | 0 | 0 | 0 | 0 | 106000 | 100% | 0 | 0
82 | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | حلقه | 75 |  |  | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 100% | 0 | 0
83 | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | کیلوگرم | 2075 |  |  | 2075 | 0 | 0 | 0 | 0 | 0 | 2075 | 100% | 0 | 0
84 | ACCESSORY | Joint Sealant Mastic JAP 81-84 | کیلوگرم | 550 |  |  | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 100% | 0 | 0
85 | ACCESSORY | Glass Cloth Mesh | کیلوگرم | 750 |  |  | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 100% | 0 | 0
|  |  |  | 606812.96 |  | 0 | 517019.001 | 8042.96 | 75058 | 8931.1 | 4720.08 | 4572.8 |  |  | 0 | 0

## Packing List Items
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-JAY-098-001 | 2022-08-30 | SACR-PL-JAY-098-001 | ADSH-P-PO-GE-098 | jahanayegh | 1 |  | Main Item | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 270 |  |  |  |  | 270 | Meter
2 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | 22 |  |  |  |  | 22 | Meter
3 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1.5 |  |  |  |  | 1.5 | Meter
4 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 3.5 |  |  |  |  | 3.5 | Meter
5 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 110 |  |  |  |  | 110 | Meter
6 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 132 |  |  |  |  | 132 | Meter
7 | OPI-JAY-098-002 | 2022-08-30 | SACR-PL-JAY-098-002 | ADSH-P-PO-GE-098 | jahanayegh | 2 |  | Main Item | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 101 |  |  |  |  | 101 | Meter
8 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1558 |  |  |  |  | 1558 | Meter
9 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 122.5 |  |  |  |  | 122.5 | Meter
10 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 4.5 |  |  |  |  | 4.5 | Meter
11 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 37.5 |  |  |  |  | 37.5 | Meter
12 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 48.5 |  |  |  |  | 48.5 | Meter
13 | OPI-JAY-098-003 | 2022-08-30 | SACR-PL-JAY-098-003 | ADSH-P-PO-GE-098 | jahanayegh | 3 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 84 |  |  |  |  | 84 | Meter
14 | OPI-JAY-098-005 | 2022-09-12 | SACR-PL-JAY-098-004 | ADSH-P-PO-GE-098 | jahanayegh | 4 |  | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 4448.7 |  |  |  |  | 4448.7 | Sq. Meter
15 | OPI-JAY-098-005 | 2022-09-12 | SACR-PL-JAY-098-004 | ADSH-P-PO-GE-098 | jahanayegh | 4 |  | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 1973.58 |  |  |  |  | 1973.58 | Sq. Meter
16 | OPI-JAY-098-004 | 2022-09-04 | SACR-PL-JAY-098-005 | ADSH-P-PO-GE-098 | jahanayegh | 5 |  | Main Item | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 180 |  |  |  |  | 180 | Meter |  |  | 180بسته 1متری
17 | OPI-JAY-098-006 | 2022-09-12 | SACR-PL-JAY-098-006 | ADSH-P-PO-GE-098 | jahanayegh | 6 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 225 |  |  |  |  | 225 | Meter
18 | OPI-JAY-098-006 | 2022-09-12 | SACR-PL-JAY-098-006 | ADSH-P-PO-GE-098 | jahanayegh | 6 |  | Main Item | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 36 |  |  |  |  | 36 | Meter
19 | OPI-JAY-098-007 | 2022-09-12 | SACR-PL-JAY-098-007 | ADSH-P-PO-GE-098 | jahanayegh | 7 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 205 |  |  |  |  | 205 | Meter
20 | OPI-JAY-098-007 | 2022-09-12 | SACR-PL-JAY-098-007 | ADSH-P-PO-GE-098 | jahanayegh | 7 |  | Main Item | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 204 |  |  |  |  | 204 | Meter
21 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Main Item | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 5869.6 |  |  |  |  | 5869.6 | Sq. Meter
22 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 2458.2 |  |  |  |  | 2458.2 | Sq. Meter
23 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 182.42 |  |  |  |  | 182.42 | Sq. Meter
24 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | تسمه استنلس استیل سایز 0/5 * 13 میلیمتر | 43500 |  |  |  |  | 43500 | Meter
25 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | تسمه استنلس استیل سایز 0/5*19 میلیمتر | 13000 |  |  |  |  | 13000 | Meter
26 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | بست استنلس استیل سایز 0/5*13 میلیمتر | 72000 |  |  |  |  | 72000 | Piece
27 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | بست استنلس استیل سایز 0/5*19میلیمتر | 3500 |  |  |  |  | 3500 | Piece
28 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 میلیمتر | 120000 |  |  |  |  | 120000 | Piece
29 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 میلیمتر | 80000 |  |  |  |  | 80000 | Piece
30 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | واشر نئو پرن | 53100 |  |  |  |  | 53100 | Piece
31 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | S کلیپس | 3200 |  |  |  |  | 3200 | Piece
32 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | سیم استنلس استیل به قطر 1 میلیمتر | 106000 |  |  |  |  | 106000 | Meter
33 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | نوار چسب نخ دار تقویت شده فیلامنت با عرض 50 میلی متر | 75 |  |  |  |  | 75 | Roll
34 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | 2075 |  |  |  |  | 2075 | Kg
35 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Joint Sealant Mastic JAP 81-84 | 550 |  |  |  |  | 550 | Kg
36 | OPI-JAY-098-008 | 2022-09-12 | SACR-PL-JAY-098-008 | ADSH-P-PO-GE-098 | jahanayegh | 8 |  | Sub Item | Insulation-Acc | ACCESSORY | Glass Cloth Mesh | 750 |  |  |  |  | 750 | Sq. Meter
37 | OPI-JAY-098-009 | 2022-09-12 | SACR-PL-JAY-098-009 | ADSH-P-PO-GE-098 | jahanayegh | 9 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 575 |  |  |  |  | 575 | Meter
38 | OPI-JAY-098-009 | 2022-09-12 | SACR-PL-JAY-098-009 | ADSH-P-PO-GE-098 | jahanayegh | 9 |  | Main Item | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 416.5 |  |  |  |  | 416.5 | Meter
39 | OPI-JAY-098-010 | 2022-09-20 | SACR-PL-JAY-098-010 | ADSH-P-PO-GE-098 | jahanayegh | 10 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 155 |  |  |  |  | 155 | Meter
40 | OPI-JAY-098-010 | 2022-09-20 | SACR-PL-JAY-098-010 | ADSH-P-PO-GE-098 | jahanayegh | 10 |  | Main Item | - | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 139 |  |  |  |  | 139 | Meter
41 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 87.78 |  |  |  |  | 87.78 | Sq. Meter
42 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 328 |  |  |  |  | 328 | Sq. Meter
43 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 223 |  |  |  |  | 223 | Sq. Meter
44 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 132 |  |  |  |  | 132 | Sq. Meter
45 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 240 |  |  |  |  | 240 | Sq. Meter
46 | OPI-JAY-098-011 | 2022-10-22 | SACR-PL-JAY-098-011 | ADSH-P-PO-GE-098 | jahanayegh | 11 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 100.8 |  |  |  |  | 100.8 | Sq. Meter
47 | OPI-JAY-098-012 | 2022-10-31 | SACR-PL-JAY-098-012 | ADSH-P-PO-GE-098 | jahanayegh | 12 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 253 |  |  |  |  | 253 | Sq. Meter
48 | OPI-JAY-098-012 | 2022-10-31 | SACR-PL-JAY-098-012 | ADSH-P-PO-GE-098 | jahanayegh | 12 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 307.2 |  |  |  |  | 307.2 | Sq. Meter
49 | OPI-JAY-098-012 | 2022-10-31 | SACR-PL-JAY-098-012 | ADSH-P-PO-GE-098 | jahanayegh | 12 | Iso Blanket Mineral Wool with Stainless Steel on One Side | Main Item | - | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 403.7 |  |  |  |  | 403.7 | Sq. Meter
50 | OPI-JAY-098-013 | 2022-11-07 | SACR-PL-JAY-098-013 | ADSH-P-PO-GE-098 | jahanayegh | 13 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 229.9 |  |  |  |  | 229.9 | Sq. Meter
51 | OPI-JAY-098-013 | 2022-11-07 | SACR-PL-JAY-098-013 | ADSH-P-PO-GE-098 | jahanayegh | 13 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 634.1 |  |  |  |  | 634.1 | Sq. Meter
52 | OPI-JAY-098-014 | 2022-11-07 | SACR-PL-JAY-098-014 | ADSH-P-PO-GE-098 | jahanayegh | 14 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 676.8 |  |  |  |  | 676.8 | Sq. Meter
53 | OPI-JAY-098-014 | 2022-11-07 | SACR-PL-JAY-098-014 | ADSH-P-PO-GE-098 | jahanayegh | 14 |  | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 187.2 |  |  |  |  | 187.2 | Sq. Meter
54 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | 1.1 |  |  |  |  | 1.1 | Meter
55 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | 20.9 |  |  |  |  | 20.9 | Meter
56 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | 1.1 |  |  |  |  | 1.1 | Meter
57 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | 5.5 |  |  |  |  | 5.5 | Meter
58 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 8.8 |  |  |  |  | 8.8 | Meter
59 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 1.1 |  |  |  |  | 1.1 | Meter
60 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 2.2 |  |  |  |  | 2.2 | Meter
61 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 908.6 |  |  |  |  | 908.6 | Meter
62 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | 193.6 |  |  |  |  | 193.6 | Meter
63 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 85.8 |  |  |  |  | 85.8 | Meter
64 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | 34.1 |  |  |  |  | 34.1 | Meter
65 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | 38.5 |  |  |  |  | 38.5 | Meter
66 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYG06 | 6" , Thk. 60mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | 125.4 |  |  |  |  | 125.4 | Meter
67 | OPI-JAY-098-018 | 2022-11-08 | SACR-PL-JAY-098-015 | ADSH-P-PO-GE-098 | jahanayegh | 15 | COLD INSULATION | Main Item | - | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | 39.6 |  |  |  |  | 39.6 | Meter
68 | OPI-JAY-098-015 | 2022-11-07 | SACR-PL-JAY-098-016 | ADSH-P-PO-GE-098 | jahanayegh | 16 |  | Main Item | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 648 |  |  |  |  | 648 | Sq. Meter
69 | OPI-JAY-098-016 | 2022-11-07 | SACR-PL-JAY-098-017 | ADSH-P-PO-GE-098 | jahanayegh | 17 |  | Main Item | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 648 |  |  |  |  | 648 | Sq. Meter
70 | OPI-JAY-098-016 | 2022-11-07 | SACR-PL-JAY-098-017 | ADSH-P-PO-GE-098 | jahanayegh | 17 |  | Main Item | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 174.84 |  |  |  |  | 174.84 | Sq. Meter
71 | OPI-JAY-098-017 | 2022-11-07 | SACR-PL-JAY-098-018 | ADSH-P-PO-GE-098 | jahanayegh | 18 |  | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 997.5 |  |  |  |  | 997.5 | Sq. Meter
72 | OPI-JAY-098-017 | 2022-11-07 | SACR-PL-JAY-098-018 | ADSH-P-PO-GE-098 | jahanayegh | 18 |  | Main Item | - | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 11.88 |  |  |  |  | 11.88 | Sq. Meter
73 | OPI-JAY-098-019 | 2022-11-13 | SACR-PL-JAY-098-019 | ADSH-P-PO-GE-098 | jahanayegh | 19 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 600 |  |  |  |  | 600 | Meter
74 | OPI-JAY-098-019 | 2022-11-13 | SACR-PL-JAY-098-019 | ADSH-P-PO-GE-098 | jahanayegh | 19 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 684 |  |  |  |  | 684 | Meter
75 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 504.5 |  |  |  |  | 504.5 | Meter
76 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 630 |  |  |  |  | 630 | Meter
77 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 96 |  |  |  |  | 96 | Meter
78 | OPI-JAY-098-020 | 2022-11-21 | SACR-PL-JAY-098-020 | ADSH-P-PO-GE-098 | jahanayegh | 20 |  | Main Item | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 57 |  |  |  |  | 57 | Meter
79 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 45 |  |  |  |  | 45 | Meter
80 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 128 |  |  |  |  | 128 | Meter
81 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 131 |  |  |  |  | 131 | Meter
82 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 20 |  |  |  |  | 20 | Meter
83 | OPI-JAY-098-021 | 2022-11-21 | SACR-PL-JAY-098-021 | ADSH-P-PO-GE-098 | jahanayegh | 21 |  | Main Item | - | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 10 |  |  |  |  | 10 | Meter
84 | OPI-JAY-098-022 | 2022-11-26 | SACR-PL-JAY-098-022 | ADSH-P-PO-GE-098 | jahanayegh | 22 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 540 |  |  |  |  | 540 | Meter
85 | OPI-JAY-098-023 | 2022-11-26 | SACR-PL-JAY-098-023 | ADSH-P-PO-GE-098 | jahanayegh | 23 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 84 |  |  |  |  | 84 | Meter
86 | OPI-JAY-098-023 | 2022-11-26 | SACR-PL-JAY-098-023 | ADSH-P-PO-GE-098 | jahanayegh | 23 |  | Sub Item | Insulation-Acc | ACCESSORY | ماستیک METAL SEALANT | 3090 |  |  |  |  | 3090 | Piece
87 | OPI-JAY-098-023 | 2022-11-26 | SACR-PL-JAY-098-023 | ADSH-P-PO-GE-098 | jahanayegh | 23 |  | Sub Item | Insulation-Acc | ACCESSORY | واشر نئوپرن | 66900 |  |  |  |  | 66900 | Piece
88 | OPI-JAY-098-024 | 2022-11-30 | SACR-PL-JAY-098-024 | ADSH-P-PO-GE-098 | jahanayegh | 24 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 252 |  |  |  |  | 252 | Meter
89 | OPI-JAY-098-024 | 2022-11-30 | SACR-PL-JAY-098-024 | ADSH-P-PO-GE-098 | jahanayegh | 24 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 381 |  |  |  |  | 381 | Meter
90 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 216 |  |  |  |  | 216 | Meter
91 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 636 |  |  |  |  | 636 | Meter
92 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 19 |  |  |  |  | 19 | Meter
93 | OPI-JAY-098-025 | 2022-11-30 | SACR-PL-JAY-098-025 | ADSH-P-PO-GE-098 | jahanayegh | 25 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 34.5 |  |  |  |  | 34.5 | Meter
94 | OPI-JAY-098-026 | 2022-12-10 | SACR-PL-JAY-098-026 | ADSH-P-PO-GE-098 | jahanayegh | 26 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 354 |  |  |  |  | 354 | Meter |  |  | طبق مکاتبات صورت گرفته ضخامت 50ارسال گردیده است
95 | OPI-JAY-098-027 | 2022-12-13 | SACR-PL-JAY-098-027 | ADSH-P-PO-GE-098 | jahanayegh | 27 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 285 |  |  |  |  | 285 | Meter
96 | OPI-JAY-098-027 | 2022-12-13 | SACR-PL-JAY-098-027 | ADSH-P-PO-GE-098 | jahanayegh | 27 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 117 |  |  |  |  | 117 | Meter
97 | OPI-JAY-098-028 | 2022-12-14 | SACR-PL-JAY-098-028 | ADSH-P-PO-GE-098 | jahanayegh | 28 |  | Main Item | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 160 |  |  |  |  | 160 | Meter
98 | OPI-JAY-098-029 | 2022-12-20 | SACR-PL-JAY-098-029 | ADSH-P-PO-GE-098 | jahanayegh | 29 |  | Main Item | - | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 323.5 |  |  |  |  | 323.5 | Meter
99 | OPI-JAY-098-029 | 2022-12-20 | SACR-PL-JAY-098-029 | ADSH-P-PO-GE-098 | jahanayegh | 29 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 320 |  |  |  |  | 320 | Meter
100 | OPI-JAY-098-029 | 2022-12-20 | SACR-PL-JAY-098-029 | ADSH-P-PO-GE-098 | jahanayegh | 29 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 139.5 |  |  |  |  | 139.5 | Meter
101 | OPI-JAY-098-030 | 2022-12-20 | SACR-PL-JAY-098-030 | ADSH-P-PO-GE-098 | jahanayegh | 30 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 143 |  |  |  |  | 143 | Meter
102 | OPI-JAY-098-031 | 2022-12-20 | SACR-PL-JAY-098-031 | ADSH-P-PO-GE-098 | jahanayegh | 31 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 112 |  |  |  |  | 112 | Meter
103 | OPI-JAY-098-031 | 2022-12-20 | SACR-PL-JAY-098-031 | ADSH-P-PO-GE-098 | jahanayegh | 31 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 99 |  |  |  |  | 99 | Meter
104 | OPI-JAY-098-031 | 2022-12-20 | SACR-PL-JAY-098-031 | ADSH-P-PO-GE-098 | jahanayegh | 31 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 220.5 |  |  |  |  | 220.5 | Meter
105 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 516 |  |  |  |  | 516 | Meter
106 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 216 |  |  |  |  | 216 | Meter
107 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 102 |  |  |  |  | 102 | Meter
108 | OPI-JAY-098-032 | 2022-12-27 | SACR-PL-JAY-098-032 | ADSH-P-PO-GE-098 | jahanayegh | 32 |  | Main Item | - | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | 277.5 |  |  |  |  | 277.5 | Meter
109 | OPI-JAY-098-033 | 2022-12-27 | SACR-PL-JAY-098-033 | ADSH-P-PO-GE-098 | jahanayegh | 33 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 139.5 |  |  |  |  | 139.5 | Meter
110 | OPI-JAY-098-033 | 2022-12-27 | SACR-PL-JAY-098-033 | ADSH-P-PO-GE-098 | jahanayegh | 33 |  | Main Item | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 540 |  |  |  |  | 540 | Meter
111 | OPI-JAY-098-033 | 2022-12-27 | SACR-PL-JAY-098-033 | ADSH-P-PO-GE-098 | jahanayegh | 33 |  | Main Item | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 171.5 |  |  |  |  | 171.5 | Meter
112 | OPI-JAY-098-034 | 2023-01-04 | SACR-PL-JAY-098-034 | ADSH-P-PO-GE-098 | jahanayegh | 34 |  | Main Item | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 146 |  |  |  |  | 146 | Meter
113 | OPI-JAY-098-034 | 2023-01-04 | SACR-PL-JAY-098-034 | ADSH-P-PO-GE-098 | jahanayegh | 34 |  | Main Item | - | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 40 |  |  |  |  | 40 | Meter
114 | OPI-JAY-098-034 | 2023-01-04 | SACR-PL-JAY-098-034 | ADSH-P-PO-GE-098 | jahanayegh | 34 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 29 |  |  |  |  | 29 | Meter
115 | OPI-JAY-098-035 | 2023-01-04 | SACR-PL-JAY-098-035 | ADSH-P-PO-GE-098 | jahanayegh | 35 | Iso Blanket Mineral Wool with Stainless Steel on One Side -FOR UNIT FLR | Main Item | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 211 |  |  |  |  | 211 | Sq. Meter
116 | OPI-JAY-098-036 | 2023-01-04 | SACR-PL-JAY-098-036 | ADSH-P-PO-GE-098 | jahanayegh | 36 |  | Main Item | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 100 |  |  |  |  | 100 | Meter
117 | OPI-JAY-098-036 | 2023-01-04 | SACR-PL-JAY-098-036 | ADSH-P-PO-GE-098 | jahanayegh | 36 |  | Main Item | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 78 |  |  |  |  | 78 | Meter
118 | OPI-JAY-098-036 | 2023-01-04 | SACR-PL-JAY-098-036 | ADSH-P-PO-GE-098 | jahanayegh | 36 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 37 |  |  |  |  | 37 | Meter
119 | OPI-JAY-098-037 | 2023-01-04 | SACR-PL-JAY-098-037 | ADSH-P-PO-GE-098 | jahanayegh | 37 |  | Main Item | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 641.5 |  |  |  |  | 641.5 | Meter
120 | OPI-JAY-098-037 | 2023-01-04 | SACR-PL-JAY-098-037 | ADSH-P-PO-GE-098 | jahanayegh | 37 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 189 |  |  |  |  | 189 | Meter
121 | OPI-JAY-098-038 | 2023-01-16 | SACR-PL-JAY-098-038 | ADSH-P-PO-GE-098 | jahanayegh | 38 |  | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 579 |  |  |  |  | 579 | Sq. Meter
122 | OPI-JAY-098-038 | 2023-01-16 | SACR-PL-JAY-098-038 | ADSH-P-PO-GE-098 | jahanayegh | 38 |  | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 223.2 |  |  |  |  | 223.2 | Sq. Meter
123 | OPI-JAY-098-038 | 2023-01-16 | SACR-PL-JAY-098-038 | ADSH-P-PO-GE-098 | jahanayegh | 38 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 153.6 |  |  |  |  | 153.6 | Sq. Meter
124 | OPI-JAY-098-039 | 2023-01-16 | SACR-PL-JAY-098-039 | ADSH-P-PO-GE-098 | jahanayegh | 39 |  | Main Item | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 102 |  |  |  |  | 102 | Meter
125 | OPI-JAY-098-039 | 2023-01-16 | SACR-PL-JAY-098-039 | ADSH-P-PO-GE-098 | jahanayegh | 39 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 14 |  |  |  |  | 14 | Meter
126 | OPI-JAY-098-039 | 2023-01-16 | SACR-PL-JAY-098-039 | ADSH-P-PO-GE-098 | jahanayegh | 39 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 39 |  |  |  |  | 39 | Meter
127 | OPI-JAY-098-040 | 2023-01-16 | SACR-PL-JAY-098-040 | ADSH-P-PO-GE-098 | jahanayegh | 40 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 86 |  |  |  |  | 86 | Meter
128 | OPI-JAY-098-040 | 2023-01-16 | SACR-PL-JAY-098-040 | ADSH-P-PO-GE-098 | jahanayegh | 40 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 77 |  |  |  |  | 77 | Meter
129 | OPI-JAY-098-041 | 2023-01-16 | SACR-PL-JAY-098-041 | ADSH-P-PO-GE-098 | jahanayegh | 41 |  | Main Item | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 24 |  |  |  |  | 24 | Sq. Meter
130 | OPI-JAY-098-041 | 2023-01-16 | SACR-PL-JAY-098-041 | ADSH-P-PO-GE-098 | jahanayegh | 41 |  | Main Item | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 18 |  |  |  |  | 18 | Sq. Meter
131 | OPI-JAY-098-041 | 2023-01-16 | SACR-PL-JAY-098-041 | ADSH-P-PO-GE-098 | jahanayegh | 41 |  | Main Item | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 280.8 |  |  |  |  | 280.8 | Sq. Meter
132 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1.5 |  |  |  |  | 1.5 | Meter
133 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1.5 |  |  |  |  | 1.5 | Meter
134 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 88.5 |  |  |  |  | 88.5 | Meter
135 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 50 |  |  |  |  | 50 | Meter
136 | OPI-JAY-098-042 | 2023-01-16 | SACR-PL-JAY-098-042 | ADSH-P-PO-GE-098 | jahanayegh | 42 |  | Sub Item | Insulation-Acc | ACCESSORY | MASTIC METAL SEALANT | 750 |  |  |  |  | 750 | Piece
137 | OPI-JAY-098-043 | 2023-01-18 | SACR-PL-JAY-098-043 | ADSH-P-PO-GE-098 | jahanayegh | 43 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 170 |  |  |  |  | 170 | Meter
138 | OPI-JAY-098-044 | 2023-01-18 | SACR-PL-JAY-098-044 | ADSH-P-PO-GE-098 | jahanayegh | 44 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 120 |  |  |  |  | 120 | Meter
139 | OPI-JAY-098-044 | 2023-01-18 | SACR-PL-JAY-098-044 | ADSH-P-PO-GE-098 | jahanayegh | 44 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 40 |  |  |  |  | 40 | Meter
140 | OPI-JAY-098-045 | 2023-01-24 | SACR-PL-JAY-098-045 | ADSH-P-PO-GE-098 | jahanayegh | 45 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 150 |  |  |  |  | 150 | Meter
141 | OPI-JAY-098-045 | 2023-01-24 | SACR-PL-JAY-098-045 | ADSH-P-PO-GE-098 | jahanayegh | 45 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 29.5 |  |  |  |  | 29.5 | Meter
142 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 97 |  |  |  |  | 97 | Meter
143 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 50.5 |  |  |  |  | 50.5 | Meter
144 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 10 |  |  |  |  | 10 | Meter
145 | OPI-JAY-098-046 | 2023-01-29 | SACR-PL-JAY-098-046 | ADSH-P-PO-GE-098 | jahanayegh | 46 |  | Main Item | - | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 68.5 |  |  |  |  | 68.5 | Meter
146 | OPI-JAY-098-047 | 2023-04-06 | SACR-PL-JAY-098-047 | ADSH-P-PO-GE-098 | jahanayegh | 47 |  | Main Item | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 348 |  |  |  |  | 348 | Sq. Meter |  |  |  | 1402/01/21
147 | OPI-JAY-098-048 | 2023-04-06 | SACR-PL-JAY-098-048 | ADSH-P-PO-GE-098 | jahanayegh | 48 | Mineral Wool Iso Blanket | Main Item | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | 352.08 |  |  |  |  | 352.08 | Sq. Meter |  |  |  | 1402/01/21
148 | OPI-JAY-098-049 | 2023-04-06 | SACR-PL-JAY-098-049 | ADSH-P-PO-GE-098 | jahanayegh | 49 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 994 |  |  |  |  | 994 | Meter
149 | OPI-JAY-098-049 | 2023-04-06 | SACR-PL-JAY-098-049 | ADSH-P-PO-GE-098 | jahanayegh | 49 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 287 |  |  |  |  | 287 | Meter
150 | OPI-JAY-098-049 | 2023-04-06 | SACR-PL-JAY-098-049 | ADSH-P-PO-GE-098 | jahanayegh | 49 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 32 |  |  |  |  | 32 | Meter
151 | OPI-JAY-098-050 | 2023-04-09 | SACR-PL-JAY-098-050 | ADSH-P-PO-GE-098 | jahanayegh | 50 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 162 |  |  |  |  | 162 | Meter
152 | OPI-JAY-098-050 | 2023-04-09 | SACR-PL-JAY-098-050 | ADSH-P-PO-GE-098 | jahanayegh | 50 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 216 |  |  |  |  | 216 | Meter
153 | OPI-JAY-098-050 | 2023-04-09 | SACR-PL-JAY-098-050 | ADSH-P-PO-GE-098 | jahanayegh | 50 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 167 |  |  |  |  | 167 | Meter
154 | OPI-JAY-098-051 | 2023-04-13 | SACR-PL-JAY-098-051 | ADSH-P-PO-GE-098 | jahanayegh | 51 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 147 |  |  |  |  | 147 | Meter |  |  |  | 1402/01/21
155 | OPI-JAY-098-051 | 2023-04-13 | SACR-PL-JAY-098-051 | ADSH-P-PO-GE-098 | jahanayegh | 51 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 270 |  |  |  |  | 270 | Meter |  |  |  | 1402/01/21
156 | OPI-JAY-098-052 | 2023-04-13 | SACR-PL-JAY-098-052 | ADSH-P-PO-GE-098 | jahanayegh | 52 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 42 |  |  |  |  | 42 | Meter |  |  |  | 1402/01/21
157 | OPI-JAY-098-052 | 2023-04-13 | SACR-PL-JAY-098-052 | ADSH-P-PO-GE-098 | jahanayegh | 52 |  | Main Item | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 450 |  |  |  |  | 450 | Meter |  |  |  | 1402/01/21
158 | OPI-JAY-098-052 | 2023-04-13 | SACR-PL-JAY-098-052 | ADSH-P-PO-GE-098 | jahanayegh | 52 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 720 |  |  |  |  | 720 | Meter |  |  |  | 1402/01/21
159 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 68 |  |  |  |  | 68 | Meter
160 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 213 |  |  |  |  | 213 | Meter
161 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 28 |  |  |  |  | 28 | Meter
162 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 879 |  |  |  |  | 879 | Meter
163 | OPI-JAY-098-053 | 2023-04-13 | SACR-PL-JAY-098-053 | ADSH-P-PO-GE-098 | jahanayegh | 53 |  | Main Item | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 42 |  |  |  |  | 42 | Meter
164 | OPI-JAY-098-055 | 2023-04-25 | SACR-PL-JAY-098-054 | ADSH-P-PO-GE-098 | jahanayegh | 54 |  | Main Item | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 111 |  |  |  |  | 111 | Meter |  |  |  | 1402/01/21
165 | OPI-JAY-098-055 | 2023-04-25 | SACR-PL-JAY-098-054 | ADSH-P-PO-GE-098 | jahanayegh | 54 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1080 |  |  |  |  | 1080 | Meter |  |  |  | 1402/01/21
166 | OPI-JAY-098-054 | 2023-04-24 | SACR-PL-JAY-098-055 | ADSH-P-PO-GE-098 | jahanayegh | 55 |  | Main Item | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | 1200 |  |  |  |  | 1200 | Meter |  |  |  | 1402/01/21
167 | OPI-JAY-098-056 | 2023-05-07 | SACR-PL-JAY-098-056 | ADSH-P-PO-GE-098 | jahanayegh | 56 | Metal Jacketing | Main Item | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 328.9 |  |  |  |  | 328.9 | Sq. Meter | 542.6
168 | OPI-JAY-098-056 | 2023-05-07 | SACR-PL-JAY-098-056 | ADSH-P-PO-GE-098 | jahanayegh | 56 | Metal Jacketing | Main Item | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 1030.5 |  |  |  |  | 1030.5 | Sq. Meter | 2267
169 | OPI-JAY-098-056 | 2023-05-07 | SACR-PL-JAY-098-056 | ADSH-P-PO-GE-098 | jahanayegh | 56 | Metal Jacketing | Main Item | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | 125.4 |  |  |  |  | 125.4 | Sq. Meter | 345
[12 empty] | 618344.98 |  |  |  |  | 618344.98

## ریز آیتم ها
# | Identity | Category | Mark No. | Description | Unit | Supply | Packing List | Receipt | PI-1 | PI-2 | PI-3 | PI-4 | Total MRS | نرخ | قراداد اولیه | 30% | نرخ تسعیر | ریال پیش پرداخت | ریال صورتحساب
1 | Bulk | - | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 277.5 | - | - |  |  |  |  | 0 | 1.077 | 298.8675 | 89.6603 | 290271 | 26025770.4278 | 0
2 | Bulk | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 22 | 22 | 22 |  | 22 |  |  | 22 | 1.508 | 33.176 | 9.9528 | 290271 | 2889009.2088 | 33.176
3 | Bulk | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | 2 | 2 |  | 1.5 |  |  | 1.5 | 2.297 | 3.4455 | 1.0336 | 290271 | 300038.6191 | 3.4455
4 | Bulk | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1558 | 1558 | 1558 |  | 1558 |  |  | 1558 | 1.149 | 1790.142 | 537.0426 | 290271 | 155887892.5446 | 1790.142
5 | Bulk | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 122.5 | 123 | 123 |  | 122.5 |  |  | 122.5 | 1.723 | 211.0675 | 63.3203 | 290271 | 18380032.2878 | 211.0675
6 | Bulk | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 4.5 | 5 | 5 |  | 4.5 |  |  | 4.5 | 2.44 | 10.98 | 3.294 | 290271 | 956152.674 | 10.98
7 | Bulk | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1104.5 | - | - |  |  |  |  | 0 | 1.192 | 1316.564 | 394.9692 | 290271 | 114648104.6532 | 0
8 | Bulk | - | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 323.5 | - | - |  |  |  |  | 0 | 1.795 | 580.6825 | 174.2047 | 290271 | 50566586.9873 | 0
9 | Bulk | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 3.5 | 4 | 4 |  | 3.5 |  |  | 3.5 | 2.656 | 9.296 | 2.7888 | 290271 | 809507.7648 | 9.296
10 | Bulk | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1697.5 | - | - |  |  |  |  | 0 | 1.508 | 2559.83 | 767.949 | 290271 | 222913324.179 | 0
11 | Bulk | - | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 131 | - | - |  |  |  |  | 0 | 2.104 | 275.624 | 82.6872 | 290271 | 24001696.2312 | 0
12 | Bulk | - | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | - | - |  |  |  |  | 0 | 2.943 | 4.4145 | 1.3244 | 290271 | 384420.3989 | 0
13 | Bulk | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 2009 | 110 | 110 | 110 |  |  |  | 110 | 1.579 | 3172.211 | 951.6633 | 290271 | 276240257.7543 | 173.69
14 | Bulk | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 956 | - | - |  |  |  |  | 0 | 2.44 | 2332.64 | 699.792 | 290271 | 203129323.632 | 0
15 | Bulk | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 37.5 | 38 | 38 | 37.5 |  |  |  | 37.5 | 3.302 | 123.825 | 37.1475 | 290271 | 10782841.9725 | 123.825
16 | Bulk | - | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1.5 | - | - |  |  |  |  | 0 | 4.235 | 6.3525 | 1.9058 | 290271 | 553183.9583 | 0
17 | Bulk | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1170.5 | 575 | 575 |  |  | 575 |  | 575 | 2.154 | 2521.257 | 756.3771 | 290271 | 219554337.1941 | 1238.55
18 | Bulk | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 620.5 | 621 | 621 | 204 |  | 416.5 |  | 620.5 | 3.086 | 1914.863 | 574.4589 | 290271 | 166748759.3619 | 1914.863
19 | Bulk | - | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 139 | - | - |  |  |  |  | 0 | 4.074 | 566.286 | 169.8858 | 290271 | 49312921.0518 | 0
20 | Bulk | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 76 | - | - |  |  |  |  | 0 | 2.496 | 189.696 | 56.9088 | 290271 | 16518974.2848 | 0
21 | Bulk | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1020 | - | - |  |  |  |  | 0 | 3.589 | 3660.78 | 1098.234 | 290271 | 318785481.414 | 0
22 | Bulk | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 133.5 | - | - |  |  |  |  | 0 | 4.737 | 632.3895 | 189.7168 | 290271 | 55069299.7664 | 0
23 | Bulk | - | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 68.5 | - | - |  |  |  |  | 0 | 5.956 | 407.986 | 122.3958 | 290271 | 35527951.2618 | 0
24 | Bulk | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 132 | 132 | 132 | 132 |  |  |  | 132 | 3.484 | 459.888 | 137.9664 | 290271 | 40047644.8944 | 459.888
25 | Bulk | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1479.5 | - | - |  |  |  |  | 0 | 4.88 | 7219.96 | 2165.988 | 290271 | 628723502.748 | 0
26 | Bulk | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 48.5 | 49 | 49 | 48.5 |  |  |  | 48.5 | 6.315 | 306.2775 | 91.8833 | 290271 | 26671042.8608 | 306.2775
27 | Bulk | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 371 | 371 | 371 | 371 |  |  |  | 371 | 7.822 | 2901.962 | 870.5886 | 290271 | 252706623.5106 | 2901.962
28 | Bulk | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 440 | 430 | 430 | 430 |  |  |  | 430 | 9.832 | 4326.08 | 1297.824 | 290271 | 376720670.304 | 4227.76
29 | Bulk | - | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 128 | - | - |  |  |  |  | 0 | 6.315 | 808.32 | 242.496 | 290271 | 70389556.416 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 132 | [6 empty] | 0 | 15.892 | 2097.744 | 629.3232 | 290271 | 182674274.5872 | 0
30 | Bulk | - | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 10 | - | - |  |  |  |  | 0 | 4.339 | 43.39 | 13.017 | 290271 | 3778457.607 | 0
31 | Bulk | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 178.5 | 84 | 84 | 84 |  |  |  | 84 | 7.751 | 1383.5535 | 415.066 | 290271 | 120481637.3995 | 651.084
32 | Bulk | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 348 | - | - |  |  |  |  | 0 | 9.472 | 3296.256 | 988.8768 | 290271 | 287042257.6128 | 0
33 | Bulk | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 238 | - | - |  |  |  |  | 0 | 11.553 | 2749.614 | 824.8842 | 290271 | 239439961.6182 | 0
34 | Bulk | - | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 187 | - | - |  |  |  |  | 0 | 7.751 | 1449.437 | 434.8311 | 290271 | 126218858.2281 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 223 | [6 empty] | 0 | 15.892 | 3543.916 | 1063.1748 | 290271 | 308608812.3708 | 0
35 | Bulk | - | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 40 | - | - |  |  |  |  | 0 | 5.134 | 205.36 | 61.608 | 290271 | 17883015.768 | 0
36 | Bulk | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 102.5 | - | - |  |  |  |  | 0 | 9.329 | 956.2225 | 286.8668 | 290271 | 83269098.3893 | 0
37 | Bulk | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 573.5 | - | - |  |  |  |  | 0 | 11.267 | 6461.6245 | 1938.4873 | 290271 | 562686661.5718 | 0
38 | Bulk | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 216 | 216 | 216 | 216 |  |  |  | 216 | 13.634 | 2944.944 | 883.4832 | 290271 | 256449551.9472 | 2944.944
39 | Bulk | - | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 241 | - | - |  |  |  |  | 0 | 9.329 | 2248.289 | 674.4867 | 290271 | 195783928.8957 | 0
|  |  | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 328 | [6 empty] | 0 | 15.892 | 5212.576 | 1563.7728 | 290271 | 453917894.4288 | 0
40 | Bulk | - | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 177.5 | - | - |  |  |  |  | 0 | 9.329 | 1655.8975 | 496.7692 | 290271 | 144197706.9667 | 0
|  |  |  | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 253 | [6 empty] | 0 | 16.7 | 4225.1 | 1267.53 | 290271 | 367927200.63 | 0
41 | Bulk | - | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | Meter | 1.1 | - | - |  |  |  |  | 0 | 10.888 | 11.9768 | 3.593 | 290271 | 1042955.3138 | 0
42 | Bulk | - | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 5.5 | - | - |  |  |  |  | 0 | 7.801 | 42.9055 | 12.8717 | 290271 | 3736266.7172 | 0
43 | Bulk | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 87.78 | - | - |  |  |  |  | 0 | 15.892 | 1394.9998 | 418.4999 | 290271 | 121478392.6005 | 0
44 | Bulk | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1007.6 | - | - |  |  |  |  | 0 | 17.508 | 17641.0608 | 5292.3182 | 290271 | 1536206507.843 | 0
45 | Bulk | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1310.1 | - | - |  |  |  |  | 0 | 18.316 | 23995.7916 | 7198.7375 | 290271 | 2089584727.0571 | 0
46 | Bulk | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1243 | - | - |  |  |  |  | 0 | 19.124 | 23771.132 | 7131.3396 | 290271 | 2070021077.0316 | 0
47 | Bulk | - | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 403.7 | - | - |  |  |  |  | 0 | 19.932 | 8046.5484 | 2413.9645 | 290271 | 700703895.1849 | 0
48 | Bulk | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 822.8 | - | - |  |  |  |  | 0 | 20.74 | 17064.872 | 5119.4616 | 290271 | 1486031238.0936 | 0
49 | Bulk | - | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 11.88 | - | - |  |  |  |  | 0 | 21.548 | 255.9902 | 76.7971 | 290271 | 22291962.8865 | 0
50 | Bulk | - | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 229.9 | - | - |  |  |  |  | 0 | 17.508 | 4025.0892 | 1207.5268 | 290271 | 350510000.152 | 0
|  |  | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 229.9 | [6 empty] | 0 | 18.316 | 4210.8484 | 1263.2545 | 290271 | 366686152.7749 | 0
51 | Bulk | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 5869.6 | 5870 | 5870 |  |  | 5869.6 |  | 5869.6 | 11.313 | 66402.7848 | 19920.8354 | 290271 | 5782440824.0042 | 66402.7848
52 | Bulk | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 6906.9 | 6907 | 6907 |  | 4448.7 | 2458.2 |  | 6906.9 | 15.084 | 104183.6796 | 31255.1039 | 290271 | 9072450258.3515 | 104183.6796
53 | Bulk | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 2156 | 2156 | 2156 |  | 1973.58 | 182.42 |  | 2156 | 18.855 | 40651.38 | 12195.414 | 290271 | 3539975017.194 | 40651.38
54 | Bulk | - | Insulation-Acc | Accessories for Insulation | Set | 1 | - | - |  |  |  |  | 0 |  | 0 | 0 | 290271 | 0 | 0
55 | Bulk | - | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | Meter | 1.1 | - | - |  |  |  |  | 0 | 6.341 | 6.9751 | 2.0925 | 290271 | 607400.7756 | 0
56 | Bulk | - | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | Meter | 20.9 | - | - |  |  |  |  | 0 | 6.95 | 145.255 | 43.5765 | 290271 | 12648994.2315 | 0
57 | Bulk | - | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 8.8 | - | - |  |  |  |  | 0 | 9.627 | 84.7176 | 25.4153 | 290271 | 7377318.7409 | 0
58 | Bulk | - | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 1.1 | - | - |  |  |  |  | 0 | 14.464 | 15.9104 | 4.7731 | 290271 | 1385498.3155 | 0
59 | Bulk | - | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 2.2 | - | - |  |  |  |  | 0 | 12.024 | 26.4528 | 7.9358 | 290271 | 2303544.2126 | 0
60 | Bulk | - | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 908.6 | - | - |  |  |  |  | 0 | 11.092 | 10078.1912 | 3023.4574 | 290271 | 877621991.3446 | 0
61 | Bulk | - | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 193.6 | - | - |  |  |  |  | 0 | 14.626 | 2831.5936 | 849.4781 | 290271 | 246578851.7597 | 0
62 | Bulk | - | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 85.8 | - | - |  |  |  |  | 0 | 21.123 | 1812.3534 | 543.706 | 290271 | 157822090.1314 | 0
63 | Bulk | - | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 34.1 | - | - |  |  |  |  | 0 | 25.184 | 858.7744 | 257.6323 | 290271 | 74783191.1587 | 0
64 | Bulk | - | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 38.5 | - | - |  |  |  |  | 0 | 33.513 | 1290.2505 | 387.0751 | 290271 | 112356690.8656 | 0
65 | Bulk | - | 4YYYYYE06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 125.4 | - | - |  |  |  |  | 0 | 56.052 | 7028.9208 | 2108.6762 | 290271 | 612087560.861 | 0
66 | Bulk | - | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 39.6 | - | - |  |  |  |  | 0 | 44.68 | 1769.328 | 530.7984 | 290271 | 154075382.3664 | 0
|  |  | ACCESSORY | تسمه استنلس استیل سایز 13mm*0/5mm | Meter | 43500 | [5 empty] | 43500 | 43500 | 0.61 | 26535 | 7960.5 | 294059 | 2340856669.5 | 26535
|  |  | ACCESSORY | تسمه استنلس استیل سایز 19mm*0/5mm | Meter | 13000 | [5 empty] | 13000 | 13000 | 1 | 13000 | 3900 | 294059 | 1146830100 | 13000
|  |  | ACCESSORY | بست استنلس استیل سایز 13mm*0/5mm | pcs | 72000 | [5 empty] | 72000 | 72000 | 0.08 | 5760 | 1728 | 294059 | 508133952 | 5760
|  |  | ACCESSORY | بست استنلس استیل سایز 19mm*0/5mm | pcs | 3500 | [5 empty] | 3500 | 3500 | 0.08 | 280 | 84 | 294059 | 24700956 | 280
|  |  | ACCESSORY | پیچ استنلس استیل سایز 13*4/8 | pcs | 120000 | [5 empty] | 120000 | 120000 | 0.066 | 7920 | 2376 | 294059 | 698684184 | 7920
|  |  | ACCESSORY | پیچ استنلس استیل سایز 9/5*4/2 | pcs | 80000 | [5 empty] | 80000 | 80000 | 0.057 | 4560 | 1368 | 294059 | 402272712 | 4560
|  |  | ACCESSORY | واشر لئوپرن | pcs | 120000 | [5 empty] | 53100 | 53100 | 0.036 | 4320 | 1296 | 294059 | 381100464 | 1911.6
|  |  | ACCESSORY | ماستیک METAL SEALANT | pcs | 3090 | [6 empty] | 0 | 6.6 | 20394 | 6118.2 | 294059 | 1799111773.8 | 0
|  |  | ACCESSORY | کلیپس S | pcs | 3200 | [5 empty] | 3200 | 3200 | 0.09 | 288 | 86.4 | 294059 | 25406697.6 | 288
|  |  | ACCESSORY | سیم استنلس استیل به قطر 1mm | Meter | 106000 | [5 empty] | 106000 | 106000 | 0.21 | 22260 | 6678 | 294059 | 1963726002 | 22260
|  |  | ACCESSORY | نوارچسب نخ دار تقویت شده فیلامنت با عرض 50 میلیمتر | Roll | 75 | [5 empty] | 75 | 75 | 15.95 | 1196.25 | 358.875 | 294059 | 105530423.625 | 1196.25
|  |  | ACCESSORY | Vapour Barrier Mastic JAP 60-90 | Kg | 2075 | [5 empty] | 2075 | 2075 | 2.65 | 5498.75 | 1649.625 | 294059 | 485087077.875 | 5498.75
|  |  | ACCESSORY | Joint Sealant Mastic JAP 81-84 | Kg | 550 | [5 empty] | 550 | 550 | 3 | 1650 | 495 | 294059 | 145559205 | 1650
|  |  | ACCESSORY | Glass Cloth Mesh | Kg | 750 | [5 empty] | 750 | 750 | 1.3 | 975 | 292.5 | 294059 | 86012257.5 | 975

## Sheet1
# | Identity | Category | Mark No. | Description | Unit | Supply | Packing List | Receipt
1 | Bulk | - | 4YYXYYD0D | 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II , density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 277 | 278 | 278 | 0
2 | Bulk | - | 4YYXYYE0D | 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II, density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 22 | 22 | 22 | 0
3 | Bulk | - | 4YYXYYF0D | 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1 | 2 | 2 | 0
4 | Bulk | - | 4YYXYYD0E | 3/4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1558 | 1558 | 1558 | 0
5 | Bulk | - | 4YYXYYE0E | 3/4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 122 | 191 | 191 | 0
6 | Bulk | - | 4YYXYYF0E | 3/4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 4 | 5 | 5 | 0
7 | Bulk | - | 4YYXYYD01 | 1" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1104 | 5099 | 5099 | 0
8 | Bulk | - | 4YYXYYE01 | 1" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 323 | 324 | 324 | 0
9 | Bulk | - | 4YYXYYF01 | 1" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 3 | 4 | 4 | 0
10 | Bulk | - | 4YYXYYD1B | 1 1/2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1697 | 1698 | 1698 | 0
11 | Bulk | - | 4YYXYYE1B | 1 1/2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 131 | 131 | 131 | 0
12 | Bulk | - | 4YYXYYF1B | 1 1/2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1 | 2 | 2 | 0
13 | Bulk | - | 4YYXYYD02 | 2" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 2009 | 3050 | 3050 | 0
14 | Bulk | - | 4YYXYYE02 | 2" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 956 | 1963 | 1963 | 0
15 | Bulk | - | 4YYXYYF02 | 2" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 37 | 38 | 38 | 0
16 | Bulk | - | 4YYXYYG02 | 2" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1 | 2 | 2 | 0
17 | Bulk | - | 4YYXYYD03 | 3" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1170 | 1171 | 1171 | 0
18 | Bulk | - | 4YYXYYE03 | 3" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 620 | 621 | 621 | 0
19 | Bulk | - | 4YYXYYF03 | 3" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 139 | 139 | 139 | 0
20 | Bulk | - | 4YYXYYD04 | 4" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 76 | 118 | 118 | 0
21 | Bulk | - | 4YYXYYE04 | 4" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1020 | 1481 | 1481 | 0
22 | Bulk | - | 4YYXYYF04 | 4" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 133 | 134 | 134 | 0
23 | Bulk | - | 4YYXYYG04 | 4" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 68 | 69 | 69 | 0
24 | Bulk | - | 4YYXYYD06 | 6" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 132 | 132 | 132 | 0
25 | Bulk | - | 4YYXYYE06 | 6" , Thk. 40mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 1480 | 1675 | 1675 | 0
26 | Bulk | - | 4YYXYYF06 | 6" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 48 | 177 | 177 | 0
27 | Bulk | - | 4YYXYYG06 | 6" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 371 | 371 | 371 | 0
28 | Bulk | - | 4YYXYYH06 | 6" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 440 | 440 | 440 | 0
29 | Bulk | - | 4YYXYYI06 | 6" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 128 | - | - | #VALUE!
30 | Bulk | - | 4YYXYYD08 | 8" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 10 | 10 | 10 | 0
31 | Bulk | - | 4YYXYYF08 | 8" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 178 | 666 | 666 | 0
32 | Bulk | - | 4YYXYYG08 | 8" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 348 | 348 | 348 | 0
33 | Bulk | - | 4YYXYYH08 | 8" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 238 | 238 | 238 | 0
34 | Bulk | - | 4YYXYYI08 | 8" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 187 | - | - | #VALUE!
35 | Bulk | - | 4YYXYYD10 | 10" , Thk. 30mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 40 | 40 | 40 | 0
36 | Bulk | - | 4YYXYYF10 | 10" , Thk. 50mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 102 | 521 | 521 | 0
37 | Bulk | - | 4YYXYYG10 | 10" , Thk. 60mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 573 | 573 | 573 | 0
38 | Bulk | - | 4YYXYYH10 | 10" , Thk. 70mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 216 | 216 | 216 | 0
39 | Bulk | - | 4YYXYYI10 | 10" , Thk. 80mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 241 | - | - | #VALUE!
40 | Bulk | - | 4YYXYYJ10 | 10" , Thk. 90mm ,Hot Insulation, Mineral wool ASTM C547, Class II density 80 kg/m3~120 kg/m3, Sectional Pipe | Meter | 177 | - | - | #VALUE!
41 | Bulk | - | 4YYYYYE0E | 3/4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | Meter | 1 | 1 | 1 | 0
42 | Bulk | - | 4YYYYYD01 | 1" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 6 | 6 | 6 | 0
43 | Bulk | - | 4YYXXYD | Hot Insulation, Mineral Wool, Blanket,Thk. 30mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 88 | 1374 | 1374 | 0
44 | Bulk | - | 4YYXXYE | Hot Insulation, Mineral Wool, Blanket,Thk. 40mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1 | 953 | 953 | 0
45 | Bulk | - | 4YYXXYF | Hot Insulation, Mineral Wool, Blanket,Thk. 50mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1008 | 1479 | 1479 | 0
46 | Bulk | - | 4YYXXYG | Hot Insulation, Mineral Wool, Blanket,Thk. 60mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1310 | 1975 | 1975 | 0
47 | Bulk | - | 4YYXXYH | Hot Insulation, Mineral Wool, Blanket, Thk. 70mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 1243 | 1243 | 1243 | 0
48 | Bulk | - | 4YYXXYI | Hot Insulation, Mineral Wool, Blanket,Thk. 80mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 404 | 404 | 404 | 0
49 | Bulk | - | 4YYXXYJ | Hot Insulation, Mineral Wool, Blanket,Thk. 90mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 823 | 1034 | 1034 | 0
50 | Bulk | - | 4YYXXYK | Hot Insulation, Mineral Wool, Blanket,Thk. 100mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 12 | 12 | 12 | 0
51 | Bulk | - | 4YYXXYL | Hot Insulation, Mineral Wool, Blanket,Thk. 110mm , ASTM C592,Class II, density 80 kg/m3~120 kg/m3, With 0.9mm 1 side stitched galvanized wire | Sq. Meter | 230 | - | - | #VALUE!
52 | Bulk | - | 4YYZZYA | 0.6 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 5870 | 6199 | 5870 | 329
53 | Bulk | - | 4YYZZYB | 0.8 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 6907 | 7937 | 6907 | 1030
54 | Bulk | - | 4YYZZYC | 1 mm Thickness Metal Jacketing-ASTM B 209, type 1100 Wrought Aluminum Alloy | Sq. Meter | 2156 | 2281 | 2156 | 125
55 | Bulk | - | Insulation-Acc | Accessories for Insulation | Set | 1 | - | - | #VALUE!
56 | Bulk | - | 4YYYYYD0D | 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C589 | Meter | 1 | 1 | 1 | 0
57 | Bulk | - | 4YYYYYD0E | 3/4" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C590 | Meter | 21 | 21 | 21 | 0
58 | Bulk | - | 4YYYYYD1B | 1 1/2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 9 | 9 | 9 | 0
59 | Bulk | - | 4YYYYYE1B | 1 1/2" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 1 | 1 | 1 | 0
60 | Bulk | - | 4YYYYYE01 | 1" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 2 | 2 | 2 | 0
61 | Bulk | - | 4YYYYYD02 | 2" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 909 | 909 | 909 | 0
62 | Bulk | - | 4YYYYYD03 | 3" , Thk. 30mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 194 | 194 | 194 | 0
63 | Bulk | - | 4YYYYYE03 | 3" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 86 | 86 | 86 | 0
64 | Bulk | - | 4YYYYYE04 | 4" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C591 | Meter | 34 | 34 | 34 | 0
65 | Bulk | - | 4YYYYYF04 | 4" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C592 | Meter | 39 | 39 | 39 | 0
66 | Bulk | - | 4YYYYYE06 | 6" , Thk. 40mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 125 | - | - | #VALUE!
67 | Bulk | - | 4YYYYYF06 | 6" , Thk. 50mm ,Cold Insulation,Polyisocyanurate rigid foam, density 125 kg/m3,Sectional Pipe,as per ASTM C593 | Meter | 40 | 40 | 40 | 0
68 | Bulk | - | 4YYYYYG06 | 6" , Thk. 60mm ,Cold Insulation,Polyisocyanurate rigid foam,density 125 kg/m3, Sectional Pipe,as per ASTM C591 | Meter | 1 | 125 | 125 | 0