## Packing List Items
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-NIG-015-002 | 2022-09-11 | SACR-PL-NIG-015-001 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 1 |  | Main Item | - | S35-PDP-5001 | POWER DISTRIBUTION PANEL (800*800*2100) | 1 |  |  |  |  | 1 | Set
2 | OPI-NIG-015-002 | 2022-09-11 | SACR-PL-NIG-015-001 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 1 |  | Main Item | - | S35-PDP-5002 | POWER DISTRIBUTION PANEL (800*800*2100) | 1 |  |  |  |  | 1 | Set
3 | OPI-NIG-015-002 | 2022-09-11 | SACR-PL-NIG-015-001 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 1 |  | Main Item | - | S35-PDP-5003 | POWER DISTRIBUTION PANEL (800*800*2100) | 1 |  |  |  |  | 1 | Set
4 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S35-DSC-5001 | DCS CONTROL CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
5 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S35-DSC-5002 | DCS CONTROL CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set |  |  | 1PCS HUB SWITH SHORTAGE
6 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S35-DMC-5001 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
7 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S35-DMC-5002 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
8 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S35-DMC-5003 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
9 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S35-DMC-5004 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
10 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S55-DSC-5001 | DCS CONTROL CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
11 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S55-DSC-5002 | DCS CONTROL CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
12 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S55-DMC-5001 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
13 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S55-DMC-5002 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
14 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S55-DMC-5003 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
15 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Main Item | - | S55-DMC-5004 | DCS MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
16 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Sub Item | NIG-PO-015-SubItems | 2304681 | PHONEIX DATA CABLE EACH PCS (15 Meter) | 30 |  |  |  |  | 30 | Piece
17 | OPI-NIG-015-001 | 2022-09-11 | SACR-PL-NIG-015-002 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 2 |  | Sub Item | NIG-PO-015-SubItems | 2302340 | PHONEIX DATA CABLE EACH PCS (15 Meter) | 75 |  |  |  |  | 75 | Piece
18 | OPI-NIG-015-003 | 2023-01-19 | SACR-PL-NIG-015-003 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 3 |  | Main Item | - | S55-PDP-5001 | POWER DISTRIBUTION PANEL (800*800*2100) | 1 |  |  |  |  | 1 | Set | 390
19 | OPI-NIG-015-003 | 2023-01-19 | SACR-PL-NIG-015-003 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 3 |  | Main Item | - | S55-PDP-5002 | POWER DISTRIBUTION PANEL (800*800*2100) | 1 |  |  |  |  | 1 | Set | 390
20 | OPI-NIG-015-003 | 2023-01-19 | SACR-PL-NIG-015-003 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 3 |  | Main Item | - | S55-PDP-5003 | POWER DISTRIBUTION PANEL (800*800*2100) | 1 |  |  |  |  | 1 | Set | 390
21 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S35-ESC-5001 | ESD CONTROL CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
22 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S35-ESC-5002 | ESD CONTROL CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
23 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S35-EMC-5001 | ESD MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
24 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S35-EMC-5002 | ESD MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
25 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S35-EMC-5003 | ESD MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
26 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S35-EMC-5004 | ESD MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
27 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S35-EMC-5005 | ESD MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
28 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S55-ESC-5001 | ESD CONTROL CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
29 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S55-EMC-5001 | ESD MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
30 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S55-EMC-5002 | ESD MARSHALLING CABINET (800*800*2100) | 1 |  |  |  |  | 1 | Set
31 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Main Item | - | S55-IRP-5001 | INTERPOSING RELAY PANEL (800*800*2100) | 1 |  |  |  |  | 1 | Set
32 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Sub Item | NIG-PO-015-SubItems | 2304681 | PHONEIX DATA CABLE (15 Meter) | 76 |  |  |  |  | 76 | Piece
33 | OPI-NIG-015-004 | 2023-01-19 | SACR-PL-NIG-015-004 | ADSH-P-PO-GE-015 | NEDA INDUSTRIAL GROUP | DDP SITE | 4 |  | Sub Item | NIG-PO-015-SubItems | 2302340 | PHONEIX DATA CABLE (15 Meter) | 29 |  |  |  |  | 29 | Piece