## پیش فاکتور1401-05-22
خلاصه مالی خرید لوله و عایق | [8 empty] | شماره پیش فاکتور: -
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [8 empty] | تاریخ پیش فاکتور: 1401/05/22
فروشنده: شرکت پویا گستر آرتا صنعت | [8 empty] | تاریخ تهیه گزارش: 1401/06/27
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (ریال) | مبلغ قرارداد (یورو) | مقدار رسید شده MRS-9001-076 | درصد کالای دریافتی | مبلغ کل (یورو) | فاکتور
1 | FOG-B335A | BRANCH PIPE | عدد | 59 | 18200000 | 1073800000 | 1 | 1.695% | 18200000 | 36 | 35 | 655200000
2 | FOG-B506A | BRACH PIPE | عدد | 9 | 21600000 | 194400000 | 9 | 100% | 194400000 | 4 | -5 | 86400000
3 | FOG-B730A | BRANCH PIPE | عدد | 9 | 26700000 | 240300000 | 9 | 100% | 240300000 | 112 | 103 | 2990400000
4 | FOG-B1350A | BRACH PIPE | عدد | 4 | 49000000 | 196000000 | 4 | 100% | 196000000 | 30 | 26 | 1470000000
5 | FOG-B2040A | BRACH PIPE | عدد | 1 | 58200000 | 58200000 | 1 | 100% | 58200000 | 54 | 53 | 3142800000
6 | HZG-30B | OUTDOOR BRANCH PIPE | عدد | 1 | 49000000 | 49000000 | 1 | 100% | 49000000 | 14 | 13 | 686000000
7 | GAS-3/8" | REFRIGERANT GAS PIPE- 3/8" | متر | 106 | 965000 | 102290000 | 106 | 100% | 102290000 | 10 | -96 | 9650000
8 | GAS-5/8" | REFRIGERANT GAS PIPE- 5/8" | متر | 140 | 2625000 | 367500000 | 142 | 101.4% | 372750000 | 6 | -136 | 15750000
9 | GAS-3/4" | REFRIGERANT GAS PIPE- 3/4" | متر | 66 | 2485000 | 164010000 | 66 | 100% | 164010000 | 12 | -54 | 29820000
10 | GAS-1.1/8" | REFRIGERANT GAS PIPE- 1.1/8" | متر | 90 | 4800000 | 432000000 | 90 | 100% | 432000000 | 10 | -80 | 48000000
11 | GAS-1.5/8" | REFRIGERANT GAS PIPE-1.5/8" | متر | 42 | 8370000 | 351540000 | 42 | 100% | 351540000 | 10 | -32 | 83700000
12 | GAS-1/2" | REFRIGERANT GAS PIPE-1/2" | متر | 193 | 1520000 | 293360000 | 198 | 102.6% | 300960000 |  | -198 | 0
13 | GAS-1.3/8" | REFRIGERANT GAS PIPE-1.3/8" | متر | 12 | 7035000 | 84420000 | 12 | 100% | 84420000 | 3 | -9 | 21105000
14 | LIQUIDE-1/2" | REFRIGERANT LIQUIDE PIPE-1/2" | متر | 84 | 1520000 | 127680000 | 84 | 100% | 127680000 | 8 | -76 | 12160000
15 | LIQUIDE-1/4" | REFRIGERANT LIQUIDE PIPE-1/4" | متر | 280 | 635000 | 177800000 | 280 | 100% | 177800000 | 2 | -278 | 1270000
16 | LIQUIDE-3/8" | REFRIGERANT LIQUIDE PIPE-3/8" | متر | 163 | 987000 | 160881000 | 164 | 100.6% | 161868000 | 4 | -160 | 3948000
17 | LIQUIDE-7/8" | REFRIGERANT LIQUIDE PIPE-7/8" | متر | 18 | 3550000 | 63900000 | 18 | 100% | 63900000 | 53 | 35 | 188150000
18 | LIQUIDE-3/4" | REFRIGERANT LIQUIDE PIPE-3/4" | متر | 40 | 2480000 | 99200000 | 42 | 105% | 104160000 | 6 | -36 | 14880000
19 | LIQUIDE-5/8" | REFRIGERANT LIQUIDE PIPE-5/8" | متر | 62 | 2625000 | 162750000 | 62 | 100% | 162750000 | 4 | -58 | 10500000
20 | OIL-3/8" | OIL EQUALIZATION PIPE-3/8" | متر | 8 | 987000 | 7896000 | 12 | 150% | 11844000 | 465 | 453 | 458955000
21 | R410A | OUT1-56.2386 | عدد | 9 | 50600000 | 455400000 | 9 | 100% | 455400000 | 97 | 88 | 4908200000
22 | pipe insulation-3/8" | عایق فوم الاستومری 3/8 | متر | 106 | 128000 | 13568000 | 106.2 | 100.2% | 13593600 | 12 | -94.2 | 1536000
23 | pipe insulation-5/8" | عایق فوم الاستومری 5/8 | متر | 140 | 152000 | 21280000 | 138.6 | 99% | 21067200 | 3 | -135.6 | 456000
24 | pipe insulation-3/4" | عایق فوم الاستومری 3/4 | متر | 66 | 164000 | 10824000 | 64.8 | 98.18% | 10627200
25 | pipe insulation-1.1/8" | عایق فوم الاستومری 1.1/8 | متر | 90 | 281000 | 25290000 | 90 | 100% | 25290000
26 | pipe insulation-1.5/8" | عایق فوم الاستومری 1.5/8 | متر | 42 | 435000 | 18270000 | 41.8 | 99.52% | 18183000
27 | pipe insulation-1/2" | عایق فوم الاستومری 1/2 | متر | 193 | 143000 | 27599000 | 192.6 | 99.79% | 27541800
28 | pipe insulation-1.3/8" | عایق فوم الاستومری 1.3/8 | متر | 12 | 335000 | 4020000 | 12.6 | 105% | 4221000
29 | pipe insulation-1/2" | عایق فوم الاستومری 1/2 | متر | 84 | 143000 | 12012000 | 84.4 | 100.5% | 12069200
30 | pipe insulation-1/4" | عایق فوم الاستومری 1/4 | متر | 280 | 115000 | 32200000 | 277.2 | 99% | 31878000
31 | pipe insulation-3/8" | عایق فوم الاستومری 3/8 | متر | 163 | 128000 | 20864000 | 162 | 99.39% | 20736000
32 | pipe insulation-7/8" | عایق فوم الاستومری 7/8 | متر | 18 | 212000 | 3816000 | 18 | 100% | 3816000
33 | pipe insulation-3/4" | عایق فوم الاستومری 3/4 | متر | 40 | 164000 | 6560000 | 41.4 | 103.5% | 6789600
34 | pipe insulation-5/8" | عایق فوم الاستومری 5/8 | متر | 62 | 152000 | 9424000 | 63 | 101.6% | 9576000
35 | pipe insulation-3/8" | عایق فوم الاستومری 3/8 | متر | 8 | 128000 | 1024000 | 10.8 | 135% | 1382400
|  | جمع کل اقلام خریداری شده |  |  |  | 5069078000 |  |  | 4036243000
خلاصه محاسبات پرداخت صورت حساب: | [5 empty] | (ريال) | توضیحات:
جمع کل کالای رسیده به انبار | [5 empty] | 4036243000 | تا تاریخ تهیه این گزارش، نسخه تایید شده ی فهرست کسری/اضافه در سامانه مدیریت پروژه پوپک بارگذاری نشده است.
مالیات و عوارض بر ارزش افزوده (9%) | [5 empty] | 363261870
جمع کل صورتحسابهای شماره 74 و 75 | [5 empty] | 4399504870
کسور:
استهلاک علی الحساب | [5 empty] | 2000000000
جمع کسور | [5 empty] | 2000000000
خالص قابل پرداخت بابت صورتحسابهای 74 و 75 | [5 empty] | 2399504870
بدهی قبلی بابت صورتحساب 52 | [5 empty] | 2092800
خالص قابل پرداخت | [5 empty] | 2401597670

## Packing List Items
# | Opi No. | Date | Project Name | Packing List No. | Purchase Order | Vendor | Purchaser | Consignee | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | لوله مسی خط مایع 11/80-1.65-مهر اصل-باهنر-وزن هر متر 1.250 کیلو سری K | 66 |  |  |  |  | 66 | Meter | 1.21
2 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | عایق الاستومتری فوم -11/8 ضخامت 10 میل روکشدار آلومینیوم 170 میکرون | 68 |  |  |  |  | 68 | Meter
3 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | زانو مسی 90 درجه 11/8 | 48 |  |  |  |  | 48 | Piece
4 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بوشن مسی 11/8 | 8 |  |  |  |  | 8 | Piece
5 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سه راه مسی90 درجه 11/8 | 4 |  |  |  |  | 4 | Piece
6 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تبدیل مسی 7/8* 11/8 | 8 |  |  |  |  | 8 | Piece
7 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بست پایه دار روکشدار- 11/4 | 48 |  |  |  |  | 48 | Piece
8 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | لوله مسی خط مکش- 25/8- 2.02 مهر اصل-باهنر وزن هرمتر3/670 کیلو سری L | 60 |  |  |  |  | 60 | Meter | 3.66
9 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | زانو مسی 25/8 | 48 |  |  |  |  | 48 | Piece
10 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بوشن مسی 25/8 | 8 |  |  |  |  | 8 | Piece
11 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سه راه مسی 90 درجه 25/8 | 4 |  |  |  |  | 4 | Piece
12 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تبدیل مسی 21/8* 25/8 | 4 |  |  |  |  | 4 | Piece
13 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | مغزی برنجی سوزنی دار- 1.4 | 8 |  |  |  |  | 8 | Piece
14 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | والف لوله مسی | 4 |  |  |  |  | 4 | Piece
15 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | درپوش برنجی 4/1 | 4 | 4 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
16 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سیم جوش مسی | 4 |  |  |  |  | 4 | Kg
17 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سیم جوش نقره | 0.2 |  |  |  |  | 0.2 | Kg
18 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تنه کار نقره نیم کیلویی flux powder | 1 |  |  |  |  | 1 | Piece
19 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | نوار درزگیر 5cm عایق | 4 |  |  |  |  | 4 | Roll
20 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | نوار درزگیر 5cm آلومینیومی | 8 |  |  |  |  | 8 | Roll
21 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | نبشی آهن 4 *50 *50 | 36 |  |  |  |  | 36 | Meter | 3.33
22 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | الکترود نمره 3/25 | 5 |  |  |  |  | 5 | Kg
23 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | رول بولت-7*10 | 20 |  |  |  |  | 20 | Piece
24 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | پیج سفید گالوازنیزه نمره 4-6سانت | 200 | 200 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
25 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | مهره گالوانیزه نمره 6 | 200 | 200 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
26 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | واشر تخت گالوانیزه همراه فنری | 200 | 200 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
27 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | اسپری رنگ | 8 | 8 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
28 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بست پایه دار روکشدار ایران 25/8 | 48 | 48 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
29 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | لوله مسی خط مایع 13/80-1.65-مهر اصل-باهنر-وزن هر متر 1.540 کیلو سری K | 120 |  |  |  |  | 120 | Meter | 1.58
30 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | عایق الاستومری فوم 13/8 ضخامت 10 میل | 136 | 4 |  |  |  | 132 | Meter |  | Advise Vendor of Overage/Shortage
31 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | زانو مسی - 90 درجه 13/8 | 96 |  |  |  |  | 96 | Piece
32 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سه راه مسی 90 درجه-90 درجه13/8 | 8 |  |  |  |  | 8 | Piece
33 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تبدیل مسی 13/80* 7/8 | 8 |  |  |  |  | 8 | Piece
34 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تبدیل مسی 13/80 11/8 | 8 |  |  |  |  | 8 | Piece
35 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بوشن مسی 13/80 | 16 |  |  |  |  | 16 | Piece
36 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بست پایه دار فلزی روکش دار 11/2 | 96 | 1 |  |  |  | 95 | Piece |  | Advise Vendor of Overage/Shortage
37 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | لوله مسی خط مایع 25/8- 2/02 میل -مهر باهنر-وزن هرمتر 3/670 کیلو سری L | 120 |  |  |  |  | 120 | Meter | 3.66
38 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | عایق الاستومری فوم 25/8 ضخامت 10 میل | 136 | 136 |  |  |  |  | Meter |  | Advise Vendor of Overage/Shortage
39 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | زانو مسی 90 درجه 25.8 | 96 |  |  |  |  | 96 | Piece
40 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بوشن مسی 25/8 | 16 |  |  |  |  | 16 | Piece
41 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سه را ه مسی 90 درجه - سایز 25/8 | 8 |  |  |  |  | 8 | Piece
42 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تبدیل مسی 21/8* 25/8 | 8 | 8 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
43 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بست پایه دار روکش دار فلزی 3 اینچ | 96 | 4 |  |  |  | 92 | Piece |  | Advise Vendor of Overage/Shortage
44 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | مغزی برنجی سوزنی دار - 1/4 | 16 |  |  |  |  | 16 | Piece
45 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | والاف لوله مسی | 8 |  |  |  |  | 8 | Piece
46 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | درپوش برنجی 4/1 | 8 | 8 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
47 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سیم جوش نقره 30 درصد | 0.4 |  |  |  |  | 0.4 | Kg
48 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | سیم جوش مسی | 8 |  |  |  |  | 8 | Kg
49 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | نوار درزگیر 5-5 سانت | 8 |  |  |  |  | 8 | Roll
50 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | نوار عایق-روکش الومینیونی | 12 |  |  |  |  | 12 | Piece
51 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | نبشی آهن4 *50* 50 | 48 |  |  |  |  | 48 | Meter | 2.91
52 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | الکترود _-نمره 3/25 | 5 |  |  |  |  | 5 | Kg
53 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | رول بونت 80*10 | 20 |  |  |  |  | 20 | Piece
54 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | پیچ سفید گالوانیزه نمره 46 سانت | 400 |  |  |  |  | 400 | Piece
55 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | مهره سفید گالوانیزه - 6 | 400 |  |  |  |  | 400 | Piece
56 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | واشر تخت گالوانیزه-و فنر دار نمره 6 | 400 |  |  |  |  | 400 | Piece
57 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | اسپری رنگ | 8 |  |  |  |  | 8 | Piece
58 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تبدیل مسی 7.8* 11/8 | 8 |  |  |  |  | 8 | Piece
59 | OPI-SLD-9001-028 | 2022-07-26 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-024 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 24 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تنه کار نقره نیم کیلویی flux powder | 1 |  |  |  |  | 1 | Piece
60 | OPI-SLD-9001-034 | 2022-07-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-034 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 34 |  | Sub Item | MISC-Goods | لوله مسی HVAC | عایق لوله ای روکش دار 25/8 ضخامت 10 میل | 136 |  |  |  |  | 136 | Meter
61 | OPI-SLD-9001-034 | 2022-07-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-034 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 34 |  | Sub Item | MISC-Goods | لوله مسی HVAC | عایق لوله ای روکش دار 25/8 ضخامت 10 میل | 68 |  |  |  |  | 68 | Meter
62 | OPI-SLD-9001-034 | 2022-07-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-034 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 34 |  | Sub Item | MISC-Goods | لوله مسی HVAC | پلیت گالوانیزه 150*150*5 | 24 |  |  |  |  | 24 | Piece
63 | OPI-SLD-9001-034 | 2022-07-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-034 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 34 |  | Sub Item | MISC-Goods | لوله مسی HVAC | پیچ نمره 6 - 4 سانت | 200 |  |  |  |  | 200 | Piece
64 | OPI-SLD-9001-034 | 2022-07-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-034 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 34 |  | Sub Item | MISC-Goods | لوله مسی HVAC | مهره گالوانیزه 6 | 200 |  |  |  |  | 200 | Piece
65 | OPI-SLD-9001-034 | 2022-07-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-034 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 34 |  | Sub Item | MISC-Goods | لوله مسی HVAC | واشر تخت 6 | 200 |  |  |  |  | 200 | Piece
66 | OPI-SLD-9001-034 | 2022-07-30 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-034 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 34 |  | Sub Item | MISC-Goods | لوله مسی HVAC | واشر فنری 6 | 200 |  |  |  |  | 200 | Piece
67 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | عایق لوله ای روکش دار 3/8 1 ضخامت 10 میل | 4 |  |  |  |  | 4 | Meter
68 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بست پایه روکش دار 5/8 2 فلزی | 48 |  |  |  |  | 48 | Piece
69 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بست پایه روکش دار 5/8 2 فلزی | 4 |  |  |  |  | 4 | Piece
70 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | اسپری رنگ | 8 | 8 |  |  |  |  | Piece |  | Advise Vendor of Overage/Shortage
71 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | در پوش برنجی 1/4 | 4 |  | 4 |  |  | 8 | Piece |  | Advise Vendor of Overage/Shortage
72 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | تبدیل مسی 1/8 2 *5/8 2 | 8 |  |  |  |  | 8 | Piece
73 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | درپوش برنجی 1/4 | 4 |  |  |  |  | 4 | Piece
74 | OPI-SLD-9001-038 | 2022-08-03 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-037 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 37 |  | Sub Item | MISC-Goods | لوله مسی HVAC | بست پایه روکش دار 1/2 1 فلزی | 1 |  |  |  |  | 1 | Piece
75 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | FOG-B335A | BRANCH PIPE | 59 | 58 |  |  |  | 1 | Set |  | Advise Vendor of Overage/Shortage
76 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | FOG-B506A | BRACH PIPE | 9 |  |  |  |  | 9 | Set
77 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | FOG-B730A | BRANCH PIPE | 9 |  |  |  |  | 9 | Set
78 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | FOG-B1350A | BRACH PIPE | 4 |  |  |  |  | 4 | Set
79 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | FOG-B2040A | BRACH PIPE | 1 |  |  |  |  | 1 | Set
80 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | HZG-30B | OUTDOOR BRANCH PIPE | 1 |  |  |  |  | 1 | Set
81 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | GAS-3/8" | REFRIGERANT GAS PIPE- 3/8" | 106 |  |  |  |  | 106 | Meter
82 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | GAS-5/8" | REFRIGERANT GAS PIPE- 5/8" | 140 |  | 2 |  |  | 142 | Meter |  | Advise Vendor of Overage/Shortage
83 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | GAS-3/4" | REFRIGERANT GAS PIPE- 3/4" | 66 |  |  |  |  | 66 | Meter
84 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | GAS-1.1/8" | REFRIGERANT GAS PIPE- 1.1/8" | 90 |  |  |  |  | 90 | Meter
85 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | GAS-1.5/8" | REFRIGERANT GAS PIPE-1.5/8" | 42 |  |  |  |  | 42 | Meter
86 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | GAS-1/2" | REFRIGERANT GAS PIPE-1/2" | 198 |  |  |  |  | 198 | Meter
87 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | GAS-1.3/8" | REFRIGERANT GAS PIPE-1.3/8" | 12 |  |  |  |  | 12 | Meter
88 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | LIQUIDE-1/2" | REFRIGERANT LIQUIDE PIPE-1/2" | 84 |  |  |  |  | 84 | Meter
89 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | LIQUIDE-1/4" | REFRIGERANT LIQUIDE PIPE-1/4" | 280 |  |  |  |  | 280 | Meter
90 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | LIQUIDE-3/8" | REFRIGERANT LIQUIDE PIPE-3/8" | 164 |  |  |  |  | 164 | Meter
91 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | LIQUIDE-7/8" | REFRIGERANT LIQUIDE PIPE-7/8" | 18 |  |  |  |  | 18 | Meter
92 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | LIQUIDE-3/4" | REFRIGERANT LIQUIDE PIPE-3/4" | 40 |  | 2 |  |  | 42 | Meter |  | Advise Vendor of Overage/Shortage
93 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | LIQUIDE-5/8" | REFRIGERANT LIQUIDE PIPE-5/8" | 62 |  |  |  |  | 62 | Meter
94 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | OIL-3/8" | OIL EQUALIZATION PIPE-3/8" | 12 |  |  |  |  | 12 | Meter
95 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | R410A | OUT1-56.2386 | 9 |  |  |  |  | 9 | Piece
96 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-3/8" | عایق فوم الاستومری 3/8 | 106 |  | 0.2 |  |  | 106.2 | Meter |  | Advise Vendor of Overage/Shortage
97 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-5/8" | عایق فوم الاستومری 5/8 | 140 | 1.4 |  |  |  | 138.6 | Meter |  | Advise Vendor of Overage/Shortage
98 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-3/4" | عایق فوم الاستومری 3/4 | 66 | 1.2 |  |  |  | 64.8 | Meter |  | Advise Vendor of Overage/Shortage
99 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-1.1/8" | عایق فوم الاستومری 1.1/8 | 90 |  |  |  |  | 90 | Meter
100 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-1.5/8" | عایق فوم الاستومری 1.5/8 | 42 | 0.2 |  |  |  | 41.8 | Meter |  | Advise Vendor of Overage/Shortage
101 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-1/2" | عایق فوم الاستومری 1/2 | 193 | 0.4 |  |  |  | 192.6 | Meter |  | Advise Vendor of Overage/Shortage
102 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-1.3/8" | عایق فوم الاستومری 1.3/8 | 12 |  | 0.6 |  |  | 12.6 | Meter |  | Advise Vendor of Overage/Shortage
103 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-1/2" | عایق فوم الاستومری 1/2 | 84 |  | 0.4 |  |  | 84.4 | Meter |  | Advise Vendor of Overage/Shortage
104 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-1/4" | عایق فوم الاستومری 1/4 | 280 | 2.8 |  |  |  | 277.2 | Meter |  | Advise Vendor of Overage/Shortage
105 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-3/8" | عایق فوم الاستومری 3/8 | 163 | 1 |  |  |  | 162 | Meter |  | Advise Vendor of Overage/Shortage
106 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-7/8" | عایق فوم الاستومری 7/8 | 18 |  |  |  |  | 18 | Meter
107 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-3/4" | عایق فوم الاستومری 3/4 | 40 |  | 1.4 |  |  | 41.4 | Meter |  | Advise Vendor of Overage/Shortage
108 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-5/8" | عایق فوم الاستومری 5/8 | 62 |  | 1 |  |  | 63 | Meter |  | Advise Vendor of Overage/Shortage
109 | OPI-SLD-9001-076 | 2022-09-04 | South Adish Gas Condensate Refinery | SACR-PL-SLD-9001-072 | ADISH-P-PO-GE-9001 | Different local Suppliers | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 72 |  | Sub Item | MISC-Goods | pipe insulation-3/8" | عایق فوم الاستومری 3/8 | 8 |  | 2.8 |  |  | 10.8 | Meter |  | Advise Vendor of Overage/Shortage