## Sheet1
# | Identity | Category | Mark No. | Description | Unit | Supply | Packing List | Receipt
1 | Bulk | - | 6843130302 | 0.6/1KV, NYRY - 3C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 330 | 311 | 311
2 | Bulk | - | 6843130403 | 0.6/1KV, NYRY - 4C-4mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 330 | 335 | 335
3 | Bulk | - | 6843130404 | 0.6/1KV, NYRY - 4C-6mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 120 | 279 | 279
4 | Bulk | - | 6843130502 | 0.6/1KV, NYRY - 5C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 330 | 338 | 338
5 | Bulk | - | 6843330117 | 0.6/1KV, N2XYRY - 1C-400mm2 XLPE Insulation, Aluminum Tape Armoured, BLACK color outer sheath | Meter | 380 | 387 | 387
6 | Bulk | - | 6843330302 | 0.6/1KV, N2XRY - 3C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 2000 | 2048 | 2048
7 | Bulk | - | 6843330402 | 0.6/1KV CABLE, N2XRY - 4C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 800 | 817 | 817
8 | Bulk | - | 6843330403 | 0.6/1KV, N2XRY - 4C-4mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 1100 | 1146 | 1146
9 | Bulk | - | 6843330404 | 0.6/1KV, N2XRY - 4C-6mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 550 | 546 | 546
10 | Bulk | - | 6843330405 | 0.6/1KV, N2XYRY - 4C-10mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 520 | 530 | 530
11 | Bulk | - | 6843330407 | 0.6/1KV, N2XRY - 4C-25mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 1040 | 1058 | 1058
12 | Bulk | - | 6843510116 | 3.3/6 (7.2)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | Meter | 250 | 256 | 256
13 | Bulk | - | 6843610114 | 6.35/11 (12)KV, N2XSEYRY - 1C-185mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | Meter | 720 | 742 | 742
14 | Bulk | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | Meter | 6140 | 6345 | 6345
15 | Bulk | - | 6843330114 | 0.6/1KV, N2XYRY - 1C-185mm2 XLPE Insulation, Aluminum Tape Armoured, BLACK color outer sheath | Meter | 50 | 288 | 288
16 | Bulk | - | 6843130802 | 0.6/1KV, NYRY - 8C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | Meter | 120 | 287 | 287

## Sheet2
# | Opi No. | Date | Packing List No. | Purchase Order | Vendor | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
1 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843130404 | 0.6/1KV, NYRY - 4C-6mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | 279 |  |  |  |  | 279 | Meter | 249
2 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843130802 | 0.6/1KV, NYRY - 8C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | 287 |  |  |  |  | 287 | Meter | 245
3 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843130403 | 0.6/1KV, NYRY - 4C-4mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | 335 |  |  |  |  | 335 | Meter | 247
4 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843130502 | 0.6/1KV, NYRY - 5C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | 338 |  |  |  |  | 338 | Meter | 197
5 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843130302 | 0.6/1KV, NYRY - 3C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | 311 |  |  |  |  | 311 | Meter | 137
6 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843330404 | 0.6/1KV, N2XRY - 4C-6mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 546 |  |  |  |  | 546 | Meter | 425
7 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843330302 | 0.6/1KV, N2XRY - 3C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 1025 |  |  |  |  | 1025 | Meter | 437
8 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843330302 | 0.6/1KV, N2XRY - 3C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 1023 |  |  |  |  | 1023 | Meter | 389
9 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843330402 | 0.6/1KV CABLE, N2XRY - 4C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 817 |  |  |  |  | 817 | Meter | 435
10 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843330403 | 0.6/1KV, N2XRY - 4C-4mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 1146 |  |  |  |  | 1146 | Meter | 655
11 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843330407 | 0.6/1KV, N2XRY - 4C-25mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 532 |  |  |  |  | 532 | Meter | 1048
12 | OPI-MOG-128-001 | 2023-07-18 | SACR-PL-MOG-128-001 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 01 |  | Main Item | - | 6843330407 | 0.6/1KV, N2XRY - 4C-25mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 526 |  |  |  |  | 526 | Meter | 1042
13 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 525 |  |  |  |  | 525 | Meter | 2283
14 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 521 |  |  |  |  | 521 | Meter | 2260
15 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 1056 |  |  |  |  | 1056 | Meter | 4557
16 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 1057 |  |  |  |  | 1057 | Meter | 4557
17 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 1074 |  |  |  |  | 1074 | Meter | 4654
18 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 1056 |  |  |  |  | 1056 | Meter | 4542
19 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 1056 |  |  |  |  | 1056 | Meter | 4564
20 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843610114 | 6.35/11 (12)KV, N2XSEYRY - 1C-185mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 742 |  |  |  |  | 742 | Meter | 2256
21 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843510116 | 3.3/6 (7.2)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | 256 |  |  |  |  | 256 | Meter | 1102
22 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843330117 | 0.6/1KV, N2XYRY - 1C-400mm2 XLPE Insulation, Aluminum Tape Armoured, BLACK color outer sheath | 387 |  |  |  |  | 387 | Meter | 1743
23 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843330114 | 0.6/1KV, N2XYRY - 1C-185mm2 XLPE Insulation, Aluminum Tape Armoured, BLACK color outer sheath | 288 |  |  |  |  | 288 | Meter | 653
24 | OPI-MOG-128-002 | 2023-07-26 | SACR-PL-MOG-128-002 | ADSH-P-PO-GE-128 | Moghan WIRE & CABLE | 2 |  | Main Item | - | 6843330405 | 0.6/1KV, N2XYRY - 4C-10mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | 530 |  |  |  |  | 530 | Meter | 528
[8 empty] | 6843610116 | 525
[8 empty] | 6843610116 | 521
[8 empty] | 6843610116 | 1056
[8 empty] | 6843610116 | 1057
[8 empty] | 6843610116 | 1074
[8 empty] | 6843610116 | 1056
[8 empty] | 6843610116 | 1056
[8 empty] | 6843610114 | 742
[8 empty] | 6843510116 | 256
[8 empty] | 6843330117 | 387
[8 empty] | 6843330114 | 288
[8 empty] | 6843330405 | 530

## Sheet3
خلاصه مالی خرید کابل | [11 empty] | شماره قرارداد: ADSH-P-PO-GE-128
خریدار: شرکت پالایشگاه میعانات گازی آدیش جنوبی | [11 empty] | تاریخ قرارداد: 1402/02/04
فروشنده: شرکت کابل مغان | [11 empty] | تاریخ تهیه گزارش: 1402/05/08
ردیف | کد کالا | شرح کالا | واحد | مقدار | بهای واحد (ریال) | مبلغ قرارداد (ریال) | مقادیر رسید شده مرحله1 | مقادیر رسید شده مرحله1 | بهای واحد (ریال) | مبلغ کالای دریافتی (ریالی) | درصد کالای دریافتی | تفاوت نرخ
1 | 6843130404 | 0.6/1KV, NYRY - 4C-6mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 120 | 1738902 | 208668240 | 279 | 0 | 1808596 | 504598284 | 232.5% | -69694
2 | 6843130802 | 0.6/1KV, NYRY - 8C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 120 | 1531739 | 183808680 | 287 | 0 | 1589981 | 456324547 | 239.2% | -58242
3 | 6843130403 | 0.6/1KV, NYRY - 4C-4mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 330 | 1291254 | 426113820 | 335 | 0 | 1337716 | 448134860 | 101.5% | -46462
4 | 6843130502 | 0.6/1KV, NYRY - 5C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 330 | 994196 | 328084680 | 338 | 0 | 1030515 | 348314070 | 102.4% | -36319
5 | 6843130302 | 0.6/1KV, NYRY - 3C-2.5mm2 PVC Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 330 | 677631 | 223618230 | 311 | 0 | 699553 | 217560983 | 94.24% | -21922
6 | 6843330404 | 0.6/1KV, N2XRY - 4C-6mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 550 | 1764259 | 970342450 | 546 | 0 | 1833953 | 1001338338 | 99.27% | -69694
7 | 6843330302 | 0.6/1KV, N2XRY - 3C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 2000 | 667635 | 1335270000 | 2048 | 0 | 689557 | 1412212736 | 102.4% | -21922
8 | 6843330402 | 0.6/1KV CABLE, N2XRY - 4C-2.5mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 800 | 882510 | 706008000 | 817 | 0 | 911631 | 744802527 | 102.1% | -29121
9 | 6843330403 | 0.6/1KV, N2XRY - 4C-4mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 1100 | 1145918 | 1260509800 | 1146 | 0 | 1192380 | 1366467480 | 104.2% | -46462
10 | 6843330407 | 0.6/1KV, N2XRY - 4C-25mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 520 | 6146725 | 3196297000 | 532 | 0 | 6437606 | 3424806392 | 102.3% | -290881
11 | 6843330407 | 0.6/1KV, N2XRY - 4C-25mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 520 | 6146725 | 3196297000 | 526 | 0 | 6437606 | 3386180756 | 101.2% | -290881
12 | 6843610116 | 6.35/11 (12)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | متر | 6140 | 17402691 | 106852522740 | 0 | 6345 | 18346990 | 116411651550 | 103.3% | -944299
13 | 6843610114 | 6.35/11 (12)KV, N2XSEYRY - 1C-185mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | متر | 720 | 12365276 | 8902998720 | 0 | 742 | 12975177 | 9627581334 | 103.1% | -609901
14 | 6843510116 | 3.3/6 (7.2)KV, N2XSEYRY - 1C-300mm2 XLPE Insulation, Aluminum Wire Armored, RED color outer sheath | متر | 250 | 18547537 | 4636884250 | 0 | 256 | 19491836 | 4989910016 | 102.4% | -944299
15 | 6843330117 | 0.6/1KV, N2XYRY - 1C-400mm2 XLPE Insulation, Aluminum Tape Armoured, BLACK color outer sheath | متر | 380 | 20581117 | 7820824460 | 0 | 387 | 21744640 | 8415175680 | 101.8% | -1163523
16 | 6843330114 | 0.6/1KV, N2XYRY - 1C-185mm2 XLPE Insulation, Aluminum Tape Armoured, BLACK color outer sheath | متر | 50 | 9853317 | 492665850 | 0 | 288 | 10391561 | 2992769568 | 576% | -538244
17 | 6843330405 | 0.6/1KV, N2XYRY - 4C-10mm2 XLPE Insulation, Steel Wire Armoured, BLACK color outer sheath | متر | 520 | 2657466 | 1381882320 | 0 | 530 | 2773949 | 1470192970 | 101.9% | -116483
|  |  |  | 14780 |  | 142122796240 | 7165 | 8548 |  | 157218022091 |  | -15095225851
معادل ریالی
جمع کالای دریافتی طبق MRS-MOG-128-001 | [5 empty] | 13310740973 |  | قیمت اولیه قرارداد 142/122/796/240 ریال بوده که با توجه به نرخ مس و باتوجه به تبصره 2 ماده 3 نرخ مس در بورس فلزات در روز پرداخت پیش پرداخت میباشد که منجر به تعدیلا و افزایش قیمت به ارزش 15/095/225/851 ریال شده است.لازم به ذکر است که بیشتر اقلام نسبت به دستور خرید و قرارداد ADSH-P-PO-GE-128 فیمابین بیشتر دریافت شده است.درصد کالای دریافت شده طبق جدول بالا قابل مشاهده میباشد.همچنین تاریخ تحویل از زمان پرداخت پیش پرداخت 70 روز تقویمی میباشد که تاریخ بارنامه محموله 1 1402/04/18 میباشد.
جمع کالای دریافتی طبق MRS-MOG-128-002 | [5 empty] | 143907281118
مالیات و عوارض بر ارزش افزوده | [5 empty] | 14149621988.19
جمع صورتحساب | [5 empty] | 171367644079.19
کسور:
پیش پرداخت (50% قرارداد) پرداخت در مورخ 1402/02/04 | [5 empty] | -71061398120
جریمه (10%)
جمع کسور | [5 empty] | -71061398120
خالص پرداختی نهایی | [5 empty] | 100306245959.19