## Sheet1
item No. | Order No. / ref No. | Manf. | Inspected Place | Responsible Person | Notification request | Notification No | Notification Date | Actual Inspection duration | assigning date | supporing dox | INSPECTION Report No | IO. No. | next step | IC
1 | KTI-0010 | KTI | korea |  | In-process Inspection | SACR-DE-GEN-MA-MRQ-5303-02- KTI-0010 (Rev.010) | 24. mar .2020 | 07&09.Apr,2021 | 06.apr.2020 | not included / sent after request | IVR-KTI-HET-010-F-Par2 Rev.01 | revised report received
2 | KTI-0011 | KTI | korea |  | In-process Inspection / shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0011 (Rev.0) | 06.Apr.2020 | 2020.04.13~29 (9days) /AM10:00 | rev 1, 8 apr.2020 | included | IVR-KTI-HET-011-F-part 3
3 | KTI-0012 | KTI | korea |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0012 (Rev.0) | 13.Apr.2020 | 2020.04.22 (1 days) /AM10:00 | 14.4.2020 | included
4 | KTI-0013 | KTI | korea |  | In-process Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0013 (Rev.0) | 22.Apr.2020 | 2020.04.29 /AM10:01 | 25.4.2020 | included | IVR-404-FSK-0013-F part1
5 | KTI-0014 | KTI | korea |  | In-process Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0014 (Rev.0) | 29.Apr.2020 | 2020.05.06~16 /AM10:00 | rev 1 assigned 11 may 2020 | not included / sent after request | IVR-303-KTI-HET-014 part 1 & 2 | report received
6 | KTI-0015 | KTI | korea |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0015 (Rev.0) | 29.May.2020 ???? | 2020.05.07 & 15 (2DAYS) /PM 10:00 | 29 apr. 2020 | not included / sent after request | IVR-KTI-HET-015-F-part1 IVR-303-KTI-HET-015-F-part2 IVR-303-KTI-HET-015-F-part3 | report received
7 | KTI-0016 | KTI | italy |  | In-process Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0016 (Rev.0) | 07. May. 2020 | 2020.05.13 / 09:30 AM | 9.may.2020 | not included / sent after request
8 | KTI-0017 | KTI | korea |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0017 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0017 (Rev.1) | 07.May.2020 22.Jul.2020 | 2020.05.14 (Thu.) /AM 10:00 2020.07.28 (1 day) /AM 10:00 | 9.may.2020 22.7.2020 | not included / sent after request | IVR-303-KTI-HET-017(Rev.1) -F-part 2
9 | KTI-0018 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0018 (Rev.0) | 12.May.2020 | 2020.05.18~30 /AM10:00 | 13.5.2020 | not included / sent after request | IVR-303-KTI-HET-018-F-part 1 | report received
10 | KTI-0019 | KTI | korea |  | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0019 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0019 (Rev.1) | 12.May.2020 11.6.2020 | 2020.05.22 (1 days) /AM10:00 | 13.5.2020 15.6.2020 | not included / sent after request | IVR-303-KTI-HET-019-F-part 1 IVR-303-KTI-HET-019(Rev.1)-F-part 1 | comment confirmed | revised notification sent to GL for Re-Inspection on 15.6.2020
11 | KTI-0020 | KTI | korea |  | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0020 (Rev.0) | 14.May.2020 | 2020.05.27~28 (2 days) /AM10:00 | 18.5.2020 | included | IVR-303-KTI-HET-020-F-part 1 | report received
12 | KTI-0021 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0021 (Rev.0) | 27.May.2020 | 2020.06.01~13 /AM 09:00 | 27.05.2020 | not included | IVR-303-KTI-HET-021-F-part 1 IVR-303-KTI-HET-021-F-part 2
13 | KTI- 022 | KTI | korea |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0022 | 29.May.2020 | 2020.06.09 (1 day) /AM10:00 | 2.6.2020 | not included / sent after request | IVR-303-KTI-HET-022-F-part 1
14 | KTI- 023 | KTI |  |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0023 | 29.May.2020 | 2020.06.10 (1 day) /A M10:00 | 2.6.2020 | not included / sent after request | IVR-303-KTI-HET-023-F-part 1
15 | kti-0025 | KTI | korea |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0025 (Rev.0) | 02.Jun.2020 | 2020.06.16 (1 day) /AM10:00 | 02.Jun.2020 |  | IVR-303-KTI-HET-025F PART1
16 | kti-0024 | KTI | korea |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0024 (Rev.0) | 02.Jun.2020 | 2020.06.15 (1 day) /AM10:00 | 02.Jun.2020 |  | IVR-303-KTI-HET-024-F-part1 IVR-303-KTI-HET-024(Rev.1)-F-part 1
17 | KTI-0026 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0026 (Rev.0) | 10.06.2020 | 2020.06.15~30 (14 days) /AM 09:00 | 10.06.2020 | not included | IVR-303-KTI-HET-026-F-part 1 IVR-303-KTI-HET-026-F-part2 | revised notification sent to GL
18 | Kti-0027 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0027 | 10.06.2020 | 1) 19-JUN-2020 10:00AM : ITP ACTIVITY NO.: 18,20,21 2) 26-JUN-2020 10:00AM : ITP ACTIVITY NO.: 22 | 10.06.2020 | not included | IVR-303-KTI-HET-027-F-part 1 | revised notification sent to GL
19 | Kti-0028 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0028 (Rev.0) | 11.Jun.2020 | 2020.06.23 (1 day) /AM10:00 | 13.06.2020 | not included | IVR-303-KTI-HET-028-F-part 1 | revised notification sent to GL
20 | Kti-0029 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0029 (Rev.0) | 18.Jun.2020 | 2020.06.26 (1 day) /AM10:00 | 20.6.2020 | not included | IVR-303-KTI-HET-029-F-part 1
21 | Kti-0030 | KTI | italy |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0030 (Rev.0) | 23.June.2020 | 2020.06.29 / 09:30 AM | 23.6.2020 | included | IVR-303-KTI-HET-030-F-part 1
22 | Kti-0031 | KTI | italy |  | final inspection/ dox review | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0031 (Rev.0) | 23.June.2020 | 14/16/17/18/19/20/21/22/23/24 for BURNER & 11/17/18/19 for UV SCANNER | 23.6.2020 | included | IVR-303-KTI-HET-031-F-part 1
23 | KTI -0032 | KTI | korea |  | in processFinal | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0032 (Rev.0) | 29. Jun. 2020 | 2020.07.01~11 (10 days) /AM 09:00 | 29.6.2020 | included | IVR-303-KTI-HET-032 part 1 IVR-303-KTI-HET-032 part 2
24 | KTI-0033 | KTI | korea |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0033 (Rev.0) | 06. Jul. 2020 | 2020.07.23 (1 day) / AM10:00 | 7.7.2020 | not included | IVR-303-KTI-HET-033 part 1
25 | KTI-0034 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0034 (Rev.0) | 09. Jul. 2020 | 2020.07.13~31 (16 days) /AM 09:00 | 11.7.2020 | not included | IVR-303-KTI-HET-034 part 1 IVR-303-KTI-HET-034 part 2 IVR-303-KTI-HET-034 part 3
26 | KTI-0035 | KTI | korea |  | shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0035 (Rev.0) | 10.JUL.2020 | 30-JUL-2020 10:00AM | 11.7.2020 | not included | IVR-303-KTI-HET-035-F-part 1
27 | KTI-0036 | KTI | korea |  | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0036 (Rev.0) | 14.Jul.2020 | 2020.07.28~29 (2 day) / AM10:00~PM 17:30 | 14.7.2020 | not included | IVR-303-KTI-HET-036-F-part 1
28 | KTI-0037 | KTI | korea |  | final/ shipment reinspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0037 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0037 (Rev.1) | 21.Jul.2020 18.Aug.2020 | 2020.08.11~12, 25 (3 day) / AM10:00~PM 17:30 | 22.7.2020 15.08.2020 | included | IVR-303-KTI-HET-017(Rev.1) -Fpart 3
29 | KTI-0038 | KTI | korea |  | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0038 (Rev.0) | 21.Jul.2020 | 2020.07.30~31 (2 days) /AM10:00 | 22.7.2020 | included | IVR-303-KTI-HET-038-F-part 1
30 | KTI-0039 | KTI | korea |  | shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0039 (Rev.0) | 22.JUL.2020 | 10-AUG-2020 10:00AM | 22.7.2020 | included | IVR-303-KTI-HET-039-F-part 1
31 | KTI-0040 | KTI | korea |  | in process/ shipment / final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0040 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0040 (Rev.1) | 22. JUL. 2020 07. AUG. 2020 | 2020.08.04~12 (7days) /AM 09:00 2020.08.04~14 (9days) /AM 09:00 | 22.7.2020 | included | IVR-303-KTI-HET-040-F-part 1
32 | KTI-0041 | KTI | korea |  | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0041 (Rev.0) | 23.JuL.2020 | 2020.08.11~12 (2 day) /AM10:00 | 23.7.2020 | not included | IVR-303-KTI-HET-041-F-part 1
33 | KTI 0042 | kti | korea |  | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0042 (Rev.0) | 23.Sep.2020 | 2020.10.06 (1 day) / AM10:00 | 23.9.2020 | included | IVR-303-KTI-HET-042-F-part 1
100 | hatco -028 | hatco | china |  | review final | INS-307(308)-HAT-0028 |  | 44180 |  |  | IVR- HAT-NIS-0028 part 2
101 | DAGHIGH SAZAN ARAZ_ Galv pipe | DAGHIGH SAZAN | china |  | final | IN- DGS-002 | 44261 | 09 Apr.2021 |  |  | IVR- DGS-002-rev.00
102 | CLA-VAL | Pedinco | India |  |  | PED-804-IN-019 | 44313 | 07.May.2021 – 10:00 AM |  |  | IVR-PED-001-Rev.00
103 | Jomont | Roodhart | France |  |  | 010-RPG-0005 | 29/04/2021 | 18-05-2021 - 21-05-2021 |  |  | IVR - RPG -01-Rev.00
104 | TehranJavan | tehran javan | italy |  | shipment | 5304-TJC-0002 | 19.May.2021 | 25.May.2021 at 9am |  | Final Tyco/Site | IVR-TJC-001-REV.00
105 | DAGHIGH SAZAN ARAZ, Flange | DAGHIGH SAZAN | china |  | final | 1 | 44355 | 44376 |  |  | IVR- Daghigh-001
106 | DAGHIGH SAZAN ARAZ, Wrought Fitting | DAGHIGH SAZAN | china |  | final | 2 | 44389 |  | 44391
107 | Iran Tablo-ABB-LV | ABB | Turkey |  | final | 10187 |  |  | 44397 |  | IVR-402108
108 | Iran Tablo-MV | ABB | Slovenia |  | final | 10121 |  |  | 44394 |  | IVR-ABB-001-Rev.00
109 | Mixer | tehran javan | Poland |  | final | 5314-TJC-0002 | 19/07/2021 |  | 19/07/2021 | Tie-co | TIE/T/108-00-0645 |  |  | YES
110 | Metering Pump | tehran javan | Germany |  | final | 5302-TJC-0001 | 44507 |  | 44507
111 | CIP | tehran javan | Germany |  | final | 5304-TJC-0004 | 44508 |  | 44508
112 | 28 inch pipe | Notash Sanat | Dubai |  | final | 1 | 44414 |  | 44414 |  | IVR-NOTAH-01-Rev.00
113 | Flow Meter | Farherman | France |  | final |  | 44476 |  | 44537
114 | Y FISCAL METERING SYSTEM PACKAGE |  | Germany |  | final |  | 20/07/2021 |  | 25/07/2021
115 | Y FISCAL METERING SYSTEM PACKAGE |  | Germany |  | final | 037-EKP-0009 | 44294 |  | 44294
117 | Water drum and steam drum | KANGWON Co., Ltd. | Korea |  | final | AFI-KW-001 | 44416 |  | 44416 | Tie-co | TIE-T-108-00-0744
118 | PSV | Leser | Germany |  | final | 20468897 | 44477 |  | 2021-10-08 | Tie-co | TIE/T/108-00-0719-01
120 | Level Guage | tehran javan | Italy |  | shipment | 5304-TJC-0005 | 14/08/2021 |  | 14/08/2021 | Tie-co | TIE/T/ 108-00-0751
121 | Prominent Pump | tehran javan | Germany |  | shipment | 5304-TJC-0006, 5302-TJC-0002 | 17/08/2021 |  | 17/08/2021 | Tie-co | TIE/T/108-00-0756 |  |  | YES
122 | Foam Package-Delauge Valve | Claval | Switzerland | Mrs. Ranjbar | in Process | FR-001-R1 |  |  |  | Tie-co | TIE/T/108-00-0739
123 | Foam package- Foam Dosing | SISICO-001 | Germany | Mrs. Ranjbar | Final + Shipment | FR-002 | 25/08/2021 |  | 25/08/2021 | Tie-co | TIE-T-108-00-0767
124 | Plates | KS Energy Limited-Fateh sanat- 002 | China | Mr. Farvani | final | FSK-IDR-038 | 25/08/2021 |  | 25/08/2021 | Tie-co | TIE/T/108-00-0770
125 | Metering System | EKP-003 | UK | Ebrahimian | final | EKP-0014 | 28/08/2021 |  | 28/08/2021 | Tie-co | TIE/T/108-00-0794
126 | Metering System | EKP-004 | Germany | Ebrahimian | final | EKP-0015 | 28/08/2021 |  | 28/08/2021 | Tie-co | TIE/T/108-00-0812
127 | Metering System | EKP-005 | UAE | Ebrahimian | final | EKP-0016 | 30/08/2021 |  | 30/08/2021 | Tie-co | TIE/T/108-00-0785
128 | Metering System | EKP-006 | UAE | Ebrahimian | final | EKP-0017 | 30/08/2021 |  | 30/08/2021 | Tie-co | TIE/T/108-00-0814
128 | Steam Package | Fateh Sanat-Kangwon-007 | Korea | Mr. Farvani | final | AFI-KW-005 | 44386 |  | 44386 | Tie-co
129 | Centrifugal Pumps | Roodhart-008 | Netherlands | Mrs. Ranjbar | final | 035-RPG-0003 |  |  |  | Tie-co
130 | Flare System | GBA-009 | Italy | Mrs. Ranjbar | in Process | 1 | 44539 |  | 44539 | Tie-co | TIE/T/108-00-0824
132 | Fitting | Daghighsazan-010 | China | Mr. Agin | final | 3 | 44539 |  | 44539 | Tie-co | TIE/T/108-00-1009 |  |  | YES
133 | Centrifugal Pumps | Roodhart-011 | Netherlands | Mrs. Ranjbar | final |  | 44479 |  | 44479 | Tie-co | TIE/T/ 108-00-0943 TIE/T/ 108-00-0957 TIE/T/108-00-0977 TIE/T/108-00-1007 TIE/T/108-00-1024
132 | Steam Package | Fateh Sanat-Kangwon-012 | Korea | Mr. Farvani | in processs | AFI-KW-006 | 18/09/2021 |  | 18/09/2021 | Tie-co | TIE/T/108-00-0871
133 | Metering System | EKP-013 | Germany | Ebrahimian | Final | EKP-0021-R.01 | 18/09/2021 |  | 18/09/2021 | Tie-co | TIE/T/ 108-00-0852
134 | Review of material certification | GBA-014 | italy | Mrs. Ranjbar | in Process | 3 | 20/10/2021 |  | 20/10/2021 | Tie-co | TIE/T/108-00-1037
135 | Tube expending | Fateh Sanat-Kangwon-015 | Korea | Mr. Farvani | in Process | AFI-KW-007 | 23/10/2021 |  | 23/10/2021 | Tie-co | TIE/T/108-00-1068
136 | Fitting | Daghighsazan-016 | china | Mr. Agin | final | 4 | 44207 |  | 44207 | Tie-co | TIE-T-108-00-1092 |  |  | YES
137 | ECONOMIZER | Fateh Sanat-Kangwon-017 | Korea | Mr. Farvani | in Process | AFI-KW-008 | 44238 |  | 44238 | Tie-co | TIE/T/108-00-1076
138 | Boiler ( Hydrostatic Test) | Fateh Sanat-Kangwon-018 | Korea | Mr. Farvani | in Process | AFI-KW-009 | 44266 |  | 44266 | Tie-co | TIE/T/108-00-1088
139 | PSV | Leser-019 | Germany | Ms. Sharifi | Final | TT20-1584 | 44358 |  | 2021-06-11 | Tie-co | TIE/T/108-00-1146
140 | Foam chamber and foam pourer | SISICO -020 | India | Ms. Ranjbar | Final | 13 | 44358 |  | 44358 | Tie-co | TIE/T/108-00-1166 |  |  | YES
141 | Self-cleaning filter | Sati -021 | Italy | Ms. Sharifi | Final |  | 44419 |  | 44419 | Tie-co | TIE/T/108-00-1509 |  |  | YES
142 | Centrifugal Pumps | Roodhart-022 | Netherlands | Mrs. Ranjbar | Final | 035-RPG-0006 | 44450 |  | 44450 | Tie-co | TIE/T/108-00-1111 TIE/T/108-00-1120 TIE/T/108-00-1142
143 | Total Flooding System(IG55) | SSICO-023 | Spain | Mrs. Ranjbar | Final | 14 | 44450 |  | 44450 | Tie-co | TIE/T/108-00-1154 |  |  | YES
144 | Material receipt and identification | GBA-024 | India | Mrs. Ranjbar | in Process | 4 | 13/11/2021 |  | 13/11/2021 | Tie-co | TIE/T/108-00-1136
145 | Steam Turbine | Fateh Sanat - 025 | India | Mr. Farvani | in Process | AFI-ITL-001 | 21/11/2021 |  | 21/11/2021 | Tie-co | TIE/T/108-00-1168
146 | Fire fighting Monitors and Monitor Nozzles | SISICO - 026 | India | Mrs. Ranjbar | Final | FR-044-001 | 24/11/2021 |  | 24/11/2021 | Tie-co | TIE/T/ 108-00-1303 |  |  | YES
147 | Flare system | GBA -027 | Italy | Mrs. Ranjbar | Final | 5 | 28/11/2021 |  | 28/11/2021 | Tie-co | TIE/T/ 108-00-1187
148 | Flare system | GBA -028 | India | Mrs. Ranjbar | in process | 6 | 28/11/2021 |  | 05,07 Jan 22 | Tie-co
149 | Steam Package | Fateh Sanat-Kangwon -029 | Korea | Mr. Farvani | Final | AFI-KW-010 | 28/11/2021 |  | 28/11/2021 | Tie-co | TIE/T/ 108-00-1191
150 | Steam Package | Fateh Sanat-Kangwon -030 | Korea | Mr. Farvani | Final | AFI-KW-011 | 28/11/2021 |  | 28/11/2021 | Tie-co | TIE/T/108-00-1198
151 | Desuperheater | KWB -031 | Korea | Mrs. Ranjbar | in Process | AFI-0001 | 29/11/2021 |  | 29/11/2021 | Tie-co | TIE/T/108-00-1255
152 | Centrifugal Pumps | Roodhart-032 | Netherlands | Mrs. Ranjbar | Final | NOI 035-RPG-0007 | 9,10/12/2021 |  | 44359 | Tie-co | TIE/T/108-00-1208
153 | Ignition Skid | GBA Flare System-033 | Italy | Mrs. Ranjbar | in Process | 7 | 13/12/2021 |  | 13/12/2021 | Tie-co | TIE/T/108-00-1288
154 | Fire Water Pump | WEG 450 kW Motor Testing-034 | Portugal | Mrs. Ranjbar | Final | 1 | 13/12/2021 |  | 13/12/2021 | Tie-co | TIE/T/108-00-1286
155 | Steam Package - Boiler and Ecpnomizer | Fateh Sanat-Kangwon-035 | korea | Mr. Farvani | in Process | AFI-KW-012 | 14/12/2021 |  | 20/12/2021 | Tie-co | TIE/T/108-00-1277 |  |  | YES
156 | zaffertec - part 2 | zaffertec | italy |  | final inspection | 2 | 16.05.2020 | 22.May.2020 9:00 AM | sent by email after reminding to the vendor 16.5.2020 | included | IVR-502-ZAF-PIP-0002-F | irn issued
156 | Fitting 48” WPB,46”WPB,46” WPL6 | Informatic General Trading-036 | Dubai | Mrs. Ranjbar | in Process | 1 | 20/12/2022 |  | 44835 | Tie-co | TIE/T/108-001283
157 | Zaffertec part 3 | zaffertec | korea |  | in process | 5511-ZSL-003 | 27.07.2020 | 30.07.2020 | 28.7.2020 | included | IVR-5511-ZAF-PIP-0001-F
157 | Centrifugal Pumps | Roodhart-037 | Netherlands | Mrs. Ranjbar | Final | 035-RPG-0008 | 44547 |  | 44551 | Tie-co | TIE/T/ 108-00-1263 TIE/T/ 108-00-1268 |  |  | YES
158 | zaffertec - part 4 | zaffertec | korea |  | final | 5511-ZSL-004 |  | 13.08.2020 | 2.8.2020 | not included | IVR-511-ZAF-PIP-0004-F
158 | Control Valve (TCV, PCV), Desuper Heater | KWB-038 | Korea | Mrs. Ranjbar | Final | AFI-0002A | 44552 |  | 29,30 & 31 Dec 2021 | Tie-co | TIE/T/108-1314 |  |  | YES
159 | zaffertec - part 5 | zaffertec | korea |  | final | 5511-ZSL-005 | 05.08.2020 | 12.08.2020 | 9.8.2020 | included | IVR-511-ZAF-PIP-0005-F
159 | Flange and Fitting | Tehran Javan-039 | Dubai | Mrs. Ranjbar | Final | 5304-TJC-0013 | 44552 |  | 27/10/2021 | Tie-co | TIE-T-108-00-1301
160 | zaffertec - part 6 | zaffertec | korea |  | final | 5511-ZSL-006 | 05.08.2020 | 13 and 14.08.2020 (Two Days) | 9.8.2020 | included | IVR-511-ZAF-PIP-0006-F
160 | Manual Valve | Godakhtar - ARFLU-040 | China | Mrs. Ranjbar | in Process | IDR-019 | 44558 |  | 44566 | Tie-co | TIE/T/108-00-1357
161 | zaffertec - part 5 | zaffertec | korea |  | final | 5511-ZSL-007 |  | 12.10.2020 and 16.10.2020 | 26.9.2020 | included | IVR-511-ZAF-PIP-0007-F part 1 IVR-511-ZAF-PIP-0007-F part 2
162 | HATCO- part 1 | hatco | china |  |  | SACR-MG-GEN-PQ-FRM-7401 | 21.1.2020 | 43853 |  |  | HAT-AIR-0001-F | commented report received | waiting for IC
161 | Centrifugal Pumps | Roodhart-041 | Netherlands | Mrs. Ranjbar | in Process | 035-RPG-0009 | 44564 |  | 44566 | Tie-co | TIE-T-108-00-1335 TIE-T-108-00-1336
162 | zaffertec | zaffertec | korea |  | final | 5511-ZSL-008 |  | 11~13, Jan. 2021
163 | HATCO- part 3 | hatco |  |  |  | INS-307-HAT-0003 | 43899 |  | assigned / not approved |  |  | cancelled
162 | Forged and Wrought fittings | Hebei Haitian Pipe Fittings-042 | china | Mrs. Ranjbar | in Process | 2_1 | 44569 |  | 12&13 Jan 22 | Tie-co | TIE/T/108-00-1380 |  |  | YES
163 | hatco - part 2 | hatco | china |  | final | INS-307-HAT-0015 | 26.Jul.2020 | 17.08.2020 at 09:00 o’clock ; End: 19.08.2020 at 15:00 o’clock | 1.8.2020 | included | IVR- HAT-AIR-0015-F.
163 | FAT TEST Of Medium Voltage Motors | Roodhart-043 | France | Mrs. Ranjbar | Final | 010-RPG-0006 | 25 Jan 22 |  | 31 Jan 22 - 4 Feb 22 | Tie-co | TIE/T/108-00-1469
164 | 4-Way Valves-Final Visual and Dimensional | EKP-044 | Netherlands | Ebrahimian | Final | 037-EKP-0037-Rev.01 | 29 Jan 22 |  | 10 feb 22 | Tie-co | TIE/T/ 108-00-1495
165 | Hatco- part 3 | hatco | the netherlands |  | final | INS-307-HAT-0017 | 15.Aug.2020 | 44068 | 15.8.2020 | included | IVR- HAT-NIS-0017
166 | Hatco -023 | hatco | china |  |  | INS-307-HAT-0023 |  | 10, 11 , 13 OCT |  | included | IVR- HAT-NIS-0023 part 1 IVR- HAT-NIS-0023 part 2 IVR- HAT-NIS-0023 part 3
165 | Dosing Pumps | Seko-045 | Italy | Sharifi | in Process | SK-010379 | 30 Jan 22 |  | 10 feb 22 | Tie-co | TIE/T/ 108-00-1496
166 | Hatco -028 | hatco | china |  |  | INS-307(308)-HAT-0028 |  | 44521 |  | included | IVR- HAT-NIS-0028 part 1
167 | hatco-025 | hatco | china |  | final | INS-307-HAT-0025 |  | 9-10 oct 2020 |  |  | IVR- HAT-NIS-0025
168 | Hisco - part 1` | hisco | korea |  | final inspection | MRQ-5702-01 | 44080 | Jun 24th,2020 | 14.06.2020 | included | IVR-MRQ-001
169 | FGS 2nd | FGS | china |  | final inspection | 401-FSK-0006 | 43836 | 20.Jan.2020
170 | FGS 2nd | FGS | china |  | final inspection | 403-FSK-0007 | 43810 | 23.Dec.2019~27.Dec.2019 |  |  | IVR-FSK-PRV-0001-F | report received
171 | FGS 2nd | FGS | china |  | final inspection | 401-FSK-0012 | 43930 | 20.Apr.2020 |  |  | IVR-401-FSK-TOW-0012 F | report received
172 | FGS 2nd | FGS | china |  | final inspection | 404-FSK-0008 Rev.00 (E-326) | 21 Apirl, 2020 | 21~25 Apirl, 2020 (one day) | 22.4.2020 | included | IVR-404-FSK | report received
173 | Rajan 2nd | Rajan | china |  | final inspection | 2 | 17.02.2020 | 18.2.2020 | sent by email after reminding to the vendor |  | IVR-RPF-SST-0003-F | report received | waiting for IC
174 | FGS 2nd | FGS | china |  | final inspection | 404-FSK-0010 | 43948 | 08.May.2020 | 28.4.2020 | included | IVR-FSK-0010-F | report received
175 | Rajan 3 | Rajan | china |  | Final/ shipment | NOTIFICATION NO.: 003 | 28.6.2020 | 44013 | 28.6.2020 | included
176 | FGS 2nd | FGS | china |  | final inspection | 404-FSK-0012 Rev.00 (E326) | 43971 | 27.May.2020 ~ 29. May.2020 | 22.5.2020 | not included / sent after request | IVR-404-FSK-0014-F part1 | report received
177 | rajan part 4 | rajan | china |  | final/ shipment | 4 | 4.8.2020 | 5.8.2020 | 4.8.2020 | included | IVR-RPF-SST-0004-F
178 | FGS 2nd | FGS | china |  | final inspection | 404-FSK-0013 Rev.00 (E326) | 43972 | 29.May.2020 | 27.5.2020 | included
179 | Rajan- 6 | Rajan | china |  | final/ shipment | 6 | 9.2.2020 | 44081 | 22.9.2020 | included | IVR-RPF-SST-0006-F
180 | FGS 2nd | FGS | china |  | final inspection | 404-FSK-0014 REV.00 (E326) | 43948 | 29.May.2020 | 27.5.2020 | included
181 | pedinco- part 1 | pedinco | Switzerland. |  | In-process Inspection | PED-804-IN-006 | 43806 | 6th & 7th of February, 2020 |  |  | IVR-PED-DLG-0001-F | report received
182 | RMT- control valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-703-0001 | 23.Feb.2020 | March, 04 (1 Day) | 25.2.2020 | not included
183 | FGS 2nd | FGS | korea |  | final inspection | 404-FSK-0015 Rev.00 (E326) | 01 Jun 2020 | 29.May.2020(1st), 02.June.2020(2ND), 04.June.2020(3rd), 08.June.2020(4th) | 31.5.2020 | not included / sent after request |  | waiting for supporting dox
184 | pedinco- part 2 | pedinco | italy |  | In-process Inspection | PED-804-IN-012 | 43890 | Friday , 06.Mar.2020 (98.12.16) - 10:00 AM | 29.2.2020 | not included / | IRN-PED-DLG-0002-F | IRN received
185 | RMT- control valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-703-0002 | 23.Feb.2020 | March, 02 (1 Day) | 25.2.2020 | not included
186 | FGS 1st | FGS | italy |  | Final/ shipment | 405-FSK-0020-A (A103) | 23.June.2020 | 03 July 2020 ( except 06 July) | 24.6.2020 | included | IVR-405-FSK-0020-F part1
187 | Pedinco- Deluge Valve | pedinco | Switzerland |  | In-process Inspection | PED-804-IN-016 | 10.06.2020 | 17.Jun.2020 – 10:00 AM | 10.06.2020 | included | IVR-804-IN-PEDINCO-016 F PART 1
188 | RMT- control valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-703-0003 | 23.Feb.2020 | March, 03 - 9.30 am (1 Day) | 25.2.2020 | not included
189 | FGS 2nd | FGS | china |  | final inspection | 404-FSK-0016 | 44008 | 5. July.2020 | 28.6.2020 | included | IVR-404-FSK-0016-F part1
190 | RMT Actuated valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-701-0002 | 22.Feb.2020 | March, 04 (1 Day)
191 | FGS- Aircooler | FGS | italy |  |  | 405-FSK-0021 (A103) | 24.Sep.2020 | 05.Oct.2020 | 26.9.2020 | included | IVR-405-FSK-0021-F part1
192 | RMT Actuated valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-701-0003 | 22.Feb.2020 | March, 02 (1 Day)
193 | RMT Actuated valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-701-0004 | 22.Feb.2020 | March, 03 - 9.30 am (1 Day)
194 | RMT Actuated valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-701-0005 | 22.Feb.2020 | March, 02 & 03 (2 Days)
195 | RMT Actuated valve | RMT | italy |  | In-process Inspection | IN-RMT-701-0006-R.1 | 10.May.202 | May, 14 to 19 (4 days) |  |  | IVR-RMT-OOV-0006-F | report received
196 | RMT- Actuated Valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-701-0008 | 27.05.2020 | June, from 3 to 10 (6 Days) | 30.5.2020 | not included / sent after request | IVR-RMT-OOV-0008-F | waiting for supporting dox
197 | RMT-Actuated valve | RMT | italy |  | in process/ doc review | IN-RMT-701-0006 | 10.Mar.2020 | May, 14 to 22 (7 days) | not assigned/ comented
198 | RMT-Actuated valve | RMT | italy |  |  | IN-RMT-701-0007 rev 1 | 43963 | May, 27 & 28 & 29 (3 days) | 8.6.2020 | notification sent + eng dept comments. | IVR-RMT-OOV-0007-F IVR-701-RMT-OOV-0007 F
199 | RMT-Control Valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-703-0004 | 01.June.2020 | June, 04 & 05 (2 Days) | 8.6.2020 | not included | IVR-RMT-OOV-0004-F | SACR-701-GEN-QM-ITP-0003-ITP - Rev. 4 (RMT Ref.: ITP 190070 )
200 | RMT-Actuated valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-701-0008 | 01.June.2020 | June, from 5 to 15 (10 Days) | 8.6.2020 | not included | IVR-RMT-OOV-0008-F
201 | RMT-Actuated valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-701-0009 | 01.June.2020 | June, from 22-23-24-25-26 (5 Days) | 8.6.2020 | not included | IVR-RMT-OOV-0009-F
202 | RMT-Motor Operated Valve | RMT | italy |  | Raw Material Inspection/ doc. Review | IN-RMT-721-0001 | 20.June.2020 | June, 24-25 ( 2 days ) | 22.6.2020 | included | IVR-RMT-721-0001-F
203 | RMT MOV | RMT | italy |  | dox review | IN-RMT-721-0002 | 27.June.2020 | July, from 7 to 10 ( 1 day confirmed ) | 29.6.2020 | not included | IVR-RMT-721-0002-F
204 | RMT MOV | RMT | italy |  | dox review | IN-RMT-721-0003 | 27.June.2021 | July, from 8 to 14 ( 5 day confirmed ) | 7.7.2020 | not included | IVR-RMT-721-0003-F
205 | RMT- control valve | RMT | italy |  |  | IN-RMT-703-0006 | 15.July.2020 | July, from 21 to 24 ( 4 Days | 18.7.2020 | not included | IVR-703-RMT-OOV-0006 F
206 | RMT- MOV | RMT | italy |  | final/ dox review | IN-RMT-721-0004 | 19.July.2020 | July, 27&28&29 ( 3 days ) | 20.7.2020 | not included | IVR-721-RMT-OOV-0004 F
207 | NEDA- part 1 | NEDA | china |  | final inspection | SACR-DE-GEN-IN-MRQ-5704-03, 5705-03, 5707-03 -0001 | 29.5.2020 | June.14-15 after double check with vendor | 8.06.2020 | included | IVR-ABB-001 Part 1
208 | RMT-Control Valve | RMT | italy |  | in process/ final/ dox | IN-RMT-703-0007 IN-RMT-703-0007 Rev.1 | 25.July.2020 | July, 30 & 31 ( 2 Days ) | 27.7.2020 | included | IVR-703-RMT-OOV-0007 F
209 | RMT-Motor Operated Valve | RMT | italy |  | in process/ dox | IN-RMT-721-0005 | 25.July.2020 | July, 29 & 30 ( 2 days ) | 27.7.2020 | not included | IVR-721-RMT-OOV-0005 F
210 | RMT - control valve | rmt | italy |  | final/ dox review | IN-RMT-703-0008 | 04.Aug.2020 | August, 6 & 7 ( 2 Days ) | 5.8.2020 | included | IVR-703-RMT-OOV-0008 F
211 | RMT- MOV | rmt | italy |  |  | IN-RMT-721-0006 | 16.8.2020 | 21.Aug.2020 | 16.8.2020 | not included | IVR-721-RMT-OOV-0006 F
212 | RMT- control valve | RMT | italy |  |  | IN-RMT-703-0009 | 18.Aug.2020 | August, 27& 28 & 31 ( 3 Days ) | 19.08.2020 | not included
213 | RMT-Control Valve | rmt | italy |  | final/ document review | IN-RMT-703-0011 Rev.1 | 09.Sep.2020 | September, 29&30 ( 2 Days ) | 22.9.2020 | included | IVR-703-RMT-OOV-0011 F
214 | RMT-Control Valve | rmt | italy |  | in process/ document review | IN-RMT-703-0010 | 09.Sep.2020 | September, 22 (1 Day ) | 13.9.2020 | included | IVR-703-RMT-OOV-0010 F
215 | IIP - first shipment | iip | china |  | In-process Inspection | SACR-301-IIP-016 | 43949 | Monday 11.May.2020 up to Sunday 17.May.2020 | rev 1 assigned 2 may 2020 | not included / sent after request | IVR-301-IIP-016-F-part 1 | revised report recievd
216 | IIP - first shipment | iip | china |  | In-process Inspection | SACR-301-IIP-017 | 43950 | Wednesday 20.May.2020 & Thursday 21.May.2020 | 2.may.2020 | not included / sent after request | IVR-301-IIP-017-F-part 2 | report commented by GL 1.6.2020
217 | rood- pupm- part 1 | Roodhart | netherlands |  | final inspection | 010-RPG-0001 | 13/03/2020 | 31-03-2020 |  |  | have been not done by GL/waiting fr final inspection in Kangan
218 | rood- pupm- part 2 | Roodhart | netherlands |  | performance test/ final | 010-RPG-0003 | 29.7.2020 | August,3,5,6,12,13 | 1.8.2020 | not included | IVR –RPG-0003-F part 1 IVR –RPG-0003-F part 2
166 | 4-Way Valves-Final Inspection for DFT and Adhesion | EKP-046 | Netherlands | Ebrahimian | Final | 037-EKP-0038 | 30 Jan 22 |  | 18 feb 22 | Tie-co | TIE/T/108-00-1515
167 | Pipe - MTO FOR STOCK/ FWA·SWS·FIS·TNK-UTL)(003) R2 | IMS-047 | Dubai | Mrs. Ranjbar | In Process | 995 & 10042 | 2 feb 22 |  | 7 feb 22 | Tie-co | TIE/T/ 108-00-1494 |  |  | YES
168 | TRUCK LOADING ARMS - Instruments | Asia Instruments LTD-048 | Dubai | Ms. Sharifi | Final | ASI-IN-11 | 9 feb 22 |  | 14 Feb 22 | Tie-co | TIE/T/108-00-1562
169 | FIRE WATER PUMP & JOCKEY PUMP WITNESS | Patterson-049 | Ireland | Mrs. Ranjbar | Final | 002 | 9 feb 22 |  | 14-18 Feb 22 | Tie-co | TIE/T/108-00-1547
170 | Gas Pipe of Burner-Hydrostatic procedure H | Fateh Sanat-050 | Spain | Mr. Farvani | Final | AFI-ICE-001 | 13 feb 22 |  | 18 Feb 22 | Tie-co | TIE/T/108-00-1538
171 | Flanges | MEMIT FORNITUTR INDUSTRIALI-051 | Italy | Mrs. Ranjbar | Final | FL-01 | 14 feb 22 |  | 18 Feb 22 | Tie-co | TIE/T/108-00-1551 TIE/T/108-00-1561
172 | Forged and Wrought fittings | HEBEI HAITIAN PIPE FITTINGS CO-052 | china | Mrs. Ranjbar | In process | 2-2 | 14 feb 22 |  | 21 Feb 22 | Tie-co | TIE/T/108-00-1544
173 | SEAMLESS PIPE | HEBEI HUIKE STEEL PIPES CO.LTD-053 | china | Mrs. Ranjbar | Final | PI-2-1 | 02 Mar 22 |  | 08 mar 22 | Tie-co | TIE/T/108-00-1604
174 | FIRE WATER PUMP & JOCKEY PUMP | Patterson-054 | Ireland | Mrs. Ranjbar | In process | 03 revised | 5 Mar 22 |  |  |  | TIE/T/108-00-1623
175 | PIPE FITTINGS - Forged and Wrought fittings - Packing Inspection | HEBEI HAITIAN PIPE FITTINGS CO-055 | china | Mrs. Ranjbar | Final | 2-3 | 5 Mar 22 |  | 08 Mar 22 |  | TIE/T/108-00-1608 |  |  | YES
176 | Top casing , Exhaust casing , Steam chest | Fateh sanat-TTLCO-056 | India | Mr. Farvani | In process | AFI-TTL-002 |  |  |  |  | TIE/T/108-00-1591
177 | Pipe Flanges - Packing Inspection | MEMIT FORNITUTR INDUSTRIALI -057 | Italy | Mrs. Ranjbar | shipment | FL-02 | 6 Mar 22 |  | 7 Mar 22 |  | TIE/T/108-00-1590
178 | PT & PDT & ANALAZER as per att.list for deoiling & polishing package | E+H Devices-058 | Italy | Ms. Sharifi | Final | 12 | 8 Mar 22 |  | 10 Mar 22 |  | TIE/T/108-01-0010
179 | Fire Alarm Panel -Quantity, visual, dimensional check, primary packing check and certificate review | Pedinco-059 | Italy | Mrs. Ranjbar | Final | PED-709-FACP-IN-001 | 9 Mar 22 |  | 16 Mar 22 |  | TIE/T/108-01-0009 |  |  | 0
180 | Centrifugal Pumps | Roodhart-060 | Netherlands | Mrs. Ranjbar | Final | 035-RPG-010 | 9 Mar 22 |  | 16 Mar 22 |  | TIE/T/108-00-1617 |  |  | YES
181 | Flow Meter | Part Kayhan-061 | Italy | Ms. Sharifi | Final | 17 | 16 Mar 22 |  | 17 Mar 22 |  | TIE/T/ 108-01-0019
182 | Burner - Functional Check of Electrical Panel (FAT test) | Fateh Sanat Kimia-062#213 | Italy | Mrs. Ranjbar | Final | AFI-ICE-002 Rev03 | 16 Mar 22 |  | 13 April 22 |  | TIE/T/108-01-0069 |  |  | YES
183 | FIRE WATER PUMP & JOCKEY PUMP Witness Inspection-Final | Patterson-063 | Ireland | Mrs. Ranjbar | Final | 004 | 27 Mar 22 |  | 31 Mar 22 |  | TIE/T/108-01-0044 |  |  | 0
184 | PSV VALVE - TAI MILANO - De-oiling & Polishing Package - | Smart Vision-064 | Italy | Ms. Sharifi | Final | 15 | 4 May 22 |  | 21 May 22 |  | TIE/T/108-01-0079
185 | SEAMLESS PIPE-Visual , Dimensional , MTC Review | HEBEI HUIKE STEEL PIPES CO. LTD-065 | china | Mrs. Ranjbar | Final | PI-2-2 | 6 May 22 |  | 12 April 22 |  | TIE/T/108-01-0054 |  |  | YES
186 | FLANGES - Final & Packing Inspection | Memit - 066 | italy | Mrs. Ranjbar | Final | FL-03 | 12 April 22 |  | 14 & 15 May 22 |  | TIE/T/108-01-0062
187 | Pumps - Final Inspection | Tehran Javan- 067 | Germany | Mrs. Ranjbar | Final | 5304-TJC-0015 | 13 April 22 |  | 19 May 22 |  | TIE T 108-01-0093
188 | PIPE - Final & Packing Inspection | IMS-068 | UAE | Mrs. Ranjbar | Final | PI-IMS-01 | 16 April 22 |  | 20 April 22 |  | TIE/T/ 108-01-0132
189 | Handol Pumps Limited-Hydrotest | Fateh Sanat Kimia-Handol-069 | korea | Mrs. Ranjbar | Final | AFI-HANDOL-001 | 16 April 22 |  | 21 April 22 |  | TIE/T/108-01-0076
190 | Pumps Packing Inspection | Tehran Javan-070 | Germany | Mrs. Ranjbar | shipment | 5304-TJC-0016 | 24 April 22 |  | 4 May 22 |  | TIE/T/108-01-0112
191 | Service Pipes / Steam Pipes | GBA Flare System-071 | India | Mrs. Ranjbar | Final | 8 | 30 April 22 |  | 11 May 22 |  | TIE/T/ 108-01-0141
192 | Air Pre-Heater for H-502-03 - Material - Major Parts & All Raw Material | KTI-072 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0001 (Rev.0) | 07 May 22 |  | 10 May 22 |  | TIE/T/108-01-0134
193 | Flanges- Final & Packing Inspection | MEMIT FORNITUTR INDUSTRIALI-073 | Italy | Mrs. Ranjbar | Final | FL-04 | 07 May 22 |  | 10 May 22 |  | TIE/T/108-01-0139 |  |  | 0
194 | CARBON SMLS PIPE for Heater Fabrication (H-502-02/03) | KTI-074 | korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0002 (Rev.2) | 15 May 22 |  | 17 & 18 May 22 |  | TIE/T/108-01-0160
195 | PIPE - Final & Packing Inspection | IMS-075 | UAE | Mrs. Ranjbar | Final | PI-IMS-02 | 20 May 22 |  |  |  | TIE/T/ 108-01-0152 |  |  | Yes
196 | 16” Flare Stack // 42” Flare Stack - Final Inspection | GBA Flare System-076 | India | Mrs. Ranjbar | Final | 9 | 21 May 22 |  | 27-31 May 22 |  | TIE/T/108-01-0223
197 | Electrical Heater - FATI | EKP-077 | Italy | Ebrahimian | In Process | 050-EKP-0001 | 23 May 22 |  | 30-31 May 22 |  | TIE/108-01-0205 |  |  | 0
198 | Pipes and Fittings -Carbon Steel Elbows | IMS-078 | UAE | Mrs. Ranjbar | In Process | 05 | 28 May 22 |  | 09 June 22 |  | TIE/T/ 108-01-0251 |  |  | 0
199 | Carbon Steel Fittings (46” Elbows Eannexure 22-10388 | IMS-079 | UAE | Mrs. Ranjbar | In Process | 04 | 28 May 22 |  | 02 June 22 |  | TIE/T/108-01-0208
200 | AIR PRE-HEATER for H-502-03 | KTI-080 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0003 (Rev.0) | 29 May 22 |  | 07 June 22 |  | TIE/T/108-01-0228
201 | Handol Pumps Limited | Fateh Sanat Kimia-Handol-081 | Korea | Mrs. Ranjbar | In Process | AFI-HANDOL-002 | 30 May 22 |  | 10 June 22 |  | TIE/T/108-01-0250
202 | Pipe Flanges - Final & Packing Inspection | MEMIT FORNITUTR INDUSTRIALI-082 | Italy | Mrs. Ranjbar | Final | 05 | 1 June 22 |  | 08 June 22 |  | TIE/T/108-01-0226 |  |  | 0
203 | AIR PRE-HEATER for H-502-03 -APH_FIT-UP and Weld Preparation check | KTI-083 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0004 (Rev.0) |  |  |  |  | TIE/T/108-01-0254
204 | Flare System | GBA-084 | India | Mrs. Ranjbar |  | 10 |  |  |  |  | TIE/T/108-01-0249 TIE/T/108-01-0267 |  |  | 0
205 | CASTING SUPPORT FOR H-502-01/02/03 | KTI-085 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0005 (Rev.0) | 15 June 22 |  | 30 June 22 |  | TIE/T/108-01-0296
206 | IR Camera | GBA Flare System-86 | Italy | Mrs. Ranjbar | Final | 11 | 17 June 22 |  | 24 June 22 |  | TIE/T/108-01-0279
207 | E&H Instrument | NEDA-087 | Germany | Ebrahimian | [6 empty] | TIE/T/108-01-0433
208 | Centrifugal Pumps | CW Hydro-088 | Korea | Ms. Sharifi | In Process | 1 | 2022-06-28 |  | 07 July 22 |  | TIE/T/108-01-0330
209 | Piping | Daghighsazan-089 | UAE | Mrs. Ranjbar | Final | 29 |  |  | 4 July 22 |  | TIE/T/108-01-0314
210 | Flare System | GBA-090 | India | Mrs. Ranjbar | Final | 12 | 2022-07-08 |  | 11-12 July 22 |  | TIE/T/108-01-0333 |  |  | 0
211 | FINTUBE/H-502-02/H-502-03 | KTI-091 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0010 (Rev.0) | 15 July 22 |  |  |  | TIE/T/108-01-0361
212 | HEATER / H-502-01/H-502-02/H-502-03 | KTI-092 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0008 (Rev.0) | 06 July 22 |  | 19 July 22 |  | TIE/T/108-01-0356
213 | FD FAN MOTOR, ID FAN MOTOR for H-502-03 | KTI-093 | Korea | Ms. Sharifi | Final Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0009 (Rev.0) | 06 July 22 |  | 20 & 21 July 22 |  | TIE/T/ 108-01-0362
214 | HEATER / H-502-01/H-502-02/H-502-03 | KTI-094 | Korea | Ms. Sharifi | Final Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0007 (Rev.0) | 12 July 22 |  | 15 July 22 |  | TIE/T/108-01-0344
215 | CASTING SUPPORTS FOR H-502-01/02/03 | KTI-095 | Korea | Ms. Sharifi | Final Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-00011 (Rev.0) | 16 July 22 |  | 1 & 2 Aug |  | TIE/T/108-01-0410
216 | HEATER / H-502-01/H-502-02/H-502-03 | KTI-096 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0012 (Rev.0) | 16 July 22 |  | 25 July - 5 Aug |  | TIE/T/ 108-01-0421
217 | FINTUBE/H-502-02/H-502-03 | KTI-097 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0013 (Rev.0) | 19 July 22 |  | 26-28 July 22 |  | TIE/T/108-01-0391
218 | Heater fabrication | KTI-098 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0014_Rev.0 | 25 July 22 |  | 08-19 Aug 22 |  | TIE/T/108-01-0434 TIE/T/ 108-01-0472
219 | FINTUBE/H-502-02/H-502-03 - Final Inspection for Finning | KTI-099 | Korea | Ms. Sharifi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0015 (Rev.0) |  |  |  |  | TIE/T/108-01-0438
220 | LEAK TEST(PNEUMATIC TEST) | KTI-100 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0016 (Rev.0) |  |  |  |  | TIE/T/108-01-0439
221 | MTO-5501 TO 5507 | Daghighsazan Araz-101 | United Arab Emirates | Mrs. Ranjbar | In Process | 30 |  |  |  |  | TIE/T 108-01-0418
222 | Packing inspection for casting supports | KTI-102 | Korea | Ms. Sharifi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0017_Rev.0 |  |  |  |  | TIE/T/ 108-01-0458
223 | HEATER / H-502-01/H-502-02/H-502-03 - Final Inspection | KTI-103 | Korea | Ms. Sharifi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0018 (Rev.0) |  |  |  |  | TIE/T/108-01-0527
224 | Davit - Final and Visual Inspection | GBA-104 | Italy | Mrs. Ranjbar | Final | 13 |  |  |  |  | TIE/T/108-01-0493 |  |  | YES
225 | PAINTING CHECK,FINAL VISUAL AND DIMENSIONAL CHECK & PACKING INSPECTION | KTI-105 | Korea | Ms. Sharifi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0019 (Rev.0) |  |  |  |  | TIE/T/108-01-0503
226 | Heater - Raw Material Inspection (for End Tube Sheet, Stack Damper, Guillotine Blind) | KTI-106 | Korea | Ms. Sharifi |  | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0020_Rev.0 |  |  |  |  | TIE/T/108-01-0481-Rev02
227 | PIPE 36 inch | TECRA S.r.l-107 | china | Mrs. Ranjbar | Final | 36-1 |  |  |  |  | TIE/T/108-01-0535 TIE/T/108-01-0573 |  |  | YES
228 | During Fabrication -FinaI Inspection - Valve | Tradic-SJV-108 | china | Mrs. Ranjbar | Final | 01 |  |  |  |  | TIE/T/108-01-0749
229 | Centrifugal Pumps | CW Hydro-109 | Korea | Ms. Sharifi | In Process | 02 | 2022-08-18 |  | 26/08 |  | TIE/T/108-01-0501
230 | FD FAN, ID FAN for H-502-03 - Final Inspection | KTI-110 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0021_Rev.0 | 2022-08-21 |  |  |  | TIE/T/108-01-0542
231 | Monel Plates | Fateh Sanat Kimia - Euroslot-111 | china | Ms. Mohammadi | In Process | ESP-Q-INS-682-013 | 2022-08-21 |  | 6 Sep 22 |  | TIE/T/108-01-0565
232 | Heater | KTI-112 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0022 (Rev.0) |  |  |  |  | TIE/T/108-01-0575
233 | Motor Inspection - FD Fan Package | Boldrocchi-113 | India | Ms. Mohammadi | Final | IN-03 |  |  |  |  | TIE/T/108-01-0578
234 | HEATER | KTI-114 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0023 (Rev.0) |  |  |  |  | TIE/T/108-01-0619
235 | FUEL SKID - HYDROSTATIC TEST | KTI-115 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0024_Rev.0 |  |  |  |  | TIE/T/108-01-0577
236 | Painting and Packing Inspection - Final & Shipment | KTI-116 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0025 (Rev.0) |  |  |  |  | TIE/T/ 108-01-0589
237 | Burner - Leakage Test (bubble test method) | KTI-117#210 | Italy | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0026_Rev.0 |  |  |  |  | TIE T 108-01-0586 |  |  | YES
238 | Deoiling & Polishing Centrifugal Pumps - Test Inspection for Motor | CW Hydro-118 | Korea | Mrs. Ranjbar | In Process | 3 |  |  |  |  | TIE/T/ 108-01-0603
239 | Monel Parts | Fateh Sanat Kimia - Euroslot-119 | China | Ms. Mohammadi | In Process | ESP-Q-INS-682-014 |  |  |  |  | TIE/T/108-01-0596
240 | Heater | KTI-120 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0027_Rev.0 |  |  |  |  | TIE/T/108-01-0700
241 | FINTUBE for H-502-01 | KTI-121 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0029_Rev.0 |  |  |  |  | TIE/T/108-01-0677
242 | FINTUBE for H-502-01 | KTI-122 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0028 (Rev.1) |  |  |  |  | TIE/T/108-01-0642
243 | Damper Actuator | KTI-123 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0030 (Rev.0) |  |  |  |  | TIE/T/108-01-0691
244 | Steam Turbine - Visual & Dimensional and PMI of rotor and disc | Fateh Sanat Kimia-TTL-124 | India | Ms. Mohammadi | In Process | AFI-TTL-003
245 | Steam Turbine - Hydro Test of Casings | Fateh Sanat Kimia-TTL-125 | India | Ms. Mohammadi | In Process | AFI-TTL-004 |  |  |  |  | TIE/T/ 108-01-0686
246 | Supply and delivery of Centrifugal Pumps | CW Hydro-126 | Korea | Mrs. Ranjbar | In Process | 4 |  |  |  |  | TIE/T/ 108-01-0676-Rev01
247 | Steam Turbine - Hydro Test of Casings | Fateh Sanat Kimia-TTL-127 | India | Ms. Mohammadi | In Process | AFI-TTL-005 |  |  |  |  | TIE/T/108-01-0668
248 | Control valve - Function Test / Visual & Dimension Inspection | KTI-128 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0035 (Rev.0) |  |  |  |  | TIE/T/108-01-0730
249 | ON-OFF VALVE | KTI-129 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0034 (Rev.0)
250 | Heater | KTI-130 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0033 (Rev.0) |  |  |  |  | TIE/T/108-01-0750
251 | FLOW METER | KTI-131 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0032 (Rev.0) |  |  |  |  | TIE/T/108-01-0678
252 | Packing Inspection | KTI-132#211 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0031 (Rev.0) |  |  |  |  | TIE/T/108-01-0706 |  |  | YES
253 | FD FAN | Fateh Sanat Kimia-133 | India | Ms. Mohammadi | In Process | AFI-Boldrocchi-002 |  |  |  |  | TIE/T/108-01-0733 TIE/T/108-01-0815
254 | Steam Turbine-Trip & Throttle body valve Hydrotest | Fateh Sanat Kimia-TTL-134 | India | Ms. Mohammadi | In Process | AFI-TTL-006 |  |  |  |  | TIE/T/108-01-0728
255 | Steam Turbine-Run-out Check (Rotor Shaft) | Fateh Sanat Kimia-TTL-135 | India | Ms. Mohammadi | In Process | AFI-TTL-007 |  |  |  |  | TIE/T/108-01-0711
256 | Steam Turbine-Top Casing, Exhaust Casing & Steam Chest Dimensional Inspection | Fateh Sanat Kimia-TTL-136 | India | Ms. Mohammadi | In Process | AFI-TTL-008 |  |  |  |  | TIE/T/108-01-0709
257 | ON-OFF VALVE | KTI-137 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0034 (Rev.1) |  |  |  |  | TIE/T/108-01-0743
258 | Steam Turbine | Fateh Sanat Kimia-TTL-138 | India | Ms. Mohammadi | In Process | Note No.AFI-TTL-010 |  |  |  |  | TIE/T/108-01-0729
259 | Steam Turbine | Fateh Sanat Kimia-TTL-139 | India | Ms. Mohammadi | In Process | Note No.AFI-TTL-009 |  |  |  |  | TIE/T/108-01-0719
260 | Hydrostatic Pressure Test for Top Casing, Exhaust Casing and Steam Chest | Triveni Turbines-140 | India | Mrs. Ranjbar | In Process | 01 |  |  |  |  | TIE/T/108-01-0769
261 | Deoiling and Polishing Centrifugal Pumps | CW Hydro-141#220 | Korea | Mrs. Ranjbar | Final Inspection | 05 | 2022-10-18 | 2022-10-24 |  |  | TIE/T/108-01-0739 |  |  | YES
262 | Heater | KTI-142 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0037 (Rev.0) | 2022-10-18 | 1 to 11 November |  |  | TIE/T/108-01-0776
263 | Heater Fabrication (Stack) | KTI-143 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0038 (Rev.0) | 2022-10-20 | 2022-11-02 |  |  | TIE/T/108-01-0765
264 | Hydrostatic Pressure Test for Top Casing, Exhaust Casing and Steam Chest | Triveni Turbines-144 | India | Mrs. Ranjbar | In Process | 02 |  |  |  |  | TIE/T/ 108-01-0800
265 | Steam Turbine-Visual and Dimensional Inspection | KTI-145 | Korea | Ms. Mohammadi | In Process | Note No.AFI-TTL-011 |  |  |  |  | TIE/T/ 108-01-0742
266 | Expansion Joint | KTI-146 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0040 (Rev.0) |  |  |  |  | TIE/T/108-01-0754
267 | Steam Trap | HISCO-147 | Korea | Mrs. Ranjbar | In Process | 01 |  |  |  |  | TIE/T/108-01-0829
268 | Heater Fabrication (OB DOOR) | KTI-148 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0039 (Rev.0) |  |  |  |  | TIE/T/108-01-0752
269 | Nitrogen System and Compressed Air System | HATCO-149 | China | Ms. Mohammadi | Final | INS-307(308)-HAT-0190 |  |  |  |  | TIE/T/108-01-0753
270 | Manual Valve | Tradic-SJV-150 | China | Mrs. Ranjbar | In Process | 02 |  |  |  |  | TIE/T/108-01-0796
271 | DESUPERHEATER | Fateh Sanat Kimia-151#215 | Korea | Ms. Mohammadi | In Process | AFI-D-0001 |  |  |  |  | TIE/T/108-01-0751 |  |  | YES
272 | Steam Turbine - Mechanical Run Test / Post MRT Strip Test | Fateh Sanat Kimia-TTL-152 | India | Ms. Mohammadi | In Process | AFI-TTL-013 |  |  |  |  | TIE/T/ 108-01-0871
273 | Steam Turbine - Low Speed Balancing – Rotor Shaft Assembly | Fateh Sanat Kimia-TTL-153 | India | Ms. Mohammadi | In Process | AFI-TTL-012 |  |  |  |  | TIE/T/108-00-0780 TIE/T/108-00-0780-Rev01
274 | Steam Turbine - Low Speed Balancing | Fateh Sanat Kimia-TTL-154 | India | Ms. Mohammadi | In Process | AFI-TTL-014 |  |  |  |  | TIE/T/108-01-0778
275 | HEATER / H-502-01/H-502-02/H-502-03 | KTI-155 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0042 (Rev.0) |  |  |  |  | TIE/T/108-01-0795
276 | Pressure Part 27,28,29,30,40,41,42 Steel Part 23, 24, 25, 41, 42, 43 | KTI-156 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0041 (Rev.0) |  |  |  |  | TIE/T/108-01-0813
277 | Steam Turbine - Low Speed Balancing | Fateh Sanat Kimia-TTL-157 | India | Ms. Mohammadi | In Process | AFI-TTL-015 |  |  |  |  | TIE/T/108-01-0814
278 | BURNER PIPING & STEAM PIPINNG | KTI-158 | Korea | Ms. Mohammadi | Shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0043_Rev.0 |  |  |  |  | TIE/T/108-01-0808 TIE/T/108-01-0833
279 | Heat Exchanger,Reactor,Tower,Vessel | Ensol-159-INV#225 | China | Ms. Mohammadi | In Process | EN-NOI-001 |  |  |  |  | TIE/T/108-01-0788 |  |  | YES
280 | Centrifugal Pumps | CW Hydro-160 | Korea | Mrs. Ranjbar | In Process | 1 |  |  |  |  | TIE/T/108-01-0806
281 | Hydrostatic Pressure Test for Trip & Throttle Valve Body | Triveni Turbines-161 | India | Mrs. Ranjbar | In Process | 03 |  |  |  |  | TIE/T/108-01-0851 TIE/T/108-01-0851-Rev01
282 | Hydrostatic Pressure Test for Trip & Throttle Valve Body | Triveni Turbines-162 | India | Mrs. Ranjbar | In Process | 04 |  |  |  |  | TIE/T/108-01-0888
283 | Heater | KTI-163 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0044 (Rev.0) |  |  |  |  | TIE/T/108-01-0837
284 | Heat Exchanger with P/L for 2nd Shipment | Ensol-164#Ensol 5 | Korea | Ms. Mohammadi | In Process | EN-NOI-002 |  |  |  |  | TIE/T/108-01-0807 TIE/T/108-01-0827 |  |  | YES
285 | Manual Valve | Tradic-SJV-165 | China | Mrs. Ranjbar | Final | 03 |  |  |  |  | TIE/T/108-01-0816
286 | Heater -Cable &amp; Bulk Material. | KTI-166 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0045 (Rev.0) |  |  |  |  | TIE/T/108-01-0847
287 | Heater Fabrication (Stack, Duct) | KTI-167 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0046 (Rev.0) |  |  |  |  | TIE/T/108-01-0832
288 | Manual Valve | Tradic-SJV-168 | China | Mrs. Ranjbar | Final | 04 |  |  |  |  | TIE/T/108-01-0845
289 | API & DAF Package | Absan Zolol(AZK)-169#231 | Austria | Ms. Mohammadi | Final | 009 |  |  |  |  | TIE/T/108-01-0828
290 | Heater | KTl-170 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0047 (Rev.0) |  |  |  |  | TIE/T/108-01-0870
291 | Magnetic Level Gauge | Fateh Sanat Kimia-171 | Italy | Ms. Mohammadi | In Process | AFI-KITRO-001 |  |  |  |  | TIE/T/108-01-0831
292 | FUEL SKID | KTl-172 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0048 (Rev.0) |  |  |  |  | TIE/T/108-01-0869
293 | Supply and delivery of Centrifugal Pumps | CW Hydro-173 | Korea | Mrs. Ranjbar | In Process | 2 |  |  |  |  | TIE/T/108-01-0855
294 | Manual Valve | Tradic-SJV-174#222#SJV2 | China | Mrs. Ranjbar | Final | 05 |  |  |  |  | TIE/T/108-01-0872 |  |  | YES
295 | Mechanical Run test for both Gearboxes | Fateh Sanat Kimia-Triveni -175 | India | Ms. Mohammadi | In Process | AFI-TTL-016-01 |  |  |  |  | TIE/T/108-01-0865
296 | Supply and delivery of Centrifugal Pumps | CW Hydro-176 | Korea | Mrs. Ranjbar | In Process | 3 |  |  |  |  | TIE/T/108-01-0917
297 | Heat Exchanger | Ensol-177 | Korea | Ms. Mohammadi | In Process | EN-NOI-003 |  |  |  |  | TIE/T/108-01-0846 |  |  | YES
298 | Steam Turbine | Fateh Sanat Kimia-Triveni -178 | India | Ms. Mohammadi | In Process | AFI-TTL-017 |  |  |  |  | TIE/T/108-01-0864 |  |  | YES
299 | Dynamic Balancing and Residual Unbalance Check for Gear Box | Triveni Turbines-179 | India | Mrs. Ranjbar | In Process | 05 |  |  |  |  | TIE/T/108-01-0857
300 | Gear Box-Mechanical Running Test | Triveni Turbines-180 | India | Mrs. Ranjbar | In Process | 06 |  |  |  |  | TIE/T/ 108-01-0861
301 | Heater Fabrication | KTl-181 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0049 (Rev.0) |  |  |  |  | TIE/T/108-01-0915 TIE/T/108-01-0955 |  |  | YES
302 | Heat Exchanger | Ensol-182#Ensol 5&9 | Korea | Ms. Mohammadi | In Process | EN-NOI-004 |  |  |  |  | TIE/T/108-01-0875 |  |  | YES
303 | Steam Trap | HISCO-183#223 | Korea | Mrs. Ranjbar | Final | 02 |  |  |  |  | TIE/T/108-01-0860 |  |  | YES
304 | Magnetic Level Gauge | Fateh Sanat Kimia-184 | Italy | Ms. Mohammadi | In Process | AFI-KITRO-002 |  |  |  |  | TIE/T/108-01-0859
305 | TRUNNION SIDE ENTRY BALL VALVES | RMT-185 | Italy | Ms. Mohammadi | In Process | 01 |  |  |  |  | TIE/T/108-01-0896
306 | FIELD REFRACTORY FOR HEATER | KTI-186 | Korea | Ms. Mohammadi | In Process | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0050 (Rev.0) |  |  |  |  | TIE/T/108-01-0898
307 | Overlay PQ Test | Ensol-187 | Korea | Ms. Mohammadi | In Process | EN-NOI-005 |  |  |  |  | TIE/T/108-01-0891
308 | Final Inspection(2nd BatcH) | Tradic-SJV-188 | China | Mrs. Ranjbar | Final | 06 |  |  |  |  | TIE/T/108-01-0904
309 | Low Speed Balancing of Rotor Shaft Assembly | Triveni Turbines-189 | India | Mrs. Ranjbar | In Process | 07 |  |  |  |  | TIE/T/108-01-0923
310 | Supply and delivery of Centrifugal Pump | CW Hydro-190 | Korea | Ms. Mohammadi | In Process | 01 |  |  |  |  | TIE/T/108-01-0919
311 | Triveni Turbines-Complete Assembly/Final Painting | Fateh Sanat Kimia-191 | India | Ms. Mohammadi | In Process | AFI-TTL-018 |  |  |  |  | TIE/T/108-01-0910
312 | Material Test Certificate (Parts of Items for Casing and Impeller) for Centrifugal Pumps | CW Hydro-192 | Korea | Ms. Mohammadi | In Process | 4 |  |  |  |  | TIE/T/ 108-01-0938
313 | API & DAF Package | Absun Zolol(AZK)-193 | Austria | Ms. Mohammadi | Final | 022 |  |  |  |  | TIE/T/ 108-01-0952
314 | Material Verification | Ensol-194#Ensol 5 | Korea | Ms. Mohammadi | In Process | EN-NOI-006 |  |  |  |  | TIE/T/108-01-0944 |  |  | YES
315 | Material Verification | Ensol-195#Ensol 3 | Belgium | Ms. Mohammadi | In Process | EN-NOI-007 |  |  |  |  | TIE/T/108-01-0956 | 0687 |  | YES
316 | Material Verification(Carbon Plate) | Ensol-196#226#Ensol 4 | china | Ms. Mohammadi | In Process | EN-NOI-008 |  |  |  |  | TIE/T/108-01-0970 |  |  | YES
317 | LUBE OIL SYSTEM-Final inspection | Fateh Sanat Kimia-197 | India | Ms. Mohammadi | In Process | AFI-Boldrocchi-003 |  |  |  |  | TIE/T/108-01-0946
318 | Steam Turbine-Final Painting (Bottom of Soleplate) | Fateh Sanat Kimia-198 | India | Ms. Mohammadi | In Process | AFI-TTL-019 |  |  |  |  | TIE/T/108-01-0966
319 | Steam Turbine Assembly Spare Parts Verification and packing / crating | Fateh Sanat Kimia-199 | India | Ms. Mohammadi | In Process | AFI-TTL-020 |  |  |  |  | TIE/T/108-01-0967
320 | Centrifugal Pumps - LV motors | CW Hydro-200 | Korea | Mrs. Ranjbar | In Process | 5 |  |  |  |  | TIE/T/108-01-0958
321 | TSTC Heater | KTI-201 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0051 (Rev.0) |  |  |  |  | TIE/T/108-01-0971
322 | TRUNNION SIDE ENTRY BALL VALVES | RMT-202 | Italy | Ms. Mohammadi | In Process | 02 |  |  |  |  | TIE/T/108-01-0978
323 | Material Verification | Ensol-203#Ensol 5 | Korea | Ms. Mohammadi | In Process | EN-NOI-009 |  |  |  |  | TIE/T/ 108-01-0980 |  |  | YES
324 | Manual Valve | Tradic-SJV-204 | China | Mrs. Ranjbar | Final | 08 |  |  |  |  | TIE/T/108-01-1015
325 | API & DAF PACKAGE | Absun Zolal(AZK)-205 | Austria | Ms. Mohammadi | Final | 026 |  |  |  |  | TIE/T/108-01-0992
326 | Centrifugal Pumps - LV motors | CW Hydro-206 | Korea | Mrs. Ranjbar | In Process | 6 |  |  |  |  | TIE/T/108-01-0984
327 | Triveni Turbines - Low Speed Balancing of Rotor Shaft Assembly | CW Hydro-207 | India | Mrs. Ranjbar | In Process | 08 |  |  |  |  | TIE/T/108-01-1008
328 | FD Fan | Fateh Sanat Kimia-Boldrocchi-208 | India | Ms. Mohammadi | In Process | AFI-Boldrocchi-004 |  |  |  |  | TIE/T/108-01-1046
329 | Heater Exchanger-U-Tube DI/VI before assembly | Ensol-209#Ensol 5 | Korea |  | In Process | EN-NOI-010 |  |  |  |  | TIE/T/108-01-1016 |  |  | YES
330 | 2 Years Spare Parts for Engine - Final Inspection-Visual inspection and document review | Derin Dayanikli-210 | Turkey | Mr. Shadi | Final | 1 |  |  |  |  | TIE/T/108-01-0993
331 | LUBE OIL SYSTEM | Fateh Sanat Kimia-Boldrocchi-211 | India |  | Final | AFI-Boldrocchi-005 |  |  |  |  | TIE/T/108-01-1013
332 | Reactor & Tower | Ensol-212 | Korea |  | In Process | EN-NOI-011 |  |  |  |  | TIE/T/108-01-1030
333 | Nitrogen System and Compressed Air System-Material Certificate, NDE, Hydrostatic shell test | Hatco-213 | Korea |  | Final | INS-307(308)-HAT-0207 |  |  |  |  | TIE/T/108-01-1029 | 0715
334 | Heater-Final Inspection | KTI-214 | Korea | Ms. Mohammadi | Final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0052 (Rev.0) |  |  |  |  | TIE-23-000008-IVR-01 |  |  | YES
335 | Dosing pump - Final Inspection | Absun Zolal(AZK)-215 | Austria |  | Final | 032 |  |  |  |  | TIE/T/ 108-01-1014 |  |  | YES
336 | FD Fan | Fateh Sanat Kimia-Boldrocchi-216 | India |  | In Process | AFI-Boldrocchi-006 |  |  |  |  | TIE/T/108-01-1048
337 | Manual Valve | Tradic-SJV-217 | China | Mrs. Ranjbar | Final | 08 |  |  |  |  | TIE-23-000007-IVR01 |  |  | YES
338 | Spare Parts for Engine | Derin Dayanikli Tuketim Mallari Ve Turizm San Tic. Ltd. Sti(DDT)-218 | Turkey | Mr. Shadi | Final | 02 |  |  |  |  | TIE/T/108-01-1041 |  |  | YES
339 | Dynamic Balancing and Residual Unbalance Check for Gear Box | Triveni Turbines-219 | India | Mrs. Ranjbar | In Process | 09 |  |  |  |  | TIE/T/108-01-1045
340 | Mechanical Running Test for Gear Box Assembly | Triveni Turbines-220 | India | Mrs. Ranjbar | In Process | 10 |  |  |  |  | TIE/T/108-01-1049
341 | Steam Turbine Assembly | Triveni Turbines-221 | India | Mrs. Ranjbar | In Process | 11 |  |  |  |  | TIE/T/ 108-01-1063
342 | LUBE OIL SYSTEM | Fateh Sanat Kimia-Boldrocchi-222 | India | Mrs. Mohamadi | Final | AFI-Boldrocchi-007 |  |  |  |  | TIE/T/108-01-1042
343 | Reactor & Tower | Ensol-223 | Korea | Mrs. Mohamadi | In Process | EN-NOI-012 |  |  |  |  | TIE-23-000002 -IVR01
344 | Reactor & Tower | Ensol-224 | Korea | Mrs. Mohamadi | In Process | EN-NOI-013 |  |  |  |  | TIE-23-0026- IVR01
345 | FD Fan | Fateh Sanat Kimia-Boldrocchi-225 | India | Mrs. Mohamadi | In Process | AFI-Boldrocchi-008 |  |  |  |  | TIE-23-0019-IVR01
346 | Steam Turbine Assembly | Triveni Turbines-226 | India | Mrs. Ranjbar | In Process | 12 |  |  |  |  | TIE-23-0015-IVR01
347 | DAGHIGH SAZAN ARAZ | DAGHIGH SAZAN | china |  | final | IN- DGS-001 | 44118 | Tianchang city on Nov.21; Cangzhou city on Nov.23 |  |  | IVR- DGS-001-rev.00 IVR- DGS -002-rev.00
347 | Nitrogen System and Compressed Air System-Control Valve | Hatco-227 | Korea | Mrs. Mohamadi | Final | INS-307(308)-HAT-0211 |  |  |  |  | TIE-23-0054-IVR02
348 | Material Verification,Material Receiving Inspection (Pipe)-Heat Exchanger and Vessel,Reactor & Tower | Ensol-228 | Korea | Mrs. Mohamadi | In Process | EN-NOI-014 |  |  |  |  | TIE-23-0057-IVR01
349 | Manual Valve - Final Inspection | Tradic-SJV-229#SJV3 | China | Mrs. Ranjbar | Final | 09 |  |  |  |  | TIE-23-0065-IVR01 |  |  | YES
350 | Centrifugal Pump | CW Hydro-230 | Korea | Mrs. Ranjbar | In Process | 2 |  |  |  |  | TIE-23-0126-IVR01
351 | Centrifugal Pump | CW Hydro-231 | Korea | Mrs. Ranjbar | In Process | 7 |  |  |  |  | TIE-23-0076-IVR01
352 | Steam Turbine Assembly Inspection | Triveni Turbines-232 | India | Mrs. Ranjbar | In Process | 13 |  |  |  |  | TIE-23-0067-IVR01
353 | Steam Turbine Assembly Inspection | Triveni Turbines-233 | India | Mrs. Ranjbar | In Process | 14 |  |  |  |  | TIE-23-0113-IVR01
354 | Material Verification,Material Receiving Inspection (Pipe)-Heat Exchanger and Vessel,Reactor & Tower | Ensol-234#Ensol 5 | Korea | Mrs. Mohamadi | In Process | EN-NOI-015 |  |  |  |  | TIE-23-0101-IVR01 |  |  | YES
355 | Material Verification,Material Receiving Inspection (Pipe)-Heat Exchanger and Vessel,Reactor & Tower | Ensol-235 | Korea | Mrs. Mohamadi | In Process | EN-NOI-016 |  |  |  |  | TIE-23-0100-IVR01
356 | Centrifugal Pumps | CW Hydro-236 | Korea | Mrs. Ranjbar | In Process | 8 |  |  |  |  | TIE-23-0110-IVR01
357 | Manual Valve | Tradic-SJV-237#SJV4 | China | Mrs. Ranjbar | Final | 010 |  |  |  |  | TIE-23-0103-IVR01 |  |  | YES
358 | Centrifugal Pumps | CW Hydro-238 | Korea | Mrs. Ranjbar | In Process | 9 |  |  |  |  | TIE-23-0136-IVR01
359 | Material Requisition for Pressure Vessels | Ensol-239 | Korea | Mrs. Mohamadi | In Process | EN-NOI-017 |  |  |  |  | TIE-23-0102-IVR01
360 | Material Requisition for Reactors,Tower and internals - Packing Inspection-Final | Ensol-240 | Korea | Mrs. Mohamadi | Final | EN-NOI-018 |  |  |  |  | TIE-23-0109-IVR01 TIE-23-0109-IVR02
361 | Final Inspection for internal and packing Inspection | Ensol-241 | Korea | Mrs. Mohamadi | Final | EN-NOI-019 |  |  |  |  | TIE-23-0107-IVR01
362 | Triveni Turbine | Fateh Sanat Kimia-Triveni-242 | India | Mrs. Mohamadi | In Process | AFI-TTL-021 |  |  |  |  | TIE-23-0117-IVR01
363 | Control Valve | RMT-243 | Italy | Mr. Shadi & Mrs. Moradi | In Process | 03 |  |  |  |  | TIE-23-0124-IVR01
364 | Supply and delivery of Centrifugal Pumps | CW Hydro-244 | Korea | Mrs. Ranjbar | In Process | 10 |  |  |  |  | TIE-23-0146-IVR-01
365 | Material Requisition for Pressure Vessels | Ensol-245#Ensol 8 | China | Mrs. Mohamadi | In Process | EN-NOI-020 |  |  |  |  | TIE-23-0138-IVR01 |  |  | YES
366 | Supply and delivery of Centrifugal Pumps | CW Hydro-246 | Korea | Mrs. Ranjbar | In Process | 11 |  |  |  |  | TIE-23-0154-IVR01 |  |  | YES
367 | Manual Valve | Tradic-SJV-247 | China | Mrs. Ranjbar | Final | 011 |  |  |  |  | TIE-23-0153-IVR01
368 | Supply and delivery of Centrifugal Pumps | CW Hydro-248 | Korea | Mrs. Ranjbar | Final | 12 |  |  |  |  | TIE-23-0164-IVR01 |  |  | YES
369 | Control Valve | RMT-249 | Italy | Mr. Shadi & Mrs. Moradi | In Process | 04 |  |  |  |  | TIE-23-0176-IVR01
370 | All Valves Except LBV valve | Tradic-SJV-250 | China | Mrs. Ranjbar | In Process | 012 |  |  |  |  | TIE-23-0173-IVR01
371 | PSV | Leser-251 | Germany | Mr. Shadi | In Process | 01 |  |  |  |  | TIE-23-0197-IVR01
372 | All Valves Except LBV valve | Tradic-SJV-252#SJV5 | China | Mrs. Ranjbar | In Process | 013 |  |  |  |  | TIE-23-0183-IVR01 |  |  | YES
373 | F&G Detectors (E2S) - ADSH-P-PO-GE-077 | Neda-253 | UK | Mr. Shadi | In Process | 01 |  |  |  |  | TIE-23-0184-IVR01
374 | Control Valve | RMT-254 | Italy | Mr. Shadi & Mrs. Moradi | In Process | 05 |  |  |  |  | TIE-23-0194-IVR01
375 | Control Valve | RMT-255 | Italy | Mr. Shadi & Mrs. Moradi | In Process | 06Rev.01 |  |  |  |  | TIE-23-0221-IVR01
376 | Pump Performance and Running Test-BFW Pump | Fateh Sanat Kimia-Handol-256 | Korea | Mrs. Mohamadi | In Process | AFI-HANDOL-003-01 |  |  |  |  | TIE-23-0206-IVR01
377 | Lube oil System | Triveni Turbines-257 | China | Mrs. Ranjbar | In Process | 15 |  |  |  |  | TIE-23-0192-IVR01
378 | Rope hoist | Firouza(FRZ)-258 | Germany | Mr. Ahmadi | Final | 05-02 |  |  |  |  | TIE-23-0198-IVR01
379 | Control Valve | RMT-259 | Italy | Mr. Shadi & Mrs. Moradi | In Process | 07 |  |  |  |  | TIE-23-0211-IVR01 TIE-23-0211-IVR02
380 | Spare Parts for Engine | Derin Dayanikli Tuketim Mallari Ve Turizm San Tic. Ltd. Sti(DDT)-260 | Turkey | Mr.Shadi | Final | 3 |  |  |  |  | TIE-23-0205-IVR01 | 0817 |  | YES
381 | Lube oil System | Triveni Turbines-261 | China | Mrs. Ranjbar | Final | 16 |  |  |  |  | TIE-23-0212-IVR01 TIE-23-0228-IVR01
382 | Supply and delivery of Centrifugal Pump with Tag No P-522-21B | CW Hydro-262 | Korea | Mrs. Ranjbar | Final | 3 |  |  |  |  | TIE-23-0227-IVR01 |  |  | YES
383 | Control Valve | RMT-263 | Italy | Mr. Shadi | In Process | 08 |  |  |  |  | TIE-23-0243-IVR01
384 | Control Valve | RMT-264 | Italy | Mr. Shadi | In Process | 09 |  |  |  |  | TIE-23-0257-IVR01
385 | Rope hoist Shipment | Firouza(FRZ)-265 | Germany | Mr. Ahmadi | Final | 07-00 |  |  |  |  | TIE-23-0239-IVR01 |  |  | YES
386 | Visual and dimensional check, Quantity check - ADSH-P-PO-GE-120 | Derin Dayanikli Tuketim Mallari Ve Turizm San Tic. Ltd. Sti(DDT)-266 | Turkey | Mr.Shadi | Final | 4 |  |  |  |  | TIE-23-0246-IVR01 |  |  | YES
387 | LBV Valve | Tradic-SJV-267 | China | Mrs. Ranjbar | In Process | 014 |  |  |  |  | TIE-23-0250-IVR01 | 0831
388 | BFW Pump | Fateh Sanat Kimia-Handol-268 | Korea | Mrs. Mohamadi | In Process | AFI-HANDOL-004 |  |  |  |  | TIE-23-0282-IVR01 | 0833
389 | PSV | Fateh Sanat Kimia-Jokwang-269 | Korea | Mrs. Mohamadi | In Process | AFI-JOKWANG-001 |  |  |  |  | TIE-23-0261-IVR01 TIE-23-0261-IVR02 | 0835
390 | MOV (MOV-101A/B) | Fateh Sanat Kimia-Wascon-270 | Korea | Mrs. Mohamadi | In Process | AFI-WASCON-001 |  |  |  |  | TIE-23-0269-IVR01 | 0837
391 | Lube oil System | Triveni Turbines-271-Related 261 | China | Mrs. Ranjbar | Final | 17 |  |  |  |  | TIE-23-0266-IVR01 | 0839 |  | YES
392 | PRV | Fateh Sanat Kimia-BFS INCORPORATION-272 | Korea | Mrs. Mohamadi | In Process | AFI-BFS-002 |  |  |  |  | TIE-23-0293-IVR01 | 0843
393 | PRV-Hydrostatic Shell Test | Fateh Sanat Kimia-BFS INCORPORATION-273 | Korea | Mrs. Mohamadi | In Process | AFI-BFS-001 |  |  |  |  | TIE-23-0272-IVR01 | 0841
394 | Control Valve | Fateh Sanat Kimia-Wascon-274 | Korea | Mrs. Mohamadi | In Process | AFI-WASCON-002 |  |  |  |  | TIE-23-0279-IVR01 | 0845
395 | MOV (MOV-101A/B) | Fateh Sanat Kimia-Wascon-275 | Korea | Mrs. Mohamadi | In Process | AFI-WASCON-003 |  |  |  |  | TIE-23-0274-IVR01 | 0847
396 | LBV valve - Final Inspection | Tradic-SJV-276#SJV6 | China | Mrs. Ranjbar | Final | 015 |  |  |  |  | TIE-23-0265-IVR01 | 0849 |  | YES
397 | Crowcon Gas Detection Equipment | Neda-277 | UK | Mr. Shadi | In Process | 02 |  |  |  |  | TIE-23-0276-IVR01 TIE-23-0276-IVR02 TIE-23-0276-IVR03 | 0851
398 | Control Valve | RMT-278 | Italy | Mr. Shadi | In Process | 10 |  |  |  |  | TIE-23-0294-IVR01 | 0853
399 | BFW Pump-Shipping | Fateh Sanat Kimia-Handol-279 | Korea | Mrs. Mohamadi | In Process | AFI-HANDOL-005 | [5 empty] | 0857 |  | YES
400 | PSV (Pressure Safety Relief Valves) | Leser-280 | Germany | Mr. Shadi | In Process | 02 |  |  |  |  | TIE-23-0197-IVR01 | 0855
401 | FEDCO High Pressure Pump | Celar-281 | USA | Mr. Ahmadi | Final | 01 | [5 empty] | 0865
402 | Acid Sulfuric Loading and Unloading Pumps for WWT/WSU | CW Hydro-282 | Korea | Mrs. Ranjbar | In Process | 1 |  |  |  |  | TIE-23-0275-IVR01 | 0861
403 | On-off Valves | Fateh Sanat Kimia-Wascon-283 | Korea | Mrs. Mohamadi | In Process | AFI-WASCON-004-01 |  |  |  |  | TIE-23-0348-IVR01 | 0863
404 | PRV-Painting Inspection, Check Name and Tag Plates and Accessories | Fateh Sanat Kimia-BFS INCORPORATION-284 | Korea | Mrs. Mohamadi | In Process | AFI-BFS-003 |  |  |  |  | TIE-23-0312-IVR01 TIE-23-0330-IVR01 | 0869
405 | PSV | Fateh Sanat Kimia-Jokwang-285 | Korea | Mrs. Mohamadi | In Process | AFI-JOKWANG-002-rev.01 |  |  |  |  | TIE-23-0296-IVR01 | 0867
406 | MOV (MOV-101A/B) | Fateh Sanat Kimia-Wascon-286 | Korea | Mrs. Mohamadi | In Process | AFI-WASCON-005 |  |  |  |  | TIE-23-0331-IVR01 | 0871
407 | Control Valve | Fateh Sanat Kimia-Wascon-287 | Korea | Mrs. Mohamadi | In Process | AFI-WASCON-006 |  |  |  |  | TIE-23-0335-IVR01 | 0873
408 | Electrical Heat Tracing | FATI-288 | Italy | Mrs. Ranjbar | Final | 01 |  |  |  |  | TIE-23-0403-IVR01 | 0875 |  | YES
409 | Control Valve | RMT-289 | Italy | Mr. Shadi | In Process | 11 |  |  |  |  | TIE-23-0358-IVR01 | 0877
410 | PSV-Packing & Marking Inspection | Fateh Sanat Kimia-Jokwang-290 | Korea | Mrs. Mohamadi | In Process | AFI-JOKWANG-003 |  |  |  |  | TIE-23-0341-IVR01 | 0879
411 | WIKA Temperature Gauges & Thermowells | BDS-291 | Italy | Mr. Shadi | In Process | 01 | [5 empty] | 0881 |  | YES
412 | E+H Magnetic flowmeters, Remote Indicators and Surge Protectors | BDS-292 | Italy | Mr. Shadi | In Process | 02 |  |  |  |  | TIE-23-0340-IVR01 TIE-23-0340-IVR02 | 0883 |  | YES
413 | Flow Indicators(Metal Tube Rotameters) | BDS-293 | Italy | Mr. Shadi | In Process | 03 |  |  |  |  | TIE-23-0349-IVR01 | 0885 |  | YES
414 | Acid Sulfuric Loading and Unloading Pumps for WWT/WSU | CW Hydro-294 | Korea | Mrs. Ranjbar | In Process | 2 |  |  |  |  | TIE-23-0344-IVR01 | 0889
415 | PRV-Packing Inspection | Fateh Sanat Kimia-BFS INCORPORATION-295 | Korea | Mrs. Mohamadi | In Process | AFI-BFS-004 |  |  |  |  | TIE-23-0342-IVR01 | 0887
416 | Gas Detection Equipment-Spectrex-Final Inspection | Neda-296 | UAE | Mr. Shadi | Final | 03 |  |  |  |  | TIE-23-0355-IVR01 | 0891 |  | YES
417 | PSV and TSV Valves - Final Packing Inspection | Leser-297 | Germany | Mr. Shadi | Final | 03 |  |  |  |  | TIE-23-0364-IVR01 TIE-23-0364-IVR02 | 0893 |  | YES
418 | Butterfly Valve MOV & On/Off | RMT-298 | Italy | Mr. Shadi | In Process | 12 |  |  |  |  | TIE-23-0365-IVR01 | 0895
419 | Control Valve | RMT-299 | Italy | Mr. Shadi | In Process | 13 |  |  |  |  | TIE-23-0379-IVR01 | 0897
420 | On-off Valves- Final Inspection | Fateh Sanat Kimia-Wascon-300 | Korea | Mrs. Mohamadi | Final | AFI-WASCON-007 |  |  |  |  | TIE-23-0382-IVR01 | 0899
421 | Control Valve-Final | Fateh Sanat Kimia-Wascon-301 | Korea | Mrs. Mohamadi | Final | AFI-WASCON-008 |  |  |  |  | TIE-23-0409-IVR01 | 0901 |  | YES
422 | Butterfly Valve MOV & On/Off | RMT-302 | Italy | Mr. Shadi | In Process | 14 |  |  |  |  | TIE-23-0448-IVR01 | 0903 |  | YES
423 | Supply of RO Desalination Package | Celar-303 | UAE | Mr. Ahmadi | Final | 02 |  |  |  |  | TIE-23-0437-IVR01 | 0905
424 | Pipe & Fitting | IMS-304 | UAE | Mrs. Ranjbar | Final | 14325 & 15155 |  |  |  |  | TIE-23-0435-IVR01 TIE-23-0436-IVR01 | 0915 |  | YES
425 | MOV (MOV-101A/B) | Fateh Sanat Kimia-Wascon-305 | Korea | Mrs. Mohamadi | In Process | AFI-WASCON-009 | [5 empty] | 0919
426 | Acid Sulfuric Loading and Unloading Pumps for WWT/WSU | CW Hydro-306 | Korea | Mrs. Ranjbar | Final | 3 |  |  |  |  | TIE-23-0474-IVR01 | 0921 |  | YES
427 | MOV (MOV-101A/B) | Fateh Sanat Kimia-Wascon-307 | Korea | Mrs. Mohamadi | Final | AFI-WASCON-010 |  |  |  |  | TIE-23-0504-IVR01 | 0929 |  | YES
428 | Supply of RO Desalination Package | Celar-308 | UAE | Mr. Ahmadi | Final | 03 |  |  |  |  | TIE-23-0529-IVR01 | 0937
429 | Pipe | IMS-309 | UAE | Mrs. Ranjbar | In Process | 41325 |  |  |  |  | TIE-23-0528-IVR01 | 0941 |  | YES
430 | Pressure Vessels | Ensol-310#Ensol 10 | Korea | Mrs. Mohamadi | In Process | EN-NOI-021 |  |  |  |  | TIE-23-0557-IVR01 | 0945 |  | YES
431 | Supply of RO Desalination Package | Celar-311 | UAE | Mr. Ahmadi | Final | 04 |  |  |  |  | TIE-23-0560-IVR01 | 0947 |  | YES
432 | Control Valve | RMT-312 | Italy | Mrs. Ranjbar | In Process | 15 |  |  |  |  | TIE-23-0603-IVR01 | 0949
433 | Pipe | IMS-313 | UAE | Mrs. Ranjbar | In Process | 15155 |  |  |  |  | TIE-23-0585-IVR01 | 0951 |  | YES
434 | Supply of RO Desalination Package - FAT for MCC AND PLC Panels | Celar-314 | UAE | Mr. Ahmadi | In Process | 05 |  |  |  |  | TIE-23-0615-IVR01 | 0953
435 | SWRO Package | Celar-315 | UAE | Mr. Ahmadi | In Process | 06 |  |  |  |  | TIE-23-0618-IVR-01
436 | On/Off Valve | RMT-316 | Italy | Mrs. Ranjbar | In Process | 16 |  |  |  |  | TIE-24-0664-IVR-01 | 0957
437 | On/Off Valve | RMT-317 | Italy | Mrs. Ranjbar | In Process | 17 |  |  |  |  | TIE-24-0733-IVR-01 | 0959
438 | On/Off Valve | RMT-318 | Italy | Mrs. Ranjbar | In Process | 18 |  |  |  |  | TIE-24-0754-IVR-01 | 0961
439 | Sight Glass | Samil Industry.Co (SIC) Dibaco-319 | Korea | Mrs. Ranjbar | In Process | 01 |  |  |  |  | TIE-24-0809-IVR-01 | 0963
440 | Material Inspection for Flange (FAD) | Tajhiz Arg Parsian.Co (TAPCO)-320 | Italy | Mrs. Ranjbar | In Process | 01 |  |  |  |  | TIE-24-0845-IVR-01 | 0965
441 | Recycle Gas Compressor | Tajhiz Arg Parsian.Co (TAPCO)-321 | Austria | Mrs. Ranjbar | In Process | SACR-MG-GEN-PQ-FRM-7401-003-00 |  |  |  |  | TIE-24-0849-IVR-01 | 0969
442 | MWM Spare Parts | BGB Energy(BGB)-322 | Turkey | Mr. Latifker | In Process | 01 |  |  |  |  | TIE-24-0839-IVR-01 | 0971 |  | YES
443 | RO Desalination Package - Final Pre-Shipment Inspection | Celar-323 | UAE | Mr. Ahmadi | In Process | 07 |  |  |  |  | TIE-24-0846-IVR-01 TIE-24-0846-IVR-02 | 0973
444 | Compressor prior MRT | Tajhiz Arg Parsian.Co (TAPCO)-324 | Austria | Mrs. Ranjbar | In Process | SACR-MG-GEN-PQ-FRM-7401-004-01 |  |  |  |  | TIE-24-0872-IVR-01 | 0975
445 | Sight Glass | Samil Industry.Co (SIC) Dibaco-325 | Korea | Mrs. Ranjbar | In Process | 02 |  |  |  |  | TIE-24-0868-IVR-01 | 0977
446 | Recycle Gas Compressor | Tajhiz Arg Parsian.Co (TAPCO)-326 | Austria | Mrs. Ranjbar | In Process | SACR-MG-GEN-PQ-FRM-7401(IN-005) |  |  |  |  | TIE-24-0886-IVR-01 | 0979
447 | Ro Package-Final Pre-Shipment | Celar-327 | UAE | Mr. Ahmadi | In Process | 08 |  |  |  |  | TIE-24-0900-IVR-01 | 0981 |  | YES
448 | ADP Project | Aljazire-328 | Spain | Mrs. Ranjbar | In Process | 02 |  |  |  |  | TIE-24-0902-IVR-01 | 0983
449 | Control Valve & On Off Valve-Last items-Final Inspection | RMT-329 | Italy | Mrs. Ranjbar | Final | [5 empty] | TIE-24-0909-IVR-01 | 0967
450 | Raw Material,Piping /Visual, Dimensional, MTC review | Asia Instruments LTD-330 | UAE | Mrs. Moradi | In Process | ASI-ME-IN-00 |  |  |  |  | TIE-24-0935-IVR-01 | 0985
451 | Manual Valve Check | Tajhiz Arg Parsian.Co (TAPCO)-331 | UAE | Mrs. Ranjbar | In Process | 07 |  |  |  |  | TIE-24-0975-IVR-01 | 0987
452 | MWM Spare Parts- Part 2 | BGB Energy(BGB)-332 | Turkey | Mr. Latifker | Final | 02 |  |  |  |  | TIE-24-0984-IVR-01 | 0989
453 | ADP Project | Aljazire-333 | Spain | Mrs. Ranjbar | In Process | 03 |  |  |  |  | TIE-24-0987-IVR-01 | 0991
454 | Ball valve Inspection as per ITP-PO:130 | Asia Instruments LTD-334 | China | Mrs. Moradi | In Process | ASI-ME-IN-002 | [5 empty] | 0993
455 | Ball valve Inspection as per ITP-PO:130 | Asia Instruments LTD-335 | China | Mrs. Moradi | In Process | ASI-ME-IN-003 |  |  |  |  | TIE-24-1025-IVR-01 | 0995
456
457
Note on D64: Sara Ebrahimian: 1. 18.09.2021 2. 20.09.2021 3. 24.09.2021
Note on D65: Sara Ebrahimian: 1. 19 Oct 2. 20 Oct 3. 21 Oct 4. 22 Oct 5. 23 Oct R 6. 24 Oct R 7. 25 Oct R
Note on D66: Sara Ebrahimian: 1. 12 Oct 2. 13 Oct 3. 15 Oct 4. 19 Oct 5. 20 Oct 6. 22 Oct R 7. 25 Oct R 8. 27 Oct R 9. 28 Oct R
Note on D67: Sara Ebrahimian: 1. 23 Sep 2. 24 Sep
Note on D71: Sara Ebrahimian: 1.03 Nov 2. 9 Nov 3. 10 Nov 4. 11 Nov
Note on D74: Sara Ebrahimian: 1. 18 Nov 2. 19 Nov
Note on D77: Sara Ebrahimian: 1. 15 Nov 2. 16 Nov 3. 18 Nov 4. 19 Nov 5. 22 Nov R 6. 23 Nov R
Note on D84: Sara Ebrahimian: 1. 01 Dec 2. 02 Dec
Note on D86: Sara Ebrahimian: 1. 16 Dec 2. 17 Dec 3. 18 Dec
Note on D87: Sara Ebrahimian: 1. 09 Dec 2. 10 Dec
Note on D88: Sara Ebrahimian: 1. 23 Dec 2. 24 Dec
Note on D96: Sara Ebrahimian: 1. 29 Dec 2. 30 Dec 3. 31 Dec
Note on C108: Sara Ebrahimian: 1. 31 Jan 2. 1 Feb 3. 2 Feb 4. 3 Feb 5. 4 Feb
Note on C167: Sara Ebrahimian: 1. 8 Feb 2. 9 Feb
Note on C169: Sara Ebrahimian: 1. 14 Feb 2. 15 Feb 3. 16 Feb 4. 17 Feb 5. 18 Feb
Note on C223: Sara Ebrahimian: 08.22-26 5 Days 08.29-31 3 Days 09.01-02 2 Days
Note on C234: Sara Ebrahimian: 1.19.09 2.21.09 3.23.09 4.26.09 5.28.09 6.30.09

## August 2020
item No. | Order No. / ref No. | Manf. | Inspected Place | Notification request | Notification No | Notification Date | Actual Inspection duration | assigning date | supporing dox | INSPECTION Report No | Status | next step | IC
1 | KTI-0037 | KTI | korea | final/ shipment reinspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0037 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0037 (Rev.1) | 21.Jul.2020 18.Aug.2020 | 2020.08.11~12, 25 (3 day) / AM10:00~PM 17:30 | 22.7.2020 15.08.2020 | included | IVR-303-KTI-HET-017(Rev.1) -Fpart 3
2 | KTI-0039 | KTI | korea | shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0039 (Rev.0) | 22.JUL.2020 | 10-AUG-2020 10:00AM | 22.7.2020 | included | IVR-303-KTI-HET-039-F-part 1
3 | KTI-0040 | KTI | korea | in process/ shipment / final | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0040 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0040 (Rev.1) | 22. JUL. 2020 07. AUG. 2020 | 2020.08.04~12 (7days) /AM 09:00 2020.08.04~14 (9days) /AM 09:00 | 22.7.2020 | included | IVR-303-KTI-HET-040-F-part 1
4 | KTI-0041 | KTI | korea | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0041 (Rev.0) | 23.JuL.2020 | 2020.08.11~12 (2 day) /AM10:00 | 23.7.2020 | not included | IVR-303-KTI-HET-041-F-part 1
5 | rajan part 4 | rajan | china | final/ shipment | 4 | 4.8.2020 | 5.8.2020 | 4.8.2020 | included | IVR-RPF-SST-0004-F
6 | rood- pupm- part 2 | Roodhart | netherlands | performance test/ final | 010-RPG-0003 | 29.7.2020 | August,3,5,6,12,13 | 1.8.2020 | not included | IVR –RPG-0003-F part 1 IVR –RPG-0003-F part 2
7 | Hatco- part 3 | hatco | germany | final | INS-307-HAT-0017 | 15.Aug.2020 | 2020-08-25 | 15.8.2020 | included | IVR- HAT-NIS-0017
8 | RMT- MOV | rmt | italy | final/ dox review | IN-RMT-703-0008 | 04.Aug.2020 | August, 6 & 7 ( 2 Days ) | 5.8.2020 | included | IVR-703-RMT-OOV-0008 F
9 | RMT- MOV | rmt | italy |  | IN-RMT-721-0006 | 16.8.2020 | 21.Aug.2020 | 16.8.2020 | not included | IVR-721-RMT-OOV-0006 F
10 | RMT- control valve | RMT | italy | final | IN-RMT-703-0009 | 18.Aug.2020 | August, 27& 28 & 31 ( 3 Days ) | 19.08.2020 | not included
11 | zaffertec - part 4 | zaffertec | korea | final | 5511-ZSL-004 |  | 13.08.2020 | 2.8.2020 | not included | IVR-511-ZAF-PIP-0004-F
12 | zaffertec - part 5 | zaffertec | korea | final | 5511-ZSL-005 | 05.08.2020 | 12.08.2020 | 9.8.2020 | included | IVR-511-ZAF-PIP-0005-F
13 | zaffertec - part 6 | zaffertec | korea | final | 5511-ZSL-006 | 05.08.2020 | 13 and 14.08.2020 (Two Days) | 9.8.2020 | included | IVR-511-ZAF-PIP-0006-F
14
15
16
17
18
59

## July 2020
item No. | Order No. / ref No. | Manf. | Inspected Place | Notification request | Notification No | Notification Date | Actual Inspection duration | assigning date | supporing dox | INSPECTION Report No | Status | next step | IC
1 | FGS 2nd | FGS | china | final inspection | 404-FSK-0016 | 2020-06-26 | 5. July.2020 | 28.6.2020 | included | IVR-404-FSK-0016-F part1
2 | KTI-0017 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0017 (Rev.1) | 22.Jul.2020 | 2020.07.28 (1 day) /AM 10:00 | 22.7.2020 | not included / sent after request | IVR-303-KTI-HET-017(Rev.1) -F-part 2
3 | KTI -0032 | KTI | korea | in processFinal | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0032 (Rev.0) | 29. Jun. 2020 | 2020.07.01~11 (10 days) /AM 09:00 | 29.6.2020 | included | IVR-303-KTI-HET-032 part 1 IVR-303-KTI-HET-032 part 2
4 | KTI-0033 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0033 (Rev.0) | 06. Jul. 2020 | 2020.07.23 (1 day) / AM10:00 | 7.7.2020 | not included | IVR-303-KTI-HET-033 part 1
5 | KTI-0034 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0034 (Rev.0) | 09. Jul. 2020 | 2020.07.13~31 (16 days) /AM 09:00 | 11.7.2020 | not included | IVR-303-KTI-HET-034 part 1 IVR-303-KTI-HET-034 part 2 IVR-303-KTI-HET-034 part 3
6 | KTI-0035 | KTI | korea | shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0035 (Rev.0) | 10.JUL.2020 | 30-JUL-2020 10:00AM | 11.7.2020 | not included | IVR-303-KTI-HET-035-F-part 1
7 | KTI-0036 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0036 (Rev.0) | 14.Jul.2020 | 2020.07.28~29 (2 day) / AM10:00~PM 17:30 | 14.7.2020 | not included | IVR-303-KTI-HET-036-F-part 1
8 | KTI-0038 | KTI | korea | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0038 (Rev.0) | 21.Jul.2020 | 2020.07.30~31 (2 days) /AM10:00 | 22.7.2020 | included | IVR-303-KTI-HET-038-F-part 1
9 | Zaffertec part 3 | zaffertec | korea | in process | 5511-ZSL-003 | 27.07.2020 | 30.07.2020 | 28.7.2020 | included | IVR-5511-ZAF-PIP-0001-F
10 | Pedinco- Deluge Valve | pedinco | Switzerland | In-process Inspection | PED-804-IN-016 | 10.06.2020 | 17.Jun.2020 – 10:00 AM | 10.06.2020 | included
11 | FGS 1st | FGS | italy | Final/ shipment | 405-FSK-0020-A (A103) | 23.June.2020 | 03 July 2020 ( except 06 July) | 24.6.2020 | included | IVR-405-FSK-0020-F part1
12 | RMT MOV | RMT | italy | dox review | IN-RMT-721-0002 | 27.June.2020 | July, from 7 to 10 ( 1 day confirmed ) | 29.6.2020 | not included | IVR-RMT-721-0002-F
13 | RMT MOV | RMT | italy | dox review | IN-RMT-721-0003 | 27.June.2021 | July, from 8 to 14 ( 5 day confirmed ) | 7.7.2020 | not included | IVR-RMT-721-0003-F
14 | RMT- control valve | RMT | italy |  | IN-RMT-703-0006 | 15.July.2020 | July, from 21 to 24 ( 4 Days | 18.7.2020 | not included | IVR-703-RMT-OOV-0006 F
15 | RMT- MOV | RMT | italy | final/ dox review | IN-RMT-721-0004 | 19.July.2020 | July, 27&28&29 ( 3 days ) | 20.7.2020 | not included | IVR-721-RMT-OOV-0004 F
16 | RMT-Control Valve | RMT | italy | in process/ final/ dox | IN-RMT-703-0007 IN-RMT-703-0007 Rev.1 | 25.July.2020 | July, 30 & 31 ( 2 Days ) | 27.7.2020 | included | IVR-703-RMT-OOV-0007 F
17 | RMT-Motor Operated Valve | RMT | italy | in process/ dox | IN-RMT-721-0005 | 25.July.2020 | July, 29 & 30 ( 2 days ) | 27.7.2020 | not included | IVR-721-RMT-OOV-0005 F
18 | Kti-0031 | KTI | italy | final inspection/ dox review | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0031 (Rev.0) | 23.June.2020 | 14/16/17/18/19/20/21/22/23/24 for BURNER & 11/17/18/19 for UV SCANNER | 23.6.2020 | included | IVR-303-KTI-HET-031-F-part 1
59 | FGS 1st | FGS | italy | Final/ shipment | 405-FSK-0020-A (A103) | 23.June.2020 | 03 July 2020 ( except 06 July) | 24.6.2020 | included | IVR-405-FSK-0020-F part1

## June 2020
item No. | Order No. / ref No. | Manf. | Inspected Place | Notification request | Notification No | Notification Date | Actual Inspection duration | assigning date | supporing dox | INSPECTION Report No | Status | next step | IC
1 | RMT-Control Valve | RMT | italy | Raw Material Inspection/ doc. Review | IN-RMT-703-0004 | 01.June.2020 | June, 04 & 05 (2 Days) | 8.6.2020 | not included | IVR-RMT-OOV-0004-F | SACR-701-GEN-QM-ITP-0003-ITP - Rev. 4 (RMT Ref.: ITP 190070 )
2 | RMT-Actuated valve | RMT | italy | Raw Material Inspection/ doc. Review | IN-RMT-701-0008 | 01.June.2020 | June, from 5 to 15 (10 Days) | 8.6.2020 | not included | IVR-RMT-OOV-0008-F
3 | RMT-Actuated valve | RMT | italy | Raw Material Inspection/ doc. Review | IN-RMT-701-0009 | 01.June.2020 | June, from 22-23-24-25-26 (5 Days) | 8.6.2020 | not included | IVR-RMT-OOV-0009-F
4 | RMT-Motor Operated Valve | RMT | italy | Raw Material Inspection/ doc. Review | IN-RMT-721-0001 | 20.June.2020 | June, 24-25 ( 2 days ) | 22.6.2020 | included | IVR-RMT-721-0001-F
5 | RMT-Actuated valve | RMT | italy |  | IN-RMT-701-0007 rev 1 | 2020-05-12 | May, 27 & 28 & 29 (3 days) | 8.6.2020 | notification sent + eng dept comments. | IVR-RMT-OOV-0007-F IVR-701-RMT-OOV-0007 F
6 | Kti-0030 | KTI | italy | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0030 (Rev.0) | 23.June.2020 | 2020.06.29 / 09:30 AM | 23.6.2020 | included | IVR-303-KTI-HET-030-F-part 1
7 | NEDA- part 1 | NEDA | china | final inspection | SACR-DE-GEN-IN-MRQ-5704-03, 5705-03, 5707-03 -0001 | 29.5.2020 | June.14-15 after double check with vendor | 8.06.2020 | included | IVR-ABB-001 Part 1
8 | FGS 2nd | FGS | korea | final inspection | 404-FSK-0015 Rev.00 (E326) | 01 Jun 2020 | 29.May.2020(1st), 02.June.2020(2ND), 04.June.2020(3rd), 08.June.2020(4th) | 31.5.2020 | not included / sent after request |  | waiting for supporting dox
9 | Hisco - part 1` | hisco | korea | final inspection | MRQ-5702-01 | 2020-09-06 | Jun 24th,2020 | 14.06.2020 | included | IVR-MRQ-001
6 | KTI-0015 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0015 (Rev.1) | 29.May.2020 ???? | 2020.05.07 & 15 (3DAYS) /PM 10:00 | 14.06.2020 | not included / sent after request | IVR-KTI-HET-015-F-part1 IVR-303-KTI-HET-015-F-part3 | report received
10 | KTI-0019 | KTI | korea | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0019 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0019 (Rev.1) | 12.May.2020 11.6.2020 | 2020.05.22 (1 days) /AM10:00 | 13.5.2020 15.6.2020 | not included / sent after request | IVR-303-KTI-HET-019-F-part 1 IVR-303-KTI-HET-019(Rev.1)-F-part 1 | comment confirmed | revised notification sent to GL for Re-Inspection on 15.6.2020
11 | KTI-0021 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0021 (Rev.0) | 27.May.2020 | 2020.06.01~13 /AM 09:00 | 27.05.2020 | not included | IVR-303-KTI-HET-021-F-part 1 IVR-303-KTI-HET-021-F-part 2
12 | FGS 2nd | FGS | china | final inspection | 401-FSK-0006 | 2020-01-06 | 20.Jan.2020
13 | FGS 2nd | FGS | china | final inspection | 403-FSK-0007 | 2019-12-11 | 23.Dec.2019~27.Dec.2019 |  |  | IVR-FSK-PRV-0001-F | report received
14 | FGS 2nd | FGS | china | final inspection | 401-FSK-0012 | 2020-04-09 | 20.Apr.2020 |  |  | IVR-401-FSK-TOW-0012 F | report received
15 | FGS 2nd | FGS | china | final inspection | 404-FSK-0008 Rev.00 (E-326) | 21 Apirl, 2020 | 21~25 Apirl, 2020 (one day) | 22.4.2020 | included | IVR-404-FSK | report received
16 | FGS 2nd | FGS | china | final inspection | 404-FSK-0010 | 2020-04-27 | 08.May.2020 | 28.4.2020 | included | IVR-FSK-0010-F | report received
17 | FGS 2nd | FGS | china | final inspection | 404-FSK-0012 Rev.00 (E326) | 2020-05-20 | 27.May.2020 ~ 29. May.2020 | 22.5.2020 | not included / sent after request | IVR-404-FSK-0014-F part1 | report received
18 | FGS 2nd | FGS | china | final inspection | 404-FSK-0013 Rev.00 (E326) | 2020-05-21 | 29.May.2020 | 27.5.2020 | included
19 | FGS 2nd | FGS | china | final inspection | 404-FSK-0014 REV.00 (E326) | 2020-04-27 | 29.May.2020 | 27.5.2020 | included
20 | FGS 2nd | FGS | korea | final inspection | 404-FSK-0015 Rev.00 (E326) | 01 Jun 2020 | 29.May.2020(1st), 02.June.2020(2ND), 04.June.2020(3rd), 08.June.2020(4th) | 31.5.2020 | not included / sent after request |  | waiting for supporting dox
21 | KTI- 022 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0022 | 29.May.2020 | 2020.06.09 (1 day) /AM10:00 | 2.6.2020 | not included / sent after request | IVR-303-KTI-HET-022-F-part 1
22 | KTI- 023 | KTI |  | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0023 | 29.May.2020 | 2020.06.10 (1 day) /A M10:00 | 2.6.2020 | not included / sent after request | IVR-303-KTI-HET-023-F-part 1
23 | kti-0025 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0025 (Rev.0) | 02.Jun.2020 | 2020.06.16 (1 day) /AM10:00 | 02.Jun.2020 |  | IVR-303-KTI-HET-025F PART1
24 | kti-0024 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0024 (Rev.0) | 02.Jun.2020 | 2020.06.15 (1 day) /AM10:00 | 02.Jun.2020 |  | IVR-303-KTI-HET-024-F-part1 IVR-303-KTI-HET-024(Rev.1)-F-part 1
25 | KTI-0026 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0026 (Rev.0) | 10.06.2020 | 2020.06.15~30 (14 days) /AM 09:00 | 10.06.2020 | not included | IVR-303-KTI-HET-026-F-part 1 IVR-303-KTI-HET-026-F-part2 | revised notification sent to GL
26 | Kti-0027 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0027 | 10.06.2020 | 1) 19-JUN-2020 10:00AM : ITP ACTIVITY NO.: 18,20,21 2) 26-JUN-2020 10:00AM : ITP ACTIVITY NO.: 22 | 10.06.2020 | not included | IVR-303-KTI-HET-027-F-part 1 | revised notification sent to GL
27 | Kti-0028 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0028 (Rev.0) | 11.Jun.2020 | 2020.06.23 (1 day) /AM10:00 | 13.06.2020 | not included | IVR-303-KTI-HET-028-F-part 1 | revised notification sent to GL
28 | Kti-0029 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0029 (Rev.0) | 18.Jun.2020 | 2020.06.26 (1 day) /AM10:00 | 20.6.2020 | not included | IVR-303-KTI-HET-029-F-part 1

## MAY2020
item No. | Order No. / ref No. | Manf. | Inspected Place | Notification request | Notification No | Notification Date | Actual Inspection duration | assigning date | supporing dox | INSPECTION Report No | Status | next step | IC
1 | RMT Actuated valve | RMT | italy | In-process Inspection | IN-RMT-701-0006-R.1 | 10.May.202 | May, 14 to 19 (4 days) |  |  | IVR-RMT-OOV-0006-F | report received
2 | zaffertec - part 2 | zaffertec | italy | final inspection | 2 | 16.05.2020 | 22.May.2020 9:00 AM | sent by email after reminding to the vendor 16.5.2020 | included | IVR-502-ZAF-PIP-0002-F | irn issued
3 | KTI-0016 | KTI | italy | In-process Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0016 (Rev.0) | 07. May. 2020 | 2020.05.13 / 09:30 AM | 9.may.2020 | not included / sent after request
4 | KTI-0013 | KTI | korea | In-process Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0013 (Rev.0) | 22.Apr.2020 | 2020.04.29 /AM10:01 | 25.4.2020 | included | IVR-404-FSK-0013-F part1
5 | KTI-0014 | KTI | korea | In-process Inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0014 (Rev.0) | 29.Apr.2020 | 2020.05.06~16 /AM10:00 | rev 1 assigned 11 may 2020 | not included / sent after request | IVR-303-KTI-HET-014 part 1 & 2 | report received
6 | KTI-0015 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0015 (Rev.0) | 29.May.2020 | 2020.05.07 & 15 (2DAYS) /PM 10:00 | 29 apr. 2020 | not included / sent after request | IVR-KTI-HET-015-F-part1 IVR-303-KTI-HET-015-F-part3 | report received
7 | KTI-0017 | KTI | korea | final inspection | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0017 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0017 (Rev.1) | 07.May.2020 22.Jul.2020 | 2020.05.14 (Thu.) /AM 10:00 2020.07.28 (1 day) /AM 10:00 | 9.may.2020 22.7.2020 | not included / sent after request | IVR-303-KTI-HET-017(Rev.1) -F-part 2
8 | KTI-0018 | KTI | korea | inprocess/ final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0018 (Rev.0) | 12.May.2020 | 2020.05.18~30 /AM10:00 | 13.5.2020 | not included / sent after request | IVR-303-KTI-HET-018-F-part 1 | report received
9 | KTI-0019 | KTI | korea | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0019 (Rev.0) SACR-DE-GEN-MA-MRQ-5303-02-KTI-0019 (Rev.1) | 12.May.2020 11.6.2020 | 2020.05.22 (1 days) /AM10:00 | 13.5.2020 15.6.2020 | not included / sent after request | IVR-303-KTI-HET-019-F-part 1 IVR-303-KTI-HET-019(Rev.1)-F-part 1 | comment confirmed | revised notification sent to GL for Re-Inspection on 15.6.2020
10 | KTI-0020 | KTI | korea | final/ shipment | SACR-DE-GEN-MA-MRQ-5303-02-KTI-0020 (Rev.0) | 14.May.2020 | 2020.05.27~28 (2 days) /AM10:00 | 18.5.2020 | included | IVR-303-KTI-HET-020-F-part 1 | report received
11 | FGS 2nd | FGS | china | final inspection | 404-FSK-0010 | 2020-04-27 | 12 May Changsu, 12,13MAy HWAN TIN | 28.4.2020 | included | IVR-FSK-0010-F | report received
12 | FGS 2nd | FGS | china | final inspection | 404-FSK-0012 Rev.00 (E326) | 2020-05-20 | 27.May.2020 ~ 29. May.2020 | 22.5.2020 | not included / sent after request | IVR-404-FSK-0014-F part1 | report received
13 | FGS 2nd | FGS | china | final inspection | 404-FSK-0013 Rev.00 (E326) | 2020-05-21 | 29.May.2020 | 27.5.2020 | included
14 | FGS 2nd | FGS | china | final inspection | 404-FSK-0014 REV.00 (E326) | 2020-04-27 | 29.May.2020 | 27.5.2020 | included
15 | IIP - first shipment | iip | china | In-process Inspection | SACR-301-IIP-016 | 2020-04-28 | Monday 11.May.2020 up to Sunday 17.May.2020 | rev 1 assigned 2 may 2020 | not included / sent after request | IVR-301-IIP-016-F-part 1 | revised report recievd
16 | IIP - first shipment | iip | china | In-process Inspection | SACR-301-IIP-017 | 2020-04-29 | Wednesday 20.May.2020 & Thursday 21.May.2020 | 2.may.2020 | not included / sent after request | IVR-301-IIP-017-F-part 2 | report commented by GL 1.6.2020