## Sheet2
# | Opi No. | Date | Project Name | Packing List No. | Purchase Order | Vendor | Purchaser | Consignee | Destination | Shipment No. | Material Description | Category | Main Material | Mark No. | Description | Pl Quantity | Shortage | Overage | Damage | Incorrect | Accepted | Unit | Weight/Unit | Action Code | Remark
401 | OPI-FAR-1001-039 | 2022-09-11 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-035 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 36 |  | Main Item | - | 4AOYTT504400 | GRP Pipe, UG, UNIAXIAL, Double bell Reka Coupling joint System, Man. Std., PN= 6 Bar, SN : 5000pa, DN : 44" | 35.79 |  |  |  |  | 35.79 | Meter | 4597.5
402 | OPI-FAR-1001-039 | 2022-09-11 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-035 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 36 |  | Main Item | - | 4AOYTT501600 | GRP Pipe, UG, UNIAXIAL, Double bell Reka Coupling joint System, Man. Std., PN= 6 Bar, SN : 5000pa, DN : 16" | 30 |  |  |  |  | 30 | Meter | 519.6
405 | OPI-FAR-1001-039 | 2022-09-11 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-035 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 36 |  | Main Item | - | 4AOYTT501600 | GRP Pipe, UG, UNIAXIAL, Double bell Reka Coupling joint System, Man. Std., PN= 6 Bar, SN : 5000pa, DN : 16" | 24 |  |  |  |  | 24 | Meter | 415.7 |  | 2947 | 8321
406 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
407 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
408 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
409 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
410 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
411 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
412 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
413 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
414 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4081516 | GRP inlet One Cut Miter with Paddle Ring,L2=815 ,Size=16",PN:6 Bar, Acc to attached drawing, Man. Std.(H=D) | 1 |  |  |  |  | 1 | Piece |  |  | 2947 | 8321
415 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4046008 | GRP inlet One Cut Miter with Paddle Ring,Pipe Lenght=1150,L2=460 ,Size=8",PN:6, Acc to attached drawing, Man. Std.(,H=250mm) | 2 |  |  |  |  | 2 | Piece |  |  | 2947 | 8321
416 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4081516 | GRP inlet One Cut Miter with Paddle Ring,L2=815 ,Size=16",PN:6 Bar, Acc to attached drawing, Man. Std.(H=D) | 1 |  |  |  |  | 1 | Piece |  |  | 2947 | 8321
417 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4066008 | GRP inlet One Cut Miter with Paddle Ring,L2=660,Size=8",PN:6 Bar, Acc to attached drawing, Man. Std.(H=450mm) | 1 |  |  |  |  | 1 | Piece
418 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4056008 | GRP inlet One Cut Miter with Paddle Ring, Length=1250 , L2=560,Size=8",PN:6 Bar, Acc to attached drawing, Man. Std.(H=350mm) | 1 |  |  |  |  | 1 | Piece |  |  | 2947
419 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4092018 | GRP inlet One Cut Miter with Paddle Ring,Pipe Lenght=1600,L2=920 ,Size=18",PN:6 Bar, Acc to attached drawing, Man. Std.(H=D) | 1 |  |  |  |  | 1 | Piece |  |  | 2947
420 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4092018 | GRP inlet One Cut Miter with Paddle Ring,Pipe Lenght=1600,L2=920 ,Size=18",PN:6 Bar, Acc to attached drawing, Man. Std.(H=D) | 1 |  |  |  |  | 1 | Piece |  |  | 2947
421 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4092018 | GRP inlet One Cut Miter with Paddle Ring,Pipe Lenght=1600,L2=920 ,Size=18",PN:6 Bar, Acc to attached drawing, Man. Std.(H=D) | 1 |  |  |  |  | 1 | Piece |  |  | 2947
422 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000024 | GRP Outlet with Paddle Ring, Size:24", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece |  |  | 2947
423 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000024 | GRP Outlet with Paddle Ring, Size:24", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece |  |  | 2947
424 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000016 | GRP Outlet with Paddle Ring, Size:16", PN:6 Bar, Acc to attached drawing, Man. Std. | 3 |  |  |  |  | 3 | Piece
425 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
426 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
427 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
428 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
429 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
430 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
431 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
432 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
433 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000044 | GRP Outlet with Paddle Ring, Size:44", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
434 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4122024 | GRP inlet One Cut Miter with Paddle Ring H=D=600mm, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
435 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4317024 | GRP inlet One Cut Miter with Paddle Ring H=2550mm, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
436 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4291516 | GRP inlet One Cut Miter with Paddle Ring H=2500 mm, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
437 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4461516 | GRP inlet One Cut Miter with Paddle Ring H=4200 mm, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
438 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000018 | GRP Outlet with Paddle Ring, Size:18", PN:6 Bar, Acc to attached drawing, Man. Std. | 2 |  |  |  |  | 2 | Piece
439 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000008 | GRP Outlet with Paddle Ring, Size:8", PN:6 Bar, Acc to attached drawing, Man. Std. | 7 |  |  |  |  | 7 | Piece
440 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000010 | GRP Outlet with Paddle Ring, Size:10", PN:6 Bar, Acc to attached drawing, Man. Std. | 2 |  |  |  |  | 2 | Piece
441 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000008 | GRP Outlet with Paddle Ring, Size:8", PN:6 Bar, Acc to attached drawing, Man. Std. | 3 |  |  |  |  | 3 | Piece
442 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000010 | GRP Outlet with Paddle Ring, Size:10", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
443 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000016 | GRP Outlet with Paddle Ring, Size:16", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
444 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000018 | GRP Outlet with Paddle Ring, Size:18", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
445 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4101008 | GRP inlet One Cut Miter with Paddle Ring H=800mm, Acc to attached drawing, Man. Std. (Pipe Length:1700) | 1 |  |  |  |  | 1 | Piece
446 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4106008 | GRP inlet One Cut Miter with Paddle Ring H=850mm, Acc to attached drawing, Man. Std. (Pipe Length:1750) | 1 |  |  |  |  | 1 | Piece
447 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4046008 | GRP inlet One Cut Miter with Paddle Ring,Pipe Lenght=1150,L2=460 ,Size=8",PN:6, Acc to attached drawing, Man. Std.(,H=250mm) | 1 |  |  |  |  | 1 | Piece |  |  | 2947 | 8321
448 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4131510 | GRP inlet One Cut Miter with Paddle Ring H=1050mm, Acc to attached drawing, Man. Std. (Pipe Length:2000) | 1 |  |  |  |  | 1 | Piece |  |  | 2947
449 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BWYU4000018 | GRP Outlet with Paddle Ring, Size:18", PN:6 Bar, Acc to attached drawing, Man. Std. | 1 |  |  |  |  | 1 | Piece
450 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4046008 | GRP inlet One Cut Miter with Paddle Ring,Pipe Lenght=1150,L2=460 ,Size=8",PN:6, Acc to attached drawing, Man. Std.(,H=250mm) | 1 |  |  |  |  | 1 | Piece |  |  | 2947 | 8321
451 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4126510 | GRP inlet One Cut Miter with Paddle Ring H=1000mm, Acc to attached drawing, Man. Std. (Pipe Length:1950) | 1 |  |  |  |  | 1 | Piece |  |  | 2947
452 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4127018 | GRP inlet One Cut Miter with Paddle Ring H=800mm, Acc to attached drawing, Man. Std. (Pipe Length:1950) | 1 |  |  |  |  | 1 | Piece
453 | OPI-FAR-1001-040 | 2022-09-28 | South Adish Gas Condensate Refinery | SACR-PL-FAR-1001-037 | ADSH-P-PO-GE-1001 | FARASAN | South Adish Condensate Refinery | South Adish Condensate Refinery | DDP Site | 38 |  | Main Item | - | 4BVYU4146516 | GRP inlet One Cut Miter with Paddle Ring H=1050, Acc to attached drawing, Man. Std.(Pipe Length:2150) | 1 |  |  |  |  | 1 | Piece