## PROGRESS TABLE
Report Date: 07/26/2025 | [7 empty] | Steel Structure Fabrication Report Purchase of 1800 tons of structure - South Adish Refinery Project
[29 empty] | Plan |  |  | -0.0001821%
Roac | Area | Area | Prioritac | acorkgroups | ROW | Description | WF% | TOTAL aceight (Kg) | Shop drawing |  | Supply Material |  | Fabrication | [7 empty] | Painting |  | Packing & shipment |  | Erection |  | ACTUAL Progress | Plan Progress | مهندسی | تامین متریال | ساخت | بازرسی و ارسال
[13 empty] | Cutting |  | Assemblac |  | Welding |  | Cleaning | [9 empty] | 10% | 15% | 65% | 10%
[8 empty] | 1620002.9506 | 10% |  | 15% |  | 10% |  | 25% |  | 15% |  | 5% |  | 10% |  | 10% |  | 0% |  | 20.51% | 74.41% | 100% | 100% | 67.48% | 51.28%
[9 empty] | 612332.9506 | 37.8% | 496332.9506 | 30.64% | 491061.3078 | 30.31% | 356738.3088 | 22.02% | 223891.647 | 13.82% | 171024.008 | 10.56% | 90371.708 | 5.579% | 71032.008 | 4.385% | 0 | 0%
[6 empty] | RO SUPPORTS | 0.8732% | 14145.608 | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% |  |  | 100% | 100% | 100% | 100% | 100% | 100%
[6 empty] | PB-548-01 | 4.766% | 77204.852 | 77204.852 | 100% | 77204.852 | 100% | 75811.2 | 98.19% | 68427.082 | 88.63% | 46802.92 | 60.62% | 28400.2 | 36.79% | 12062.1 | 15.62% | 8920.1 | 11.55% |  |  | 70.63% | 100% | 100% | 100% | 100% | 100%
[6 empty] | PB-548-02 | 11.22% | 181686.8108 | 181686.8108 | 100% | 181686.8108 | 100% | 177808.82 | 97.87% | 163825.7 | 90.17% | 119133.5 | 65.57% | 107886.2 | 59.38% | 64164 | 35.32% | 47966.3 | 26.4% |  |  | 76.31% | 100% | 100% | 100% | 100% | 100%
[6 empty] | PR-502-06 | 4.342% | 70335.4798 | 70335.4798 | 100% | 70335.4798 | 100% | 70335.4798 | 100% | 60841.6388 | 86.5% | 32473.619 | 46.17% | 20592 | 29.28% | 0 | 0% | 0 | 0% |  |  | 65.01% | 100% | 100% | 100% | 100% | 100%
[6 empty] | PB-502-01 | 4.578% | 74162.8 | 74162.8 | 100% | 74162.8 | 100% | 74162.8 | 100% | 29442.7 | 39.7% | 11336 | 15.29% | 0 | 0% | 0 | 0% | 0 | 0% |  |  | 47.22% | 99.3% | 100% | 100% | 100% | 93%
[6 empty] | V-502-23 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-25 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-26 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | F-502-01 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | PR-502-01 | 10.8% | 175000 | [19 empty] | 64.04% | 100% | 100% | 57.6% | 16%
[6 empty] | PR-502-02 | 12.35% | 200000 | [19 empty] | 60.66% | 100% | 100% | 52.7% | 14%
[6 empty] | PR-502-03 | 14.2% | 230000 | [19 empty] | 43.88% | 100% | 100% | 29.05% | 0%
[6 empty] | PR-502-04 | 14.51% | 235000 | [19 empty] | 36.12% | 100% | 100% | 17.1% | 0%
[6 empty] | PR-502-05 | 4.864% | 78797.4 | 78797.4 | 100% | 78797.4 | 100% | 78797.4 | 100% | 20055.58 | 25.45% | 0 | 0% | 0 | 0% |  | 0% |  | 0% |  |  | 41.36% | 100% | 100% | 100% | 100% | 100%
[6 empty] | STR-502-01 | 4.63% | 75000 | 30000 | 40% | [17 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | STR-502-02 | 3.704% | 60000 | 60000 | 100% | [17 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | STR-502-03 | 4.012% | 65000 | 26000 | 40% | [17 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | SH-502-01 | 3.086% | 50000 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-01 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-02 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-11 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-12 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-13 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-14 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-15 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-16 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[6 empty] | V-502-17 | 0.1599% | 2590 | [19 empty] | 100% | 100% | 100% | 100% | 100%
[7 empty] | 0% | [20 empty] | 25%

## STRUCTURE DETAIL
Purchase of 1800 tons of structure - South Adish Refinery Project
Area | Workgroups | Priority | Item |  |  |  | QTY | UNIT WEIGHT | TOTALWeight (Kg) | Shop Drawing |  | Supply Material |  | Fabrication | [7 empty] | INSPECTION |  | painting |  | INSPECTION |  | Packing & Shipment |  | PL NO | Erection |  | DATE
[14 empty] | Cutting |  | Assembly |  | Welding |  | Cleaning
[10 empty] | 10% |  | 15% |  | 10% |  | 25% |  | 15% |  | 5%
[24 empty] | 10% |  |  |  | 10% |  |  | 0%
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34
|  |  | RO SUPPORTS | [5 empty] | 14145.608 | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% | 14145.608 | 100% |  |  | 14145.608 | 100% |  |  | 14145.608 | 100% |  | 0 | 0%
|  | IPE200 | RO SUPPORTS | B1 | BEAM |  | 5 | 67.1 | 335.5 | 335.5 | 100% | 335.5 | 100% | 335.5 | 100% | 335.5 | 100% | 335.5 | 100% | 335.5 | 100% |  |  | 335.5 | 100% |  |  | 335.5 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B2 | BEAM |  | 18 | 83 | 1494 | 1494 | 100% | 1494 | 100% | 1494 | 100% | 1494 | 100% | 1494 | 100% | 1494 | 100% |  |  | 1494 | 100% |  |  | 1494 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B3 | BEAM |  | 2 | 99.7 | 199.4 | 199.4 | 100% | 199.4 | 100% | 199.4 | 100% | 199.4 | 100% | 199.4 | 100% | 199.4 | 100% |  |  | 199.4 | 100% |  |  | 199.4 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B4 | BEAM |  | 1 | 99.7 | 99.7 | 99.7 | 100% | 99.7 | 100% | 99.7 | 100% | 99.7 | 100% | 99.7 | 100% | 99.7 | 100% |  |  | 99.7 | 100% |  |  | 99.7 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B5 | BEAM |  | 1 | 91.3 | 91.3 | 91.3 | 100% | 91.3 | 100% | 91.3 | 100% | 91.3 | 100% | 91.3 | 100% | 91.3 | 100% |  |  | 91.3 | 100% |  |  | 91.3 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B6 | BEAM |  | 2 | 95.6 | 191.2 | 191.2 | 100% | 191.2 | 100% | 191.2 | 100% | 191.2 | 100% | 191.2 | 100% | 191.2 | 100% |  |  | 191.2 | 100% |  |  | 191.2 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B7 | BEAM |  | 2 | 78.7 | 157.4 | 157.4 | 100% | 157.4 | 100% | 157.4 | 100% | 157.4 | 100% | 157.4 | 100% | 157.4 | 100% |  |  | 157.4 | 100% |  |  | 157.4 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B8 | BEAM |  | 2 | 47.8 | 95.6 | 95.6 | 100% | 95.6 | 100% | 95.6 | 100% | 95.6 | 100% | 95.6 | 100% | 95.6 | 100% |  |  | 95.6 | 100% |  |  | 95.6 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B9 | BEAM |  | 6 | 76.2 | 457.2 | 457.2 | 100% | 457.2 | 100% | 457.2 | 100% | 457.2 | 100% | 457.2 | 100% | 457.2 | 100% |  |  | 457.2 | 100% |  |  | 457.2 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B10 | BEAM |  | 4 | 81.4 | 325.6 | 325.6 | 100% | 325.6 | 100% | 325.6 | 100% | 325.6 | 100% | 325.6 | 100% | 325.6 | 100% |  |  | 325.6 | 100% |  |  | 325.6 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B11 | BEAM |  | 3 | 44.2 | 132.6 | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% |  |  | 132.6 | 100% |  |  | 132.6 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B12 | BEAM |  | 3 | 111.7 | 335.1 | 335.1 | 100% | 335.1 | 100% | 335.1 | 100% | 335.1 | 100% | 335.1 | 100% | 335.1 | 100% |  |  | 335.1 | 100% |  |  | 335.1 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | B13 | BEAM |  | 2 | 21.8 | 43.6 | 43.6 | 100% | 43.6 | 100% | 43.6 | 100% | 43.6 | 100% | 43.6 | 100% | 43.6 | 100% |  |  | 43.6 | 100% |  |  | 43.6 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | C1 | COLUMN |  | 1 | 136.2 | 136.2 | 136.2 | 100% | 136.2 | 100% | 136.2 | 100% | 136.2 | 100% | 136.2 | 100% | 136.2 | 100% |  |  | 136.2 | 100% |  |  | 136.2 | 100% | PL04 | 0
|  | IPE200 | RO SUPPORTS | FR1 | FRAME |  | 2 | 298.8 | 597.6 | 597.6 | 100% | 597.6 | 100% | 597.6 | 100% | 597.6 | 100% | 597.6 | 100% | 597.6 | 100% |  |  | 597.6 | 100% |  |  | 597.6 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR2 | FRAME |  | 2 | 252.9 | 505.8 | 505.8 | 100% | 505.8 | 100% | 505.8 | 100% | 505.8 | 100% | 505.8 | 100% | 505.8 | 100% |  |  | 505.8 | 100% |  |  | 505.8 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR3 | FRAME |  | 1 | 265.6 | 265.6 | 265.6 | 100% | 265.6 | 100% | 265.6 | 100% | 265.6 | 100% | 265.6 | 100% | 265.6 | 100% |  |  | 265.6 | 100% |  |  | 265.6 | 100% | PL01 | 0
|  | IPE180 | RO SUPPORTS | FR4 | FRAME |  | 12 | 183.3 | 2199.6 | 2199.6 | 100% | 2199.6 | 100% | 2199.6 | 100% | 2199.6 | 100% | 2199.6 | 100% | 2199.6 | 100% |  |  | 2199.6 | 100% |  |  | 2199.6 | 100% | PL02 | 0
|  | IPE200 | RO SUPPORTS | FR5 | FRAME |  | 3 | 354.1 | 1062.3 | 1062.3 | 100% | 1062.3 | 100% | 1062.3 | 100% | 1062.3 | 100% | 1062.3 | 100% | 1062.3 | 100% |  |  | 1062.3 | 100% |  |  | 1062.3 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR6 | FRAME |  | 9 | 343.7 | 3093.3 | 3093.3 | 100% | 3093.3 | 100% | 3093.3 | 100% | 3093.3 | 100% | 3093.3 | 100% | 3093.3 | 100% |  |  | 3093.3 | 100% |  |  | 3093.3 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR7 | FRAME |  | 1 | 303 | 303 | 303 | 100% | 303 | 100% | 303 | 100% | 303 | 100% | 303 | 100% | 303 | 100% |  |  | 303 | 100% |  |  | 303 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR8 | FRAME |  | 1 | 279.9 | 279.9 | 279.9 | 100% | 279.9 | 100% | 279.9 | 100% | 279.9 | 100% | 279.9 | 100% | 279.9 | 100% |  |  | 279.9 | 100% |  |  | 279.9 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR9 | FRAME |  | 1 | 297.8 | 297.8 | 297.8 | 100% | 297.8 | 100% | 297.8 | 100% | 297.8 | 100% | 297.8 | 100% | 297.8 | 100% |  |  | 297.8 | 100% |  |  | 297.8 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR10 | FRAME |  | 4 | 268.1 | 1072.4 | 1072.4 | 100% | 1072.4 | 100% | 1072.4 | 100% | 1072.4 | 100% | 1072.4 | 100% | 1072.4 | 100% |  |  | 1072.4 | 100% |  |  | 1072.4 | 100% | PL01 | 0
|  | IPE200 | RO SUPPORTS | FR11 | FRAME |  | 1 | 279.3 | 279.3 | 279.3 | 100% | 279.3 | 100% | 279.3 | 100% | 279.3 | 100% | 279.3 | 100% | 279.3 | 100% |  |  | 279.3 | 100% |  |  | 279.3 | 100% | PL01 | 0
|  |  | RO SUPPORTS | BOLT 16X60 | BOLT |  | 688 | 0.117 | 80.496 | 80.496 | 100% | 80.496 | 100% | 80.496 | 100% | 80.496 | 100% | 80.496 | 100% | 80.496 | 100% |  |  | 80.496 | 100% |  |  | 80.496 | 100% | PL03 | 0
|  |  | RO SUPPORTS | BOLT 20X60 | BOLT |  | 72 | 0.196 | 14.112 | 14.112 | 100% | 14.112 | 100% | 14.112 | 100% | 14.112 | 100% | 14.112 | 100% | 14.112 | 100% |  |  | 14.112 | 100% |  |  | 14.112 | 100% | PL03 | 0
|  |  | PB-548-01 | [5 empty] | 77204.852 | 77204.852 | 100% | 77204.852 | 100% | 75811.2 | 98.19% | 68427.082 | 88.63% | 46802.92 | 60.62% | 28400.2 | 36.79% |  |  | 12062.1 | 15.62% |  |  | 8920.1 | 11.55% |  | 0 | 0%
|  | PGB330I*8*1*** | PB-548-01 | B1 | BEAM |  | 1 | 553 | 553 | 553 | 100% | 553 | 100% | 553 | 100% | 553 | 100% | 221.2 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330I*8*1*** | PB-548-01 | B2 | BEAM |  | 1 | 464.5 | 464.5 | 464.5 | 100% | 464.5 | 100% | 464.5 | 100% | 464.5 | 100% | 464.5 | 100% | 464.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6**** | PB-548-01 | B3 | BEAM |  | 2 | 262.8 | 525.6 | 525.6 | 100% | 525.6 | 100% | 525.6 | 100% | 525.6 | 100% | 525.6 | 100% | 525.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6**** | PB-548-01 | B4 | BEAM |  | 1 | 438.5 | 438.5 | 438.5 | 100% | 438.5 | 100% | 438.5 | 100% | 438.5 | 100% | 438.5 | 100% | 438.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6**** | PB-548-01 | B5 | BEAM |  | 1 | 354.4 | 354.4 | 354.4 | 100% | 354.4 | 100% | 354.4 | 100% | 354.4 | 100% | 354.4 | 100% | 354.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10**** | PB-548-01 | B6 | BEAM |  | 2 | 1571 | 3142 | 3142 | 100% | 3142 | 100% | 3142 | 100% | 3142 | 100% | 3142 | 100% | 3142 | 100% |  |  | 3142 | 100% |  |  | 0 |  |  | 0
|  | PGB450*10*2*** | PB-548-01 | B7 | BEAM |  | 2 | 1390.5 | 2781 | 2781 | 100% | 2781 | 100% | 2781 | 100% | 2781 | 100% | 2781 | 100% | 2781 | 100% |  |  | 2781 | 100% |  |  | 2781 | 100% | PL07 | 0
|  | PGB450*10*2*** | PB-548-01 | B8 | BEAM |  | 1 | 1414.3 | 1414.3 | 1414.3 | 100% | 1414.3 | 100% | 1414.3 | 100% | 1414.3 | 100% | 1414.3 | 100% | 1414.3 | 100% |  |  | 1414.3 | 100% |  |  | 1414.3 | 100% | PL07 | 0
|  | HEA180 | PB-548-01 | B9 | BEAM |  | 2 | 79.1 | 158.2 | 158.2 | 100% | 158.2 | 100% | 158.2 | 100% | 82.264 | 52% | 63.28 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330I*8*1*** | PB-548-01 | B10 | BEAM |  | 2 | 270.1 | 540.2 | 540.2 | 100% | 540.2 | 100% | 540.2 | 100% | 540.2 | 100% | 540.2 | 100% | 540.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B11 | BEAM |  | 3 | 130.1 | 390.3 | 390.3 | 100% | 390.3 | 100% | 390.3 | 100% | 390.3 | 100% | 390.3 | 100% | 390.3 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B12 | BEAM |  | 1 | 143.5 | 143.5 | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330II*8**** | PB-548-01 | B13 | BEAM |  | 1 | 2158.5 | 2158.5 | 2158.5 | 100% | 2158.5 | 100% | 2158.5 | 100% | 2158.5 | 100% | 863.4 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330II*8**** | PB-548-01 | B14 | BEAM |  | 1 | 2112 | 2112 | 2112 | 100% | 2112 | 100% | 2112 | 100% | 2112 | 100% | 844.8 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330II*8**** | PB-548-01 | B15 | BEAM |  | 1 | 1976.1 | 1976.1 | 1976.1 | 100% | 1976.1 | 100% | 1976.1 | 100% | 1976.1 | 100% | 790.44 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330II*8**** | PB-548-01 | B16 | BEAM |  | 1 | 1976.1 | 1976.1 | 1976.1 | 100% | 1976.1 | 100% | 1976.1 | 100% | 1976.1 | 100% | 1976.1 | 100% | 1976.1 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330II*8**** | PB-548-01 | B17 | BEAM |  | 1 | 2521.6 | 2521.6 | 2521.6 | 100% | 2521.6 | 100% | 2521.6 | 100% | 2521.6 | 100% | 2521.6 | 100% | 2521.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330II*8**** | PB-548-01 | B18 | BEAM |  | 1 | 2565.3 | 2565.3 | 2565.3 | 100% | 2565.3 | 100% | 2565.3 | 100% | 2565.3 | 100% | 1026.12 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330II*8**** | PB-548-01 | B19 | BEAM |  | 2 | 2240.3 | 4480.6 | 4480.6 | 100% | 4480.6 | 100% | 4480.6 | 100% | 4480.6 | 100% | 4480.6 | 100% | 4480.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B20 | BEAM |  | 2 | 358.2 | 716.4 | 716.4 | 100% | 716.4 | 100% | 716.4 | 100% | 716.4 | 100% | 716.4 | 100% | 716.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B21 | BEAM |  | 2 | 363.7 | 727.4 | 727.4 | 100% | 727.4 | 100% | 727.4 | 100% | 727.4 | 100% | 727.4 | 100% | 727.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B22 | BEAM |  | 6 | 367.1 | 2202.6 | 2202.6 | 100% | 2202.6 | 100% | 2202.6 | 100% | 2202.6 | 100% | 2202.6 | 100% | 2202.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB450*10*2*** | PB-548-01 | B23 | BEAM |  | 1 | 1684.8 | 1684.8 | 1684.8 | 100% | 1684.8 | 100% | 1684.8 | 100% | 1684.8 | 100% | 1684.8 | 100% | 1684.8 | 100% |  |  | 1684.8 | 100% |  |  | 1684.8 | 100% | PL07 | 0
|  | PGA274I*6*1*** | PB-548-01 | B24 | BEAM |  | 1 | 162.4 | 162.4 | 162.4 | 100% | 162.4 | 100% | 162.4 | 100% | 162.4 | 100% | 162.4 | 100% | 162.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B25 | BEAM |  | 1 | 175.7 | 175.7 | 175.7 | 100% | 175.7 | 100% | 175.7 | 100% | 175.7 | 100% | 175.7 | 100% | 175.7 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB450*10*2*** | PB-548-01 | B26 | BEAM |  | 1 | 1453.5 | 1453.5 | 1453.5 | 100% | 1453.5 | 100% | 1453.5 | 100% | 1453.5 | 100% | 1453.5 | 100% | 1453.5 | 100% |  |  | 1453.5 | 100% |  |  | 1453.5 | 100% | PL07 | 0
|  | PGA274I*6*1*** | PB-548-01 | B27 | BEAM |  | 1 | 168.4 | 168.4 | 168.4 | 100% | 168.4 | 100% | 168.4 | 100% | 168.4 | 100% | 168.4 | 100% | 168.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B28 | BEAM |  | 1 | 168.7 | 168.7 | 168.7 | 100% | 168.7 | 100% | 168.7 | 100% | 168.7 | 100% | 168.7 | 100% | 168.7 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*1*** | PB-548-01 | B29 | BEAM |  | 1 | 213 | 213 | 213 | 100% | 213 | 100% | 213 | 100% | 213 | 100% | 85.2 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB450*10*2*** | PB-548-01 | B30 | BEAM |  | 1 | 1586.5 | 1586.5 | 1586.5 | 100% | 1586.5 | 100% | 1586.5 | 100% | 1586.5 | 100% | 1586.5 | 100% | 1586.5 | 100% |  |  | 1586.5 | 100% |  |  | 1586.5 | 100% | PL07 | 0
|  | PGA274I*6*1*** | PB-548-01 | B31 | BEAM |  | 1 | 181.2 | 181.2 | 181.2 | 100% | 181.2 | 100% | 181.2 | 100% | 181.2 | 100% | 181.2 | 100% | 181.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*2*** | PB-548-01 | C1 | COLUMN |  | 1 | 1484.2 | 1484.2 | 1484.2 | 100% | 1484.2 | 100% | 1484.2 | 100% | 786.626 | 53% | 593.68 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*2*** | PB-548-01 | C2 | COLUMN |  | 1 | 1484.2 | 1484.2 | 1484.2 | 100% | 1484.2 | 100% | 1484.2 | 100% | 1484.2 | 100% | 32 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*2*** | PB-548-01 | C3 | COLUMN |  | 1 | 2871.1 | 2871.1 | 2871.1 | 100% | 2871.1 | 100% | 2871.1 | 100% | 2871.1 | 100% | 1148.44 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*2*** | PB-548-01 | C4 | COLUMN |  | 1 | 2888.1 | 2888.1 | 2888.1 | 100% | 2888.1 | 100% | 2888.1 | 100% | 2888.1 | 100% | 1155.24 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15**** | PB-548-01 | C5 | COLUMN |  | 1 | 3790.1 | 3790.1 | 3790.1 | 100% | 3790.1 | 100% | 3790.1 | 100% | 3790.1 | 100% | 1516.04 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15**** | PB-548-01 | C6 | COLUMN |  | 1 | 3790.1 | 3790.1 | 3790.1 | 100% | 3790.1 | 100% | 3790.1 | 100% | 3790.1 | 100% | 1516.04 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15**** | PB-548-01 | C7 | COLUMN |  | 1 | 3797.5 | 3797.5 | 3797.5 | 100% | 3797.5 | 100% | 3797.5 | 100% | 3797.5 | 100% | 1519 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15**** | PB-548-01 | C8 | COLUMN |  | 1 | 3797.5 | 3797.5 | 3797.5 | 100% | 3797.5 | 100% | 3797.5 | 100% | 3797.5 | 100% | 1519 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB1 | H BRACING |  | 1 | 86 | 86 | 86 | 100% | 86 | 100% | 86 | 100% | 44.72 | 52% | 34.4 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB2 | H BRACING |  | 1 | 111.2 | 111.2 | 111.2 | 100% | 111.2 | 100% | 111.2 | 100% | 57.824 | 52% | 44.48 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB3 | H BRACING |  | 1 | 107.6 | 107.6 | 107.6 | 100% | 107.6 | 100% | 107.6 | 100% | 55.952 | 52% | 43.04 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB4 | H BRACING |  | 2 | 97.2 | 194.4 | 194.4 | 100% | 194.4 | 100% | 194.4 | 100% | 101.088 | 52% | 77.76 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB5 | H BRACING |  | 8 | 89.8 | 718.4 | 718.4 | 100% | 718.4 | 100% | 718.4 | 100% | 373.568 | 52% | 287.36 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB6 | H BRACING |  | 8 | 93.1 | 744.8 | 744.8 | 100% | 744.8 | 100% | 744.8 | 100% | 387.296 | 52% | 297.92 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB7 | H BRACING |  | 40 | 78.1 | 3124 | 3124 | 100% | 3124 | 100% | 3124 | 100% | 1624.48 | 52% | 1249.6 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB8 | H BRACING |  | 1 | 77.4 | 77.4 | 77.4 | 100% | 77.4 | 100% | 77.4 | 100% | 40.248 | 52% | 30.96 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | HB9 | H BRACING |  | 4 | 122.4 | 489.6 | 489.6 | 100% | 489.6 | 100% | 489.6 | 100% | 254.592 | 52% | 195.84 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-01 | SU1 | SUPPORT |  | 1 | 34.5 | 34.5 | 34.5 | 100% | 34.5 | 100% | 34.5 | 100% | 17.94 | 52% | 13.8 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-01 | SU2 | SUPPORT |  | 16 | 36.4 | 582.4 | 582.4 | 100% | 582.4 | 100% | 582.4 | 100% | 302.848 | 52% | 232.96 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB1 | V BRACING |  | 2 | 245.1 | 490.2 | 490.2 | 100% | 490.2 | 100% | 490.2 | 100% | 254.904 | 52% | 196.08 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB2 | V BRACING |  | 2 | 270.3 | 540.6 | 540.6 | 100% | 540.6 | 100% | 540.6 | 100% | 281.112 | 52% | 216.24 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB3 | V BRACING |  | 2 | 269.2 | 538.4 | 538.4 | 100% | 538.4 | 100% | 538.4 | 100% | 279.968 | 52% | 215.36 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB4 | V BRACING |  | 2 | 247.8 | 495.6 | 495.6 | 100% | 495.6 | 100% | 495.6 | 100% | 257.712 | 52% | 198.24 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB5 | V BRACING |  | 2 | 369.3 | 738.6 | 738.6 | 100% | 738.6 | 100% | 738.6 | 100% | 384.072 | 52% | 295.44 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB6 | V BRACING |  | 2 | 350 | 700 | 700 | 100% | 700 | 100% | 700 | 100% | 364 | 52% | 280 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB7 | V BRACING |  | 6 | 306.4 | 1838.4 | 1838.4 | 100% | 1838.4 | 100% | 1838.4 | 100% | 955.968 | 52% | 735.36 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-548-01 | VB8 | V BRACING |  | 2 | 51.8 | 103.6 | 103.6 | 100% | 103.6 | 100% | 103.6 | 100% | 53.872 | 52% | 41.44 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-01 | VB9 | V BRACING |  | 4 | 309 | 1236 | 1236 | 100% | 1236 | 100% | 1236 | 100% | 642.72 | 52% | 494.4 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | VB10 | V BRACING |  | 2 | 81.7 | 163.4 | 163.4 | 100% | 163.4 | 100% | 163.4 | 100% | 84.968 | 52% | 65.36 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | VB11 | V BRACING |  | 2 | 81.4 | 162.8 | 162.8 | 100% | 162.8 | 100% | 162.8 | 100% | 84.656 | 52% | 65.12 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | VB12 | V BRACING |  | 4 | 80.7 | 322.8 | 322.8 | 100% | 322.8 | 100% | 322.8 | 100% | 167.856 | 52% | 129.12 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-01 | VB13 | V BRACING |  | 2 | 85.7 | 171.4 | 171.4 | 100% | 171.4 | 100% | 171.4 | 100% | 89.128 | 52% | 68.56 | 40% | 0 | 0% |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 16X50 | BOLT |  | 64 | 0.103 | 6.592 | 6.592 | 100% | 6.592 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 16X60 | BOLT |  | 12 | 0.117 | 1.404 | 1.404 | 100% | 1.404 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 20X60 | BOLT |  | 160 | 0.196 | 31.36 | 31.36 | 100% | 31.36 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 24X65 | BOLT |  | 160 | 0.319 | 51.04 | 51.04 | 100% | 51.04 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 24X75 | BOLT |  | 12 | 0.348 | 4.176 | 4.176 | 100% | 4.176 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 24X85 | BOLT |  | 48 | 0.378 | 18.144 | 18.144 | 100% | 18.144 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 27X70 | BOLT |  | 1320 | 0.454 | 599.28 | 599.28 | 100% | 599.28 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 27X95 | BOLT |  | 164 | 0.55 | 90.2 | 90.2 | 100% | 90.2 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 30X100 | BOLT |  | 56 | 0.732 | 40.992 | 40.992 | 100% | 40.992 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 30X115 | BOLT |  | 192 | 0.802 | 153.984 | 153.984 | 100% | 153.984 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-01 | BOLT 30X95 | BOLT |  | 560 | 0.708 | 396.48 | 396.48 | 100% | 396.48 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | [5 empty] | 181686.8108 | 181686.8108 | 100% | 181686.8108 | 100% | 177808.82 | 97.87% | 163825.7 | 90.17% | 119133.5 | 65.57% | 107886.2 | 59.38% |  |  | 64164 | 35.32% |  |  | 47966.3 | 26.4% |  | 0
|  | PGB450*10*25*300 | PB-548-02 | B1 | BEAM |  | 1 | 1513.5 | 1513.5 | 1513.5 | 100% | 1513.5 | 100% | 1513.5 | 100% | 1513.5 | 100% | 1513.5 | 100% | 1513.5 | 100% |  |  | 1513.5 | 100% |  |  | 1513.5 | 100% | PL 04 | 0
|  | PGB450*10*25*300 | PB-548-02 | B3 | BEAM |  | 1 | 1746 | 1746 | 1746 | 100% | 1746 | 100% | 1746 | 100% | 1746 | 100% | 1746 | 100% | 1746 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB450*10*25*300 | PB-548-02 | B4 | BEAM |  | 1 | 1564.8 | 1564.8 | 1564.8 | 100% | 1564.8 | 100% | 1564.8 | 100% | 1564.8 | 100% | 1564.8 | 100% | 1564.8 | 100% |  |  | 1564.8 | 100% |  |  | 1564.8 | 100% | PL 07 | 0
|  | PGB450*10*25*300 | PB-548-02 | B5 | BEAM |  | 1 | 1432.9 | 1432.9 | 1432.9 | 100% | 1432.9 | 100% | 1432.9 | 100% | 1432.9 | 100% | 1432.9 | 100% | 1432.9 | 100% |  |  | 1432.9 | 100% |  |  | 1432.9 | 100% | PL 04 | 0
|  | PGB415*10*20*300 | PB-548-02 | B8 | BEAM |  | 4 | 607.7 | 2430.8 | 2430.8 | 100% | 2430.8 | 100% | 2430.8 | 100% | 2430.8 | 100% | 2430.8 | 100% | 2430.8 | 100% |  |  | 2430.8 | 100% |  |  | 0 |  |  | 0
|  | PGB330I*8*15*250 | PB-548-02 | B9 | BEAM |  | 2 | 553 | 1106 | 1106 | 100% | 1106 | 100% | 1106 | 100% | 1106 | 100% | 1106 | 100% | 1106 | 100% |  |  | 1106 | 100% |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PB-548-02 | B10 | BEAM |  | 2 | 438.5 | 877 | 877 | 100% | 877 | 100% | 877 | 100% | 877 | 100% | 877 | 100% | 877 | 100% |  |  | 877 | 100% |  |  | 438.5 | 50% | PL 07 | 0
|  | PGA274I*6*12*200 | PB-548-02 | B11 | BEAM |  | 2 | 122 | 244 | 244 | 100% | 244 | 100% | 244 | 100% | 244 | 100% | 244 | 100% | 244 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B15 | BEAM |  | 1 | 176.8 | 176.8 | 176.8 | 100% | 176.8 | 100% | 176.8 | 100% | 176.8 | 100% | 176.8 | 100% | 176.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B17 | BEAM |  | 2 | 179.5 | 359 | 359 | 100% | 359 | 100% | 359 | 100% | 359 | 100% | 359 | 100% | 359 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB450*10*25*300 | PB-548-02 | B18 | BEAM |  | 1 | 1935.2 | 1935.2 | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% |  |  | 1935.2 | 100% |  |  | 1935.2 | 100% | PL06 | 0
|  | PGB330II*8*15*300 | PB-548-02 | B19 | BEAM |  | 1 | 1054.8 | 1054.8 | 1054.8 | 100% | 1054.8 | 100% | 1054.8 | 100% | 1054.8 | 100% | 1054.8 | 100% | 1054.8 | 100% |  |  | 1054.8 | 100% |  |  | 1054.8 | 100% | PL 04 | 0
|  | PGB330II*8*15*300 | PB-548-02 | B20 | BEAM |  | 1 | 1056.7 | 1056.7 | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% |  |  | 1056.7 | 100% |  |  | 1056.7 | 100% | PL 04 | 0
|  | PGB330II*8*15*300 | PB-548-02 | B21 | BEAM |  | 1 | 1056.7 | 1056.7 | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% | 1056.7 | 100% |  |  | 1056.7 | 100% |  |  | 1056.7 | 100% | PL 04 | 0
|  | PGB330II*8*15*300 | PB-548-02 | B33 | BEAM |  | 1 | 1080.5 | 1080.5 | 1080.5 | 100% | 1080.5 | 100% | 1080.5 | 100% | 1080.5 | 100% | 1080.5 | 100% | 1080.5 | 100% |  |  | 1080.5 | 100% |  |  | 1080.5 | 100% | PL 04 | 0
|  | PGB450*10*25*300 | PB-548-02 | B34 | BEAM |  | 1 | 1915.1 | 1915.1 | 1915.1 | 100% | 1915.1 | 100% | 1915.1 | 100% | 1915.1 | 100% | 1915.1 | 100% | 1915.1 | 100% |  |  | 1915.1 | 100% |  |  | 1915.1 | 100% | PL 04 | 0
|  | PGB450*10*25*300 | PB-548-02 | B35 | BEAM |  | 1 | 3269.2 | 3269.2 | 3269.2 | 100% | 3269.2 | 100% | 3269.2 | 100% | 3269.2 | 100% | 0 | 0% | 0 |  |  |  | 3269.2 | 100% |  |  | 0 |  |  | 0
|  | PGB450*10*25*300 | PB-548-02 | B38 | BEAM |  | 1 | 1951.5 | 1951.5 | 1951.5 | 100% | 1951.5 | 100% | 1951.5 | 100% | 1951.5 | 100% | 1951.5 | 100% | 1951.5 | 100% |  |  | 1951.5 | 100% |  |  | 1951.5 | 100% | PL 04 | 0
|  | PGB450*10*25*300 | PB-548-02 | B39 | BEAM |  | 1 | 1968.8 | 1968.8 | 1968.8 | 100% | 1968.8 | 100% | 1968.8 | 100% | 1968.8 | 100% | 1968.8 | 100% | 1968.8 | 100% |  |  | 1968.8 | 100% |  |  | 1968.8 | 100% | PL06 | 0
|  | PGB450*10*25*300 | PB-548-02 | B40 | BEAM |  | 1 | 2501.8 | 2501.8 | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% |  |  | 2501.8 | 100% |  |  | 2501.8 | 100% | PL05 | 0
|  | PGB450*10*25*300 | PB-548-02 | B41 | BEAM |  | 1 | 2501.8 | 2501.8 | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% | 2501.8 | 100% |  |  | 2501.8 | 100% |  |  | 2501.8 | 100% | PL06 | 0
|  | PGB450*10*25*300 | PB-548-02 | B42 | BEAM |  | 1 | 2305.2 | 2305.2 | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% |  |  | 2305.2 | 100% |  |  | 2305.2 | 100% | PL05 | 0
|  | PGB450*10*25*300 | PB-548-02 | B43 | BEAM |  | 1 | 2305.2 | 2305.2 | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% | 2305.2 | 100% |  |  | 2305.2 | 100% |  |  | 2305.2 | 100% | PL05 | 0
|  | PGB450*10*25*300 | PB-548-02 | B45 | BEAM |  | 1 | 3315.2 | 3315.2 | 3315.2 | 100% | 3315.2 | 100% | 3315.2 | 100% | 3315.2 | 100% | 3315.2 | 100% | 3315.2 | 100% |  |  | 3315.2 | 100% |  |  | 0 |  |  | 0
|  | PGB450*10*25*300 | PB-548-02 | B46 | BEAM |  | 2 | 2199.7 | 4399.4 | 4399.4 | 100% | 4399.4 | 100% | 4399.4 | 100% | 4399.4 | 100% | 4399.4 | 100% | 4399.4 | 100% |  |  | 2199.7 | 50% |  |  | 2199.7 | 50% | PL05 | 0
|  | PGA274I*6*12*200 | PB-548-02 | B47 | BEAM |  | 1 | 180.6 | 180.6 | 180.6 | 100% | 180.6 | 100% | 180.6 | 100% | 180.6 | 100% | 180.6 | 100% | 180.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B49 | BEAM |  | 4 | 371.7 | 1486.8 | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% |  |  | 371.7 | 25% |  |  | 371.7 | 25% | PL 04 | 0
|  | PGA274I*6*12*200 | PB-548-02 | B50 | BEAM |  | 4 | 367.1 | 1468.4 | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% |  |  | 734.2 | 50% |  |  | 734.2 | 50% | PL 04 | 0
|  | PGB330I*8*15*250 | PB-548-02 | B52 | BEAM |  | 4 | 483.8 | 1935.2 | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% |  |  | 1451.4 | 75% |  |  | 1451.4 | 75% | PL06 , PL07 | 0
|  | PGB330I*8*15*250 | PB-548-02 | B53 | BEAM |  | 4 | 479.2 | 1916.8 | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% |  |  | 958.4 | 50% |  |  | 958.4 | 50% | PL 04 | 0
|  | PGA274I*6*12*200 | PB-548-02 | B58 | BEAM |  | 2 | 160.7 | 321.4 | 321.4 | 100% | 321.4 | 100% | 321.4 | 100% | 321.4 | 100% | 321.4 | 100% | 321.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PB-548-02 | C3 | COLUMN |  | 1 | 1660.6 | 1660.6 | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% |  |  | 1660.6 | 100% |  |  | 1660.6 | 100% | PL06 | 0
|  | PGC425*10*25*300 | PB-548-02 | C4 | COLUMN |  | 1 | 1660.6 | 1660.6 | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% | 1660.6 | 100% |  |  | 1660.6 | 100% |  |  | 1660.6 | 100% | PL06 | 0
|  | PGC425*10*25*300 | PB-548-02 | C5 | COLUMN |  | 1 | 1672.6 | 1672.6 | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% |  |  | 1672.6 | 100% |  |  | 1672.6 | 100% | PL06 | 0
|  | PGC425*10*25*300 | PB-548-02 | C6 | COLUMN |  | 1 | 1672.6 | 1672.6 | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% | 1672.6 | 100% |  |  | 1672.6 | 100% |  |  | 1672.6 | 100% | PL06 | 0
|  | PGC425*10*25*300 | PB-548-02 | C9 | COLUMN |  | 1 | 2822.5 | 2822.5 | 2822.5 | 100% | 2822.5 | 100% | 2822.5 | 100% | 2822.5 | 100% | 2822.5 | 100% | 2822.5 | 100% |  |  | 2822.5 | 100% |  |  | 2822.5 | 100% | PL05 | 0
|  | PGC425*10*25*300 | PB-548-02 | C10 | COLUMN |  | 1 | 2840.9 | 2840.9 | 2840.9 | 100% | 2840.9 | 100% | 2840.9 | 100% | 2840.9 | 100% | 2840.9 | 100% | 2840.9 | 100% |  |  | 2840.9 | 100% |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PB-548-02 | C11 | COLUMN |  | 1 | 2797.1 | 2797.1 | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% |  |  | 2797.1 | 100% |  |  | 2797.1 | 100% | PL05 | 0
|  | PGC425*10*25*300 | PB-548-02 | C12 | COLUMN |  | 1 | 2797.1 | 2797.1 | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% | 2797.1 | 100% |  |  | 2797.1 | 100% |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB1 | H BRACING |  | 80 | 78.1 | 6248 | 6248 | 100% | 6248 | 100% | 6248 | 100% | 6248 | 100% | 6248 | 100% | 6248 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB4 | H BRACING |  | 2 | 98.9 | 197.8 | 197.8 | 100% | 197.8 | 100% | 197.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB6 | H BRACING |  | 2 | 94.8 | 189.6 | 189.6 | 100% | 189.6 | 100% | 189.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB7 | H BRACING |  | 1 | 96.3 | 96.3 | 96.3 | 100% | 96.3 | 100% | 96.3 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB8 | H BRACING |  | 1 | 96.3 | 96.3 | 96.3 | 100% | 96.3 | 100% | 96.3 | 100% | 96.3 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL25*300 | PB-548-02 | SP1 | PLATE |  | 16 | 63.6 | 1017.6 | 1017.6 | 100% | 1017.6 | 100% | 1017.6 | 100% | 1017.6 | 100% | 1017.6 | 100% | 1017.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL25*120 | PB-548-02 | SP2 | PLATE |  | 32 | 25.4 | 812.8 | 812.8 | 100% | 812.8 | 100% | 812.8 | 100% | 812.8 | 100% | 812.8 | 100% | 812.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL12*325 | PB-548-02 | SP3 | PLATE |  | 16 | 11 | 176 | 176 | 100% | 176 | 100% | 176 | 100% | 176 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-02 | SU1 | SUPPORT |  | 1 | 38.8 | 38.8 | 38.8 | 100% | 38.8 | 100% | 38.8 | 100% | 38.8 | 100% | 38.8 | 100% | 38.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-02 | SU2 | SUPPORT |  | 17 | 36.8 | 625.6 | 625.6 | 100% | 625.6 | 100% | 625.6 | 100% | 625.6 | 100% | 625.6 | 100% | 625.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-02 | SU3 | SUPPORT |  | 4 | 38.6 | 154.4 | 154.4 | 100% | 154.4 | 100% | 154.4 | 100% | 154.4 | 100% | 154.4 | 100% | 154.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB1 | V BRACING |  | 4 | 248.3 | 993.2 | 993.2 | 100% | 993.2 | 100% | 993.2 | 100% | 993.2 | 100% | 993.2 | 100% | 993.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB6 | V BRACING |  | 2 | 302.8 | 605.6 | 605.6 | 100% | 605.6 | 100% | 605.6 | 100% | 605.6 | 100% | 605.6 | 100% | 605.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB7 | V BRACING |  | 2 | 308.5 | 617 | 617 | 100% | 617 | 100% | 617 | 100% | 617 | 100% | 617 | 100% | 617 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB8 | V BRACING |  | 2 | 302.1 | 604.2 | 604.2 | 100% | 604.2 | 100% | 604.2 | 100% | 604.2 | 100% | 604.2 | 100% | 604.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB9 | V BRACING |  | 8 | 302.9 | 2423.2 | 2423.2 | 100% | 2423.2 | 100% | 2423.2 | 100% | 2423.2 | 100% | 2423.2 | 100% | 2423.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB10 | V BRACING |  | 4 | 302.5 | 1210 | 1210 | 100% | 1210 | 100% | 1210 | 100% | 1210 | 100% | 1210 | 100% | 1210 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB11 | V BRACING |  | 2 | 295.8 | 591.6 | 591.6 | 100% | 591.6 | 100% | 591.6 | 100% | 591.6 | 100% | 591.6 | 100% | 591.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | VB13 | V BRACING |  | 2 | 77.4 | 154.8 | 154.8 | 100% | 154.8 | 100% | 154.8 | 100% | 154.8 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | VB14 | V BRACING |  | 10 | 74.3 | 743 | 743 | 100% | 743 | 100% | 743 | 100% | 743 | 100% | 743 | 100% | 743 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | VB15 | V BRACING |  | 2 | 78.9 | 157.8 | 157.8 | 100% | 157.8 | 100% | 157.8 | 100% | 157.8 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | VB16 | V BRACING |  | 2 | 74.1 | 148.2 | 148.2 | 100% | 148.2 | 100% | 148.2 | 100% | 148.2 | 100% | 148.2 | 100% | 148.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB450*10*25*300 | PB-548-02 | B2 | BEAM |  | 2 | 1390.5 | 2781 | 2781 | 100% | 2781 | 100% | 2781 | 100% | 2781 | 100% | 2781 | 100% | 2781 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB450*10*25*300 | PB-548-02 | B6 | BEAM |  | 1 | 1420.5 | 1420.5 | 1420.5 | 100% | 1420.5 | 100% | 1420.5 | 100% | 1420.5 | 100% | 1420.5 | 100% | 1420.5 | 100% |  |  | 1420.5 | 100% |  |  | 1420.5 | 100% | PL07 | 0
|  | PGB450*10*25*300 | PB-548-02 | B7 | BEAM |  | 1 | 1452.2 | 1452.2 | 1452.2 | 100% | 1452.2 | 100% | 1452.2 | 100% | 1452.2 | 100% | 1452.2 | 100% | 1452.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B12 | BEAM |  | 3 | 128.6 | 385.8 | 385.8 | 100% | 385.8 | 100% | 385.8 | 100% | 385.8 | 100% | 385.8 | 100% | 385.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B13 | BEAM |  | 1 | 143.5 | 143.5 | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% | 143.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B14 | BEAM |  | 1 | 215.6 | 215.6 | 215.6 | 100% | 215.6 | 100% | 215.6 | 100% | 215.6 | 100% | 215.6 | 100% | 215.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B16 | BEAM |  | 1 | 181.3 | 181.3 | 181.3 | 100% | 181.3 | 100% | 181.3 | 100% | 181.3 | 100% | 181.3 | 100% | 181.3 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B22 | BEAM |  | 1 | 2951.3 | 2951.3 | 2951.3 | 100% | 2951.3 | 100% | 2951.3 | 100% | 2951.3 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B23 | BEAM |  | 1 | 2491.1 | 2491.1 | 2491.1 | 100% | 2491.1 | 100% | 2491.1 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B24 | BEAM |  | 1 | 1708.1 | 1708.1 | 1708.1 | 100% | 1708.1 | 100% | 1708.1 | 100% | 1708.1 | 100% | 1708.1 | 100% | 1708.1 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B25 | BEAM |  | 1 | 1619.1 | 1619.1 | 1619.1 | 100% | 1619.1 | 100% | 1619.1 | 100% | 1619.1 | 100% | 1619.1 | 100% | 1619.1 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B26 | BEAM |  | 1 | 3363.8 | 3363.8 | 3363.8 | 100% | 3363.8 | 100% | 3363.8 | 100% | 3363.8 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B27 | BEAM |  | 1 | 3363.8 | 3363.8 | 3363.8 | 100% | 3363.8 | 100% | 3363.8 | 100% | 3363.8 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B28 | BEAM |  | 1 | 3058.9 | 3058.9 | 3058.9 | 100% | 3058.9 | 100% | 3058.9 | 100% | 3058.9 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B29 | BEAM |  | 1 | 3058.9 | 3058.9 | 3058.9 | 100% | 3058.9 | 100% | 3058.9 | 100% | 3058.9 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B30 | BEAM |  | 1 | 2538.7 | 2538.7 | 2538.7 | 100% | 2538.7 | 100% | 2538.7 | 100% | 2538.7 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B31 | BEAM |  | 1 | 3011.5 | 3011.5 | 3011.5 | 100% | 3011.5 | 100% | 3011.5 | 100% | 3011.5 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B32 | BEAM |  | 1 | 3411.9 | 3411.9 | 3411.9 | 100% | 3411.9 | 100% | 3411.9 | 100% | 3411.9 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B36 | BEAM |  | 1 | 2300.5 | 2300.5 | 2300.5 | 100% | 2300.5 | 100% | 2300.5 | 100% | 2300.5 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B37 | BEAM |  | 1 | 2300.5 | 2300.5 | 2300.5 | 100% | 2300.5 | 100% | 2300.5 | 100% | 2300.5 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B44 | BEAM |  | 1 | 3439.1 | 3439.1 | 3439.1 | 100% | 3439.1 | 100% | 3439.1 | 100% | 3439.1 | 100% | 3439.1 | 100% | 3439.1 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B48 | BEAM |  | 1 | 180.6 | 180.6 | 180.6 | 100% | 180.6 | 100% | 180.6 | 100% | 180.6 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B49 | BEAM |  | 4 | 371.7 | 1486.8 | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% | 1486.8 | 100% |  |  | 1115.1 | 75% |  |  | 1115.1 | 75% | PL06 , PL07 | 0
|  | PGA274I*6*12*200 | PB-548-02 | B50 | BEAM |  | 4 | 367.1 | 1468.4 | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% | 1468.4 | 100% |  |  | 367.1 | 25% |  |  | 367.1 | 25% | PL06 | 0
|  | PGA274I*6*12*200 | PB-548-02 | B51 | BEAM |  | 1 | 372 | 372 | 372 | 100% | 372 | 100% | 372 | 100% | 372 | 100% | 372 | 100% | 372 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330I*8*15*250 | PB-548-02 | B52 | BEAM |  | 4 | 483.8 | 1935.2 | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% | 1935.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330I*8*15*250 | PB-548-02 | B53 | BEAM |  | 4 | 479.2 | 1916.8 | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% | 1916.8 | 100% |  |  | 479.2 | 25% |  |  | 479.2 | 25% | PL07 | 0
|  | PGB330I*8*15*250 | PB-548-02 | B54 | BEAM |  | 1 | 484.1 | 484.1 | 484.1 | 100% | 484.1 | 100% | 484.1 | 100% | 484.1 | 100% | 484.1 | 100% | 484.1 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B55 | BEAM |  | 1 | 170 | 170 | 170 | 100% | 170 | 100% | 170 | 100% | 170 | 100% | 170 | 100% | 170 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B56 | BEAM |  | 1 | 164.2 | 164.2 | 164.2 | 100% | 164.2 | 100% | 164.2 | 100% | 164.2 | 100% | 164.2 | 100% | 164.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-548-02 | B57 | BEAM |  | 1 | 165.4 | 165.4 | 165.4 | 100% | 165.4 | 100% | 132.32 | 80% | 165.4 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB550I*10*25*300 | PB-548-02 | B59 | BEAM |  | 2 | 1571 | 3142 | 3142 | 100% | 3142 | 100% | 3142 | 100% | 3142 | 100% | 3142 | 100% | 3142 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGB330I*8*15*250 | PB-548-02 | B60 | BEAM |  | 2 | 267.7 | 535.4 | 535.4 | 100% | 535.4 | 100% | 535.4 | 100% | 535.4 | 100% | 535.4 | 100% | 535.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PB-548-02 | C1 | COLUMN |  | 1 | 3745.1 | 3745.1 | 3745.1 | 100% | 3745.1 | 100% | 3745.1 | 100% | 3745.1 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PB-548-02 | C2 | COLUMN |  | 1 | 3745.1 | 3745.1 | 3745.1 | 100% | 3745.1 | 100% | 3745.1 | 100% | 3745.1 | 100% | 3745.1 | 100% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PB-548-02 | C7 | COLUMN |  | 1 | 3751.1 | 3751.1 | 3751.1 | 100% | 3751.1 | 100% | 3751.1 | 100% | 3751.1 | 100% | 3751.1 | 100% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PB-548-02 | C8 | COLUMN |  | 1 | 3751.1 | 3751.1 | 3751.1 | 100% | 3751.1 | 100% | 3751.1 | 100% | 3751.1 | 100% | 3751.1 | 100% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB1 | H BRACING |  | 72 | 78.1 | 5623.2 | 5623.2 | 100% | 5623.2 | 100% | 5623.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB2 | H BRACING |  | 4 | 122.4 | 489.6 | 489.6 | 100% | 489.6 | 100% | 489.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB3 | H BRACING |  | 1 | 106.5 | 106.5 | 106.5 | 100% | 106.5 | 100% | 106.5 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB4 | H BRACING |  | 2 | 98.9 | 197.8 | 197.8 | 100% | 197.8 | 100% | 197.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB5 | H BRACING |  | 1 | 102.9 | 102.9 | 102.9 | 100% | 102.9 | 100% | 102.9 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB9 | H BRACING |  | 1 | 87.4 | 87.4 | 87.4 | 100% | 87.4 | 100% | 87.4 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB10 | H BRACING |  | 4 | 70.8 | 283.2 | 283.2 | 100% | 283.2 | 100% | 283.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | HB11 | H BRACING |  | 1 | 78.6 | 78.6 | 78.6 | 100% | 78.6 | 100% | 78.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL25*300 | PB-548-02 | SP1 | PLATE |  | 16 | 63.6 | 1017.6 | 1017.6 | 100% | 1017.6 | 100% | 1017.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL25*120 | PB-548-02 | SP2 | PLATE |  | 32 | 25.4 | 812.8 | 812.8 | 100% | 812.8 | 100% | 812.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL12*440 | PB-548-02 | SP4 | PLATE |  | 16 | 12 | 192 | 192 | 100% | 192 | 100% | 192 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-02 | SU1 | SUPPORT |  | 1 | 38.8 | 38.8 | 38.8 | 100% | 38.8 | 100% | 38.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-02 | SU2 | SUPPORT |  | 1 | 36.8 | 36.8 | 36.8 | 100% | 36.8 | 100% | 36.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-548-02 | SU4 | SUPPORT |  | 19 | 35.2 | 668.8 | 668.8 | 100% | 668.8 | 100% | 668.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB1 | V BRACING |  | 4 | 248.3 | 993.2 | 993.2 | 100% | 993.2 | 100% | 993.2 | 100% | 993.2 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB2 | V BRACING |  | 2 | 277 | 554 | 554 | 100% | 554 | 100% | 554 | 100% | 554 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB3 | V BRACING |  | 2 | 247 | 494 | 494 | 100% | 494 | 100% | 494 | 100% | 494 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | VB4 | V BRACING |  | 4 | 76.1 | 304.4 | 304.4 | 100% | 304.4 | 100% | 304.4 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PB-548-02 | VB5 | V BRACING |  | 18 | 297 | 5346 | 5346 | 100% | 5346 | 100% | 5346 | 100% | 5346 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L100*10 | PB-548-02 | VB12 | V BRACING |  | 14 | 71.5 | 1001 | 1001 | 100% | 1001 | 100% | 1001 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 16X45 | BOLT |  | 8 | 0.0971 | 0.7768 | 0.7768 | 100% | 0.7768 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 16X50 | BOLT |  | 16 | 0.103 | 1.648 | 1.648 | 100% | 1.648 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 16X60 | BOLT |  | 148 | 0.117 | 17.316 | 17.316 | 100% | 17.316 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 20X60 | BOLT |  | 528 | 0.196 | 103.488 | 103.488 | 100% | 103.488 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 20X65 | BOLT |  | 224 | 0.207 | 46.368 | 46.368 | 100% | 46.368 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 24X65 | BOLT |  | 280 | 0.319 | 89.32 | 89.32 | 100% | 89.32 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 24X70 | BOLT |  | 128 | 0.334 | 42.752 | 42.752 | 100% | 42.752 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 24X85 | BOLT |  | 48 | 0.378 | 18.144 | 18.144 | 100% | 18.144 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 27X70 | BOLT |  | 3440 | 0.454 | 1561.76 | 1561.76 | 100% | 1561.76 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 27X95 | BOLT |  | 438 | 0.55 | 240.9 | 240.9 | 100% | 240.9 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 27X105 | BOLT |  | 30 | 0.589 | 17.67 | 17.67 | 100% | 17.67 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 27X115 | BOLT |  | 768 | 0.628 | 482.304 | 482.304 | 100% | 482.304 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 30X95 | BOLT |  | 1400 | 0.708 | 991.2 | 991.2 | 100% | 991.2 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-548-02 | BOLT 30X115 | BOLT |  | 288 | 0.803 | 231.264 | 231.264 | 100% | 231.264 | 100% | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | [5 empty] | 70335.4798 | 70335.4798 | 100% | 70335.4798 | 100% | 70335.4798 | 100% | 60841.6388 | 86.5% | 32473.619 | 46.17% | 20592 | 29.28% |  |  | 0 | 0% |  |  | 0 | 0% |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B1 | BEAM |  | 1 | 390.6 | 390.6 | 390.6 | 100% | 390.6 | 100% | 390.6 | 100% | 234.36 | 60% | 167.958 | 43% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B2 | BEAM |  | 1 | 394.5 | 394.5 | 394.5 | 100% | 394.5 | 100% | 394.5 | 100% | 394.5 | 100% | 394.5 | 100% | 394.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B3 | BEAM |  | 1 | 367.8 | 367.8 | 367.8 | 100% | 367.8 | 100% | 367.8 | 100% | 367.8 | 100% | 367.8 | 100% | 367.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B4 | BEAM |  | 1 | 457 | 457 | 457 | 100% | 457 | 100% | 457 | 100% | 457 | 100% | 457 | 100% | 457 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B5 | BEAM |  | 1 | 385.4 | 385.4 | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B6 | BEAM |  | 1 | 428.8 | 428.8 | 428.8 | 100% | 428.8 | 100% | 428.8 | 100% | 257.28 | 60% | 184.384 | 43% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B7 | BEAM |  | 2 | 300.1 | 600.2 | 600.2 | 100% | 600.2 | 100% | 600.2 | 100% | 600.2 | 100% | 600.2 | 100% | 600.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B8 | BEAM |  | 1 | 240.6 | 240.6 | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B9 | BEAM |  | 1 | 348 | 348 | 348 | 100% | 348 | 100% | 348 | 100% | 348 | 100% | 348 | 100% | 348 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B10 | BEAM |  | 1 | 348 | 348 | 348 | 100% | 348 | 100% | 348 | 100% | 348 | 100% | 348 | 100% | 348 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B11 | BEAM |  | 1 | 368.3 | 368.3 | 368.3 | 100% | 368.3 | 100% | 368.3 | 100% | 368.3 | 100% | 368.3 | 100% | 368.3 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B12 | BEAM |  | 1 | 403.6 | 403.6 | 403.6 | 100% | 403.6 | 100% | 403.6 | 100% | 403.6 | 100% | 403.6 | 100% | 403.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B13 | BEAM |  | 1 | 395.7 | 395.7 | 395.7 | 100% | 395.7 | 100% | 395.7 | 100% | 395.7 | 100% | 395.7 | 100% | 395.7 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B14 | BEAM |  | 1 | 367.5 | 367.5 | 367.5 | 100% | 367.5 | 100% | 367.5 | 100% | 367.5 | 100% | 158.025 | 43% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B15 | BEAM |  | 1 | 289.6 | 289.6 | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PR-502-06 | B16 | BEAM |  | 1 | 289.6 | 289.6 | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% | 289.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B17 | BEAM |  | 1 | 97.7 | 97.7 | 97.7 | 100% | 97.7 | 100% | 97.7 | 100% | 97.7 | 100% | 97.7 | 100% | 97.7 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B18 | BEAM |  | 2 | 332.3 | 664.6 | 664.6 | 100% | 664.6 | 100% | 664.6 | 100% | 664.6 | 100% | 664.6 | 100% | 664.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B19 | BEAM |  | 1 | 105.5 | 105.5 | 105.5 | 100% | 105.5 | 100% | 105.5 | 100% | 105.5 | 100% | 105.5 | 100% | 105.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B20 | BEAM |  | 2 | 885.3 | 1770.6 | 1770.6 | 100% | 1770.6 | 100% | 1770.6 | 100% | 1770.6 | 100% | 761.358 | 43% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PR-502-06 | B21 | BEAM |  | 1 | 22.1 | 22.1 | 22.1 | 100% | 22.1 | 100% | 22.1 | 100% | 13.26 | 60% | 9.503 | 43% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B22 | BEAM |  | 1 | 538.6 | 538.6 | 538.6 | 100% | 538.6 | 100% | 538.6 | 100% | 538.6 | 100% | 538.6 | 100% | 538.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B23 | BEAM |  | 1 | 557.6 | 557.6 | 557.6 | 100% | 557.6 | 100% | 557.6 | 100% | 557.6 | 100% | 239.768 | 43% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B24 | BEAM |  | 1 | 117.2 | 117.2 | 117.2 | 100% | 117.2 | 100% | 117.2 | 100% | 117.2 | 100% | 117.2 | 100% | 117.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B25 | BEAM |  | 2 | 175 | 350 | 350 | 100% | 350 | 100% | 350 | 100% | 350 | 100% | 350 | 100% | 350 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B26 | BEAM |  | 1 | 110.8 | 110.8 | 110.8 | 100% | 110.8 | 100% | 110.8 | 100% | 110.8 | 100% | 110.8 | 100% | 110.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B27 | BEAM |  | 1 | 125.6 | 125.6 | 125.6 | 100% | 125.6 | 100% | 125.6 | 100% | 125.6 | 100% | 125.6 | 100% | 125.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B28 | BEAM |  | 1 | 429 | 429 | 429 | 100% | 429 | 100% | 429 | 100% | 429 | 100% | 429 | 100% | 429 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B29 | BEAM |  | 1 | 349.6 | 349.6 | 349.6 | 100% | 349.6 | 100% | 349.6 | 100% | 349.6 | 100% | 349.6 | 100% | 349.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B30 | BEAM |  | 1 | 409.1 | 409.1 | 409.1 | 100% | 409.1 | 100% | 409.1 | 100% | 245.46 | 60% | 175.913 | 43% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B31 | BEAM |  | 1 | 403.4 | 403.4 | 403.4 | 100% | 403.4 | 100% | 403.4 | 100% | 403.4 | 100% | 121.02 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B32 | BEAM |  | 2 | 375.2 | 750.4 | 750.4 | 100% | 750.4 | 100% | 750.4 | 100% | 450.24 | 60% | 225.12 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B33 | BEAM |  | 1 | 424.4 | 424.4 | 424.4 | 100% | 424.4 | 100% | 424.4 | 100% | 254.64 | 60% | 127.32 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B34 | BEAM |  | 1 | 375.2 | 375.2 | 375.2 | 100% | 375.2 | 100% | 375.2 | 100% | 225.12 | 60% | 112.56 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B35 | BEAM |  | 1 | 112.2 | 112.2 | 112.2 | 100% | 112.2 | 100% | 112.2 | 100% | 112.2 | 100% | 112.2 | 100% | 112.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B36 | BEAM |  | 1 | 117 | 117 | 117 | 100% | 117 | 100% | 117 | 100% | 117 | 100% | 117 | 100% | 117 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B37 | BEAM |  | 1 | 125.2 | 125.2 | 125.2 | 100% | 125.2 | 100% | 125.2 | 100% | 125.2 | 100% | 125.2 | 100% | 125.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B38 | BEAM |  | 1 | 132.6 | 132.6 | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% | 132.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B39 | BEAM |  | 2 | 221.5 | 443 | 443 | 100% | 443 | 100% | 443 | 100% | 443 | 100% | 443 | 100% | 443 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B40 | BEAM |  | 1 | 228.4 | 228.4 | 228.4 | 100% | 228.4 | 100% | 228.4 | 100% | 228.4 | 100% | 228.4 | 100% | 228.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PR-502-06 | B41 | BEAM |  | 1 | 225.5 | 225.5 | 225.5 | 100% | 225.5 | 100% | 225.5 | 100% | 225.5 | 100% | 225.5 | 100% | 225.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B42 | BEAM |  | 1 | 534.9 | 534.9 | 534.9 | 100% | 534.9 | 100% | 534.9 | 100% | 534.9 | 100% | 160.47 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B43 | BEAM |  | 1 | 298.9 | 298.9 | 298.9 | 100% | 298.9 | 100% | 298.9 | 100% | 298.9 | 100% | 89.67 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B44 | BEAM |  | 1 | 381.7 | 381.7 | 381.7 | 100% | 381.7 | 100% | 381.7 | 100% | 381.7 | 100% | 381.7 | 100% | 381.7 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PR-502-06 | B45 | BEAM |  | 1 | 195.4 | 195.4 | 195.4 | 100% | 195.4 | 100% | 195.4 | 100% | 195.4 | 100% | 195.4 | 100% | 195.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PR-502-06 | B46 | BEAM |  | 1 | 132.3 | 132.3 | 132.3 | 100% | 132.3 | 100% | 132.3 | 100% | 132.3 | 100% | 39.69 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PR-502-06 | B47 | BEAM |  | 1 | 44.9 | 44.9 | 44.9 | 100% | 44.9 | 100% | 44.9 | 100% | 26.94 | 60% | 13.47 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PR-502-06 | B48 | BEAM |  | 1 | 46.2 | 46.2 | 46.2 | 100% | 46.2 | 100% | 46.2 | 100% | 27.72 | 60% | 13.86 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PR-502-06 | B49 | BEAM |  | 1 | 31.7 | 31.7 | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 9.51 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220II*6*10*200 | PR-502-06 | B50 | BEAM |  | 1 | 307.8 | 307.8 | 307.8 | 100% | 307.8 | 100% | 307.8 | 100% | 307.8 | 100% | 92.34 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220II*6*10*200 | PR-502-06 | B51 | BEAM |  | 1 | 84.6 | 84.6 | 84.6 | 100% | 84.6 | 100% | 84.6 | 100% | 50.76 | 60% | 25.38 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220II*6*10*200 | PR-502-06 | B52 | BEAM |  | 1 | 84.6 | 84.6 | 84.6 | 100% | 84.6 | 100% | 84.6 | 100% | 84.6 | 100% | 84.6 | 100% | 84.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PR-502-06 | B53 | BEAM |  | 4 | 39.7 | 158.8 | 158.8 | 100% | 158.8 | 100% | 158.8 | 100% | 158.8 | 100% | 47.64 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B54 | BEAM |  | 4 | 186.3 | 745.2 | 745.2 | 100% | 745.2 | 100% | 745.2 | 100% | 745.2 | 100% | 745.2 | 100% | 745.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B55 | BEAM |  | 2 | 233.4 | 466.8 | 466.8 | 100% | 466.8 | 100% | 466.8 | 100% | 466.8 | 100% | 466.8 | 100% | 466.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B56 | BEAM |  | 1 | 541.2 | 541.2 | 541.2 | 100% | 541.2 | 100% | 541.2 | 100% | 541.2 | 100% | 162.36 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | B57 | BEAM |  | 1 | 494 | 494 | 494 | 100% | 494 | 100% | 494 | 100% | 494 | 100% | 148.2 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B58 | BEAM |  | 1 | 59.7 | 59.7 | 59.7 | 100% | 59.7 | 100% | 59.7 | 100% | 59.7 | 100% | 59.7 | 100% | 59.7 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B59 | BEAM |  | 1 | 68.5 | 68.5 | 68.5 | 100% | 68.5 | 100% | 68.5 | 100% | 68.5 | 100% | 68.5 | 100% | 68.5 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PR-502-06 | B60 | BEAM |  | 1 | 148.4 | 148.4 | 148.4 | 100% | 148.4 | 100% | 148.4 | 100% | 148.4 | 100% | 148.4 | 100% | 148.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | B61 | BEAM |  | 1 | 240.6 | 240.6 | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% | 240.6 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF1 | BEAM FIREPROOF |  | 1 | 384.8 | 384.8 | 384.8 | 100% | 384.8 | 100% | 384.8 | 100% | 384.8 | 100% | 384.8 | 100% | 384.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF2 | BEAM FIREPROOF |  | 1 | 430.4 | 430.4 | 430.4 | 100% | 430.4 | 100% | 430.4 | 100% | 258.24 | 60% | 129.12 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF3 | BEAM FIREPROOF |  | 1 | 383.5 | 383.5 | 383.5 | 100% | 383.5 | 100% | 383.5 | 100% | 383.5 | 100% | 115.05 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF4 | BEAM FIREPROOF |  | 1 | 413.2 | 413.2 | 413.2 | 100% | 413.2 | 100% | 413.2 | 100% | 413.2 | 100% | 413.2 | 100% | 413.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF5 | BEAM FIREPROOF |  | 1 | 380.9 | 380.9 | 380.9 | 100% | 380.9 | 100% | 380.9 | 100% | 380.9 | 100% | 380.9 | 100% | 380.9 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF6 | BEAM FIREPROOF |  | 1 | 458.7 | 458.7 | 458.7 | 100% | 458.7 | 100% | 458.7 | 100% | 458.7 | 100% | 458.7 | 100% | 458.7 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF7 | BEAM FIREPROOF |  | 1 | 408.9 | 408.9 | 408.9 | 100% | 408.9 | 100% | 408.9 | 100% | 408.9 | 100% | 408.9 | 100% | 408.9 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF8 | BEAM FIREPROOF |  | 1 | 411.8 | 411.8 | 411.8 | 100% | 411.8 | 100% | 411.8 | 100% | 411.8 | 100% | 411.8 | 100% | 411.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF9 | BEAM FIREPROOF |  | 1 | 385.4 | 385.4 | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% | 385.4 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF10 | BEAM FIREPROOF |  | 1 | 323.8 | 323.8 | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA405*6*15*250 | PR-502-06 | BF11 | BEAM FIREPROOF |  | 1 | 323.8 | 323.8 | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% | 323.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | BF12 | BEAM FIREPROOF |  | 1 | 332.3 | 332.3 | 332.3 | 100% | 332.3 | 100% | 332.3 | 100% | 332.3 | 100% | 332.3 | 100% | 332.3 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PR-502-06 | BF13 | BEAM FIREPROOF |  | 2 | 538.2 | 1076.4 | 1076.4 | 100% | 1076.4 | 100% | 1076.4 | 100% | 1076.4 | 100% | 322.92 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PR-502-06 | BF14 | BEAM FIREPROOF |  | 2 | 520.6 | 1041.2 | 1041.2 | 100% | 1041.2 | 100% | 1041.2 | 100% | 1041.2 | 100% | 1041.2 | 100% | 1041.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | BF15 | BEAM FIREPROOF |  | 1 | 402.8 | 402.8 | 402.8 | 100% | 402.8 | 100% | 402.8 | 100% | 402.8 | 100% | 402.8 | 100% | 402.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | BF16 | BEAM FIREPROOF |  | 5 | 375.2 | 1876 | 1876 | 100% | 1876 | 100% | 1876 | 100% | 1876 | 100% | 1876 | 100% | 1876 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PR-502-06 | BF17 | BEAM FIREPROOF |  | 3 | 195.4 | 586.2 | 586.2 | 100% | 586.2 | 100% | 586.2 | 100% | 586.2 | 100% | 586.2 | 100% | 586.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PR-502-06 | BF18 | BEAM FIREPROOF |  | 1 | 359.8 | 359.8 | 359.8 | 100% | 359.8 | 100% | 359.8 | 100% | 359.8 | 100% | 359.8 | 100% | 359.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PR-502-06 | BF19 | BEAM FIREPROOF |  | 2 | 215.6 | 431.2 | 431.2 | 100% | 431.2 | 100% | 431.2 | 100% | 431.2 | 100% | 431.2 | 100% | 431.2 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PR-502-06 | BF20 | BEAM FIREPROOF |  | 1 | 197.9 | 197.9 | 197.9 | 100% | 197.9 | 100% | 197.9 | 100% | 197.9 | 100% | 197.9 | 100% | 197.9 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PR-502-06 | C1 | COLUMN |  | 1 | 784.9 | 784.9 | 784.9 | 100% | 784.9 | 100% | 784.9 | 100% | 470.94 | 60% | 235.47 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PR-502-06 | C2 | COLUMN |  | 1 | 769.7 | 769.7 | 769.7 | 100% | 769.7 | 100% | 769.7 | 100% | 461.82 | 60% | 230.91 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PR-502-06 | C3 | COLUMN |  | 1 | 1104.8 | 1104.8 | 1104.8 | 100% | 1104.8 | 100% | 1104.8 | 100% | 662.88 | 60% | 331.44 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PR-502-06 | C4 | COLUMN |  | 1 | 1044.7 | 1044.7 | 1044.7 | 100% | 1044.7 | 100% | 1044.7 | 100% | 626.82 | 60% | 313.41 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PR-502-06 | C5 | COLUMN |  | 1 | 1044.7 | 1044.7 | 1044.7 | 100% | 1044.7 | 100% | 1044.7 | 100% | 626.82 | 60% | 313.41 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PR-502-06 | C6 | COLUMN |  | 1 | 1089.5 | 1089.5 | 1089.5 | 100% | 1089.5 | 100% | 1089.5 | 100% | 653.7 | 60% | 326.85 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PR-502-06 | CF1 | COLUM FIREPROOF |  | 1 | 3041.9 | 3041.9 | 3041.9 | 100% | 3041.9 | 100% | 3041.9 | 100% | 3041.9 | 100% | 912.57 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PR-502-06 | CF2 | COLUM FIREPROOF |  | 1 | 3659.9 | 3659.9 | 3659.9 | 100% | 3659.9 | 100% | 3659.9 | 100% | 2195.94 | 60% | 1097.97 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PR-502-06 | CF3 | COLUM FIREPROOF |  | 1 | 2998.9 | 2998.9 | 2998.9 | 100% | 2998.9 | 100% | 2998.9 | 100% | 2998.9 | 100% | 899.67 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PR-502-06 | CF4 | COLUM FIREPROOF |  | 1 | 3004.2 | 3004.2 | 3004.2 | 100% | 3004.2 | 100% | 3004.2 | 100% | 3004.2 | 100% | 901.26 | 30% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PR-502-06 | CF5 | COLUM FIREPROOF |  | 1 | 3004.2 | 3004.2 | 3004.2 | 100% | 3004.2 | 100% | 3004.2 | 100% | 1802.52 | 60% | 450.63 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550I*15*25*300 | PR-502-06 | CF6 | COLUM FIREPROOF |  | 1 | 3616.9 | 3616.9 | 3616.9 | 100% | 3616.9 | 100% | 3616.9 | 100% | 3616.9 | 100% | 542.535 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PR-502-06 | CF7 | COLUM FIREPROOF |  | 1 | 2604 | 2604 | 2604 | 100% | 2604 | 100% | 2604 | 100% | 2604 | 100% | 390.6 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PR-502-06 | CF8 | COLUM FIREPROOF |  | 1 | 2604 | 2604 | 2604 | 100% | 2604 | 100% | 2604 | 100% | 2604 | 100% | 390.6 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB1 | H BRACING |  | 8 | 29.9 | 239.2 | 239.2 | 100% | 239.2 | 100% | 239.2 | 100% | 143.52 | 60% | 35.88 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB2 | H BRACING |  | 16 | 35.7 | 571.2 | 571.2 | 100% | 571.2 | 100% | 571.2 | 100% | 342.72 | 60% | 85.68 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB3 | H BRACING |  | 4 | 35.2 | 140.8 | 140.8 | 100% | 140.8 | 100% | 140.8 | 100% | 84.48 | 60% | 21.12 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB4 | H BRACING |  | 1 | 38.8 | 38.8 | 38.8 | 100% | 38.8 | 100% | 38.8 | 100% | 23.28 | 60% | 5.82 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB5 | H BRACING |  | 4 | 33.8 | 135.2 | 135.2 | 100% | 135.2 | 100% | 135.2 | 100% | 81.12 | 60% | 20.28 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB6 | H BRACING |  | 4 | 28.5 | 114 | 114 | 100% | 114 | 100% | 114 | 100% | 68.4 | 60% | 17.1 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB7 | H BRACING |  | 5 | 29.8 | 149 | 149 | 100% | 149 | 100% | 149 | 100% | 89.4 | 60% | 22.35 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB8 | H BRACING |  | 2 | 28.4 | 56.8 | 56.8 | 100% | 56.8 | 100% | 56.8 | 100% | 34.08 | 60% | 8.52 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB9 | H BRACING |  | 2 | 27.8 | 55.6 | 55.6 | 100% | 55.6 | 100% | 55.6 | 100% | 33.36 | 60% | 8.34 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB10 | H BRACING |  | 4 | 25.1 | 100.4 | 100.4 | 100% | 100.4 | 100% | 100.4 | 100% | 60.24 | 60% | 15.06 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB11 | H BRACING |  | 2 | 24.1 | 48.2 | 48.2 | 100% | 48.2 | 100% | 48.2 | 100% | 28.92 | 60% | 7.23 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB12 | H BRACING |  | 1 | 24.3 | 24.3 | 24.3 | 100% | 24.3 | 100% | 24.3 | 100% | 14.58 | 60% | 3.645 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB13 | H BRACING |  | 1 | 26.7 | 26.7 | 26.7 | 100% | 26.7 | 100% | 26.7 | 100% | 16.02 | 60% | 4.005 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB14 | H BRACING |  | 2 | 21.9 | 43.8 | 43.8 | 100% | 43.8 | 100% | 43.8 | 100% | 26.28 | 60% | 6.57 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB15 | H BRACING |  | 1 | 19 | 19 | 19 | 100% | 19 | 100% | 19 | 100% | 11.4 | 60% | 2.85 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB16 | H BRACING |  | 1 | 21.7 | 21.7 | 21.7 | 100% | 21.7 | 100% | 21.7 | 100% | 13.02 | 60% | 3.255 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB17 | H BRACING |  | 2 | 19 | 38 | 38 | 100% | 38 | 100% | 38 | 100% | 22.8 | 60% | 5.7 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB18 | H BRACING |  | 1 | 10.2 | 10.2 | 10.2 | 100% | 10.2 | 100% | 10.2 | 100% | 6.12 | 60% | 1.53 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB19 | H BRACING |  | 2 | 6.5 | 13 | 13 | 100% | 13 | 100% | 13 | 100% | 7.8 | 60% | 1.95 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB20 | H BRACING |  | 2 | 7.3 | 14.6 | 14.6 | 100% | 14.6 | 100% | 14.6 | 100% | 8.76 | 60% | 2.19 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | HB21 | H BRACING |  | 4 | 23.4 | 93.6 | 93.6 | 100% | 93.6 | 100% | 93.6 | 100% | 56.16 | 60% | 14.04 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | D14 | PR-502-06 | HI1 | HING |  | 2 | 0.2 | 0.4 | 0.4 | 100% | 0.4 | 100% | 0.4 | 100% | 0.24 | 60% | 0.06 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR1 | HANDRAIL |  | 1 | 52.9 | 52.9 | 52.9 | 100% | 52.9 | 100% | 52.9 | 100% | 52.9 | 100% | 7.935 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR2 | HANDRAIL |  | 1 | 23.8 | 23.8 | 23.8 | 100% | 23.8 | 100% | 23.8 | 100% | 14.28 | 60% | 3.57 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR3 | HANDRAIL |  | 1 | 97 | 97 | 97 | 100% | 97 | 100% | 97 | 100% | 97 | 100% | 14.55 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR4 | HANDRAIL |  | 1 | 63.1 | 63.1 | 63.1 | 100% | 63.1 | 100% | 63.1 | 100% | 37.86 | 60% | 9.465 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR5 | HANDRAIL |  | 1 | 52.6 | 52.6 | 52.6 | 100% | 52.6 | 100% | 52.6 | 100% | 52.6 | 100% | 7.89 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR6 | HANDRAIL |  | 2 | 48.9 | 97.8 | 97.8 | 100% | 97.8 | 100% | 97.8 | 100% | 97.8 | 100% | 14.67 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR7 | HANDRAIL |  | 2 | 27.5 | 55 | 55 | 100% | 55 | 100% | 55 | 100% | 55 | 100% | 8.25 | 15% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR8 | HANDRAIL |  | 1 | 42.1 | 42.1 | 42.1 | 100% | 42.1 | 100% | 42.1 | 100% | 12.63 | 30% | 4.21 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR9 | HANDRAIL |  | 1 | 19.3 | 19.3 | 19.3 | 100% | 19.3 | 100% | 19.3 | 100% | 5.79 | 30% | 1.93 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PR-502-06 | HR10 | HANDRAIL |  | 1 | 103.5 | 103.5 | 103.5 | 100% | 103.5 | 100% | 103.5 | 100% | 103.5 | 100% | 10.35 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PR-502-06 | LD1 | LADDER |  | 1 | 290.8 | 290.8 | 290.8 | 100% | 290.8 | 100% | 290.8 | 100% | 87.24 | 30% | 29.08 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PR-502-06 | LD2 | LADDER |  | 1 | 227.1 | 227.1 | 227.1 | 100% | 227.1 | 100% | 227.1 | 100% | 68.13 | 30% | 22.71 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL5*50 | PR-502-06 | LD3 | HANDRAIL |  | 2 | 2.8 | 5.6 | 5.6 | 100% | 5.6 | 100% | 5.6 | 100% | 1.68 | 30% | 0.56 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L120*12 | PR-502-06 | LV1 | ANGLE VB |  | 16 | 14.2 | 227.2 | 227.2 | 100% | 227.2 | 100% | 227.2 | 100% | 68.16 | 30% | 22.72 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L120*12 | PR-502-06 | LV2 | ANGLE VB |  | 16 | 14.2 | 227.2 | 227.2 | 100% | 227.2 | 100% | 227.2 | 100% | 68.16 | 30% | 22.72 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE33.7*3.56 | PR-502-06 | SF1 | SAFETY GATE |  | 1 | 5.2 | 5.2 | 5.2 | 100% | 5.2 | 100% | 5.2 | 100% | 1.56 | 30% | 0.52 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE33.7*3.56 | PR-502-06 | SF2 | SAFETY GATE |  | 1 | 5.2 | 5.2 | 5.2 | 100% | 5.2 | 100% | 5.2 | 100% | 1.56 | 30% | 0.52 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL12*300 | PR-502-06 | SP1 | PLATE |  | 12 | 20.9 | 250.8 | 250.8 | 100% | 250.8 | 100% | 250.8 | 100% | 250.8 | 100% | 250.8 | 100% | 250.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL20*120 | PR-502-06 | SP2 | PLATE |  | 24 | 13.9 | 333.6 | 333.6 | 100% | 333.6 | 100% | 333.6 | 100% | 100.08 | 30% | 33.36 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL10*260 | PR-502-06 | SP3 | PLATE |  | 12 | 5.9 | 70.8 | 70.8 | 100% | 70.8 | 100% | 70.8 | 100% | 70.8 | 100% | 70.8 | 100% | 70.8 | 100% |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | VB1 | V BRACING |  | 2 | 17.2 | 34.4 | 34.4 | 100% | 34.4 | 100% | 34.4 | 100% | 10.32 | 30% | 3.44 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | VB2 | V BRACING |  | 2 | 30.9 | 61.8 | 61.8 | 100% | 61.8 | 100% | 61.8 | 100% | 18.54 | 30% | 6.18 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | VB3 | V BRACING |  | 4 | 28.1 | 112.4 | 112.4 | 100% | 112.4 | 100% | 112.4 | 100% | 33.72 | 30% | 11.24 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PR-502-06 | VB4 | V BRACING |  | 2 | 17.4 | 34.8 | 34.8 | 100% | 34.8 | 100% | 34.8 | 100% | 10.44 | 30% | 3.48 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HI230*6*15*210 | PR-502-06 | VB5 | V BRACING |  | 4 | 192.2 | 768.8 | 768.8 | 100% | 768.8 | 100% | 768.8 | 100% | 768.8 | 100% | 76.88 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PR-502-06 | VB6 | V BRACING |  | 4 | 232.1 | 928.4 | 928.4 | 100% | 928.4 | 100% | 928.4 | 100% | 928.4 | 100% | 92.84 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PR-502-06 | VB7 | V BRACING |  | 4 | 252.1 | 1008.4 | 1008.4 | 100% | 1008.4 | 100% | 1008.4 | 100% | 1008.4 | 100% | 100.84 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L150*15 | PR-502-06 | VB8 | V BRACING |  | 4 | 221.5 | 886 | 886 | 100% | 886 | 100% | 886 | 100% | 886 | 100% | 88.6 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 16X45 | BOLT |  | 128 | 0.0971 | 12.4288 | 12.4288 | 100% | 12.4288 | 100% | 12.4288 | 100% | 12.4288 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 16X50 | BOLT |  | 16 | 0.103 | 1.648 | 1.648 | 100% | 1.648 | 100% | 1.648 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 16X60 | BOLT |  | 64 | 0.117 | 7.488 | 7.488 | 100% | 7.488 | 100% | 7.488 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 16X80 | BOLT |  | 2 | 0.144 | 0.288 | 0.288 | 100% | 0.288 | 100% | 0.288 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 20X60 | BOLT |  | 1037 | 0.196 | 203.252 | 203.252 | 100% | 203.252 | 100% | 203.252 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 20X65 | BOLT |  | 60 | 0.207 | 12.42 | 12.42 | 100% | 12.42 | 100% | 12.42 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 20X70 | BOLT |  | 3 | 0.217 | 0.651 | 0.651 | 100% | 0.651 | 100% | 0.651 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 20X90 | BOLT |  | 96 | 0.258 | 24.768 | 24.768 | 100% | 24.768 | 100% | 24.768 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 24X65 | BOLT |  | 460 | 0.319 | 146.74 | 146.74 | 100% | 146.74 | 100% | 146.74 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 24X70 | BOLT |  | 24 | 0.334 | 8.016 | 8.016 | 100% | 8.016 | 100% | 8.016 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 27X95 | BOLT |  | 192 | 0.55 | 105.6 | 105.6 | 100% | 105.6 | 100% | 105.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 30X95 | BOLT |  | 448 | 0.708 | 317.184 | 317.184 | 100% | 317.184 | 100% | 317.184 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-06 | BOLT 30X115 | BOLT |  | 432 | 0.803 | 346.896 | 346.896 | 100% | 346.896 |  | 346.896 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PB-502-01 | [5 empty] | 74162.8 | 74162.8 | 100% | 74162.8 | 100% | 74162.8 | 100% | 29442.7 | 39.7% | 11336 | 15.29% | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B1 | BEAM |  | 1 | 967.3 | 967.3 | 967.3 | 100% | 967.3 | 100% | 967.3 | 100% | 386.92 | 40% | 193.46 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B2 | BEAM |  | 1 | 927 | 927 | 927 | 100% | 927 | 100% | 927 | 100% | 370.8 | 40% | 185.4 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B3 | BEAM |  | 1 | 927 | 927 | 927 | 100% | 927 | 100% | 927 | 100% | 370.8 | 40% | 185.4 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B4 | BEAM |  | 1 | 360.2 | 360.2 | 360.2 | 100% | 360.2 | 100% | 360.2 | 100% | 144.08 | 40% | 72.04 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B5 | BEAM |  | 1 | 379.8 | 379.8 | 379.8 | 100% | 379.8 | 100% | 379.8 | 100% | 379.8 | 100% | 75.96 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B6 | BEAM |  | 2 | 379.8 | 759.6 | 759.6 | 100% | 759.6 | 100% | 759.6 | 100% | 759.6 | 100% | 151.92 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B7 | BEAM |  | 1 | 201.3 | 201.3 | 201.3 | 100% | 201.3 | 100% | 201.3 | 100% | 80.52 | 40% | 40.26 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B8 | BEAM |  | 1 | 73.3 | 73.3 | 73.3 | 100% | 73.3 | 100% | 73.3 | 100% | 29.32 | 40% | 14.66 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B9 | BEAM |  | 1 | 73.3 | 73.3 | 73.3 | 100% | 73.3 | 100% | 73.3 | 100% | 29.32 | 40% | 14.66 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B10 | BEAM |  | 1 | 84.3 | 84.3 | 84.3 | 100% | 84.3 | 100% | 84.3 | 100% | 33.72 | 40% | 16.86 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B11 | BEAM |  | 1 | 176.9 | 176.9 | 176.9 | 100% | 176.9 | 100% | 176.9 | 100% | 70.76 | 40% | 35.38 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B12 | BEAM |  | 1 | 176.9 | 176.9 | 176.9 | 100% | 176.9 | 100% | 176.9 | 100% | 70.76 | 40% | 35.38 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B13 | BEAM |  | 2 | 711.7 | 1423.4 | 1423.4 | 100% | 1423.4 | 100% | 1423.4 | 100% | 1423.4 | 100% | 284.68 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B14 | BEAM |  | 1 | 710.9 | 710.9 | 710.9 | 100% | 710.9 | 100% | 710.9 | 100% | 710.9 | 100% | 142.18 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B15 | BEAM |  | 1 | 419.3 | 419.3 | 419.3 | 100% | 419.3 | 100% | 419.3 | 100% | 167.72 | 40% | 83.86 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B16 | BEAM |  | 1 | 54.7 | 54.7 | 54.7 | 100% | 54.7 | 100% | 54.7 | 100% | 21.88 | 40% | 10.94 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B17 | BEAM |  | 1 | 87.8 | 87.8 | 87.8 | 100% | 87.8 | 100% | 87.8 | 100% | 35.12 | 40% | 17.56 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B18 | BEAM |  | 1 | 181.4 | 181.4 | 181.4 | 100% | 181.4 | 100% | 181.4 | 100% | 72.56 | 40% | 36.28 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B19 | BEAM |  | 1 | 125.2 | 125.2 | 125.2 | 100% | 125.2 | 100% | 125.2 | 100% | 50.08 | 40% | 25.04 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B20 | BEAM |  | 2 | 25.9 | 51.8 | 51.8 | 100% | 51.8 | 100% | 51.8 | 100% | 20.72 | 40% | 10.36 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B21 | BEAM |  | 1 | 48.9 | 48.9 | 48.9 | 100% | 48.9 | 100% | 48.9 | 100% | 19.56 | 40% | 9.78 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B22 | BEAM |  | 1 | 68.7 | 68.7 | 68.7 | 100% | 68.7 | 100% | 68.7 | 100% | 27.48 | 40% | 13.74 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B23 | BEAM |  | 1 | 27.4 | 27.4 | 27.4 | 100% | 27.4 | 100% | 27.4 | 100% | 10.96 | 40% | 5.48 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B24 | BEAM |  | 2 | 32.8 | 65.6 | 65.6 | 100% | 65.6 | 100% | 65.6 | 100% | 26.24 | 40% | 13.12 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B25 | BEAM |  | 1 | 76.9 | 76.9 | 76.9 | 100% | 76.9 | 100% | 76.9 | 100% | 30.76 | 40% | 15.38 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B26 | BEAM |  | 1 | 33.6 | 33.6 | 33.6 | 100% | 33.6 | 100% | 33.6 | 100% | 13.44 | 40% | 6.72 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B27 | BEAM |  | 1 | 64.7 | 64.7 | 64.7 | 100% | 64.7 | 100% | 64.7 | 100% | 25.88 | 40% | 12.94 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B28 | BEAM |  | 1 | 67.7 | 67.7 | 67.7 | 100% | 67.7 | 100% | 67.7 | 100% | 27.08 | 40% | 13.54 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B29 | BEAM |  | 1 | 135.5 | 135.5 | 135.5 | 100% | 135.5 | 100% | 135.5 | 100% | 54.2 | 40% | 27.1 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B30 | BEAM |  | 1 | 180.5 | 180.5 | 180.5 | 100% | 180.5 | 100% | 180.5 | 100% | 72.2 | 40% | 36.1 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B31 | BEAM |  | 1 | 124.1 | 124.1 | 124.1 | 100% | 124.1 | 100% | 124.1 | 100% | 49.64 | 40% | 24.82 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B32 | BEAM |  | 2 | 181.8 | 363.6 | 363.6 | 100% | 363.6 | 100% | 363.6 | 100% | 145.44 | 40% | 72.72 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B33 | BEAM |  | 1 | 181.8 | 181.8 | 181.8 | 100% | 181.8 | 100% | 181.8 | 100% | 72.72 | 40% | 36.36 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B34 | BEAM |  | 1 | 48.4 | 48.4 | 48.4 | 100% | 48.4 | 100% | 48.4 | 100% | 19.36 | 40% | 9.68 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PB-502-01 | B35 | BEAM |  | 1 | 437.6 | 437.6 | 437.6 | 100% | 437.6 | 100% | 437.6 | 100% | 175.04 | 40% | 87.52 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B36 | BEAM |  | 1 | 1925.5 | 1925.5 | 1925.5 | 100% | 1925.5 | 100% | 1925.5 | 100% | 770.2 | 40% | 385.1 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B37 | BEAM |  | 6 | 31.6 | 189.6 | 189.6 | 100% | 189.6 | 100% | 189.6 | 100% | 75.84 | 40% | 37.92 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B38 | BEAM |  | 1 | 900.2 | 900.2 | 900.2 | 100% | 900.2 | 100% | 900.2 | 100% | 360.08 | 40% | 180.04 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B39 | BEAM |  | 1 | 1825 | 1825 | 1825 | 100% | 1825 | 100% | 1825 | 100% | 730 | 40% | 365 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B40 | BEAM |  | 1 | 1861.2 | 1861.2 | 1861.2 | 100% | 1861.2 | 100% | 1861.2 | 100% | 744.48 | 40% | 372.24 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | B41 | BEAM |  | 1 | 1852 | 1852 | 1852 | 100% | 1852 | 100% | 1852 | 100% | 740.8 | 40% | 370.4 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PB-502-01 | B42 | BEAM |  | 1 | 514.4 | 514.4 | 514.4 | 100% | 514.4 | 100% | 514.4 | 100% | 514.4 | 100% | 102.88 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PB-502-01 | B43 | BEAM |  | 1 | 512.4 | 512.4 | 512.4 | 100% | 512.4 | 100% | 512.4 | 100% | 512.4 | 100% | 102.48 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*200 | PB-502-01 | B44 | BEAM |  | 1 | 221.4 | 221.4 | 221.4 | 100% | 221.4 | 100% | 221.4 | 100% | 88.56 | 40% | 44.28 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B45 | BEAM |  | 1 | 398.6 | 398.6 | 398.6 | 100% | 398.6 | 100% | 398.6 | 100% | 398.6 | 100% | 79.72 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B46 | BEAM |  | 1 | 408.8 | 408.8 | 408.8 | 100% | 408.8 | 100% | 408.8 | 100% | 163.52 | 40% | 81.76 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B47 | BEAM |  | 1 | 420.6 | 420.6 | 420.6 | 100% | 420.6 | 100% | 420.6 | 100% | 168.24 | 40% | 84.12 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B48 | BEAM |  | 2 | 398.6 | 797.2 | 797.2 | 100% | 797.2 | 100% | 797.2 | 100% | 318.88 | 40% | 159.44 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B49 | BEAM |  | 1 | 398.6 | 398.6 | 398.6 | 100% | 398.6 | 100% | 398.6 | 100% | 159.44 | 40% | 79.72 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B50 | BEAM |  | 1 | 424.9 | 424.9 | 424.9 | 100% | 424.9 | 100% | 424.9 | 100% | 169.96 | 40% | 84.98 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B51 | BEAM |  | 1 | 413.5 | 413.5 | 413.5 | 100% | 413.5 | 100% | 413.5 | 100% | 165.4 | 40% | 82.7 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B52 | BEAM |  | 2 | 414.7 | 829.4 | 829.4 | 100% | 829.4 | 100% | 829.4 | 100% | 331.76 | 40% | 165.88 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B53 | BEAM |  | 1 | 439.5 | 439.5 | 439.5 | 100% | 439.5 | 100% | 439.5 | 100% | 175.8 | 40% | 87.9 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B54 | BEAM |  | 3 | 437.5 | 1312.5 | 1312.5 | 100% | 1312.5 | 100% | 1312.5 | 100% | 525 | 40% | 262.5 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B55 | BEAM |  | 2 | 229 | 458 | 458 | 100% | 458 | 100% | 458 | 100% | 183.2 | 40% | 91.6 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B56 | BEAM |  | 1 | 265 | 265 | 265 | 100% | 265 | 100% | 265 | 100% | 106 | 40% | 53 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B57 | BEAM |  | 1 | 173.9 | 173.9 | 173.9 | 100% | 173.9 | 100% | 173.9 | 100% | 69.56 | 40% | 34.78 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B58 | BEAM |  | 2 | 269.3 | 538.6 | 538.6 | 100% | 538.6 | 100% | 538.6 | 100% | 215.44 | 40% | 107.72 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B59 | BEAM |  | 1 | 261.9 | 261.9 | 261.9 | 100% | 261.9 | 100% | 261.9 | 100% | 104.76 | 40% | 52.38 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B60 | BEAM |  | 1 | 169.5 | 169.5 | 169.5 | 100% | 169.5 | 100% | 169.5 | 100% | 67.8 | 40% | 33.9 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B61 | BEAM |  | 1 | 90.3 | 90.3 | 90.3 | 100% | 90.3 | 100% | 90.3 | 100% | 36.12 | 40% | 18.06 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B62 | BEAM |  | 1 | 635.4 | 635.4 | 635.4 | 100% | 635.4 | 100% | 635.4 | 100% | 254.16 | 40% | 127.08 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B63 | BEAM |  | 1 | 594.5 | 594.5 | 594.5 | 100% | 594.5 | 100% | 594.5 | 100% | 237.8 | 40% | 118.9 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274II*6*12*250 | PB-502-01 | B64 | BEAM |  | 1 | 459.8 | 459.8 | 459.8 | 100% | 459.8 | 100% | 459.8 | 100% | 183.92 | 40% | 91.96 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B65 | BEAM |  | 1 | 274.7 | 274.7 | 274.7 | 100% | 274.7 | 100% | 274.7 | 100% | 109.88 | 40% | 54.94 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B66 | BEAM |  | 1 | 607 | 607 | 607 | 100% | 607 | 100% | 607 | 100% | 242.8 | 40% | 121.4 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | B67 | BEAM |  | 1 | 607 | 607 | 607 | 100% | 607 | 100% | 607 | 100% | 242.8 | 40% | 121.4 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B68 | BEAM |  | 1 | 131.4 | 131.4 | 131.4 | 100% | 131.4 | 100% | 131.4 | 100% | 131.4 | 100% | 26.28 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B69 | BEAM |  | 1 | 188.6 | 188.6 | 188.6 | 100% | 188.6 | 100% | 188.6 | 100% | 188.6 | 100% | 37.72 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B70 | BEAM |  | 1 | 130.5 | 130.5 | 130.5 | 100% | 130.5 | 100% | 130.5 | 100% | 130.5 | 100% | 26.1 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B71 | BEAM |  | 1 | 151.6 | 151.6 | 151.6 | 100% | 151.6 | 100% | 151.6 | 100% | 151.6 | 100% | 30.32 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-502-01 | B72 | BEAM |  | 2 | 20.5 | 41 | 41 | 100% | 41 | 100% | 41 | 100% | 16.4 | 40% | 8.2 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-502-01 | B73 | BEAM |  | 4 | 20.1 | 80.4 | 80.4 | 100% | 80.4 | 100% | 80.4 | 100% | 32.16 | 40% | 16.08 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B74 | BEAM |  | 1 | 230.8 | 230.8 | 230.8 | 100% | 230.8 | 100% | 230.8 | 100% | 230.8 | 100% | 46.16 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B75 | BEAM |  | 1 | 203 | 203 | 203 | 100% | 203 | 100% | 203 | 100% | 203 | 100% | 40.6 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B76 | BEAM |  | 1 | 88.9 | 88.9 | 88.9 | 100% | 88.9 | 100% | 88.9 | 100% | 35.56 | 40% | 17.78 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | IPE160 | PB-502-01 | B77 | BEAM |  | 3 | 21.1 | 63.3 | 63.3 | 100% | 63.3 | 100% | 63.3 | 100% | 25.32 | 40% | 12.66 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B78 | BEAM |  | 1 | 192.4 | 192.4 | 192.4 | 100% | 192.4 | 100% | 192.4 | 100% | 76.96 | 40% | 38.48 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B79 | BEAM |  | 1 | 187.8 | 187.8 | 187.8 | 100% | 187.8 | 100% | 187.8 | 100% | 75.12 | 40% | 37.56 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B80 | BEAM |  | 1 | 187.8 | 187.8 | 187.8 | 100% | 187.8 | 100% | 187.8 | 100% | 75.12 | 40% | 37.56 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B81 | BEAM |  | 2 | 354.2 | 708.4 | 708.4 | 100% | 708.4 | 100% | 708.4 | 100% | 283.36 | 40% | 141.68 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA274I*6*12*200 | PB-502-01 | B82 | BEAM |  | 1 | 354.9 | 354.9 | 354.9 | 100% | 354.9 | 100% | 354.9 | 100% | 141.96 | 40% | 70.98 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B83 | BEAM |  | 2 | 77.9 | 155.8 | 155.8 | 100% | 155.8 | 100% | 155.8 | 100% | 62.32 | 40% | 31.16 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEA160 | PB-502-01 | B84 | BEAM |  | 2 | 77.9 | 155.8 | 155.8 | 100% | 155.8 | 100% | 155.8 | 100% | 62.32 | 40% | 31.16 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B85 | BEAM |  | 1 | 198.8 | 198.8 | 198.8 | 100% | 198.8 | 100% | 198.8 | 100% | 79.52 | 40% | 39.76 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA220I*6*10*150 | PB-502-01 | B86 | BEAM |  | 1 | 192.6 | 192.6 | 192.6 | 100% | 192.6 | 100% | 192.6 | 100% | 77.04 | 40% | 38.52 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA440*6*20*300 | PB-502-01 | BF1 | BEAM *** |  | 1 | 938.3 | 938.3 | 938.3 | 100% | 938.3 | 100% | 938.3 | 100% | 375.32 | 40% | 187.66 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PB-502-01 | C1 | COLUMN |  | 1 | 2403.8 | 2403.8 | 2403.8 | 100% | 2403.8 | 100% | 2403.8 | 100% | 961.52 | 40% | 480.76 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PB-502-01 | C2 | COLUMN |  | 1 | 2540.6 | 2540.6 | 2540.6 | 100% | 2540.6 | 100% | 2540.6 | 100% | 1016.24 | 40% | 508.12 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PB-502-01 | C3 | COLUMN |  | 1 | 2768.3 | 2768.3 | 2768.3 | 100% | 2768.3 | 100% | 2768.3 | 100% | 1107.32 | 40% | 553.66 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC425*10*25*300 | PB-502-01 | C4 | COLUMN |  | 1 | 2582.8 | 2582.8 | 2582.8 | 100% | 2582.8 | 100% | 2582.8 | 100% | 1033.12 | 40% | 516.56 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PB-502-01 | C5 | COLUMN |  | 1 | 1929.2 | 1929.2 | 1929.2 | 100% | 1929.2 | 100% | 1929.2 | 100% | 771.68 | 40% | 385.84 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PB-502-01 | C6 | COLUMN |  | 1 | 1833.6 | 1833.6 | 1833.6 | 100% | 1833.6 | 100% | 1833.6 | 100% | 733.44 | 40% | 366.72 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550II*15*25*400 | PB-502-01 | CF1 | COLUM*** |  | 1 | 3132.4 | 3132.4 | 3132.4 | 100% | 3132.4 | 100% | 3132.4 | 100% | 1252.96 | 40% | 626.48 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC550II*15*25*400 | PB-502-01 | CF2 | COLUM*** |  | 1 | 2918.8 | 2918.8 | 2918.8 | 100% | 2918.8 | 100% | 2918.8 | 100% | 1167.52 | 40% | 583.76 | 20% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB1 | H BRACING |  | 4 | 78.2 | 312.8 | 312.8 | 100% | 312.8 | 100% | 312.8 | 100% | 93.84 | 30% | 31.28 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB2 | H BRACING |  | 2 | 86.3 | 172.6 | 172.6 | 100% | 172.6 | 100% | 172.6 | 100% | 51.78 | 30% | 17.26 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB3 | H BRACING |  | 8 | 69.5 | 556 | 556 | 100% | 556 | 100% | 556 | 100% | 166.8 | 30% | 55.6 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB4 | H BRACING |  | 12 | 70.5 | 846 | 846 | 100% | 846 | 100% | 846 | 100% | 253.8 | 30% | 84.6 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB5 | H BRACING |  | 4 | 66.7 | 266.8 | 266.8 | 100% | 266.8 | 100% | 266.8 | 100% | 80.04 | 30% | 26.68 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB6 | H BRACING |  | 2 | 44 | 88 | 88 | 100% | 88 | 100% | 88 | 100% | 26.4 | 30% | 8.8 | 10% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB7 | H BRACING |  | 2 | 38.2 | 76.4 | 76.4 | 100% | 76.4 | 100% | 76.4 | 100% | 22.92 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB8 | H BRACING |  | 6 | 39.2 | 235.2 | 235.2 | 100% | 235.2 | 100% | 235.2 | 100% | 70.56 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB9 | H BRACING |  | 2 | 39.6 | 79.2 | 79.2 | 100% | 79.2 | 100% | 79.2 | 100% | 23.76 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB10 | H BRACING |  | 2 | 29 | 58 | 58 | 100% | 58 | 100% | 58 | 100% | 17.4 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB11 | H BRACING |  | 2 | 28.2 | 56.4 | 56.4 | 100% | 56.4 | 100% | 56.4 | 100% | 16.92 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB12 | H BRACING |  | 6 | 17.6 | 105.6 | 105.6 | 100% | 105.6 | 100% | 105.6 | 100% | 31.68 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB13 | H BRACING |  | 3 | 20.1 | 60.3 | 60.3 | 100% | 60.3 | 100% | 60.3 | 100% | 18.09 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB14 | H BRACING |  | 4 | 20 | 80 | 80 | 100% | 80 | 100% | 80 | 100% | 24 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | HB15 | H BRACING |  | 4 | 13.7 | 54.8 | 54.8 | 100% | 54.8 | 100% | 54.8 | 100% | 16.44 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L50*5 | PB-502-01 | HBS1 | STAIR BRACING |  | 2 | 5.6 | 11.2 | 11.2 | 100% | 11.2 | 100% | 11.2 | 100% | 3.36 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L50*5 | PB-502-01 | HBS2 | STAIR BRACING |  | 1 | 5.6 | 5.6 | 5.6 | 100% | 5.6 | 100% | 5.6 | 100% | 1.68 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L50*5 | PB-502-01 | HBS3 | STAIR BRACING |  | 4 | 6.2 | 24.8 | 24.8 | 100% | 24.8 | 100% | 24.8 | 100% | 7.44 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L50*5 | PB-502-01 | HBS4 | STAIR BRACING |  | 5 | 6.2 | 31 | 31 | 100% | 31 | 100% | 31 | 100% | 9.3 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L50*5 | PB-502-01 | HBS5 | STAIR BRACING |  | 4 | 5.8 | 23.2 | 23.2 | 100% | 23.2 | 100% | 23.2 | 100% | 6.96 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L50*5 | PB-502-01 | HBS6 | STAIR BRACING |  | 2 | 5.8 | 11.6 | 11.6 | 100% | 11.6 | 100% | 11.6 | 100% | 3.48 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR1 | HANDRAIL |  | 1 | 77.3 | 77.3 | 77.3 | 100% | 77.3 | 100% | 77.3 | 100% | 23.19 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR2 | HANDRAIL |  | 1 | 77.3 | 77.3 | 77.3 | 100% | 77.3 | 100% | 77.3 | 100% | 23.19 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR3 | HANDRAIL |  | 1 | 72.9 | 72.9 | 72.9 | 100% | 72.9 | 100% | 72.9 | 100% | 21.87 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR4 | HANDRAIL |  | 1 | 57.5 | 57.5 | 57.5 | 100% | 57.5 | 100% | 57.5 | 100% | 17.25 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR5 | HANDRAIL |  | 1 | 51.2 | 51.2 | 51.2 | 100% | 51.2 | 100% | 51.2 | 100% | 15.36 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR6 | HANDRAIL |  | 1 | 53.4 | 53.4 | 53.4 | 100% | 53.4 | 100% | 53.4 | 100% | 16.02 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR7 | HANDRAIL |  | 1 | 51.2 | 51.2 | 51.2 | 100% | 51.2 | 100% | 51.2 | 100% | 15.36 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR8 | HANDRAIL |  | 3 | 38.8 | 116.4 | 116.4 | 100% | 116.4 | 100% | 116.4 | 100% | 34.92 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR9 | HANDRAIL |  | 1 | 31.7 | 31.7 | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 9.51 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR10 | HANDRAIL |  | 1 | 32.4 | 32.4 | 32.4 | 100% | 32.4 | 100% | 32.4 | 100% | 9.72 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR11 | HANDRAIL |  | 2 | 111.9 | 223.8 | 223.8 | 100% | 223.8 | 100% | 223.8 | 100% | 67.14 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR12 | HANDRAIL |  | 3 | 43.3 | 129.9 | 129.9 | 100% | 129.9 | 100% | 129.9 | 100% | 38.97 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR13 | HANDRAIL |  | 1 | 21.7 | 21.7 | 21.7 | 100% | 21.7 | 100% | 21.7 | 100% | 6.51 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR14 | HANDRAIL |  | 1 | 114 | 114 | 114 | 100% | 114 | 100% | 114 | 100% | 34.2 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR15 | HANDRAIL |  | 3 | 113.5 | 340.5 | 340.5 | 100% | 340.5 | 100% | 340.5 | 100% | 102.15 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR16 | HANDRAIL |  | 1 | 81.8 | 81.8 | 81.8 | 100% | 81.8 | 100% | 81.8 | 100% | 24.54 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR17 | HANDRAIL |  | 1 | 86.4 | 86.4 | 86.4 | 100% | 86.4 | 100% | 86.4 | 100% | 25.92 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR18 | HANDRAIL |  | 1 | 56.5 | 56.5 | 56.5 | 100% | 56.5 | 100% | 56.5 | 100% | 16.95 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR19 | HANDRAIL |  | 1 | 57.8 | 57.8 | 57.8 | 100% | 57.8 | 100% | 57.8 | 100% | 17.34 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR20 | HANDRAIL |  | 1 | 58.2 | 58.2 | 58.2 | 100% | 58.2 | 100% | 58.2 | 100% | 17.46 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR21 | HANDRAIL |  | 1 | 43.2 | 43.2 | 43.2 | 100% | 43.2 | 100% | 43.2 | 100% | 12.96 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR22 | HANDRAIL |  | 1 | 43.8 | 43.8 | 43.8 | 100% | 43.8 | 100% | 43.8 | 100% | 13.14 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR23 | HANDRAIL |  | 1 | 44 | 44 | 44 | 100% | 44 | 100% | 44 | 100% | 13.2 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR24 | HANDRAIL |  | 1 | 47.4 | 47.4 | 47.4 | 100% | 47.4 | 100% | 47.4 | 100% | 14.22 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR25 | HANDRAIL |  | 2 | 43.3 | 86.6 | 86.6 | 100% | 86.6 | 100% | 86.6 | 100% | 25.98 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR26 | HANDRAIL |  | 1 | 25.1 | 25.1 | 25.1 | 100% | 25.1 | 100% | 25.1 | 100% | 7.53 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR27 | HANDRAIL |  | 1 | 22.1 | 22.1 | 22.1 | 100% | 22.1 | 100% | 22.1 | 100% | 6.63 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR28 | HANDRAIL |  | 1 | 23.2 | 23.2 | 23.2 | 100% | 23.2 | 100% | 23.2 | 100% | 6.96 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR29 | HANDRAIL |  | 1 | 25.7 | 25.7 | 25.7 | 100% | 25.7 | 100% | 25.7 | 100% | 7.71 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR30 | HANDRAIL |  | 1 | 23.2 | 23.2 | 23.2 | 100% | 23.2 | 100% | 23.2 | 100% | 6.96 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR31 | HANDRAIL |  | 1 | 27.6 | 27.6 | 27.6 | 100% | 27.6 | 100% | 27.6 | 100% | 8.28 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR32 | HANDRAIL |  | 1 | 26.7 | 26.7 | 26.7 | 100% | 26.7 | 100% | 26.7 | 100% | 8.01 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR33 | HANDRAIL |  | 1 | 22.7 | 22.7 | 22.7 | 100% | 22.7 | 100% | 22.7 | 100% | 6.81 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR34 | HANDRAIL |  | 1 | 22.7 | 22.7 | 22.7 | 100% | 22.7 | 100% | 22.7 | 100% | 6.81 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR35 | HANDRAIL |  | 1 | 31.6 | 31.6 | 31.6 | 100% | 31.6 | 100% | 31.6 | 100% | 9.48 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR36 | HANDRAIL |  | 1 | 31.1 | 31.1 | 31.1 | 100% | 31.1 | 100% | 31.1 | 100% | 9.33 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR37 | HANDRAIL |  | 1 | 31.1 | 31.1 | 31.1 | 100% | 31.1 | 100% | 31.1 | 100% | 9.33 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR38 | HANDRAIL |  | 1 | 78.3 | 78.3 | 78.3 | 100% | 78.3 | 100% | 78.3 | 100% | 23.49 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR39 | HANDRAIL |  | 2 | 78.3 | 156.6 | 156.6 | 100% | 156.6 | 100% | 156.6 | 100% | 46.98 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR40 | HANDRAIL |  | 1 | 79.3 | 79.3 | 79.3 | 100% | 79.3 | 100% | 79.3 | 100% | 23.79 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR41 | HANDRAIL |  | 1 | 77.7 | 77.7 | 77.7 | 100% | 77.7 | 100% | 77.7 | 100% | 23.31 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR42 | HANDRAIL |  | 1 | 79.6 | 79.6 | 79.6 | 100% | 79.6 | 100% | 79.6 | 100% | 23.88 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR43 | HANDRAIL |  | 1 | 57.9 | 57.9 | 57.9 | 100% | 57.9 | 100% | 57.9 | 100% | 17.37 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR44 | HANDRAIL |  | 1 | 25.7 | 25.7 | 25.7 | 100% | 25.7 | 100% | 25.7 | 100% | 7.71 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR45 | HANDRAIL |  | 1 | 26.3 | 26.3 | 26.3 | 100% | 26.3 | 100% | 26.3 | 100% | 7.89 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR46 | HANDRAIL |  | 1 | 43.4 | 43.4 | 43.4 | 100% | 43.4 | 100% | 43.4 | 100% | 13.02 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR47 | HANDRAIL |  | 1 | 23 | 23 | 23 | 100% | 23 | 100% | 23 | 100% | 6.9 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR48 | HANDRAIL |  | 2 | 22.5 | 45 | 45 | 100% | 45 | 100% | 45 | 100% | 13.5 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR49 | HANDRAIL |  | 1 | 31.5 | 31.5 | 31.5 | 100% | 31.5 | 100% | 31.5 | 100% | 9.45 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR50 | HANDRAIL |  | 1 | 65 | 65 | 65 | 100% | 65 | 100% | 65 | 100% | 19.5 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR51 | HANDRAIL |  | 1 | 67 | 67 | 67 | 100% | 67 | 100% | 67 | 100% | 20.1 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR52 | HANDRAIL |  | 3 | 58.9 | 176.7 | 176.7 | 100% | 176.7 | 100% | 176.7 | 100% | 53.01 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE42*3.56 | PB-502-01 | HR53 | HANDRAIL |  | 3 | 58.9 | 176.7 | 176.7 | 100% | 176.7 | 100% | 176.7 | 100% | 53.01 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PB-502-01 | LD1 | LADDER |  | 3 | 72.9 | 218.7 | 218.7 | 100% | 218.7 | 100% | 218.7 | 100% | 65.61 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L60*6 | PB-502-01 | LD2 | LADDER |  | 3 | 36 | 108 | 108 | 100% | 108 | 100% | 108 | 100% | 32.4 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PL5*50 | PB-502-01 | LD3 | LADDER |  | 2 | 2.9 | 5.8 | 5.8 | 100% | 5.8 | 100% | 5.8 | 100% | 1.74 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEB160 | PB-502-01 | PO1 | POST |  | 3 | 106.5 | 319.5 | 319.5 | 100% | 319.5 | 100% | 319.5 | 100% | 95.85 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO2 | POST |  | 1 | 226 | 226 | 226 | 100% | 226 | 100% | 226 | 100% | 67.8 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO3 | POST |  | 1 | 285.6 | 285.6 | 285.6 | 100% | 285.6 | 100% | 285.6 | 100% | 85.68 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO4 | POST |  | 1 | 280.4 | 280.4 | 280.4 | 100% | 280.4 | 100% | 280.4 | 100% | 84.12 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO5 | POST |  | 2 | 190.9 | 381.8 | 381.8 | 100% | 381.8 | 100% | 381.8 | 100% | 114.54 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO6 | POST |  | 1 | 190.9 | 190.9 | 190.9 | 100% | 190.9 | 100% | 190.9 | 100% | 57.27 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PB-502-01 | PO7 | POST |  | 1 | 387.1 | 387.1 | 387.1 | 100% | 387.1 | 100% | 387.1 | 100% | 116.13 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO8 | POST |  | 1 | 182.8 | 182.8 | 182.8 | 100% | 182.8 | 100% | 182.8 | 100% | 54.84 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO9 | POST |  | 1 | 80.4 | 80.4 | 80.4 | 100% | 80.4 | 100% | 80.4 | 100% | 24.12 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO10 | POST |  | 2 | 171 | 342 | 342 | 100% | 342 | 100% | 342 | 100% | 102.6 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC230*8*15*200 | PB-502-01 | PO11 | POST |  | 2 | 171 | 342 | 342 | 100% | 342 | 100% | 342 | 100% | 102.6 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGC340*8*20*300 | PB-502-01 | PO12 | POST |  | 1 | 366.3 | 366.3 | 366.3 | 100% | 366.3 | 100% | 366.3 | 100% | 109.89 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEB160 | PB-502-01 | PO13 | POST |  | 4 | 213.7 | 854.8 | 854.8 | 100% | 854.8 | 100% | 854.8 | 100% | 256.44 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEB160 | PB-502-01 | PO14 | POST |  | 2 | 214.5 | 429 | 429 | 100% | 429 | 100% | 429 | 100% | 128.7 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEB160 | PB-502-01 | PO15 | POST |  | 2 | 215.2 | 430.4 | 430.4 | 100% | 430.4 | 100% | 430.4 | 100% | 129.12 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | HEB160 | PB-502-01 | PO16 | POST |  | 2 | 213.7 | 427.4 | 427.4 | 100% | 427.4 | 100% | 427.4 | 100% | 128.22 | 30% | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PIPE33.7*3.56 | PB-502-01 | SF1 | SAFETY GATE |  | 6 | 5.2 | 31.2 | 31.2 | 100% | 31.2 | 100% | 31.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST1 | STAIR |  | 1 | 106.5 | 106.5 | 106.5 | 100% | 106.5 | 100% | 106.5 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST2 | STAIR |  | 1 | 106.5 | 106.5 | 106.5 | 100% | 106.5 | 100% | 106.5 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST3 | STAIR |  | 1 | 139.2 | 139.2 | 139.2 | 100% | 139.2 | 100% | 139.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST4 | STAIR |  | 1 | 139.2 | 139.2 | 139.2 | 100% | 139.2 | 100% | 139.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST5 | STAIR |  | 1 | 139.2 | 139.2 | 139.2 | 100% | 139.2 | 100% | 139.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST6 | STAIR |  | 1 | 138.7 | 138.7 | 138.7 | 100% | 138.7 | 100% | 138.7 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST7 | STAIR |  | 1 | 139.2 | 139.2 | 139.2 | 100% | 139.2 | 100% | 139.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST8 | STAIR |  | 1 | 138.7 | 138.7 | 138.7 | 100% | 138.7 | 100% | 138.7 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST9 | STAIR |  | 1 | 138.3 | 138.3 | 138.3 | 100% | 138.3 | 100% | 138.3 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST10 | STAIR |  | 1 | 138.9 | 138.9 | 138.9 | 100% | 138.9 | 100% | 138.9 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST11 | STAIR |  | 1 | 138.3 | 138.3 | 138.3 | 100% | 138.3 | 100% | 138.3 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | UNP200 | PB-502-01 | ST12 | STAIR |  | 1 | 138.9 | 138.9 | 138.9 | 100% | 138.9 | 100% | 138.9 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | ST13 | STAIR |  | 11 | 11 | 121 | 121 | 100% | 121 | 100% | 121 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | SU1 | SUPPORT |  | 1 | 321.8 | 321.8 | 321.8 | 100% | 321.8 | 100% | 321.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | PGA330*6*15*250 | PB-502-01 | SU2 | SUPPORT |  | 1 | 453.3 | 453.3 | 453.3 | 100% | 453.3 | 100% | 453.3 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | VB1 | V BRACING |  | 2 | 23.1 | 46.2 | 46.2 | 100% | 46.2 | 100% | 46.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L120*12 | PB-502-01 | VB2 | V BRACING |  | 6 | 167.6 | 1005.6 | 1005.6 | 100% | 1005.6 | 100% | 1005.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L120*12 | PB-502-01 | VB3 | V BRACING |  | 4 | 152.4 | 609.6 | 609.6 | 100% | 609.6 | 100% | 609.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L120*12 | PB-502-01 | VB4 | V BRACING |  | 2 | 143.1 | 286.2 | 286.2 | 100% | 286.2 | 100% | 286.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | VB5 | V BRACING |  | 4 | 63.6 | 254.4 | 254.4 | 100% | 254.4 | 100% | 254.4 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | VB6 | V BRACING |  | 6 | 65.1 | 390.6 | 390.6 | 100% | 390.6 | 100% | 390.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | VB7 | V BRACING |  | 2 | 61.8 | 123.6 | 123.6 | 100% | 123.6 | 100% | 123.6 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L120*12 | PB-502-01 | VB8 | V BRACING |  | 2 | 183.5 | 367 | 367 | 100% | 367 | 100% | 367 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L120*12 | PB-502-01 | VB9 | V BRACING |  | 2 | 167.1 | 334.2 | 334.2 | 100% | 334.2 | 100% | 334.2 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | VB10 | V BRACING |  | 1 | 18 | 18 | 18 | 100% | 18 | 100% | 18 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | L80*8 | PB-502-01 | VB11 | V BRACING |  | 2 | 22.9 | 45.8 | 45.8 | 100% | 45.8 | 100% | 45.8 | 100% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  | PR-502-05 | [5 empty] | 78797.4 | 78797.4 | 100% | 78797.4 | 100% | 78797.4 | 100% | 20055.58 | 25.45% | 0 | 0% | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B1 | BEAM |  | 1 | 65.5 | 65.5 | 65.5 | 100% | 65.5 | 100% | 65.5 | 100% | 32.75 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B2 | BEAM |  | 1 | 65.5 | 65.5 | 65.5 | 100% | 65.5 | 100% | 65.5 | 100% | 32.75 | 50% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | B3 | BEAM |  | 3 | 266.6 | 799.8 | 799.8 | 100% | 799.8 | 100% | 799.8 | 100% | 399.9 | 50% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | B4 | BEAM |  | 1 | 413.8 | 413.8 | 413.8 | 100% | 413.8 | 100% | 413.8 | 100% | 206.9 | 50% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | B5 | BEAM |  | 1 | 287.3 | 287.3 | 287.3 | 100% | 287.3 | 100% | 287.3 | 100% | 143.65 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B6 | BEAM |  | 1 | 131.3 | 131.3 | 131.3 | 100% | 131.3 | 100% | 131.3 | 100% | 65.65 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B7 | BEAM |  | 2 | 96.2 | 192.4 | 192.4 | 100% | 192.4 | 100% | 192.4 | 100% | 96.2 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B8 | BEAM |  | 1 | 53.2 | 53.2 | 53.2 | 100% | 53.2 | 100% | 53.2 | 100% | 26.6 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B9 | BEAM |  | 1 | 52.4 | 52.4 | 52.4 | 100% | 52.4 | 100% | 52.4 | 100% | 26.2 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B10 | BEAM |  | 1 | 133.2 | 133.2 | 133.2 | 100% | 133.2 | 100% | 133.2 | 100% | 66.6 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B11 | BEAM |  | 1 | 171.8 | 171.8 | 171.8 | 100% | 171.8 | 100% | 171.8 | 100% | 85.9 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B12 | BEAM |  | 2 | 337.8 | 675.6 | 675.6 | 100% | 675.6 | 100% | 675.6 | 100% | 337.8 | 50% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | B13 | BEAM |  | 2 | 292.4 | 584.8 | 584.8 | 100% | 584.8 | 100% | 584.8 | 100% | 292.4 | 50% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | B14 | BEAM |  | 1 | 524.6 | 524.6 | 524.6 | 100% | 524.6 | 100% | 524.6 | 100% | 262.3 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B15 | BEAM |  | 1 | 214.2 | 214.2 | 214.2 | 100% | 214.2 | 100% | 214.2 | 100% | 107.1 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B16 | BEAM |  | 1 | 195.1 | 195.1 | 195.1 | 100% | 195.1 | 100% | 195.1 | 100% | 97.55 | 50% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | B17 | BEAM |  | 1 | 303 | 303 | 303 | 100% | 303 | 100% | 303 | 100% | 151.5 | 50% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | B18 | BEAM |  | 2 | 211.8 | 423.6 | 423.6 | 100% | 423.6 | 100% | 423.6 | 100% | 211.8 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B19 | BEAM |  | 1 | 303.2 | 303.2 | 303.2 | 100% | 303.2 | 100% | 303.2 | 100% | 151.6 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B20 | BEAM |  | 1 | 326.4 | 326.4 | 326.4 | 100% | 326.4 | 100% | 326.4 | 100% | 163.2 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B21 | BEAM |  | 1 | 658.2 | 658.2 | 658.2 | 100% | 658.2 | 100% | 658.2 | 100% | 329.1 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B22 | BEAM |  | 1 | 664.7 | 664.7 | 664.7 | 100% | 664.7 | 100% | 664.7 | 100% | 332.35 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B23 | BEAM |  | 1 | 525 | 525 | 525 | 100% | 525 | 100% | 525 | 100% | 262.5 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B24 | BEAM |  | 1 | 500 | 500 | 500 | 100% | 500 | 100% | 500 | 100% | 250 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B25 | BEAM |  | 1 | 340.9 | 340.9 | 340.9 | 100% | 340.9 | 100% | 340.9 | 100% | 170.45 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B26 | BEAM |  | 1 | 288.9 | 288.9 | 288.9 | 100% | 288.9 | 100% | 288.9 | 100% | 144.45 | 50% | 0 |  | 0
|  | HEA160 | PR-502-05 | B27 | BEAM |  | 1 | 35.3 | 35.3 | 35.3 | 100% | 35.3 | 100% | 35.3 | 100% | 17.65 | 50% | 0 |  | 0
|  | HEA160 | PR-502-05 | B28 | BEAM |  | 1 | 35.3 | 35.3 | 35.3 | 100% | 35.3 | 100% | 35.3 | 100% | 17.65 | 50% | 0 |  | 0
|  | PGA220II*6*10*200 | PR-502-05 | B29 | BEAM |  | 1 | 70.5 | 70.5 | 70.5 | 100% | 70.5 | 100% | 70.5 | 100% | 35.25 | 50% | 0 |  | 0
|  | PGA220II*6*10*200 | PR-502-05 | B30 | BEAM |  | 1 | 70.5 | 70.5 | 70.5 | 100% | 70.5 | 100% | 70.5 | 100% | 35.25 | 50% | 0 |  | 0
|  | HEA160 | PR-502-05 | B31 | BEAM |  | 1 | 238.1 | 238.1 | 238.1 | 100% | 238.1 | 100% | 238.1 | 100% | 119.05 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B32 | BEAM |  | 1 | 306.9 | 306.9 | 306.9 | 100% | 306.9 | 100% | 306.9 | 100% | 153.45 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B33 | BEAM |  | 2 | 215.6 | 431.2 | 431.2 | 100% | 431.2 | 100% | 431.2 | 100% | 215.6 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B34 | BEAM |  | 1 | 227.6 | 227.6 | 227.6 | 100% | 227.6 | 100% | 227.6 | 100% | 113.8 | 50% | 0 |  | 0
|  | UNP200 | PR-502-05 | B35 | BEAM |  | 1 | 43.1 | 43.1 | 43.1 | 100% | 43.1 | 100% | 43.1 | 100% | 21.55 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B36 | BEAM |  | 1 | 249.7 | 249.7 | 249.7 | 100% | 249.7 | 100% | 249.7 | 100% | 124.85 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B37 | BEAM |  | 2 | 237.6 | 475.2 | 475.2 | 100% | 475.2 | 100% | 475.2 | 100% | 237.6 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B38 | BEAM |  | 1 | 238.7 | 238.7 | 238.7 | 100% | 238.7 | 100% | 238.7 | 100% | 119.35 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B39 | BEAM |  | 3 | 239.7 | 719.1 | 719.1 | 100% | 719.1 | 100% | 719.1 | 100% | 359.55 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B40 | BEAM |  | 1 | 139.7 | 139.7 | 139.7 | 100% | 139.7 | 100% | 139.7 | 100% | 69.85 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B41 | BEAM |  | 1 | 150.8 | 150.8 | 150.8 | 100% | 150.8 | 100% | 150.8 | 100% | 75.4 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B42 | BEAM |  | 4 | 151.8 | 607.2 | 607.2 | 100% | 607.2 | 100% | 607.2 | 100% | 303.6 | 50% | 0 |  | 0
|  | IPE160 | PR-502-05 | B43 | BEAM |  | 2 | 20.1 | 40.2 | 40.2 | 100% | 40.2 | 100% | 40.2 | 100% | 20.1 | 50% | 0 |  | 0
|  | IPE160 | PR-502-05 | B44 | BEAM |  | 1 | 21.3 | 21.3 | 21.3 | 100% | 21.3 | 100% | 21.3 | 100% | 10.65 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B45 | BEAM |  | 1 | 187.6 | 187.6 | 187.6 | 100% | 187.6 | 100% | 187.6 | 100% | 93.8 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B46 | BEAM |  | 1 | 545 | 545 | 545 | 100% | 545 | 100% | 545 | 100% | 272.5 | 50% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | B47 | BEAM |  | 1 | 381.4 | 381.4 | 381.4 | 100% | 381.4 | 100% | 381.4 | 100% | 190.7 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B48 | BEAM |  | 1 | 117.7 | 117.7 | 117.7 | 100% | 117.7 | 100% | 117.7 | 100% | 58.85 | 50% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B49 | BEAM |  | 1 | 281.5 | 281.5 | 281.5 | 100% | 281.5 | 100% | 281.5 | 100% | 84.45 | 30% | 0 |  | 0
|  | IPE160 | PR-502-05 | B50 | BEAM |  | 1 | 21.7 | 21.7 | 21.7 | 100% | 21.7 | 100% | 21.7 | 100% | 4.34 | 20% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | B51 | BEAM |  | 1 | 423 | 423 | 423 | 100% | 423 | 100% | 423 | 100% | 84.6 | 20% | 0 |  | 0
|  | IPE160 | PR-502-05 | B52 | BEAM |  | 2 | 28.4 | 56.8 | 56.8 | 100% | 56.8 | 100% | 56.8 | 100% | 11.36 | 20% | 0 |  | 0
|  | IPE160 | PR-502-05 | B53 | BEAM |  | 9 | 30 | 270 | 270 | 100% | 270 | 100% | 270 | 100% | 54 | 20% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | B54 | BEAM |  | 2 | 57.3 | 114.6 | 114.6 | 100% | 114.6 | 100% | 114.6 | 100% | 22.92 | 20% | 0 |  | 0
|  | PGA220II*6*10*200 | PR-502-05 | B55 | BEAM |  | 1 | 301.5 | 301.5 | 301.5 | 100% | 301.5 | 100% | 301.5 | 100% | 60.3 | 20% | 0 |  | 0
|  | PGA220II*6*10*200 | PR-502-05 | B56 | BEAM |  | 1 | 58.9 | 58.9 | 58.9 | 100% | 58.9 | 100% | 58.9 | 100% | 11.78 | 20% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | B57 | BEAM |  | 1 | 565.6 | 565.6 | 565.6 | 100% | 565.6 | 100% | 565.6 | 100% | 113.12 | 20% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | B58 | BEAM |  | 1 | 944.2 | 944.2 | 944.2 | 100% | 944.2 | 100% | 944.2 | 100% | 188.84 | 20% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | B59 | BEAM |  | 1 | 255.7 | 255.7 | 255.7 | 100% | 255.7 | 100% | 255.7 | 100% | 51.14 | 20% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | B60 | BEAM |  | 1 | 299.2 | 299.2 | 299.2 | 100% | 299.2 | 100% | 299.2 | 100% | 59.84 | 20% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | BF1 | BEAM FIREPROOF |  | 2 | 266.6 | 533.2 | 533.2 | 100% | 533.2 | 100% | 533.2 | 100% | 106.64 | 20% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | BF2 | BEAM FIREPROOF |  | 1 | 281.9 | 281.9 | 281.9 | 100% | 281.9 | 100% | 281.9 | 100% | 56.38 | 20% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | BF3 | BEAM FIREPROOF |  | 3 | 117.3 | 351.9 | 351.9 | 100% | 351.9 | 100% | 351.9 | 100% | 70.38 | 20% | 0 |  | 0
|  | PGA220I*6*10*150 | PR-502-05 | BF4 | BEAM FIREPROOF |  | 6 | 96.2 | 577.2 | 577.2 | 100% | 577.2 | 100% | 577.2 | 100% | 115.44 | 20% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | BF5 | BEAM FIREPROOF |  | 1 | 208 | 208 | 208 | 100% | 208 | 100% | 208 | 100% | 41.6 | 20% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | BF6 | BEAM FIREPROOF |  | 2 | 292.4 | 584.8 | 584.8 | 100% | 584.8 | 100% | 584.8 | 100% | 116.96 | 20% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | BF7 | BEAM FIREPROOF |  | 3 | 530.5 | 1591.5 | 1591.5 | 100% | 1591.5 | 100% | 1591.5 | 100% | 318.3 | 20% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | BF8 | BEAM FIREPROOF |  | 1 | 166.2 | 166.2 | 166.2 | 100% | 166.2 | 100% | 166.2 | 100% | 33.24 | 20% | 0 |  | 0
|  | PGA274II*6*12*250 | PR-502-05 | BF9 | BEAM FIREPROOF |  | 1 | 377 | 377 | 377 | 100% | 377 | 100% | 377 | 100% | 75.4 | 20% | 0 |  | 0
|  | PGA330*6*15*250 | PR-502-05 | BF10 | BEAM FIREPROOF |  | 1 | 305.9 | 305.9 | 305.9 | 100% | 305.9 | 100% | 305.9 | 100% | 61.18 | 20% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | BF11 | BEAM FIREPROOF |  | 1 | 699.1 | 699.1 | 699.1 | 100% | 699.1 | 100% | 699.1 | 100% | 139.82 | 20% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | BF12 | BEAM FIREPROOF |  | 1 | 672.5 | 672.5 | 672.5 | 100% | 672.5 | 100% | 672.5 | 100% | 134.5 | 20% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | BF13 | BEAM FIREPROOF |  | 1 | 328.1 | 328.1 | 328.1 | 100% | 328.1 | 100% | 328.1 | 100% | 65.62 | 20% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | BF14 | BEAM FIREPROOF |  | 1 | 329.8 | 329.8 | 329.8 | 100% | 329.8 | 100% | 329.8 | 100% | 65.96 | 20% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | BF15 | BEAM FIREPROOF |  | 1 | 285.9 | 285.9 | 285.9 | 100% | 285.9 | 100% | 285.9 | 100% | 57.18 | 20% | 0 |  | 0
|  | PGA274I*6*12*200 | PR-502-05 | BF16 | BEAM FIREPROOF |  | 1 | 312.5 | 312.5 | 312.5 | 100% | 312.5 | 100% | 312.5 | 100% | 62.5 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF17 | BEAM FIREPROOF |  | 1 | 726.2 | 726.2 | 726.2 | 100% | 726.2 | 100% | 726.2 | 100% | 145.24 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF18 | BEAM FIREPROOF |  | 1 | 517.2 | 517.2 | 517.2 | 100% | 517.2 | 100% | 517.2 | 100% | 103.44 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF19 | BEAM FIREPROOF |  | 1 | 859.3 | 859.3 | 859.3 | 100% | 859.3 | 100% | 859.3 | 100% | 171.86 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA330*6*15*250 | PR-502-05 | BF20 | BEAM FIREPROOF |  | 1 | 571.2 | 571.2 | 571.2 | 100% | 571.2 | 100% | 571.2 | 100% | 114.24 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF21 | BEAM FIREPROOF |  | 3 | 232.2 | 696.6 | 696.6 | 100% | 696.6 | 100% | 696.6 | 100% | 139.32 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF22 | BEAM FIREPROOF |  | 1 | 233.1 | 233.1 | 233.1 | 100% | 233.1 | 100% | 233.1 | 100% | 46.62 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF23 | BEAM FIREPROOF |  | 1 | 231.9 | 231.9 | 231.9 | 100% | 231.9 | 100% | 231.9 | 100% | 46.38 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274II*6*12*250 | PR-502-05 | BF24 | BEAM FIREPROOF |  | 2 | 395.3 | 790.6 | 790.6 | 100% | 790.6 | 100% | 790.6 | 100% | 158.12 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274II*6*12*250 | PR-502-05 | BF25 | BEAM FIREPROOF |  | 1 | 395.2 | 395.2 | 395.2 | 100% | 395.2 | 100% | 395.2 | 100% | 79.04 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA440*6*20*300 | PR-502-05 | BF26 | BEAM FIREPROOF |  | 1 | 1112 | 1112 | 1112 | 100% | 1112 | 100% | 1112 | 100% | 222.4 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF27 | BEAM FIREPROOF |  | 1 | 150.9 | 150.9 | 150.9 | 100% | 150.9 | 100% | 150.9 | 100% | 30.18 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA330*6*15*250 | PR-502-05 | BF28 | BEAM FIREPROOF |  | 1 | 373.4 | 373.4 | 373.4 | 100% | 373.4 | 100% | 373.4 | 100% | 74.68 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF29 | BEAM FIREPROOF |  | 1 | 186.7 | 186.7 | 186.7 | 100% | 186.7 | 100% | 186.7 | 100% | 37.34 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA330*6*15*250 | PR-502-05 | BF30 | BEAM FIREPROOF |  | 1 | 498.4 | 498.4 | 498.4 | 100% | 498.4 | 100% | 498.4 | 100% | 99.68 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA330*6*15*250 | PR-502-05 | BF31 | BEAM FIREPROOF |  | 2 | 357.1 | 714.2 | 714.2 | 100% | 714.2 | 100% | 714.2 | 100% | 142.84 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF32 | BEAM FIREPROOF |  | 1 | 215.3 | 215.3 | 215.3 | 100% | 215.3 | 100% | 215.3 | 100% | 43.06 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA274I*6*12*200 | PR-502-05 | BF33 | BEAM FIREPROOF |  | 1 | 214.1 | 214.1 | 214.1 | 100% | 214.1 | 100% | 214.1 | 100% | 42.82 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGA330*6*15*250 | PR-502-05 | BF34 | BEAM FIREPROOF |  | 1 | 305.9 | 305.9 | 305.9 | 100% | 305.9 | 100% | 305.9 | 100% | 61.18 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF1 | COLUM FIREPROOF |  | 1 | 2335.3 | 2335.3 | 2335.3 | 100% | 2335.3 | 100% | 2335.3 | 100% | 467.06 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF2 | COLUM FIREPROOF |  | 1 | 1475.1 | 1475.1 | 1475.1 | 100% | 1475.1 | 100% | 1475.1 | 100% | 295.02 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF3 | COLUM FIREPROOF |  | 1 | 2431.8 | 2431.8 | 2431.8 | 100% | 2431.8 | 100% | 2431.8 | 100% | 486.36 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF4 | COLUM FIREPROOF |  | 1 | 2426.2 | 2426.2 | 2426.2 | 100% | 2426.2 | 100% | 2426.2 | 100% | 485.24 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF5 | COLUM FIREPROOF |  | 1 | 2850.2 | 2850.2 | 2850.2 | 100% | 2850.2 | 100% | 2850.2 | 100% | 570.04 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF6 | COLUM FIREPROOF |  | 1 | 2891.6 | 2891.6 | 2891.6 | 100% | 2891.6 | 100% | 2891.6 | 100% | 578.32 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF7 | COLUM FIREPROOF |  | 1 | 2754.7 | 2754.7 | 2754.7 | 100% | 2754.7 | 100% | 2754.7 | 100% | 550.94 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF8 | COLUM FIREPROOF |  | 1 | 2852.3 | 2852.3 | 2852.3 | 100% | 2852.3 | 100% | 2852.3 | 100% | 570.46 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF9 | COLUM FIREPROOF |  | 1 | 2831 | 2831 | 2831 | 100% | 2831 | 100% | 2831 | 100% | 566.2 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF10 | COLUM FIREPROOF |  | 1 | 2818.3 | 2818.3 | 2818.3 | 100% | 2818.3 | 100% | 2818.3 | 100% | 563.66 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF11 | COLUM FIREPROOF |  | 1 | 2796.2 | 2796.2 | 2796.2 | 100% | 2796.2 | 100% | 2796.2 | 100% | 559.24 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PGC340*8*20*300 | PR-502-05 | CF12 | COLUM FIREPROOF |  | 1 | 2790.6 | 2790.6 | 2790.6 | 100% | 2790.6 | 100% | 2790.6 | 100% | 558.12 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L80*8 | PR-502-05 | HB1 | H BRACING |  | 2 | 45 | 90 | 90 | 100% | 90 | 100% | 90 | 100% | 18 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L80*8 | PR-502-05 | HB2 | H BRACING |  | 4 | 92.2 | 368.8 | 368.8 | 100% | 368.8 | 100% | 368.8 | 100% | 73.76 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L80*8 | PR-502-05 | HB3 | H BRACING |  | 1 | 93.3 | 93.3 | 93.3 | 100% | 93.3 | 100% | 93.3 | 100% | 18.66 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L80*8 | PR-502-05 | HB4 | H BRACING |  | 2 | 86.9 | 173.8 | 173.8 | 100% | 173.8 | 100% | 173.8 | 100% | 34.76 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L80*8 | PR-502-05 | HB5 | H BRACING |  | 1 | 86.2 | 86.2 | 86.2 | 100% | 86.2 | 100% | 86.2 | 100% | 17.24 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L60*6 | PR-502-05 | HB6 | H BRACING |  | 1 | 21.5 | 21.5 | 21.5 | 100% | 21.5 | 100% | 21.5 | 100% | 4.3 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L60*6 | PR-502-05 | HB7 | H BRACING |  | 1 | 24.1 | 24.1 | 24.1 | 100% | 24.1 | 100% | 24.1 | 100% | 4.82 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L60*6 | PR-502-05 | HB8 | H BRACING |  | 1 | 21.3 | 21.3 | 21.3 | 100% | 21.3 | 100% | 21.3 | 100% | 4.26 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L60*6 | PR-502-05 | HB9 | H BRACING |  | 1 | 42.5 | 42.5 | 42.5 | 100% | 42.5 | 100% | 42.5 | 100% | 8.5 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS1 | STAIR BRACING |  | 2 | 6.4 | 12.8 | 12.8 | 100% | 12.8 | 100% | 12.8 | 100% | 2.56 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS2 | STAIR BRACING |  | 2 | 6.4 | 12.8 | 12.8 | 100% | 12.8 | 100% | 12.8 | 100% | 2.56 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS3 | STAIR BRACING |  | 2 | 6.5 | 13 | 13 | 100% | 13 | 100% | 13 | 100% | 2.6 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS4 | STAIR BRACING |  | 2 | 6.5 | 13 | 13 | 100% | 13 | 100% | 13 | 100% | 2.6 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS5 | STAIR BRACING |  | 3 | 7.1 | 21.3 | 21.3 | 100% | 21.3 | 100% | 21.3 | 100% | 4.26 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS6 | STAIR BRACING |  | 3 | 7.1 | 21.3 | 21.3 | 100% | 21.3 | 100% | 21.3 | 100% | 4.26 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS7 | STAIR BRACING |  | 2 | 7 | 14 | 14 | 100% | 14 | 100% | 14 | 100% | 2.8 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS8 | STAIR BRACING |  | 1 | 7 | 7 | 7 | 100% | 7 | 100% | 7 | 100% | 1.4 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS9 | STAIR BRACING |  | 2 | 6.6 | 13.2 | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 2.64 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L50*5 | PR-502-05 | HBS10 | STAIR BRACING |  | 2 | 6.6 | 13.2 | 13.2 | 100% | 13.2 | 100% | 13.2 | 100% | 2.64 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR1 | HANDRAIL |  | 1 | 94.7 | 94.7 | 94.7 | 100% | 94.7 | 100% | 94.7 | 100% | 18.94 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR2 | HANDRAIL |  | 1 | 91 | 91 | 91 | 100% | 91 | 100% | 91 | 100% | 18.2 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR3 | HANDRAIL |  | 1 | 53.9 | 53.9 | 53.9 | 100% | 53.9 | 100% | 53.9 | 100% | 10.78 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR4 | HANDRAIL |  | 1 | 54.3 | 54.3 | 54.3 | 100% | 54.3 | 100% | 54.3 | 100% | 10.86 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR5 | HANDRAIL |  | 1 | 55 | 55 | 55 | 100% | 55 | 100% | 55 | 100% | 11 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR6 | HANDRAIL |  | 1 | 53.1 | 53.1 | 53.1 | 100% | 53.1 | 100% | 53.1 | 100% | 10.62 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR7 | HANDRAIL |  | 1 | 91.1 | 91.1 | 91.1 | 100% | 91.1 | 100% | 91.1 | 100% | 18.22 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR8 | HANDRAIL |  | 1 | 70.7 | 70.7 | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 14.14 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR9 | HANDRAIL |  | 1 | 63.9 | 63.9 | 63.9 | 100% | 63.9 | 100% | 63.9 | 100% | 12.78 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR10 | HANDRAIL |  | 1 | 57.2 | 57.2 | 57.2 | 100% | 57.2 | 100% | 57.2 | 100% | 11.44 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR11 | HANDRAIL |  | 2 | 44.1 | 88.2 | 88.2 | 100% | 88.2 | 100% | 88.2 | 100% | 17.64 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR12 | HANDRAIL |  | 1 | 35.9 | 35.9 | 35.9 | 100% | 35.9 | 100% | 35.9 | 100% | 7.18 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR13 | HANDRAIL |  | 1 | 30.3 | 30.3 | 30.3 | 100% | 30.3 | 100% | 30.3 | 100% | 6.06 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR14 | HANDRAIL |  | 3 | 102 | 306 | 306 | 100% | 306 | 100% | 306 | 100% | 61.2 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR15 | HANDRAIL |  | 1 | 104.9 | 104.9 | 104.9 | 100% | 104.9 | 100% | 104.9 | 100% | 20.98 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR16 | HANDRAIL |  | 1 | 105.8 | 105.8 | 105.8 | 100% | 105.8 | 100% | 105.8 | 100% | 21.16 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR17 | HANDRAIL |  | 3 | 47.9 | 143.7 | 143.7 | 100% | 143.7 | 100% | 143.7 | 100% | 28.74 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR18 | HANDRAIL |  | 1 | 49 | 49 | 49 | 100% | 49 | 100% | 49 | 100% | 9.8 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR19 | HANDRAIL |  | 1 | 102.3 | 102.3 | 102.3 | 100% | 102.3 | 100% | 102.3 | 100% | 20.46 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR20 | HANDRAIL |  | 1 | 102.8 | 102.8 | 102.8 | 100% | 102.8 | 100% | 102.8 | 100% | 20.56 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR21 | HANDRAIL |  | 1 | 106.1 | 106.1 | 106.1 | 100% | 106.1 | 100% | 106.1 | 100% | 21.22 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR22 | HANDRAIL |  | 1 | 89.9 | 89.9 | 89.9 | 100% | 89.9 | 100% | 89.9 | 100% | 17.98 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR23 | HANDRAIL |  | 1 | 58.4 | 58.4 | 58.4 | 100% | 58.4 | 100% | 58.4 | 100% | 11.68 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR24 | HANDRAIL |  | 2 | 44.4 | 88.8 | 88.8 | 100% | 88.8 | 100% | 88.8 | 100% | 17.76 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR25 | HANDRAIL |  | 1 | 112.7 | 112.7 | 112.7 | 100% | 112.7 | 100% | 112.7 | 100% | 22.54 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR26 | HANDRAIL |  | 1 | 21.1 | 21.1 | 21.1 | 100% | 21.1 | 100% | 21.1 | 100% | 4.22 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR27 | HANDRAIL |  | 1 | 27.6 | 27.6 | 27.6 | 100% | 27.6 | 100% | 27.6 | 100% | 5.52 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR28 | HANDRAIL |  | 1 | 28 | 28 | 28 | 100% | 28 | 100% | 28 | 100% | 5.6 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR29 | HANDRAIL |  | 1 | 21.2 | 21.2 | 21.2 | 100% | 21.2 | 100% | 21.2 | 100% | 4.24 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR30 | HANDRAIL |  | 1 | 92.5 | 92.5 | 92.5 | 100% | 92.5 | 100% | 92.5 | 100% | 18.5 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | PIPE42*3.56 | PR-502-05 | HR31 | HANDRAIL |  | 1 | 84.9 | 84.9 | 84.9 | 100% | 84.9 | 100% | 84.9 | 100% | 16.98 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST1 | STAIR |  | 1 | 165.4 | 165.4 | 165.4 | 100% | 165.4 | 100% | 165.4 | 100% | 33.08 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST2 | STAIR |  | 1 | 165.4 | 165.4 | 165.4 | 100% | 165.4 | 100% | 165.4 | 100% | 33.08 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST3 | STAIR |  | 1 | 185 | 185 | 185 | 100% | 185 | 100% | 185 | 100% | 37 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST4 | STAIR |  | 1 | 185 | 185 | 185 | 100% | 185 | 100% | 185 | 100% | 37 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST5 | STAIR |  | 1 | 182.6 | 182.6 | 182.6 | 100% | 182.6 | 100% | 182.6 | 100% | 36.52 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST6 | STAIR |  | 1 | 183.3 | 183.3 | 183.3 | 100% | 183.3 | 100% | 183.3 | 100% | 36.66 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST7 | STAIR |  | 1 | 182.6 | 182.6 | 182.6 | 100% | 182.6 | 100% | 182.6 | 100% | 36.52 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST8 | STAIR |  | 1 | 183.3 | 183.3 | 183.3 | 100% | 183.3 | 100% | 183.3 | 100% | 36.66 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST9 | STAIR |  | 1 | 182.9 | 182.9 | 182.9 | 100% | 182.9 | 100% | 182.9 | 100% | 36.58 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST10 | STAIR |  | 1 | 182.9 | 182.9 | 182.9 | 100% | 182.9 | 100% | 182.9 | 100% | 36.58 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST11 | STAIR |  | 1 | 184.7 | 184.7 | 184.7 | 100% | 184.7 | 100% | 184.7 | 100% | 36.94 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | UNP200 | PR-502-05 | ST12 | STAIR |  | 1 | 186 | 186 | 186 | 100% | 186 | 100% | 186 | 100% | 37.2 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L80*8 | PR-502-05 | ST13 | STAIR |  | 11 | 11 | 121 | 121 | 100% | 121 | 100% | 121 | 100% | 24.2 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L60*6 | PR-502-05 | VB1 | V BRACING |  | 2 | 22 | 44 | 44 | 100% | 44 | 100% | 44 | 100% | 8.8 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L60*6 | PR-502-05 | VB2 | V BRACING |  | 2 | 11.9 | 23.8 | 23.8 | 100% | 23.8 | 100% | 23.8 | 100% | 4.76 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L60*6 | PR-502-05 | VB3 | V BRACING |  | 2 | 22.9 | 45.8 | 45.8 | 100% | 45.8 | 100% | 45.8 | 100% | 9.16 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L150*15 | PR-502-05 | VB4 | V BRACING |  | 2 | 308.1 | 616.2 | 616.2 | 100% | 616.2 | 100% | 616.2 | 100% | 123.24 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB5 | V BRACING |  | 2 | 88.5 | 177 | 177 | 100% | 177 | 100% | 177 | 100% | 35.4 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB6 | V BRACING |  | 2 | 86.4 | 172.8 | 172.8 | 100% | 172.8 | 100% | 172.8 | 100% | 34.56 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB7 | V BRACING |  | 2 | 145 | 290 | 290 | 100% | 290 | 100% | 290 | 100% | 58 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB8 | V BRACING |  | 2 | 200.4 | 400.8 | 400.8 | 100% | 400.8 | 100% | 400.8 | 100% | 80.16 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L150*15 | PR-502-05 | VB9 | V BRACING |  | 2 | 401.3 | 802.6 | 802.6 | 100% | 802.6 | 100% | 802.6 | 100% | 160.52 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB10 | V BRACING |  | 2 | 248.3 | 496.6 | 496.6 | 100% | 496.6 | 100% | 496.6 | 100% | 99.32 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB11 | V BRACING |  | 4 | 217.5 | 870 | 870 | 100% | 870 | 100% | 870 | 100% | 174 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB12 | V BRACING |  | 2 | 196.4 | 392.8 | 392.8 | 100% | 392.8 | 100% | 392.8 | 100% | 78.56 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB13 | V BRACING |  | 2 | 189.3 | 378.6 | 378.6 | 100% | 378.6 | 100% | 378.6 | 100% | 75.72 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB14 | V BRACING |  | 4 | 173.1 | 692.4 | 692.4 | 100% | 692.4 | 100% | 692.4 | 100% | 138.48 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB15 | V BRACING |  | 2 | 178.2 | 356.4 | 356.4 | 100% | 356.4 | 100% | 356.4 | 100% | 71.28 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB16 | V BRACING |  | 4 | 175.2 | 700.8 | 700.8 | 100% | 700.8 | 100% | 700.8 | 100% | 140.16 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB17 | V BRACING |  | 2 | 181.2 | 362.4 | 362.4 | 100% | 362.4 | 100% | 362.4 | 100% | 72.48 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%
|  | L120*12 | PR-502-05 | VB18 | V BRACING |  | 4 | 166.5 | 666 | 666 | 100% | 666 | 100% | 666 | 100% | 133.2 | 20% | 0 |  | 0 |  |  |  |  | 0% |  |  |  | 0% |  | 0 | 0%

## Project S-Curve(Plan Vs.Actual) (hidden)
Steel Structure Fabrication Report SOUTHERN ADISH GAS CONDENSATE Project S-Curve(Plan Vs.Actual)
[28 empty] | 1 |  |  |  | 1
| weekly | 1400/5/02 | 1400/5/09 | 1400/5/16 | 1400/5/23 | 1400/5/30 | 1400/6/06 | 1400/6/13 | 1400/6/20 | 1400/6/27 | 1400/7/03 | 1400/7/10 | 1400/7/17 | 1400/7/24 | 1400/8/01 | 1400/8/08 | 1400/8/15 | 1400/8/22 | 1400/8/29 | 1400/9/06 | 1400/9/13 | 1400/9/20 | 1400/9/27 | 1400/10/04 | 1400/10/11 | 1400/10/18 | 1400/10/25 | 1400/10/30 | 1400/11/09 | 1400/11/13 | 1400/11/23 | 1400/11/30 | 1400/12/07 | 1400/12/14 | 1400/12/21 | 1400/12/25 | 1401/01/13 | 1401/01/20
Plan | Periodic Plan Progress | 0.41% | 1.23% | 1.64% | 3.28% | 2.46% | 3.28% | 3.28% | 4.92% | 3.28% | 4.92% | 2.46% | 3.28% | 4.92% | 4.1% | 4.92% | 4.1% | 4.1% | 3.28% | 2.4% | 3.28% | 4.92% | 4.1% | 3.28% | 1.64% | 1.1% | 1.8% | 1.5% | 2.8% | 3.01% | 3.56% | 3% | 1% | 0.5% | 0.5% | 0.75% | 0.5% | 0.5%
| Cumulative Plan Progress | 0.41% | 1.64% | 3.28% | 6.56% | 9.02% | 12.3% | 15.58% | 20.5% | 23.78% | 28.7% | 31.16% | 34.44% | 39.36% | 43.46% | 48.38% | 52.48% | 56.58% | 59.86% | 62.26% | 65.54% | 70.46% | 74.56% | 77.84% | 79.48% | 80.58% | 82.38% | 83.88% | 86.68% | 89.69% | 93.25% | 96.25% | 97.25% | 97.75% | 98.25% | 99% | 99.5% | 100%
| Plan delivery weight |  |  | 0 | 0 | 0 | 0 | 65000 | 11000 | 51888 | 58046 | 52065 | 125600 | 64400 | 29000 | 64125 | 132425 | 116200 | 104170 | 107050 | 123500 | 126000 | 158100 | 92031 | 57120 | 54600 | 141000 | 135000 | 57120 | 54600 | 141000 | 135000
| Monthly Cumulative Plan delivery weight | 62030 |  |  |  |  | 217846 |  |  |  | 286750 |  |  |  | 382500 |  |  |  |  | 477100 |  |  |  | 433774 |  |  |  |  | 160298
Actual | Periodic Actual Progress | 4% | 5% | 5.5% | 1% | 1.9% | 0.9% | 1.2% | 4.8% | 2.6% | 3.8% | 1.1% | 3.1% | 2.9% | 3.2% | 3.3% | 3% | 2.9% | 1.4% | 0.6% | 0.9% | 1.2% | 3.4% | 2.1% | 0.8% | 2% | 9.45% | 2% | 0.5% | 1.55% | 5.1% | 1% | 1% | 1.25% | 3.16% | 0.28% | 0.96% | 0.63%
| Cumulative Actual Progress | 4% | 9% | 14.5% | 15.5% | 17.4% | 18.3% | 19.5% | 24.3% | 26.9% | 30.7% | 31.8% | 34.9% | 37.8% | 41% | 44.3% | 47.3% | 50.2% | 51.6% | 52.2% | 53.1% | 54.3% | 57.7% | 59.8% | 60.6% | 62.6% | 72.05% | 74.05% | 74.55% | 76.1% | 81.2% | 82.2% | 83.2% | 84.45% | 87.61% | 87.89% | 88.85% | 89.48%
Monthly Cumulative Actual delivery weight