## Monthly Plan Feb
| South Adish Gas Condensate Refinery Project Construction, testing and commissioning EL, Tel & IN Cut Of Date: | [16 empty] | 2024-02-01
Feb 2024
| Row | Unit | Description | Activity Name | Discipline | UOM | #REF! | Plan W.V | February Plan | [7 empty] | Remark
[8 empty] | 11.79% | February Plan | Today Plan | Plan Up to Now | Today Actual Done | Actual Up to Now | Plan Start | Plan Finish | Executive Variance |  | تاریخ شروع برنامه | Work/Non Work
FA-25160020 | 1 | Unit - CDU | Installation of conduits | Handling | Electrical | M | 7850 | 0.09547% | 4000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160021 | 2 | Unit - CDU | Installation of conduits | Installation of Conduit | Electrical | M | 7850 | 0.8115% | 4000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160025 | 3 | Unit - CDU | Supports | Material Supply & Handling | Electrical | KG | 2500 | 0.01006% | 200 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160026 | 4 | Unit - CDU | Supports | Fabrication | Electrical | KG | 2500 | 0.03018% | 1500 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160027 | 5 | Unit - CDU | Supports | Installation | Electrical | KG | 2500 | 0.03773% | 1500 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160038 | 6 | Unit - CDU | Local Control Station | Handling | Electrical | PCS | 55 | 0.01255% | 55 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160039 | 7 | Unit - CDU | Local Control Station | Installation | Electrical | PCS | 55 | 0.1066% | 55 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160052 | 8 | Unit - CDU | Lighting JB | Fixing in place | Electrical | PCS | 142 | 0.05412% | 102 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160056 | 9 | Unit - CDU | Lighting Fixture | Installation of lighting poles | Electrical | PCS | 107 | 0.02759% | 42 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160057 | 10 | Unit - CDU | Lighting Fixture | Installation Fixture | Electrical | PCS | 221 | 0.1612% | 156 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160060 | 11 | Unit - CDU | Lighting Socket | Handling | Electrical | PCS | 21 | 0.00486% | 21 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160061 | 12 | Unit - CDU | Lighting Socket | Fixing in place | Electrical | PCS | 21 | 0.04131% | 21 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160072 | 13 | Unit - CDU | LV Cable | Handling | Electrical | M | 24124 | 0.04246% | 12125 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160073 | 14 | Unit - CDU | LV Cable | Cable laying | Electrical | M | 24124 | 0.2972% | 12125 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160079 | 15 | Unit - CDU | Control Cable | Handling | Electrical | M | 18127 | 0.02846% | 8127 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160080 | 16 | Unit - CDU | Control Cable | Cable laying | Electrical | M | 18127 | 0.1992% | 8127 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160086 | 17 | Unit - CDU | Lighting Cable | Handling | Electrical | M | 10665 | 0.01867% | 5332.5 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160087 | 18 | Unit - CDU | Lighting Cable | Cable laying | Electrical | M | 10665 | 0.1307% | 5332.5 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160123 | 19 | Unit - LPG/LPT | Installation of conduits | Handling | Electrical | M | 4344 | 0.07161% | 3000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160124 | 20 | Unit - LPG/LPT | Installation of conduits | Installation of Conduit | Electrical | M | 4344 | 0.6087% | 3000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160129 | 21 | Unit - LPG/LPT | Supports | Fabrication | Electrical | KG | 1725 | 0.02187% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160130 | 22 | Unit - LPG/LPT | Supports | Installation | Electrical | KG | 1725 | 0.02734% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160141 | 23 | Unit - LPG/LPT | Local Control Station | Handling | Electrical | PCS | 32 | 0.006843% | 30 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160142 | 24 | Unit - LPG/LPT | Local Control Station | Installation | Electrical | PCS | 32 | 0.05816% | 30 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160155 | 25 | Unit - LPG/LPT | Lighting JB | Fixing in place | Electrical | PCS | 99 | 0.0313% | 59 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160159 | 26 | Unit - LPG/LPT | Lighting Fixture | Installation of lighting poles | Electrical | PCS | 262 | 0.06657% | 132 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160160 | 27 | Unit - LPG/LPT | Lighting Fixture | Installation Fixture | Electrical | PCS | 369 | 0.2781% | 239 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160163 | 28 | Unit - LPG/LPT | Lighting Socket | Handling | Electrical | PCS | 10 | 0.002314% | 10 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160164 | 29 | Unit - LPG/LPT | Lighting Socket | Fixing in place | Electrical | PCS | 10 | 0.01967% | 10 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160176 | 30 | Unit - LPG/LPT | LV Cable | Handling | Electrical | M | 13450 | 0.0471% | 13450 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160177 | 31 | Unit - LPG/LPT | LV Cable | Cable laying | Electrical | M | 13450 | 0.3297% | 13450 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160183 | 32 | Unit - LPG/LPT | Control Cable | Handling | Electrical | M | 9994 | 0.035% | 9994 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160184 | 33 | Unit - LPG/LPT | Control Cable | Cable laying | Electrical | M | 9994 | 0.245% | 9994 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160190 | 34 | Unit - LPG/LPT | Lighting Cable | Handling | Electrical | M | 5035 | 0.008817% | 2517.5 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160191 | 35 | Unit - LPG/LPT | Lighting Cable | Cable laying | Electrical | M | 5035 | 0.06172% | 2517.5 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160211 | 36 | Unit - UTILITY | Installation of Primary Tray, ladder | Handling | Electrical | M | 282 | 0.004668% | 282 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160212 | 37 | Unit - UTILITY | Installation of Primary Tray, ladder | Tray/ Ladder Assembling | Electrical | M | 282 | 0.03034% | 282 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160213 | 38 | Unit - UTILITY | Installation of Primary Tray, ladder | Fixing & alignment | Electrical | M | 282 | 0.004668% | 282 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160229 | 39 | Unit - UTILITY | Supports | Fabrication | Electrical | KG | 2300 | 0.0503% | 2300 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160230 | 40 | Unit - UTILITY | Supports | Installation | Electrical | KG | 2300 | 0.06288% | 2300 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160254 | 41 | Unit - UTILITY | Lighting JB | Handling | Electrical | PCS | 50 | 0.001248% | 20 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160255 | 42 | Unit - UTILITY | Lighting JB | Fixing in place | Electrical | PCS | 50 | 0.01061% | 20 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160258 | 43 | Unit - UTILITY | Lighting Fixture | Handling | Electrical | PCS | 231 | 0.0297% | 231 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160259 | 44 | Unit - UTILITY | Lighting Fixture | Installation of lighting poles | Electrical | PCS | 132 | 0.0225% | 50 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160260 | 45 | Unit - UTILITY | Lighting Fixture | Installation Fixture | Electrical | PCS | 231 | 0.08356% | 100 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160268 | 46 | Unit - UTILITY | MV Cable | Handling | Electrical | M | 1490 | 0.005218% | 1490 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160269 | 47 | Unit - UTILITY | MV Cable | Cable laying | Electrical | M | 1490 | 0.03653% | 1490 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160270 | 48 | Unit - UTILITY | MV Cable | Cable arrangements and fixing | Electrical | M | 1490 | 0.002609% | 1490 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160275 | 49 | Unit - UTILITY | LV Cable | Handling | Electrical | M | 27582 | 0.09659% | 27582 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160276 | 50 | Unit - UTILITY | LV Cable | Cable laying | Electrical | M | 27582 | 0.6762% | 27582 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160277 | 51 | Unit - UTILITY | LV Cable | Cable arrangements and fixing | Electrical | M | 27582 | 0.0483% | 27582 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160282 | 52 | Unit - UTILITY | Control Cable | Handling | Electrical | M | 13087 | 0.04583% | 13087 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160283 | 53 | Unit - UTILITY | Control Cable | Cable laying | Electrical | M | 13087 | 0.3208% | 13087 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160284 | 54 | Unit - UTILITY | Control Cable | Cable arrangements and fixing | Electrical | M | 13087 | 0.02292% | 13087 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | منوط به تکمیل Paving
FA-25160367 | 55 | Unit - FWS | MV Cable | Handling | Electrical | M | 1050 | 0.003677% | 1050 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160368 | 56 | Unit - FWS | MV Cable | Cable laying | Electrical | M | 1050 | 0.02574% | 1050 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160374 | 57 | Unit - FWS | LV Cable | Handling | Electrical | M | 5741 | 0.02011% | 5741 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160375 | 58 | Unit - FWS | LV Cable | Cable laying | Electrical | M | 5741 | 0.1407% | 5741 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160381 | 59 | Unit - FWS | Control Cable | Handling | Electrical | M | 20 | 7.004e-05% | 20 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160382 | 60 | Unit - FWS | Control Cable | Cable laying | Electrical | M | 20 | 0.0004903% | 20 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160478 | 61 | Unit - SWS | LV Cable | Handling | Electrical | M | 7145 | 0.02502% | 7145 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160479 | 62 | Unit - SWS | LV Cable | Cable laying | Electrical | M | 7145 | 0.1752% | 7145 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25160485 | 63 | Unit - SWS | Control Cable | Handling | Electrical | M | 4765 | 0.01669% | 4765 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160486 | 64 | Unit - SWS | Control Cable | Cable laying | Electrical | M | 4765 | 0.1168% | 4765 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160783 | 65 | Unit - INT | Installation of Primary Tray, ladder | Handling | Electrical | M | 2602 | 0.02317% | 1400 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160784 | 66 | Unit - INT | Installation of Primary Tray, ladder | Tray/ Ladder Assembling | Electrical | M | 2602 | 0.1184% | 1100 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160785 | 67 | Unit - INT | Installation of Primary Tray, ladder | Fixing & alignment | Electrical | M | 2602 | 0.01821% | 1100 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160827 | 68 | Unit - INT | Street Lighting | Handling | Electrical | PCS | 199 | 0.05382% | 70 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160828 | 69 | Unit - INT | Street Lighting | Installation of lighting poles | Electrical | PCS | 131 | 0.1425% | 61 |  |  |  |  | 2024-02-01 | 2024-02-29 |  | منوط به تهیه کابل بدون Armor و فنداسیون
FA-25160829 | 70 | Unit - INT | Street Lighting | Installation Fixture | Electrical | PCS | 199 | 0.2153% | 70 |  |  |  |  | 2024-02-01 | 2024-02-29 |  | منوط به تهیه کابل بدون Armor و فنداسیون
FA-25160830 | 71 | Unit - INT | Street Lighting | Installation JB | Electrical | PCS | 147 | 0.1483% | 57 |  |  |  |  | 2024-02-01 | 2024-02-29 |  | منوط به تهیه کابل بدون Armor و فنداسیون
FA-25160849 | 72 | Unit - INT | Lighting Cable | Handling | Electrical | M | 11605 | 0.003502% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160850 | 73 | Unit - INT | Lighting Cable | Cable laying | Electrical | M | 11605 | 0.02451% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160858 | 74 | Unit - INT | Cable Gland & Termination | Gland Installation | Electrical | SET | 258 | 0.007057% | 38 |  |  |  |  | 2024-02-01 | 2024-02-29 |  | منوط به تهیه کابل بدون Armor و فنداسیون
FA-25160859 | 75 | Unit - INT | Cable Gland & Termination | Termination | Electrical | SET | 258 | 0.00294% | 38 |  |  |  |  | 2024-02-01 | 2024-02-29 |  | منوط به تهیه کابل بدون Armor و فنداسیون
FA-25160926 | 76 | Unit - TNK | Street Lighting | Handling | Electrical | PCS | 318 | 0.04496% | 138 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160927 | 77 | Unit - TNK | Street Lighting | Installation of lighting poles | Electrical | PCS | 53 | 0.08993% | 23 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160928 | 78 | Unit - TNK | Street Lighting | Installation Fixture | Electrical | PCS | 318 | 0.1799% | 138 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160929 | 79 | Unit - TNK | Street Lighting | Installation JB | Electrical | PCS | 106 | 0.1124% | 46 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160962 | 80 | Unit - TNK | Lighting Cable | Handling | Electrical | M | 15130 | 0.003502% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160963 | 81 | Unit - TNK | Lighting Cable | Cable laying | Electrical | M | 15130 | 0.02451% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160971 | 82 | Unit - TNK | Cable Gland & Termination | Gland Installation | Electrical | SET | 867 | 0.0598% | 322 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160972 | 83 | Unit - TNK | Cable Gland & Termination | Termination | Electrical | SET | 867 | 0.02491% | 322 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160973 | 84 | Unit - TNK | Cable Gland & Termination | QC | Electrical | SET | 867 | 0.004983% | 322 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25160998 | 85 | Substation - S55 | Transformer | Handling | Electrical | PCS | 3 | 0.009393% | 3 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25160999 | 86 | Substation - S55 | Transformer | Installation | Electrical | PCS | 3 | 0.05166% | 3 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161004 | 87 | Substation - S55 | LV Switchgear | Handling | Electrical | PCS | 28 | 0.03307% | 28 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161005 | 88 | Substation - S55 | LV Switchgear | Installation | Electrical | PCS | 28 | 0.248% | 28 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161006 | 89 | Substation - S55 | LV Switchgear | Fixing | Electrical | PCS | 28 | 0.03307% | 28 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161009 | 90 | Substation - S55 | MV Switchgear | Handling | Electrical | PCS | 24 | 0.02834% | 24 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161010 | 91 | Substation - S55 | MV Switchgear | Installation | Electrical | PCS | 24 | 0.2126% | 24 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161011 | 92 | Substation - S55 | MV Switchgear | Fixing | Electrical | PCS | 24 | 0.02834% | 24 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161014 | 93 | Substation - S55 | UPS,DC charger and Battries | Handling | Electrical | PCS | 4 | 0.006299% | 2 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161015 | 94 | Substation - S55 | UPS,DC charger and Battries | Installation | Electrical | PCS | 4 | 0.04724% | 2 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161016 | 95 | Substation - S55 | UPS,DC charger and Battries | Fixing | Electrical | PCS | 4 | 0.006299% | 2 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161019 | 96 | Substation - S55 | Main Lighting Panel | Handling | Electrical | PCS | 5 | 0.006889% | 5 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161020 | 97 | Substation - S55 | Main Lighting Panel | Installation | Electrical | PCS | 5 | 0.05167% | 5 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161078 | 98 | Unit - CDU | Installation of Primary Tray, ladder | Handling | Instrument | M | 3000 | 0.03311% | 2000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161079 | 99 | Unit - CDU | Installation of Primary Tray, ladder | Tray/ Ladder Assembling | Instrument | M | 3000 | 0.2152% | 2000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161080 | 100 | Unit - CDU | Installation of Primary Tray, ladder | Fixing & alignment | Instrument | M | 3000 | 0.03311% | 2000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161096 | 101 | Unit - CDU | Supports | Fabrication | Instrument | KG | 2300 | 0.0328% | 1500 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161097 | 102 | Unit - CDU | Supports | Installation | Instrument | KG | 2300 | 0.04101% | 1500 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161113 | 103 | Unit - CDU | Junction Box | Handling | Instrument | PCS | 72 | 0.0242% | 72 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161114 | 104 | Unit - CDU | Junction Box | Installation | Instrument | PCS | 72 | 0.2057% | 72 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161122 | 105 | Unit - CDU | Main Cabling | Handling | Instrument | M | 50369 | 0.1426% | 25000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161123 | 106 | Unit - CDU | Main Cabling | Cable laying | Instrument | M | 50369 | 0.9984% | 25000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161158 | 107 | Unit - LPG/LPT | Installation of Primary Tray, ladder | Handling | Instrument | M | 2988 | 0.03311% | 2000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161159 | 108 | Unit - LPG/LPT | Installation of Primary Tray, ladder | Tray/ Ladder Assembling | Instrument | M | 2988 | 0.2152% | 2000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161160 | 109 | Unit - LPG/LPT | Installation of Primary Tray, ladder | Fixing & alignment | Instrument | M | 2988 | 0.03311% | 2000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161193 | 110 | Unit - LPG/LPT | Junction Box | Handling | Instrument | PCS | 86 | 0.02891% | 86 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25161194 | 111 | Unit - LPG/LPT | Junction Box | Installation | Instrument | PCS | 86 | 0.2457% | 86 |  |  |  |  | 2024-02-21 | 2024-02-29
FA-25161202 | 112 | Unit - LPG/LPT | Main Cabling | Handling | Instrument | M | 43650 | 0.1084% | 19000 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161203 | 113 | Unit - LPG/LPT | Main Cabling | Cable laying | Instrument | M | 43650 | 0.7588% | 19000 |  |  |  |  | 2024-02-15 | 2024-02-29
FA-25161799 | 114 | ITR - ITR55 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | Handling | Instrument | PCS | 32 | 0.02334% | 32 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | 4 عدد منوط به تهیه پنل ها
FA-25161800 | 115 | ITR - ITR55 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | Installation | Instrument | PCS | 32 | 0.1751% | 32 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | 4 عدد منوط به تهیه پنل ها
FA-25161801 | 116 | ITR - ITR55 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | Fixing | Instrument | PCS | 32 | 0.02334% | 32 |  |  |  |  | 2024-02-15 | 2024-02-29 |  | 4 عدد منوط به تهیه پنل ها
FA-25161970 | 117 | Unit - INT | Civil Work( Excavation, sand fill, backfill ,…. | Material Handling (Soil) | Civil | M3 | 7078 | 0.05368% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
FA-25161974 | 118 | Unit - INT | Civil Work( Excavation, sand fill, backfill ,…. | Sand preparation and sand filling cable trench | Civil | M3 | 7078 | 0.1949% | 1000 |  |  |  |  | 2024-02-01 | 2024-02-29
*تمامی فعالیت هایی که Plan آن ها شروع نشده است قابل مشاهده نیستند

## PMS Rev 01
South Adish Gas Condensate Refinery Project
[15 empty] | STC Company - Construction, testing and commissioning EL, Tel & IN PMS Rev 01 |  | 0%
[15 empty] | Report NO : |  | 0%
[15 empty] | Date : |  | 0%
[12 empty] | Task & WBS Description | [7 empty] | Work Done |  |  | Progress status |  |  | Action Plan | [7 empty] | Remark
|  |  |  | Plan Jan | Plan Feb | Level | Unit | Discipline | Level 5 | Activity Code | Activity ID |  |  | Activity ID | Description | W.Factor % | W.V% | UOM | Estimate | Up to Last | Today | Up To Date | Up to Last | Today | Up To Date | January Plan QTY | January Plan % | Done until End Of Jan | February Plan QTY | February Plan | February Plan % |  |  |  | January Plan QTY | January Plan % | February Plan QTY | February Plan %
Plan Feb | [5 empty] | 1 | Total | Adish |  |  | 1 |  | 1 | 1 | South Adish Gas Condensate Refinery | 100% | 100% |  |  |  |  | 0 | 8.887% | 3.292% | 12.18% |  | 6.984% | 0 |  |  | 11.93% | Plan Start | Plan Finish |  |  | 6.984% |  | 11.79%
[6 empty] | 2 |  | Mobilization |  |  | FA-25160000 |  |  | FA-25160000 | Mobilization | 5% | 5% |  |  |  |  | 0 | 100% | 0% | 100% |  |  | 0
[6 empty] | 6 | General | Mobilization | Mobilization |  | FA-25160001 |  |  | FA-25160001 | Offices Preparation | 75% | 3.75% |  | 100 |  | 100 | 100 | 100% | 0% | 100% |  |  | 100
[6 empty] | 6 | General | Mobilization | Mobilization |  | FA-25160002 |  |  | FA-25160002 | Generator and Office Electricity | 10% | 0.5% |  | 100 |  | 100 | 100 | 100% | 0% | 100% |  |  | 100
[6 empty] | 6 | General | Mobilization | Mobilization |  | FA-25160003 |  |  | FA-25160003 | Warehouse Preparation | 15% | 0.75% |  | 100 |  | 100 | 100 | 100% | 0% | 100% |  |  | 100
Plan |  |  |  | Plan Jan | Plan Feb | 2 |  | Electrical |  |  | FA-25160004 |  |  | FA-25160004 | Electrical | 39.02% | 39.02% |  |  |  |  | 0 | 7.794% | 8.09% | 15.88% |  | 5.84% | 0 |  |  | 8.307% |  |  |  |  | 5.84% |  | 8.169%
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Electrical |  |  | FA-25160005 |  |  | FA-25160005 | Unit - CDU | 13.85% | 5.405% |  |  |  |  | 0 | 11.33% | 20.14% | 31.47% |  | 1.139% | 0 |  |  | 2.1% |  |  |  |  | 1.139% |  | 2.1%
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160006 |  |  | FA-25160006 | Cable Tray, ladder, Conduits | 37.97% | 2.052% |  |  |  |  | 0 | 5.504% | 9.184% | 14.69% |  | 0.2071% | 0 |  |  | 0.907% |  |  |  |  | 0.2071% |  | 0.907%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160007 |  |  | FA-25160007 | Installation of Primary Tray, ladder | 4.355% | 0.08939% |  |  |  |  | 0 | 57.34% | 12.52% | 69.86% |  | 0.1224% | 0 | [7 empty] | 0.1224%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | Installation of Primary Tray, ladder |  | FA-25160008 |  |  | FA-25160008 | Handling | 10% | 0.008939% |  | 540 |  | 540 | 540 | 99.81% | 0.1852% | 100% | 539 | 0.01784% | 540 | [6 empty] | 539 | 0.01784%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160009 |  |  | FA-25160009 | Tray/ Ladder Assembling | 65% | 0.0581% |  | 540 |  | 431 | 431 | 63.15% | 16.67% | 79.81% | 421 | 0.0906% | 431 | [6 empty] | 421 | 0.0906%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | Installation of Primary Tray, ladder |  | FA-25160010 |  |  | FA-25160010 | Fixing & alignment | 10% | 0.008939% |  | 540 |  | 431 | 431 | 63.15% | 16.67% | 79.81% | 421 | 0.01394% | 431 | [6 empty] | 421 | 0.01394%
[6 empty] | 6 | Unit - CDU | Electrical | Installation of Primary Tray, ladder |  | FA-25160011 |  |  | FA-25160011 | Installation of covers | 10% | 0.008939% |  | 540 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Installation of Primary Tray, ladder |  | FA-25160012 |  |  | FA-25160012 | QC | 5% | 0.004469% |  | 540 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160013 |  |  | FA-25160013 | Installation of Secondary Tray | 4.355% | 0.08939% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Installation of Secondary Tray |  | FA-25160014 |  |  | FA-25160014 | Handling | 10% | 0.008939% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Installation of Secondary Tray | 50001 | FA-25160015 |  |  | FA-25160015 | Tray/ Ladder Assembling | 65% | 0.0581% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Installation of Secondary Tray |  | FA-25160016 |  |  | FA-25160016 | Fixing & alignment | 10% | 0.008939% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Installation of Secondary Tray |  | FA-25160017 |  |  | FA-25160017 | Installation of covers | 10% | 0.008939% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Installation of Secondary Tray |  | FA-25160018 |  |  | FA-25160018 | QC | 5% | 0.004469% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160019 |  |  | FA-25160019 | Installation of conduits | 91.29% | 1.874% |  |  |  |  | 0 | 3.294% | 9.463% | 12.76% |  | 0.08473% | 0 |  |  | 0.907% |  |  |  |  | 0.08473% |  | 0.907%
Plan | 0.00095475 | 1.216e-05% | 2.279e-08% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | Installation of conduits |  | FA-25160020 |  |  | FA-25160020 | Handling | 10% | 0.1874% |  | 7850 |  | 1200 | 1200 | 15.29% | 0% | 15.29% | 1000 | 0.02387% | 1200 | 4000 | 0.50955 | 0.09547% | Week 1 | Week 4 |  | 1000 | 0.02387% | 4000 | 0.09547% | ok | 12.74% | 0.02387%
Plan | 0.0081153 | 0.0001034% | 1.646e-06% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | Installation of conduits | 50010 | FA-25160021 |  |  | FA-25160021 | Installation of Conduit | 85% | 1.593% |  | 7850 |  | 1036.95 | 1036.95 | 2.076% | 11.13% | 13.21% | 300 | 0.06087% | 1036.95 | 4000 | 0.50955 | 0.8115% | Week 1 | Week 4 |  | 300 | 0.06087% | 4000 | 0.8115% | ok | 3.822% | 0.06087%
[6 empty] | 6 | Unit - CDU | Electrical | Installation of conduits |  | FA-25160022 |  |  | FA-25160022 | QC | 5% | 0.09368% |  | 7850 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160023 |  |  | FA-25160023 | Supports | 4.653% | 0.2515% |  |  |  |  | 0 | 64.3% | 16.48% | 80.78% |  | 0.1258% | 0 |  |  | 0.06791% |  |  |  |  | 0.1258% |  | 0.06791%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160024 |  |  | FA-25160024 | Supports | 100% | 0.2515% |  |  |  |  | 0 | 64.3% | 16.48% | 80.78% |  | 0.1258% | 0 |  |  | 0.06791% |  |  |  |  | 0.1258% |  | 0.06791%
| 0 | 0% | 0% | Plan Jan |  | 6 | Unit - CDU | Electrical | Supports |  | FA-25160025 |  |  | FA-25160025 | Material Supply & Handling | 50% | 0.1258% |  | 2500 |  | 2500 | 2500 | 100% | 0% | 100% | 2300 | 0.1258% | 2500 |  | 0 | 0% |  |  |  | 2300 | 0.1258% |  | 0% | ok | 92% | 0.1157%
Plan | 0.00030181 | 1.207e-05% | 6.072e-09% |  | Plan Feb | 6 | Unit - CDU | Electrical | Supports | 50020 | FA-25160026 |  |  | FA-25160026 | Fabrication | 20% | 0.0503% |  | 2500 |  | 1709.8416 | 1709.8416 | 31.78% | 36.61% | 68.39% |  |  | 1709.8416 | 1500 | 0.6 | 0.03018% | Week 1 | Week 4 |  |  |  | 1500 | 0.03018% | ok | 0% | 0%
Plan | 0.00037726 | 1.509e-05% | 9.488e-09% |  | Plan Feb | 6 | Unit - CDU | Electrical | Supports | 50030 | FA-25160027 |  |  | FA-25160027 | Installation | 25% | 0.06288% |  | 2500 |  | 1709.8416 | 1709.8416 | 31.78% | 36.61% | 68.39% |  |  | 1709.8416 | 1500 | 0.6 | 0.03773% | Week 1 | Week 4 |  |  |  | 1500 | 0.03773% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Electrical | Supports |  | FA-25160028 |  |  | FA-25160028 | QC | 5% | 0.01258% |  | 2500 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160029 |  |  | FA-25160029 | EL Transformer/ Panel/ JB | 3.065% | 0.1657% |  |  |  |  | 0 | 4.151% | 0% | 4.151% |  | 0.00764% | 0 |  |  | 0.1192% |  |  |  |  | 0.00764% |  | 0.1192%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160030 |  |  | FA-25160030 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 21.85% | 0.03619% |  |  |  |  | 0 | 19% | 0% | 19% |  | 0.00764% | 0 | [7 empty] | 0.00764%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160031 |  |  | FA-25160031 | Handling | 10% | 0.003619% |  | 10 |  | 2 | 2 | 20% | 0% | 20% | 2 | 0.0008042% | 2 | [6 empty] | 2 | 0.0008042%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160032 |  |  | FA-25160032 | Installation | 85% | 0.03076% |  | 10 |  | 2 | 2 | 20% | 0% | 20% | 2 | 0.006836% | 2 | [6 empty] | 2 | 0.006836%
[6 empty] | 6 | Unit - CDU | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160033 |  |  | FA-25160033 | QC | 5% | 0.001809% |  | 10 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160034 |  |  | FA-25160034 | Test and Energizing Local Panels Inside Units | 2.427% | 0.004021% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160035 |  |  | FA-25160035 | Energizing | 90% | 0.003619% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160036 |  |  | FA-25160036 | Document | 10% | 0.0004021% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160037 |  |  | FA-25160037 | Local Control Station | 75.73% | 0.1255% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.1192% | [6 empty] | 0.1192%
Plan | 0.00012545 | 0.0002281% | 2.861e-08% |  | Plan Feb | 6 | Unit - CDU | Electrical | Local Control Station |  | FA-25160038 |  |  | FA-25160038 | Handling | 10% | 0.01255% |  | 55 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 55 | 1 | 0.01255% | Week 4 | Week 4 |  |  |  | 55 | 0.01255% | ok | 0% | 0%
Plan | 0.0010663 | 0.001939% | 2.067e-06% |  | Plan Feb | 6 | Unit - CDU | Electrical | Local Control Station | 50110 | FA-25160039 |  |  | FA-25160039 | Installation | 85% | 0.1066% |  | 55 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 55 | 1 | 0.1066% | Week 4 | Week 4 |  |  |  | 55 | 0.1066% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Electrical | Local Control Station |  | FA-25160040 |  |  | FA-25160040 | QC | 5% | 0.006273% |  | 55 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160041 |  |  | FA-25160041 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Power Junction Box |  | FA-25160042 |  |  | FA-25160042 | Handling | 10% | 0% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Power Junction Box | 50120 | FA-25160043 |  |  | FA-25160043 | Installation | 85% | 0% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Power Junction Box |  | FA-25160044 |  |  | FA-25160044 | QC | 5% | 0% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160045 |  |  | FA-25160045 | Motor Free Run Test | 3.574% | 0.1932% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160046 |  |  | FA-25160046 | Motor Free Run Test | 100% | 0.1932% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Motor Free Run Test | 50130 | FA-25160047 |  |  | FA-25160047 | Motor Free Run | 95% | 0.1835% |  | 63 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Motor Free Run Test |  | FA-25160048 |  |  | FA-25160048 | QC | 5% | 0.009658% |  | 63 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160049 |  |  | FA-25160049 | Lighting & Small Power System | 9.041% | 0.4886% |  |  |  |  | 0 | 33.53% | 23.47% | 57% |  | 0.1444% | 0 |  |  | 0.2891% |  |  |  |  | 0.1444% |  | 0.2891%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160050 |  |  | FA-25160050 | Lighting JB | 18.14% | 0.08864% |  |  |  |  | 0 | 15.6% | 7.57% | 23.17% |  | 0.02478% | 0 |  |  | 0.05412% |  |  |  |  | 0.02478% |  | 0.05412%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | Lighting JB |  | FA-25160051 |  |  | FA-25160051 | Handling | 10% | 0.008864% |  | 142 |  | 142 | 142 | 78.17% | 21.83% | 100% | 142 | 0.008864% | 142 | [6 empty] | 142 | 0.008864% |  |  | ok | 100% | 0.008864%
Plan | 0.0005412 | 0.0003811% | 2.872e-07% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | Lighting JB | 50140 | FA-25160052 |  |  | FA-25160052 | Fixing in place | 85% | 0.07534% |  | 142 |  | 22 | 22 | 9.155% | 6.338% | 15.49% | 30 | 0.01592% | 22 | 102 | 0.71831 | 0.05412% | Week 1 | Week 4 |  | 30 | 0.01592% | 102 | 0.05412% | ok | 21.13% | 0.01592%
[6 empty] | 6 | Unit - CDU | Electrical | Lighting JB |  | FA-25160053 |  |  | FA-25160053 | QC | 5% | 0.004432% |  | 142 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160054 |  |  | FA-25160054 | Lighting Fixture | 71.92% | 0.3514% |  |  |  |  | 0 | 42.69% | 30.73% | 73.41% |  | 0.1197% | 0 |  |  | 0.1888% |  |  |  |  | 0.1197% |  | 0.1888%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | Lighting Fixture |  | FA-25160055 |  |  | FA-25160055 | Handling | 10% | 0.03514% |  | 245 |  | 245 | 245 | 100% | 0% | 100% | 245 | 0.03514% | 245 | [6 empty] | 245 | 0.03514% |  |  | ok | 100% | 0.03514%
Plan | 0.00027587 | 0.0002578% | 1.812e-07% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | Lighting Fixture | 50150 | FA-25160056 |  |  | FA-25160056 | Installation of lighting poles | 20% | 0.07028% |  | 107 |  | 141 | 141 | 56.07% | 75.7% | 131.8% | 50 | 0.03284% | 141 | 42 | 0.39252 | 0.02759% | Week 1 | Week 4 |  | 50 | 0.03284% | 42 | 0.02759% | ok | 46.73% | 0.03284%
Plan | 0.0016124 | 0.0007296% | 1.666e-06% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | Lighting Fixture | 50160 | FA-25160057 |  |  | FA-25160057 | Installation Fixture | 65% | 0.2284% |  | 221 |  | 126 | 126 | 33.03% | 23.98% | 57.01% | 50 | 0.05168% | 126 | 156 | 0.70588 | 0.1612% | Week 1 | Week 4 |  | 50 | 0.05168% | 156 | 0.1612% | ok | 22.62% | 0.05168%
[6 empty] | 6 | Unit - CDU | Electrical | Lighting Fixture |  | FA-25160058 |  |  | FA-25160058 | QC | 5% | 0.01757% |  | 245 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160059 |  |  | FA-25160059 | Lighting Socket | 9.945% | 0.0486% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.04617% | [6 empty] | 0.04617%
Plan | 4.8597e-05 | 0.0002314% | 1.125e-08% |  | Plan Feb | 6 | Unit - CDU | Electrical | Lighting Socket |  | FA-25160060 |  |  | FA-25160060 | Handling | 10% | 0.00486% |  | 21 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 21 | 1 | 0.00486% | Week 4 | Week 4 |  |  |  | 21 | 0.00486% | ok | 0% | 0%
Plan | 0.00041307 | 0.001967% | 8.125e-07% |  | Plan Feb | 6 | Unit - CDU | Electrical | Lighting Socket | 50170 | FA-25160061 |  |  | FA-25160061 | Fixing in place | 85% | 0.04131% |  | 21 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 21 | 1 | 0.04131% | Week 4 | Week 4 |  |  |  | 21 | 0.04131% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Electrical | Lighting Socket |  | FA-25160062 |  |  | FA-25160062 | QC | 5% | 0.00243% |  | 21 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160063 |  |  | FA-25160063 | Electrical Cabling | 35.16% | 1.9% |  |  |  |  | 0 | 8.009% | 39.84% | 47.85% |  | 0.6542% | 0 |  |  | 0.7168% |  |  |  |  | 0.6542% |  | 0.7168%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160064 |  |  | FA-25160064 | MV Cable | 2.488% | 0.04728% |  |  |  |  | 0 | 0% | 76.73% | 76.73% |  | 0.03782% | 0 | [7 empty] | 0.03782%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | MV Cable |  | FA-25160065 |  |  | FA-25160065 | Handling | 10% | 0.004728% |  | 1350 |  | 1350 | 1350 | 0% | 100% | 100% | 1350 | 0.004728% | 1350 | [6 empty] | 1350 | 0.004728% |  |  | ok | 100% | 0.004728%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Electrical | MV Cable | 50180 | FA-25160066 |  |  | FA-25160066 | Cable laying | 70% | 0.03309% |  | 1350 |  | 1287 | 1287 | 0% | 95.33% | 95.33% | 1350 | 0.03309% | 1287 | [6 empty] | 1350 | 0.03309% |  |  | ok | 100% | 0.03309%
[6 empty] | 6 | Unit - CDU | Electrical | MV Cable |  | FA-25160067 |  |  | FA-25160067 | Cable arrangements and fixing | 5% | 0.002364% |  | 1350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | MV Cable |  | FA-25160068 |  |  | FA-25160068 | Cable Marking | 5% | 0.002364% |  | 1350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | MV Cable |  | FA-25160069 |  |  | FA-25160069 | Continuity & Megger Test | 5% | 0.002364% |  | 1350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | MV Cable |  | FA-25160070 |  |  | FA-25160070 | QC | 5% | 0.002364% |  | 1350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160071 |  |  | FA-25160071 | LV Cable | 44.46% | 0.8448% |  |  |  |  | 0 | 10% | 34.99% | 44.99% |  | 0.3362% | 0 |  |  | 0.3397% |  |  |  |  | 0.3362% |  | 0.3397%
Plan | 0.00042463 | 1.76e-06% | 1.487e-09% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | LV Cable |  | FA-25160072 |  |  | FA-25160072 | Handling | 10% | 0.08448% |  | 24124 |  | 24124 | 24124 | 100% | 0% | 100% | 11999 | 0.04202% | 24124 | 12125 | 0.50261 | 0.04246% | Week 2 | Week 4 |  | 11999 | 0.04202% | 12125 | 0.04246% | ok | 49.74% | 0.04202%
Plan | 0.0029724 | 1.232e-05% | 7.287e-08% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | LV Cable | 50190 | FA-25160073 |  |  | FA-25160073 | Cable laying | 70% | 0.5914% |  | 24124 |  | 12059 | 12059 | 0% | 49.99% | 49.99% | 11999 | 0.2942% | 12059 | 12125 | 0.50261 | 0.2972% | Week 2 | Week 4 |  | 11999 | 0.2942% | 12125 | 0.2972% | ok | 49.74% | 0.2942%
[6 empty] | 6 | Unit - CDU | Electrical | LV Cable |  | FA-25160074 |  |  | FA-25160074 | Cable arrangements and fixing | 5% | 0.04224% |  | 24124 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | LV Cable |  | FA-25160075 |  |  | FA-25160075 | Cable Marking | 5% | 0.04224% |  | 24124 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | LV Cable |  | FA-25160076 |  |  | FA-25160076 | Continuity & Megger Test | 5% | 0.04224% |  | 24124 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | LV Cable |  | FA-25160077 |  |  | FA-25160077 | QC | 5% | 0.04224% |  | 24124 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160078 |  |  | FA-25160078 | Control Cable | 33.4% | 0.6348% |  |  |  |  | 0 | 10% | 67.67% | 77.67% |  | 0.2802% | 0 |  |  | 0.2277% |  |  |  |  | 0.2802% |  | 0.2277%
Plan | 0.00028461 | 1.57e-06% | 9.967e-10% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | Control Cable |  | FA-25160079 |  |  | FA-25160079 | Handling | 10% | 0.06348% |  | 18127 |  | 18127 | 18127 | 100% | 0% | 100% | 10000 | 0.03502% | 18127 | 8127 | 0.44834 | 0.02846% | Week 1 | Week 4 |  | 10000 | 0.03502% | 8127 | 0.02846% | ok | 55.17% | 0.03502%
Plan | 0.0019923 | 1.099e-05% | 4.884e-08% | Plan Jan | Plan Feb | 6 | Unit - CDU | Electrical | Control Cable | 50200 | FA-25160080 |  |  | FA-25160080 | Cable laying | 70% | 0.4444% |  | 18127 |  | 17523 | 17523 | 0% | 96.67% | 96.67% | 10000 | 0.2451% | 17523 | 8127 | 0.44834 | 0.1992% | Week 1 | Week 4 |  | 10000 | 0.2451% | 8127 | 0.1992% | ok | 55.17% | 0.2451%
[6 empty] | 6 | Unit - CDU | Electrical | Control Cable |  | FA-25160081 |  |  | FA-25160081 | Cable arrangements and fixing | 5% | 0.03174% |  | 18127 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Control Cable |  | FA-25160082 |  |  | FA-25160082 | Cable Marking | 5% | 0.03174% |  | 18127 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Control Cable |  | FA-25160083 |  |  | FA-25160083 | Continuity & Megger Test | 5% | 0.03174% |  | 18127 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Control Cable |  | FA-25160084 |  |  | FA-25160084 | QC | 5% | 0.03174% |  | 18127 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160085 |  |  | FA-25160085 | Lighting Cable | 19.65% | 0.3735% |  |  |  |  | 0 | 1.136% | -1.136% | 0% |  |  | 0 |  |  | 0.1494% | [6 empty] | 0.1494%
Plan | 0.00018675 | 1.751e-06% | 6.54e-10% |  | Plan Feb | 6 | Unit - CDU | Electrical | Lighting Cable |  | FA-25160086 |  |  | FA-25160086 | Handling | 10% | 0.03735% |  | 10665 |  | 0 | 0 | 1.336% | -1.336% | 0% |  |  | 0 | 5332.5 | 0.5 | 0.01867% | Week 1 | Week 4 |  |  |  | 5332.5 | 0.01867% | ok | 0% | 0%
Plan | 0.0013072 | 1.226e-05% | 3.205e-08% |  | Plan Feb | 6 | Unit - CDU | Electrical | Lighting Cable | 50210 | FA-25160087 |  |  | FA-25160087 | Cable laying | 70% | 0.2614% |  | 10665 |  | 0 | 0 | 1.336% | -1.336% | 0% |  |  | 0 | 5332.5 | 0.5 | 0.1307% | Week 1 | Week 4 |  |  |  | 5332.5 | 0.1307% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Electrical | Lighting Cable |  | FA-25160088 |  |  | FA-25160088 | Cable arrangements and fixing | 5% | 0.01867% |  | 10665 |  | 0 | 0 | 1.336% | -1.336% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Lighting Cable |  | FA-25160089 |  |  | FA-25160089 | Cable Marking | 5% | 0.01867% |  | 10665 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Lighting Cable |  | FA-25160090 |  |  | FA-25160090 | Continuity & Megger Test | 5% | 0.01867% |  | 10665 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Lighting Cable |  | FA-25160091 |  |  | FA-25160091 | QC | 5% | 0.01867% |  | 10665 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160092 |  |  | FA-25160092 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 3.842% | 0.2077% |  |  |  |  | 0 | 7.221% | -6.461% | 0.7601% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160093 |  |  | FA-25160093 | Cable Gland & Termination | 80.63% | 0.1674% |  |  |  |  | 0 | 8.956% | -8.013% | 0.9427% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Cable Gland & Termination |  | FA-25160094 |  |  | FA-25160094 | Handling | 10% | 0.01674% |  | 541 |  | 51 | 51 | 9.427% | 0% | 9.427% |  |  | 51
[6 empty] | 6 | Unit - CDU | Electrical | Cable Gland & Termination | 50220 | FA-25160095 |  |  | FA-25160095 | Gland Installation | 60% | 0.1005% |  | 541 |  | 0 | 0 | 9.427% | -9.427% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Cable Gland & Termination | 50230 | FA-25160096 |  |  | FA-25160096 | Termination | 25% | 0.04186% |  | 541 |  | 0 | 0 | 9.427% | -9.427% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Cable Gland & Termination |  | FA-25160097 |  |  | FA-25160097 | QC | 5% | 0.008372% |  | 541 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160098 |  |  | FA-25160098 | MV Cable Termination kit | 19.37% | 0.04021% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | MV Cable Termination kit |  | FA-25160099 |  |  | FA-25160099 | Handling | 10% | 0.004021% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | MV Cable Termination kit | 50240 | FA-25160100 |  |  | FA-25160100 | Termination Kit | 85% | 0.03418% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | MV Cable Termination kit |  | FA-25160101 |  |  | FA-25160101 | QC | 5% | 0.002011% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160102 |  |  | FA-25160102 | Grounding/ Earthing System | 2.691% | 0.1455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160103 |  |  | FA-25160103 | Earthing Cable Pulling | 100% | 0.1455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Earthing Cable Pulling |  | FA-25160104 |  |  | FA-25160104 | Handling | 10% | 0.01455% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Earthing Cable Pulling | 50250 | FA-25160105 |  |  | FA-25160105 | Cable laying | 75% | 0.1091% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Earthing Cable Pulling |  | FA-25160106 |  |  | FA-25160106 | Cable arrangements and fixing | 10% | 0.01455% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Electrical | Earthing Cable Pulling |  | FA-25160107 |  |  | FA-25160107 | QC | 5% | 0.007273% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Electrical |  |  | FA-25160108 |  |  | FA-25160108 | Unit - LPG/LPT | 9.665% | 3.771% |  |  |  |  | 0 | 11.6% | 10.98% | 22.58% |  | 0.5372% | 0 |  |  | 1.924% |  |  |  |  | 0.5372% |  | 1.924%
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160109 |  |  | FA-25160109 | Cable Tray, ladder, Conduits | 29.71% | 1.12% |  |  |  |  | 0 | 6.631% | 19.34% | 25.97% |  | 0.1556% | 0 |  |  | 0.7295% |  |  |  |  | 0.1556% |  | 0.7295%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160110 |  |  | FA-25160110 | Installation of Primary Tray, ladder | 3.724% | 0.04171% |  |  |  |  | 0 | 57.62% | 5.655% | 63.27% |  | 0.07092% | 0 | [7 empty] | 0.07092%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Installation of Primary Tray, ladder |  | FA-25160111 |  |  | FA-25160111 | Handling | 10% | 0.004171% |  | 252 |  | 252 | 252 | 100% | 0% | 100% | 252 | 0.008343% | 252 | [6 empty] | 252 | 0.008343%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160112 |  |  | FA-25160112 | Tray/ Ladder Assembling | 65% | 0.02711% |  | 252 |  | 179 | 179 | 63.49% | 7.54% | 71.03% | 252 | 0.05423% | 179 | [6 empty] | 252 | 0.05423%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Installation of Primary Tray, ladder |  | FA-25160113 |  |  | FA-25160113 | Fixing & alignment | 10% | 0.004171% |  | 252 |  | 179 | 179 | 63.49% | 7.54% | 71.03% | 252 | 0.008343% | 179 | [6 empty] | 252 | 0.008343%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of Primary Tray, ladder |  | FA-25160114 |  |  | FA-25160114 | Installation of covers | 10% | 0.004171% |  | 252 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of Primary Tray, ladder |  | FA-25160115 |  |  | FA-25160115 | QC | 5% | 0.002086% |  | 252 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160116 |  |  | FA-25160116 | Installation of Secondary Tray | 3.724% | 0.04171% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of Secondary Tray |  | FA-25160117 |  |  | FA-25160117 | Handling | 10% | 0.004171% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of Secondary Tray | 50001 | FA-25160118 |  |  | FA-25160118 | Tray/ Ladder Assembling | 65% | 0.02711% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of Secondary Tray |  | FA-25160119 |  |  | FA-25160119 | Fixing & alignment | 10% | 0.004171% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of Secondary Tray |  | FA-25160120 |  |  | FA-25160120 | Installation of covers | 10% | 0.004171% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of Secondary Tray |  | FA-25160121 |  |  | FA-25160121 | QC | 5% | 0.002086% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160122 |  |  | FA-25160122 | Installation of conduits | 92.55% | 1.037% |  |  |  |  | 0 | 4.846% | 20.67% | 25.51% |  | 0.08473% | 0 |  |  | 0.6803% |  |  |  |  | 0.08473% |  | 0.6803%
Plan | 0.00071606 | 1.648e-05% | 1.709e-08% | Plan Jan | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Installation of conduits |  | FA-25160123 |  |  | FA-25160123 | Handling | 10% | 0.1037% |  | 4344 |  | 1200 | 1200 | 27.62% | 0% | 27.62% | 1000 | 0.02387% | 1200 | 3000 | 0.69061 | 0.07161% | Week 1 | Week 4 |  | 1000 | 0.02387% | 3000 | 0.07161% | ok | 23.02% | 0.02387%
Plan | 0.0060865 | 0.0001401% | 1.235e-06% | Plan Jan | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Installation of conduits | 50010 | FA-25160124 |  |  | FA-25160124 | Installation of Conduit | 85% | 0.8813% |  | 4344 |  | 1162.7 | 1162.7 | 2.452% | 24.31% | 26.77% | 300 | 0.06087% | 1162.7 | 3000 | 0.69061 | 0.6087% | Week 1 | Week 4 |  | 300 | 0.06087% | 3000 | 0.6087% | ok | 6.906% | 0.06087%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Installation of conduits |  | FA-25160125 |  |  | FA-25160125 | QC | 5% | 0.05184% |  | 4344 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160126 |  |  | FA-25160126 | Supports | 5.002% | 0.1886% |  |  |  |  | 0 | 68.52% | 30.02% | 98.54% |  | 0.1189% | 0 | [7 empty] | 0.1189%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160127 |  |  | FA-25160127 | Supports | 100% | 0.1886% |  |  |  |  | 0 | 68.52% | 30.02% | 98.54% |  | 0.1189% | 0 |  |  | 0.04921% |  |  |  |  | 0.1189% |  | 0.04921%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Supports |  | FA-25160128 |  |  | FA-25160128 | Material Supply & Handling | 50% | 0.09431% |  | 1725 |  | 1725 | 1725 | 100% | 0% | 100% | 1725 | 0.09431% | 1725 | [6 empty] | 1725 | 0.09431% |  |  | ok | 100% | 0.09431%
Plan | 0.0002187 | 1.268e-05% | 4.783e-09% | Plan Jan | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Supports | 50020 | FA-25160129 |  |  | FA-25160129 | Fabrication | 20% | 0.03773% |  | 1725 |  | 1860.5763 | 1860.5763 | 41.15% | 66.71% | 107.9% | 500 | 0.01093% | 1860.5763 | 1000 | 0.57971 | 0.02187% | Week 1 | Week 4 |  | 500 | 0.01093% | 1000 | 0.02187% | ok | 28.99% | 0.01093%
Plan | 0.00027337 | 1.585e-05% | 7.473e-09% | Plan Jan | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Supports | 50030 | FA-25160130 |  |  | FA-25160130 | Installation | 25% | 0.04716% |  | 1725 |  | 1860.5763 | 1860.5763 | 41.15% | 66.71% | 107.9% | 500 | 0.01367% | 1860.5763 | 1000 | 0.57971 | 0.02734% | Week 1 | Week 4 |  | 500 | 0.01367% | 1000 | 0.02734% | ok | 28.99% | 0.01367%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Supports |  | FA-25160131 |  |  | FA-25160131 | QC | 5% | 0.009431% |  | 1725 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160132 |  |  | FA-25160132 | EL Transformer/ Panel/ JB | 2.576% | 0.09712% |  |  |  |  | 0 | 7.08% | 0% | 7.08% |  | 0.00764% | 0 |  |  | 0.06934% |  |  |  |  | 0.00764% |  | 0.06934%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160133 |  |  | FA-25160133 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 22.36% | 0.02171% |  |  |  |  | 0 | 31.67% | 0% | 31.67% |  | 0.00764% | 0 | [7 empty] | 0.00764%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160134 |  |  | FA-25160134 | Handling | 10% | 0.002171% |  | 6 |  | 2 | 2 | 33.33% | 0% | 33.33% | 2 | 0.0008042% | 2 | [6 empty] | 2 | 0.0008042%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160135 |  |  | FA-25160135 | Installation | 85% | 0.01846% |  | 6 |  | 2 | 2 | 33.33% | 0% | 33.33% | 2 | 0.006836% | 2 | [6 empty] | 2 | 0.006836%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160136 |  |  | FA-25160136 | QC | 5% | 0.001086% |  | 6 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160137 |  |  | FA-25160137 | Test and Energizing Local Panels Inside Units | 2.484% | 0.002413% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160138 |  |  | FA-25160138 | Energizing | 90% | 0.002171% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160139 |  |  | FA-25160139 | Document | 10% | 0.0002413% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160140 |  |  | FA-25160140 | Local Control Station | 75.16% | 0.07299% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.06934% | [6 empty] | 0.06934%
Plan | 7.2989e-05 | 0.0002281% | 1.665e-08% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Local Control Station |  | FA-25160141 |  |  | FA-25160141 | Handling | 10% | 0.007299% |  | 32 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 32 | 1 | 0.007299% | Week 4 | Week 4 |  |  |  | 32 | 0.007299% | ok | 0% | 0%
Plan | 0.00062041 | 0.001939% | 1.203e-06% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Local Control Station | 50110 | FA-25160142 |  |  | FA-25160142 | Installation | 85% | 0.06204% |  | 32 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 32 | 1 | 0.06204% | Week 4 | Week 4 |  |  |  | 32 | 0.06204% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Local Control Station |  | FA-25160143 |  |  | FA-25160143 | QC | 5% | 0.003649% |  | 32 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160144 |  |  | FA-25160144 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Power Junction Box |  | FA-25160145 |  |  | FA-25160145 | Handling | 10% | 0% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Power Junction Box | 50120 | FA-25160146 |  |  | FA-25160146 | Installation | 85% | 0% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Power Junction Box |  | FA-25160147 |  |  | FA-25160147 | QC | 5% | 0% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160148 |  |  | FA-25160148 | Motor Free Run Test | 3.415% | 0.1288% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160149 |  |  | FA-25160149 | Motor Free Run Test | 100% | 0.1288% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Motor Free Run Test | 50130 | FA-25160150 |  |  | FA-25160150 | Motor Free Run | 95% | 0.1223% |  | 42 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Motor Free Run Test |  | FA-25160151 |  |  | FA-25160151 | QC | 5% | 0.006439% |  | 42 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160152 |  |  | FA-25160152 | Lighting & Small Power System | 19.77% | 0.7456% |  |  |  |  | 0 | 28.4% | 20.92% | 49.32% |  | 0.255% | 0 |  |  | 0.398% |  |  |  |  | 0.255% |  | 0.398%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160153 |  |  | FA-25160153 | Lighting JB | 8.288% | 0.0618% |  |  |  |  | 0 | 38.33% | 8.586% | 46.92% |  | 0.0221% | 0 |  |  | 0.0313% |  |  |  |  | 0.0221% |  | 0.0313%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Lighting JB |  | FA-25160154 |  |  | FA-25160154 | Handling | 10% | 0.00618% |  | 99 |  | 99 | 99 | 100% | 0% | 100% | 99 | 0.00618% | 99 | [6 empty] | 99 | 0.00618% |  |  | ok | 100% | 0.00618%
Plan | 0.00031305 | 0.0003162% | 1.661e-07% | Plan Jan | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Lighting JB | 50140 | FA-25160155 |  |  | FA-25160155 | Fixing in place | 85% | 0.05253% |  | 99 |  | 43 | 43 | 33.33% | 10.1% | 43.43% | 30 | 0.01592% | 43 | 59 | 0.59596 | 0.0313% | Week 1 | Week 4 |  | 30 | 0.01592% | 59 | 0.0313% | ok | 30.3% | 0.01592%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Lighting JB |  | FA-25160156 |  |  | FA-25160156 | QC | 5% | 0.00309% |  | 99 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160157 |  |  | FA-25160157 | Lighting Fixture | 88.61% | 0.6606% |  |  |  |  | 0 | 28.46% | 22.81% | 51.27% |  | 0.2329% | 0 |  |  | 0.3447% |  |  |  |  | 0.2329% |  | 0.3447%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Electrical | Lighting Fixture |  | FA-25160158 |  |  | FA-25160158 | Handling | 10% | 0.06606% |  | 397 |  | 397 | 397 | 100% | 0% | 100% | 397 | 0.06606% | 397 | [6 empty] | 397 | 0.06606% |  |  | ok | 100% | 0.06606%
Plan | 0.00066569 | 0.0002541% | 3.357e-07% | Plan Jan | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Lighting Fixture | 50150 | FA-25160159 |  |  | FA-25160159 | Installation of lighting poles | 20% | 0.1321% |  | 262 |  | 123 | 123 | 18.32% | 28.63% | 46.95% | 100 | 0.05043% | 123 | 132 | 0.50382 | 0.06657% | Week 1 | Week 4 |  | 100 | 0.05043% | 132 | 0.06657% | ok | 38.17% | 0.05043%
Plan | 0.0027813 | 0.0007538% | 3.237e-06% | Plan Jan | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Lighting Fixture | 50160 | FA-25160160 |  |  | FA-25160160 | Installation Fixture | 65% | 0.4294% |  | 369 |  | 181 | 181 | 22.76% | 26.29% | 49.05% | 100 | 0.1164% | 181 | 239 | 0.6477 | 0.2781% | Week 1 | Week 4 |  | 100 | 0.1164% | 239 | 0.2781% | ok | 27.1% | 0.1164%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Lighting Fixture |  | FA-25160161 |  |  | FA-25160161 | QC | 5% | 0.03303% |  | 397 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160162 |  |  | FA-25160162 | Lighting Socket | 3.104% | 0.02314% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.02198% | [6 empty] | 0.02198%
Plan | 2.3141e-05 | 0.0002314% | 5.355e-09% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Lighting Socket |  | FA-25160163 |  |  | FA-25160163 | Handling | 10% | 0.002314% |  | 10 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 10 | 1 | 0.002314% | Week 4 | Week 4 |  |  |  | 10 | 0.002314% | ok | 0% | 0%
Plan | 0.0001967 | 0.001967% | 3.869e-07% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Lighting Socket | 50170 | FA-25160164 |  |  | FA-25160164 | Fixing in place | 85% | 0.01967% |  | 10 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 10 | 1 | 0.01967% | Week 4 | Week 4 |  |  |  | 10 | 0.01967% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Lighting Socket |  | FA-25160165 |  |  | FA-25160165 | QC | 5% | 0.001157% |  | 10 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160166 |  |  | FA-25160166 | Electrical Heat Tracing | 3.801% | 0.1433% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160167 |  |  | FA-25160167 | Electrical Heat Tracing Cabling | 100% | 0.1433% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Electrical Heat Tracing Cabling |  | FA-25160168 |  |  | FA-25160168 | Handling | 10% | 0.01433% |  | 927 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Electrical Heat Tracing Cabling | 80001 | FA-25160169 |  |  | FA-25160169 | Cable laying | 45% | 0.0645% |  | 927 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Electrical Heat Tracing Cabling |  | FA-25160170 |  |  | FA-25160170 | Cable arrangements and fixing | 10% | 0.01433% |  | 927 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Electrical Heat Tracing Cabling | 80010 | FA-25160171 |  |  | FA-25160171 | Gland Installation | 20% | 0.02867% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Electrical Heat Tracing Cabling | 80020 | FA-25160172 |  |  | FA-25160172 | Termination | 10% | 0.01433% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Electrical Heat Tracing Cabling |  | FA-25160173 |  |  | FA-25160173 | QC | 5% | 0.007167% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160174 |  |  | FA-25160174 | Electrical Cabling | 26.45% | 0.9974% |  |  |  |  | 0 | 0.3403% | -0.3403% | 0% |  |  | 0 |  |  | 0.7274% | [6 empty] | 0.7274%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160175 |  |  | FA-25160175 | LV Cable | 47.23% | 0.471% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.3768% | [6 empty] | 0.3768%
Plan | 0.00047103 | 3.502e-06% | 1.65e-09% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | LV Cable |  | FA-25160176 |  |  | FA-25160176 | Handling | 10% | 0.0471% |  | 13450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 13450 | 1 | 0.0471% | Week 2 | Week 4 |  |  |  | 13450 | 0.0471% | ok | 0% | 0%
Plan | 0.0032972 | 2.451e-05% | 8.083e-08% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | LV Cable | 50190 | FA-25160177 |  |  | FA-25160177 | Cable laying | 70% | 0.3297% |  | 13450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 13450 | 1 | 0.3297% | Week 2 | Week 4 |  |  |  | 13450 | 0.3297% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | LV Cable |  | FA-25160178 |  |  | FA-25160178 | Cable arrangements and fixing | 5% | 0.02355% |  | 13450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | LV Cable |  | FA-25160179 |  |  | FA-25160179 | Cable Marking | 5% | 0.02355% |  | 13450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | LV Cable |  | FA-25160180 |  |  | FA-25160180 | Continuity & Megger Test | 5% | 0.02355% |  | 13450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | LV Cable |  | FA-25160181 |  |  | FA-25160181 | QC | 5% | 0.02355% |  | 13450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160182 |  |  | FA-25160182 | Control Cable | 35.09% | 0.35% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.28% | [6 empty] | 0.28%
Plan | 0.00035 | 3.502e-06% | 1.226e-09% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Control Cable |  | FA-25160183 |  |  | FA-25160183 | Handling | 10% | 0.035% |  | 9994 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 9994 | 1 | 0.035% | Week 2 | Week 4 |  |  |  | 9994 | 0.035% | ok | 0% | 0%
Plan | 0.00245 | 2.451e-05% | 6.006e-08% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Control Cable | 50200 | FA-25160184 |  |  | FA-25160184 | Cable laying | 70% | 0.245% |  | 9994 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 9994 | 1 | 0.245% | Week 2 | Week 4 |  |  |  | 9994 | 0.245% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Control Cable |  | FA-25160185 |  |  | FA-25160185 | Cable arrangements and fixing | 5% | 0.0175% |  | 9994 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Control Cable |  | FA-25160186 |  |  | FA-25160186 | Cable Marking | 5% | 0.0175% |  | 9994 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Control Cable |  | FA-25160187 |  |  | FA-25160187 | Continuity & Megger Test | 5% | 0.0175% |  | 9994 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Control Cable |  | FA-25160188 |  |  | FA-25160188 | QC | 5% | 0.0175% |  | 9994 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160189 |  |  | FA-25160189 | Lighting Cable | 17.68% | 0.1763% |  |  |  |  | 0 | 1.925% | -1.925% | 0% |  |  | 0 |  |  | 0.07053% | [6 empty] | 0.07053%
Plan | 8.8165e-05 | 1.751e-06% | 3.088e-10% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Lighting Cable |  | FA-25160190 |  |  | FA-25160190 | Handling | 10% | 0.01763% |  | 5035 |  | 0 | 0 | 2.264% | -2.264% | 0% |  |  | 0 | 2517.5 | 0.5 | 0.008817% | Week 1 | Week 4 |  |  |  | 2517.5 | 0.008817% | ok | 0% | 0%
Plan | 0.00061716 | 1.226e-05% | 1.513e-08% |  | Plan Feb | 6 | Unit - LPG/LPT | Electrical | Lighting Cable | 50210 | FA-25160191 |  |  | FA-25160191 | Cable laying | 70% | 0.1234% |  | 5035 |  | 0 | 0 | 2.264% | -2.264% | 0% |  |  | 0 | 2517.5 | 0.5 | 0.06172% | Week 1 | Week 4 |  |  |  | 2517.5 | 0.06172% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Lighting Cable |  | FA-25160192 |  |  | FA-25160192 | Cable arrangements and fixing | 5% | 0.008817% |  | 5035 |  | 0 | 0 | 2.264% | -2.264% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Lighting Cable |  | FA-25160193 |  |  | FA-25160193 | Cable Marking | 5% | 0.008817% |  | 5035 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Lighting Cable |  | FA-25160194 |  |  | FA-25160194 | Continuity & Megger Test | 5% | 0.008817% |  | 5035 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Lighting Cable |  | FA-25160195 |  |  | FA-25160195 | QC | 5% | 0.008817% |  | 5035 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160196 |  |  | FA-25160196 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 4.933% | 0.186% |  |  |  |  | 0 | 6.323% | -6.323% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160197 |  |  | FA-25160197 | Cable Gland & Termination | 100% | 0.186% |  |  |  |  | 0 | 6.323% | -6.323% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Cable Gland & Termination |  | FA-25160198 |  |  | FA-25160198 | Handling | 10% | 0.0186% | No | 601 |  | 0 | 0 | 6.656% | -6.656% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Cable Gland & Termination | 50220 | FA-25160199 |  |  | FA-25160199 | Gland Installation | 60% | 0.1116% | No | 601 |  | 0 | 0 | 6.656% | -6.656% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Cable Gland & Termination | 50230 | FA-25160200 |  |  | FA-25160200 | Termination | 25% | 0.0465% | Core | 601 |  | 0 | 0 | 6.656% | -6.656% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Cable Gland & Termination |  | FA-25160201 |  |  | FA-25160201 | QC | 5% | 0.0093% | No | 601 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160202 |  |  | FA-25160202 | Grounding/ Earthing System | 4.34% | 0.1636% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160203 |  |  | FA-25160203 | Earthing Cable Pulling | 100% | 0.1636% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Earthing Cable Pulling |  | FA-25160204 |  |  | FA-25160204 | Handling | 10% | 0.01636% | M | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Earthing Cable Pulling | 50250 | FA-25160205 |  |  | FA-25160205 | Cable laying | 75% | 0.1227% | M | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Earthing Cable Pulling |  | FA-25160206 |  |  | FA-25160206 | Cable arrangements and fixing | 10% | 0.01636% | M | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Electrical | Earthing Cable Pulling |  | FA-25160207 |  |  | FA-25160207 | QC | 5% | 0.008182% | M | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Electrical |  |  | FA-25160208 |  |  | FA-25160208 | Unit - UTILITY | 9.8% | 3.823% |  |  |  |  | 0 | 3.411% | 0.7116% | 4.123% |  | 0.1258% | 0 |  |  | 1.555% |  |  |  |  | 0.1258% |  | 1.555%
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160209 |  |  | FA-25160209 | Cable Tray, ladder, Conduits | 22.07% | 0.8438% |  |  |  |  | 0 | 0.5532% | 0% | 0.5532% |  |  | 0 |  |  | 0.03968% | [6 empty] | 0.03968%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160210 |  |  | FA-25160210 | Installation of Primary Tray, ladder | 5.532% | 0.04668% |  |  |  |  | 0 | 10% | 0% | 10% |  |  | 0 |  |  | 0.03968% | [6 empty] | 0.03968%
Plan | 4.6681e-05 | 1.655e-05% | 7.727e-10% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Installation of Primary Tray, ladder |  | FA-25160211 |  |  | FA-25160211 | Handling | 10% | 0.004668% |  | 282 |  | 282 | 282 | 100% | 0% | 100% |  |  | 282 | 282 | 1 | 0.004668% | Week 3 | Week 4 |  |  |  | 282 | 0.004668% | ok | 0% | 0%
Plan | 0.00030343 | 0.0001076% | 3.265e-08% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160212 |  |  | FA-25160212 | Tray/ Ladder Assembling | 65% | 0.03034% |  | 282 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 282 | 1 | 0.03034% | Week 3 | Week 4 |  |  |  | 282 | 0.03034% | ok | 0% | 0%
Plan | 4.6681e-05 | 1.655e-05% | 7.727e-10% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Installation of Primary Tray, ladder |  | FA-25160213 |  |  | FA-25160213 | Fixing & alignment | 10% | 0.004668% |  | 282 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 282 | 1 | 0.004668% | Week 3 | Week 4 |  |  |  | 282 | 0.004668% | ok | 0% | 0%
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of Primary Tray, ladder |  | FA-25160214 |  |  | FA-25160214 | Installation of covers | 10% | 0.004668% |  | 282 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of Primary Tray, ladder |  | FA-25160215 |  |  | FA-25160215 | QC | 5% | 0.002334% |  | 282 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160216 |  |  | FA-25160216 | Installation of Secondary Tray | 5.532% | 0.04668% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of Secondary Tray |  | FA-25160217 |  |  | FA-25160217 | Handling | 10% | 0.004668% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of Secondary Tray | 50001 | FA-25160218 |  |  | FA-25160218 | Tray/ Ladder Assembling | 65% | 0.03034% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of Secondary Tray |  | FA-25160219 |  |  | FA-25160219 | Fixing & alignment | 10% | 0.004668% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of Secondary Tray |  | FA-25160220 |  |  | FA-25160220 | Installation of covers | 10% | 0.004668% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of Secondary Tray |  | FA-25160221 |  |  | FA-25160221 | QC | 5% | 0.002334% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160222 |  |  | FA-25160222 | Installation of conduits | 88.94% | 0.7504% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of conduits |  | FA-25160223 |  |  | FA-25160223 | Handling | 10% | 0.07504% |  | 3144 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of conduits | 50010 | FA-25160224 |  |  | FA-25160224 | Installation of Conduit | 85% | 0.6379% |  | 3144 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Installation of conduits |  | FA-25160225 |  |  | FA-25160225 | QC | 5% | 0.03752% |  | 3144 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160226 |  |  | FA-25160226 | Supports | 6.578% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 |  |  | 0.1132% |  |  |  |  | 0.1258% |  | 0.1132%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160227 |  |  | FA-25160227 | Supports | 100% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 |  |  | 0.1132% |  |  |  |  | 0.1258% |  | 0.1132%
|  |  |  | Plan Jan |  | 6 | Unit - UTILITY | Electrical | Supports |  | FA-25160228 |  |  | FA-25160228 | Material Supply & Handling | 50% | 0.1258% |  | 2300 |  | 2300 | 2300 | 100% | 0% | 100% | 2300 | 0.1258% | 2300 | [6 empty] | 2300 | 0.1258%
Plan | 0.00050301 | 2.187e-05% | 1.1e-08% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Supports | 50020 | FA-25160229 |  |  | FA-25160229 | Fabrication | 20% | 0.0503% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2300 | 1 | 0.0503% | Week 3 | Week 4 |  |  |  | 2300 | 0.0503% | ok | 0% | 0%
Plan | 0.00062876 | 2.734e-05% | 1.719e-08% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Supports | 50030 | FA-25160230 |  |  | FA-25160230 | Installation | 25% | 0.06288% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2300 | 1 | 0.06288% | Week 3 | Week 4 |  |  |  | 2300 | 0.06288% | ok | 0% | 0%
[6 empty] | 6 | Unit - UTILITY | Electrical | Supports |  | FA-25160231 |  |  | FA-25160231 | QC | 5% | 0.01258% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160232 |  |  | FA-25160232 | EL Transformer/ Panel/ JB | 4.755% | 0.1818% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160233 |  |  | FA-25160233 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 69.67% | 0.1267% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160234 |  |  | FA-25160234 | Handling | 10% | 0.01267% |  | 35 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160235 |  |  | FA-25160235 | Installation | 85% | 0.1077% |  | 35 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160236 |  |  | FA-25160236 | QC | 5% | 0.006333% |  | 35 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160237 |  |  | FA-25160237 | Test and Energizing Local Panels Inside Units | 7.742% | 0.01407% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160238 |  |  | FA-25160238 | Energizing | 90% | 0.01267% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160239 |  |  | FA-25160239 | Document | 10% | 0.001407% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160240 |  |  | FA-25160240 | Local Control Station | 22.58% | 0.04106% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Local Control Station |  | FA-25160241 |  |  | FA-25160241 | Handling | 10% | 0.004106% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Local Control Station | 50110 | FA-25160242 |  |  | FA-25160242 | Installation | 85% | 0.0349% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Local Control Station |  | FA-25160243 |  |  | FA-25160243 | QC | 5% | 0.002053% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160244 |  |  | FA-25160244 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Power Junction Box |  | FA-25160245 |  |  | FA-25160245 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Power Junction Box | 50120 | FA-25160246 |  |  | FA-25160246 | Installation | 85% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Power Junction Box |  | FA-25160247 |  |  | FA-25160247 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160248 |  |  | FA-25160248 | Motor Free Run Test | 6.415% | 0.2453% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160249 |  |  | FA-25160249 | Motor Free Run Test | 100% | 0.2453% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Motor Free Run Test | 50130 | FA-25160250 |  |  | FA-25160250 | Motor Free Run | 95% | 0.233% |  | 80 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Motor Free Run Test |  | FA-25160251 |  |  | FA-25160251 | QC | 5% | 0.01226% |  | 80 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160252 |  |  | FA-25160252 | Lighting & Small Power System | 10.04% | 0.3837% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.1476% | [6 empty] | 0.1476%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160253 |  |  | FA-25160253 | Lighting JB | 8.134% | 0.03121% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.01186% | [6 empty] | 0.01186%
Plan | 1.2484e-05 | 2.497e-05% | 7.793e-10% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Lighting JB |  | FA-25160254 |  |  | FA-25160254 | Handling | 10% | 0.003121% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 20 | 0.4 | 0.001248% | Week 3 | Week 4 |  |  |  | 20 | 0.001248% | ok | 0% | 0%
Plan | 0.00010612 | 0.0002122% | 5.63e-08% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Lighting JB | 50140 | FA-25160255 |  |  | FA-25160255 | Fixing in place | 85% | 0.02653% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 20 | 0.4 | 0.01061% | Week 3 | Week 4 |  |  |  | 20 | 0.01061% | ok | 0% | 0%
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting JB |  | FA-25160256 |  |  | FA-25160256 | QC | 5% | 0.001561% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160257 |  |  | FA-25160257 | Lighting Fixture | 77.39% | 0.297% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.1358% | [6 empty] | 0.1358%
Plan | 0.00029697 | 0.0001286% | 3.818e-08% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Lighting Fixture |  | FA-25160258 |  |  | FA-25160258 | Handling | 10% | 0.0297% |  | 231 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 231 | 1 | 0.0297% | Week 3 | Week 4 |  |  |  | 231 | 0.0297% | ok | 0% | 0%
Plan | 0.00022498 | 0.0001704% | 1.012e-07% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Lighting Fixture | 50150 | FA-25160259 |  |  | FA-25160259 | Installation of lighting poles | 20% | 0.05939% |  | 132 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 50 | 0.37879 | 0.0225% | Week 3 | Week 4 |  |  |  | 50 | 0.0225% | ok | 0% | 0%
Plan | 0.00083562 | 0.0003617% | 6.983e-07% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Lighting Fixture | 50160 | FA-25160260 |  |  | FA-25160260 | Installation Fixture | 65% | 0.193% |  | 231 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 100 | 0.4329 | 0.08356% | Week 3 | Week 4 |  |  |  | 100 | 0.08356% | ok | 0% | 0%
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Fixture |  | FA-25160261 |  |  | FA-25160261 | QC | 5% | 0.01485% |  | 231 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160262 |  |  | FA-25160262 | Lighting Socket | 14.47% | 0.05554% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Socket |  | FA-25160263 |  |  | FA-25160263 | Handling | 10% | 0.005554% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Socket | 50170 | FA-25160264 |  |  | FA-25160264 | Fixing in place | 85% | 0.04721% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Socket |  | FA-25160265 |  |  | FA-25160265 | QC | 5% | 0.002777% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160266 |  |  | FA-25160266 | Electrical Cabling | 43.2% | 1.652% |  |  |  |  | 0 | 0% | 1.647% | 1.647% |  |  | 0 |  |  | 1.255% | [6 empty] | 1.255%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160267 |  |  | FA-25160267 | MV Cable | 3.16% | 0.05218% |  |  |  |  | 0 | 0% | 52.14% | 52.14% |  |  | 0 |  |  | 0.04435% | [6 empty] | 0.04435%
Plan | 5.2181e-05 | 3.502e-06% | 1.827e-10% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | MV Cable |  | FA-25160268 |  |  | FA-25160268 | Handling | 10% | 0.005218% |  | 1490 |  | 1490 | 1490 | 0% | 100% | 100% |  |  | 1490 | 1490 | 1 | 0.005218% | Week 3 | Week 4 |  |  |  | 1490 | 0.005218% | ok | 0% | 0%
Plan | 0.00036527 | 2.451e-05% | 8.954e-09% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | MV Cable | 50180 | FA-25160269 |  |  | FA-25160269 | Cable laying | 70% | 0.03653% |  | 1490 |  | 897 | 897 | 0% | 60.2% | 60.2% |  |  | 897 | 1490 | 1 | 0.03653% | Week 3 | Week 4 |  |  |  | 1490 | 0.03653% | ok | 0% | 0%
Plan | 2.6091e-05 | 1.751e-06% | 4.569e-11% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | MV Cable |  | FA-25160270 |  |  | FA-25160270 | Cable arrangements and fixing | 5% | 0.002609% |  | 1490 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 1490 | 1 | 0.002609% | Week 3 | Week 4 |  |  |  | 1490 | 0.002609% | ok | 0% | 0%
[6 empty] | 6 | Unit - UTILITY | Electrical | MV Cable |  | FA-25160271 |  |  | FA-25160271 | Cable Marking | 5% | 0.002609% |  | 1490 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | MV Cable |  | FA-25160272 |  |  | FA-25160272 | Continuity & Megger Test | 5% | 0.002609% |  | 1490 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | MV Cable |  | FA-25160273 |  |  | FA-25160273 | QC | 5% | 0.002609% |  | 1490 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160274 |  |  | FA-25160274 | LV Cable | 58.49% | 0.9659% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.8211% | [6 empty] | 0.8211%
Plan | 0.00096595 | 3.502e-06% | 3.383e-09% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | LV Cable |  | FA-25160275 |  |  | FA-25160275 | Handling | 10% | 0.09659% |  | 27582 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 27582 | 1 | 0.09659% | Week 3 | Week 4 | Conditional by other discipline |  |  | 27582 | 0.09659% | ok | 0% | 0%
Plan | 0.0067616 | 2.451e-05% | 1.658e-07% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | LV Cable | 50190 | FA-25160276 |  |  | FA-25160276 | Cable laying | 70% | 0.6762% |  | 27582 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 27582 | 1 | 0.6762% | Week 3 | Week 4 | Conditional by other discipline |  |  | 27582 | 0.6762% | ok | 0% | 0%
Plan | 0.00048297 | 1.751e-06% | 8.457e-10% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | LV Cable |  | FA-25160277 |  |  | FA-25160277 | Cable arrangements and fixing | 5% | 0.0483% |  | 27582 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 27582 | 1 | 0.0483% | Week 3 | Week 4 | Conditional by other discipline |  |  | 27582 | 0.0483% | ok | 0% | 0%
[6 empty] | 6 | Unit - UTILITY | Electrical | LV Cable |  | FA-25160278 |  |  | FA-25160278 | Cable Marking | 5% | 0.0483% |  | 27582 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | LV Cable |  | FA-25160279 |  |  | FA-25160279 | Continuity & Megger Test | 5% | 0.0483% |  | 27582 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | LV Cable |  | FA-25160280 |  |  | FA-25160280 | QC | 5% | 0.0483% |  | 27582 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160281 |  |  | FA-25160281 | Control Cable | 27.75% | 0.4583% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.3896% | [6 empty] | 0.3896%
Plan | 0.00045832 | 3.502e-06% | 1.605e-09% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Control Cable |  | FA-25160282 |  |  | FA-25160282 | Handling | 10% | 0.04583% |  | 13087 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 13087 | 1 | 0.04583% | Week 3 | Week 4 | Conditional by other discipline |  |  | 13087 | 0.04583% | ok | 0% | 0%
Plan | 0.0032082 | 2.451e-05% | 7.865e-08% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Control Cable | 50200 | FA-25160283 |  |  | FA-25160283 | Cable laying | 70% | 0.3208% |  | 13087 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 13087 | 1 | 0.3208% | Week 3 | Week 4 | Conditional by other discipline |  |  | 13087 | 0.3208% | ok | 0% | 0%
Plan | 0.00022916 | 1.751e-06% | 4.013e-10% |  | Plan Feb | 6 | Unit - UTILITY | Electrical | Control Cable |  | FA-25160284 |  |  | FA-25160284 | Cable arrangements and fixing | 5% | 0.02292% |  | 13087 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 13087 | 1 | 0.02292% | Week 3 | Week 4 | Conditional by other discipline |  |  | 13087 | 0.02292% | ok | 0% | 0%
[6 empty] | 6 | Unit - UTILITY | Electrical | Control Cable |  | FA-25160285 |  |  | FA-25160285 | Cable Marking | 5% | 0.02292% |  | 13087 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Control Cable |  | FA-25160286 |  |  | FA-25160286 | Continuity & Megger Test | 5% | 0.02292% |  | 13087 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Control Cable |  | FA-25160287 |  |  | FA-25160287 | QC | 5% | 0.02292% |  | 13087 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160288 |  |  | FA-25160288 | Lighting Cable | 10.6% | 0.1751% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Cable |  | FA-25160289 |  |  | FA-25160289 | Handling | 10% | 0.01751% |  | 5000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Cable | 50210 | FA-25160290 |  |  | FA-25160290 | Cable laying | 70% | 0.1226% |  | 5000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Cable |  | FA-25160291 |  |  | FA-25160291 | Cable arrangements and fixing | 5% | 0.008755% |  | 5000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Cable |  | FA-25160292 |  |  | FA-25160292 | Cable Marking | 5% | 0.008755% |  | 5000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Cable |  | FA-25160293 |  |  | FA-25160293 | Continuity & Megger Test | 5% | 0.008755% |  | 5000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Lighting Cable |  | FA-25160294 |  |  | FA-25160294 | QC | 5% | 0.008755% |  | 5000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160295 |  |  | FA-25160295 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 4.573% | 0.1748% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160296 |  |  | FA-25160296 | Cable Gland & Termination | 77% | 0.1346% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Cable Gland & Termination |  | FA-25160297 |  |  | FA-25160297 | Handling | 10% | 0.01346% |  | 435 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Cable Gland & Termination | 50220 | FA-25160298 |  |  | FA-25160298 | Gland Installation | 60% | 0.08078% |  | 435 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Cable Gland & Termination | 50230 | FA-25160299 |  |  | FA-25160299 | Termination | 25% | 0.03366% |  | 435 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Cable Gland & Termination |  | FA-25160300 |  |  | FA-25160300 | QC | 5% | 0.006732% |  | 435 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160301 |  |  | FA-25160301 | MV Cable Termination kit | 23% | 0.04021% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | MV Cable Termination kit |  | FA-25160302 |  |  | FA-25160302 | Handling | 10% | 0.004021% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | MV Cable Termination kit | 50240 | FA-25160303 |  |  | FA-25160303 | Termination Kit | 85% | 0.03418% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | MV Cable Termination kit |  | FA-25160304 |  |  | FA-25160304 | QC | 5% | 0.002011% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160305 |  |  | FA-25160305 | Grounding/ Earthing System | 2.378% | 0.09091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160306 |  |  | FA-25160306 | Earthing Cable Pulling | 100% | 0.09091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Earthing Cable Pulling |  | FA-25160307 |  |  | FA-25160307 | Handling | 10% | 0.009091% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Earthing Cable Pulling | 50250 | FA-25160308 |  |  | FA-25160308 | Cable laying | 75% | 0.06819% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Earthing Cable Pulling |  | FA-25160309 |  |  | FA-25160309 | Cable arrangements and fixing | 10% | 0.009091% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Electrical | Earthing Cable Pulling |  | FA-25160310 |  |  | FA-25160310 | QC | 5% | 0.004546% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Electrical |  |  | FA-25160311 |  |  | FA-25160311 | Unit - FWS | 2.547% | 0.9939% |  |  |  |  | 0 | 3.493% | 0% | 3.493% |  | 0.03144% | 0 |  |  | 0.2451% |  |  |  |  | 0.03144% |  | 0.1908%
[5 empty] | Plan Feb | 4 |  | Electrical |  |  | FA-25160312 |  |  | FA-25160312 | Cable Tray, ladder, Conduits | 21.87% | 0.2174% |  |  |  |  | 0 | 1.508% | 0% | 1.508% |  |  | 0 |  |  | 0.01055%
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160313 |  |  | FA-25160313 | Installation of Primary Tray, ladder | 15.08% | 0.03278% |  |  |  |  | 0 | 10% | 0% | 10% |  |  | 0 |  |  | 0.01055%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160314 |  |  | FA-25160314 | Handling | 10% | 0.003278% |  | 198 |  | 198 | 198 | 100% | 0% | 100% |  |  | 198 | 75 | 0.37879 | 0.001242%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160315 |  |  | FA-25160315 | Tray/ Ladder Assembling | 65% | 0.0213% |  | 198 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 75 | 0.37879 | 0.00807%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160316 |  |  | FA-25160316 | Fixing & alignment | 10% | 0.003278% |  | 198 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 75 | 0.37879 | 0.001242%
[6 empty] | 6 | Unit - FWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160317 |  |  | FA-25160317 | Installation of covers | 10% | 0.003278% |  | 198 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160318 |  |  | FA-25160318 | QC | 5% | 0.001639% |  | 198 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160319 |  |  | FA-25160319 | Installation of Secondary Tray | 15.08% | 0.03278% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of Secondary Tray |  | FA-25160320 |  |  | FA-25160320 | Handling | 10% | 0.003278% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of Secondary Tray | 50001 | FA-25160321 |  |  | FA-25160321 | Tray/ Ladder Assembling | 65% | 0.0213% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of Secondary Tray |  | FA-25160322 |  |  | FA-25160322 | Fixing & alignment | 10% | 0.003278% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of Secondary Tray |  | FA-25160323 |  |  | FA-25160323 | Installation of covers | 10% | 0.003278% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of Secondary Tray |  | FA-25160324 |  |  | FA-25160324 | QC | 5% | 0.001639% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160325 |  |  | FA-25160325 | Installation of conduits | 69.84% | 0.1518% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of conduits |  | FA-25160326 |  |  | FA-25160326 | Handling | 10% | 0.01518% |  | 636 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of conduits | 50010 | FA-25160327 |  |  | FA-25160327 | Installation of Conduit | 85% | 0.129% |  | 636 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Installation of conduits |  | FA-25160328 |  |  | FA-25160328 | QC | 5% | 0.00759% |  | 636 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160329 |  |  | FA-25160329 | Supports | 6.326% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160330 |  |  | FA-25160330 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - FWS | Electrical | Supports |  | FA-25160331 |  |  | FA-25160331 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% | 575 | 0.03144% | 575 | [6 empty] | 575 | 0.03144%
[6 empty] | 6 | Unit - FWS | Electrical | Supports | 50020 | FA-25160332 |  |  | FA-25160332 | Fabrication | 20% | 0.01258% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Supports | 50030 | FA-25160333 |  |  | FA-25160333 | Installation | 25% | 0.01572% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Supports |  | FA-25160334 |  |  | FA-25160334 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160335 |  |  | FA-25160335 | EL Transformer/ Panel/ JB | 4.855% | 0.04825% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160336 |  |  | FA-25160336 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 90% | 0.04343% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160337 |  |  | FA-25160337 | Handling | 10% | 0.004343% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160338 |  |  | FA-25160338 | Installation | 85% | 0.03691% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160339 |  |  | FA-25160339 | QC | 5% | 0.002171% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160340 |  |  | FA-25160340 | Test and Energizing Local Panels Inside Units | 10% | 0.004825% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160341 |  |  | FA-25160341 | Energizing | 90% | 0.004343% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160342 |  |  | FA-25160342 | Document | 10% | 0.0004825% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160343 |  |  | FA-25160343 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Power Junction Box |  | FA-25160344 |  |  | FA-25160344 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Power Junction Box | 50120 | FA-25160345 |  |  | FA-25160345 | Installation | 85% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Power Junction Box |  | FA-25160346 |  |  | FA-25160346 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160347 |  |  | FA-25160347 | Motor Free Run Test | 7.095% | 0.07052% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160348 |  |  | FA-25160348 | Motor Free Run Test | 100% | 0.07052% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Motor Free Run Test | 50130 | FA-25160349 |  |  | FA-25160349 | Motor Free Run | 95% | 0.06699% |  | 23 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Motor Free Run Test |  | FA-25160350 |  |  | FA-25160350 | QC | 5% | 0.003526% |  | 23 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[5 empty] | Plan Feb | 4 |  | Electrical |  |  | FA-25160351 |  |  | FA-25160351 | Lighting & Small Power System | 10.8% | 0.1074% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.04376%
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160352 |  |  | FA-25160352 | Lighting JB | 10.46% | 0.01124% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.004744%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Lighting JB |  | FA-25160353 |  |  | FA-25160353 | Handling | 10% | 0.001124% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 8 | 0.44444 | 0.0004994%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Lighting JB | 50140 | FA-25160354 |  |  | FA-25160354 | Fixing in place | 85% | 0.009551% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 8 | 0.44444 | 0.004245%
[6 empty] | 6 | Unit - FWS | Electrical | Lighting JB |  | FA-25160355 |  |  | FA-25160355 | QC | 5% | 0.0005618% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160356 |  |  | FA-25160356 | Lighting Fixture | 85.23% | 0.09152% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.03462%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Lighting Fixture |  | FA-25160357 |  |  | FA-25160357 | Handling | 10% | 0.009152% |  | 46 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 20 | 0.43478 | 0.003979%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Lighting Fixture | 50150 | FA-25160358 |  |  | FA-25160358 | Installation of lighting poles | 20% | 0.0183% |  | 46 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 12 | 0.26087 | 0.004775%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Lighting Fixture | 50160 | FA-25160359 |  |  | FA-25160359 | Installation Fixture | 65% | 0.05949% |  | 46 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 20 | 0.43478 | 0.02587%
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Fixture |  | FA-25160360 |  |  | FA-25160360 | QC | 5% | 0.004576% |  | 46 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160361 |  |  | FA-25160361 | Lighting Socket | 4.31% | 0.004628% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.004397%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Lighting Socket |  | FA-25160362 |  |  | FA-25160362 | Handling | 10% | 0.0004628% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2 | 1 | 0.0004628%
[5 empty] | Plan Feb | 6 | Unit - FWS | Electrical | Lighting Socket | 50170 | FA-25160363 |  |  | FA-25160363 | Fixing in place | 85% | 0.003934% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2 | 1 | 0.003934%
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Socket |  | FA-25160364 |  |  | FA-25160364 | QC | 5% | 0.0002314% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160365 |  |  | FA-25160365 | Electrical Cabling | 36.4% | 0.3618% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.1908% | [6 empty] | 0.1908%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160366 |  |  | FA-25160366 | MV Cable | 10.16% | 0.03677% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.02942% | [6 empty] | 0.02942%
Plan | 3.6772e-05 | 3.502e-06% | 1.288e-10% |  | Plan Feb | 6 | Unit - FWS | Electrical | MV Cable |  | FA-25160367 |  |  | FA-25160367 | Handling | 10% | 0.003677% |  | 1050 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 1050 | 1 | 0.003677% | Week 4 | Week 4 | موط به آمادگی ترچ ها |  |  | 1050 | 0.003677% | ok | 0% | 0%
Plan | 0.0002574 | 2.451e-05% | 6.31e-09% |  | Plan Feb | 6 | Unit - FWS | Electrical | MV Cable | 50180 | FA-25160368 |  |  | FA-25160368 | Cable laying | 70% | 0.02574% |  | 1050 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 1050 | 1 | 0.02574% | Week 4 | Week 4 | موط به آمادگی ترچ ها |  |  | 1050 | 0.02574% | ok | 0% | 0%
[6 empty] | 6 | Unit - FWS | Electrical | MV Cable |  | FA-25160369 |  |  | FA-25160369 | Cable arrangements and fixing | 5% | 0.001839% |  | 1050 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | MV Cable |  | FA-25160370 |  |  | FA-25160370 | Cable Marking | 5% | 0.001839% |  | 1050 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | MV Cable |  | FA-25160371 |  |  | FA-25160371 | Continuity & Megger Test | 5% | 0.001839% |  | 1050 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | MV Cable |  | FA-25160372 |  |  | FA-25160372 | QC | 5% | 0.001839% |  | 1050 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160373 |  |  | FA-25160373 | LV Cable | 55.57% | 0.2011% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.1608% | [6 empty] | 0.1608%
Plan | 0.00020105 | 3.502e-06% | 7.041e-10% |  | Plan Feb | 6 | Unit - FWS | Electrical | LV Cable |  | FA-25160374 |  |  | FA-25160374 | Handling | 10% | 0.02011% |  | 5741 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 5741 | 1 | 0.02011% | Week 4 | Week 4 | موط به آمادگی ترچ ها |  |  | 5741 | 0.02011% | ok | 0% | 0%
Plan | 0.0014074 | 2.451e-05% | 3.45e-08% |  | Plan Feb | 6 | Unit - FWS | Electrical | LV Cable | 50190 | FA-25160375 |  |  | FA-25160375 | Cable laying | 70% | 0.1407% |  | 5741 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 5741 | 1 | 0.1407% | Week 4 | Week 4 | موط به آمادگی ترچ ها |  |  | 5741 | 0.1407% | ok | 0% | 0%
[6 empty] | 6 | Unit - FWS | Electrical | LV Cable |  | FA-25160376 |  |  | FA-25160376 | Cable arrangements and fixing | 5% | 0.01005% |  | 5741 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | LV Cable |  | FA-25160377 |  |  | FA-25160377 | Cable Marking | 5% | 0.01005% |  | 5741 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | LV Cable |  | FA-25160378 |  |  | FA-25160378 | Continuity & Megger Test | 5% | 0.01005% |  | 5741 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | LV Cable |  | FA-25160379 |  |  | FA-25160379 | QC | 5% | 0.01005% |  | 5741 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160380 |  |  | FA-25160380 | Control Cable | 0.1936% | 0.0007004% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.0005603% | [6 empty] | 0.0005603%
Plan | 7.0042e-07 | 3.502e-06% | 2.453e-12% |  | Plan Feb | 6 | Unit - FWS | Electrical | Control Cable |  | FA-25160381 |  |  | FA-25160381 | Handling | 10% | 7.004e-05% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 20 | 1 | 7.004e-05% | Week 1 | Week 4 | موط به آمادگی ترچ ها |  |  | 20 | 7.004e-05% | ok | 0% | 0%
Plan | 4.9029e-06 | 2.451e-05% | 1.202e-10% |  | Plan Feb | 6 | Unit - FWS | Electrical | Control Cable | 50200 | FA-25160382 |  |  | FA-25160382 | Cable laying | 70% | 0.0004903% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 20 | 1 | 0.0004903% | Week 1 | Week 4 | موط به آمادگی ترچ ها |  |  | 20 | 0.0004903% | ok | 0% | 0%
[6 empty] | 6 | Unit - FWS | Electrical | Control Cable |  | FA-25160383 |  |  | FA-25160383 | Cable arrangements and fixing | 5% | 3.502e-05% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Control Cable |  | FA-25160384 |  |  | FA-25160384 | Cable Marking | 5% | 3.502e-05% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Control Cable |  | FA-25160385 |  |  | FA-25160385 | Continuity & Megger Test | 5% | 3.502e-05% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Control Cable |  | FA-25160386 |  |  | FA-25160386 | QC | 5% | 3.502e-05% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160387 |  |  | FA-25160387 | Lighting Cable | 34.07% | 0.1233% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Cable |  | FA-25160388 |  |  | FA-25160388 | Handling | 10% | 0.01233% |  | 3520 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Cable | 50210 | FA-25160389 |  |  | FA-25160389 | Cable laying | 70% | 0.08629% |  | 3520 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Cable |  | FA-25160390 |  |  | FA-25160390 | Cable arrangements and fixing | 5% | 0.006164% |  | 3520 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Cable |  | FA-25160391 |  |  | FA-25160391 | Cable Marking | 5% | 0.006164% |  | 3520 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Cable |  | FA-25160392 |  |  | FA-25160392 | Continuity & Megger Test | 5% | 0.006164% |  | 3520 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Lighting Cable |  | FA-25160393 |  |  | FA-25160393 | QC | 5% | 0.006164% |  | 3520 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160394 |  |  | FA-25160394 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 7.16% | 0.07116% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160395 |  |  | FA-25160395 | Cable Gland & Termination | 43.49% | 0.03095% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Cable Gland & Termination |  | FA-25160396 |  |  | FA-25160396 | Handling | 10% | 0.003095% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Cable Gland & Termination | 50220 | FA-25160397 |  |  | FA-25160397 | Gland Installation | 60% | 0.01857% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Cable Gland & Termination | 50230 | FA-25160398 |  |  | FA-25160398 | Termination | 25% | 0.007737% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Cable Gland & Termination |  | FA-25160399 |  |  | FA-25160399 | QC | 5% | 0.001547% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160400 |  |  | FA-25160400 | MV Cable Termination kit | 56.51% | 0.04021% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | MV Cable Termination kit |  | FA-25160401 |  |  | FA-25160401 | Handling | 10% | 0.004021% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | MV Cable Termination kit | 50240 | FA-25160402 |  |  | FA-25160402 | Termination Kit | 85% | 0.03418% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | MV Cable Termination kit |  | FA-25160403 |  |  | FA-25160403 | QC | 5% | 0.002011% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160404 |  |  | FA-25160404 | Grounding/ Earthing System | 5.488% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160405 |  |  | FA-25160405 | Earthing Cable Pulling | 100% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Earthing Cable Pulling |  | FA-25160406 |  |  | FA-25160406 | Handling | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Earthing Cable Pulling | 50250 | FA-25160407 |  |  | FA-25160407 | Cable laying | 75% | 0.04091% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Earthing Cable Pulling |  | FA-25160408 |  |  | FA-25160408 | Cable arrangements and fixing | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Electrical | Earthing Cable Pulling |  | FA-25160409 |  |  | FA-25160409 | QC | 5% | 0.002727% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Electrical |  |  | FA-25160410 |  |  | FA-25160410 | Unit - SWS | 3.163% | 1.234% |  |  |  |  | 0 | 2.737% | 0% | 2.737% |  | 0.03144% | 0 |  |  | 0.4168% |  |  |  |  | 0.03144% |  | 0.3337%
[5 empty] | Plan Feb | 4 |  | Electrical |  |  | FA-25160411 |  |  | FA-25160411 | Cable Tray, ladder, Conduits | 17.83% | 0.22% |  |  |  |  | 0 | 1.061% | 0% | 1.061% |  |  | 0 |  |  | 0.009849%
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160412 |  |  | FA-25160412 | Installation of Primary Tray, ladder | 10.61% | 0.02334% |  |  |  |  | 0 | 10% | 0% | 10% |  |  | 0 |  |  | 0.009849%
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160413 |  |  | FA-25160413 | Handling | 10% | 0.002334% |  | 141 |  | 141 | 141 | 100% | 0% | 100% | 575 |  | 141 | 70 | 0.49645 | 0.001159% | Week 1 | Week 4 |  | 575
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160414 |  |  | FA-25160414 | Tray/ Ladder Assembling | 65% | 0.01517% |  | 141 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 70 | 0.49645 | 0.007532% | Week 1 | Week 4
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160415 |  |  | FA-25160415 | Fixing & alignment | 10% | 0.002334% |  | 141 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 70 | 0.49645 | 0.001159% | Week 1 | Week 4
[6 empty] | 6 | Unit - SWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160416 |  |  | FA-25160416 | Installation of covers | 10% | 0.002334% |  | 141 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of Primary Tray, ladder |  | FA-25160417 |  |  | FA-25160417 | QC | 5% | 0.001167% |  | 141 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160418 |  |  | FA-25160418 | Installation of Secondary Tray | 10.61% | 0.02334% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of Secondary Tray |  | FA-25160419 |  |  | FA-25160419 | Handling | 10% | 0.002334% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of Secondary Tray | 50001 | FA-25160420 |  |  | FA-25160420 | Tray/ Ladder Assembling | 65% | 0.01517% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of Secondary Tray |  | FA-25160421 |  |  | FA-25160421 | Fixing & alignment | 10% | 0.002334% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of Secondary Tray |  | FA-25160422 |  |  | FA-25160422 | Installation of covers | 10% | 0.002334% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of Secondary Tray |  | FA-25160423 |  |  | FA-25160423 | QC | 5% | 0.001167% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160424 |  |  | FA-25160424 | Installation of conduits | 78.78% | 0.1733% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of conduits |  | FA-25160425 |  |  | FA-25160425 | Handling | 10% | 0.01733% |  | 726 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of conduits | 50010 | FA-25160426 |  |  | FA-25160426 | Installation of Conduit | 85% | 0.1473% |  | 726 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Installation of conduits |  | FA-25160427 |  |  | FA-25160427 | QC | 5% | 0.008664% |  | 726 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160428 |  |  | FA-25160428 | Supports | 5.095% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160429 |  |  | FA-25160429 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - SWS | Electrical | Supports |  | FA-25160430 |  |  | FA-25160430 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% | 575 | 0.03144% | 575 | [6 empty] | 575 | 0.03144%
[6 empty] | 6 | Unit - SWS | Electrical | Supports | 50020 | FA-25160431 |  |  | FA-25160431 | Fabrication | 20% | 0.01258% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Supports | 50030 | FA-25160432 |  |  | FA-25160432 | Installation | 25% | 0.01572% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Supports |  | FA-25160433 |  |  | FA-25160433 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160434 |  |  | FA-25160434 | EL Transformer/ Panel/ JB | 3.521% | 0.04346% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160435 |  |  | FA-25160435 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 33.31% | 0.01448% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160436 |  |  | FA-25160436 | Handling | 10% | 0.001448% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160437 |  |  | FA-25160437 | Installation | 85% | 0.0123% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160438 |  |  | FA-25160438 | QC | 5% | 0.0007238% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160439 |  |  | FA-25160439 | Test and Energizing Local Panels Inside Units | 3.701% | 0.001608% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160440 |  |  | FA-25160440 | Energizing | 90% | 0.001448% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160441 |  |  | FA-25160441 | Document | 10% | 0.0001608% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160442 |  |  | FA-25160442 | Local Control Station | 62.99% | 0.02737% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Local Control Station |  | FA-25160443 |  |  | FA-25160443 | Handling | 10% | 0.002737% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Local Control Station | 50110 | FA-25160444 |  |  | FA-25160444 | Installation | 85% | 0.02327% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Local Control Station |  | FA-25160445 |  |  | FA-25160445 | QC | 5% | 0.001369% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160446 |  |  | FA-25160446 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Power Junction Box |  | FA-25160447 |  |  | FA-25160447 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Power Junction Box | 50120 | FA-25160448 |  |  | FA-25160448 | Installation | 85% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Power Junction Box |  | FA-25160449 |  |  | FA-25160449 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160450 |  |  | FA-25160450 | Motor Free Run Test | 2.982% | 0.03679% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160451 |  |  | FA-25160451 | Motor Free Run Test | 100% | 0.03679% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Motor Free Run Test | 50130 | FA-25160452 |  |  | FA-25160452 | Motor Free Run | 95% | 0.03495% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Motor Free Run Test |  | FA-25160453 |  |  | FA-25160453 | QC | 5% | 0.00184% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[5 empty] | Plan Feb | 4 |  | Electrical |  |  | FA-25160454 |  |  | FA-25160454 | Lighting & Small Power System | 17.05% | 0.2104% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.07329%
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160455 |  |  | FA-25160455 | Lighting JB | 8.308% | 0.01748% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.009488%
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Lighting JB |  | FA-25160456 |  |  | FA-25160456 | Handling | 10% | 0.001748% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 16 | 0.57143 | 0.0009988% | Week 1 | Week 4
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Lighting JB | 50140 | FA-25160457 |  |  | FA-25160457 | Fixing in place | 85% | 0.01486% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 16 | 0.57143 | 0.008489% | Week 1 | Week 4
[6 empty] | 6 | Unit - SWS | Electrical | Lighting JB |  | FA-25160458 |  |  | FA-25160458 | QC | 5% | 0.0008739% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160459 |  |  | FA-25160459 | Lighting Fixture | 82.89% | 0.1744% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.055%
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Lighting Fixture |  | FA-25160460 |  |  | FA-25160460 | Handling | 10% | 0.01744% |  | 108 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 30 | 0.27778 | 0.004844% | Week 1 | Week 4
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Lighting Fixture | 50150 | FA-25160461 |  |  | FA-25160461 | Installation of lighting poles | 20% | 0.03488% |  | 71 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 30 | 0.42254 | 0.01474% | Week 1 | Week 4
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Lighting Fixture | 50160 | FA-25160462 |  |  | FA-25160462 | Installation Fixture | 65% | 0.1134% |  | 96 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 30 | 0.3125 | 0.03542% | Week 1 | Week 4
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Fixture |  | FA-25160463 |  |  | FA-25160463 | QC | 5% | 0.00872% |  | 108 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[5 empty] | Plan Feb | 5 |  | Electrical |  |  | FA-25160464 |  |  | FA-25160464 | Lighting Socket | 8.8% | 0.01851% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.008794%
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Lighting Socket |  | FA-25160465 |  |  | FA-25160465 | Handling | 10% | 0.001851% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 4 | 0.5 | 0.0009257% | Week 1 | Week 4
[5 empty] | Plan Feb | 6 | Unit - SWS | Electrical | Lighting Socket | 50170 | FA-25160466 |  |  | FA-25160466 | Fixing in place | 85% | 0.01574% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 4 | 0.5 | 0.007868% | Week 1 | Week 4
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Socket |  | FA-25160467 |  |  | FA-25160467 | QC | 5% | 0.0009257% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160468 |  |  | FA-25160468 | Electrical Heat Tracing | 0.9799% | 0.01209% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160469 |  |  | FA-25160469 | Electrical Heat Tracing Cabling | 100% | 0.01209% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Heat Tracing Cabling |  | FA-25160470 |  |  | FA-25160470 | Handling | 10% | 0.001209% |  | 82 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Heat Tracing Cabling | 80001 | FA-25160471 |  |  | FA-25160471 | Cable laying | 45% | 0.005441% |  | 82 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Heat Tracing Cabling |  | FA-25160472 |  |  | FA-25160472 | Cable arrangements and fixing | 10% | 0.001209% |  | 82 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Heat Tracing Cabling | 80010 | FA-25160473 |  |  | FA-25160473 | Gland Installation | 20% | 0.002418% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Heat Tracing Cabling | 80020 | FA-25160474 |  |  | FA-25160474 | Termination | 10% | 0.001209% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Electrical Heat Tracing Cabling |  | FA-25160475 |  |  | FA-25160475 | QC | 5% | 0.0006046% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160476 |  |  | FA-25160476 | Electrical Cabling | 43.99% | 0.5428% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.3337% | [6 empty] | 0.3337%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160477 |  |  | FA-25160477 | LV Cable | 46.1% | 0.2502% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2002% | [6 empty] | 0.2002%
Plan | 0.00025022 | 3.502e-06% | 8.763e-10% |  | Plan Feb | 6 | Unit - SWS | Electrical | LV Cable |  | FA-25160478 |  |  | FA-25160478 | Handling | 10% | 0.02502% |  | 7145 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 7145 | 1 | 0.02502% | Week 4 | Week 4 |  |  |  | 7145 | 0.02502% | ok | 0% | 0%
Plan | 0.0017516 | 2.451e-05% | 4.294e-08% |  | Plan Feb | 6 | Unit - SWS | Electrical | LV Cable | 50190 | FA-25160479 |  |  | FA-25160479 | Cable laying | 70% | 0.1752% |  | 7145 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 7145 | 1 | 0.1752% | Week 4 | Week 4 | موط به آمادگی ترچ ها |  |  | 7145 | 0.1752% | ok | 0% | 0%
[6 empty] | 6 | Unit - SWS | Electrical | LV Cable |  | FA-25160480 |  |  | FA-25160480 | Cable arrangements and fixing | 5% | 0.01251% |  | 7145 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | LV Cable |  | FA-25160481 |  |  | FA-25160481 | Cable Marking | 5% | 0.01251% |  | 7145 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | LV Cable |  | FA-25160482 |  |  | FA-25160482 | Continuity & Megger Test | 5% | 0.01251% |  | 7145 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | LV Cable |  | FA-25160483 |  |  | FA-25160483 | QC | 5% | 0.01251% |  | 7145 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160484 |  |  | FA-25160484 | Control Cable | 30.74% | 0.1669% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.1335% | [6 empty] | 0.1335%
Plan | 0.00016687 | 3.502e-06% | 5.844e-10% |  | Plan Feb | 6 | Unit - SWS | Electrical | Control Cable |  | FA-25160485 |  |  | FA-25160485 | Handling | 10% | 0.01669% |  | 4765 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 4765 | 1 | 0.01669% | Week 1 | Week 4 |  |  |  | 4765 | 0.01669% | ok | 0% | 0%
Plan | 0.0011681 | 2.451e-05% | 2.864e-08% |  | Plan Feb | 6 | Unit - SWS | Electrical | Control Cable | 50200 | FA-25160486 |  |  | FA-25160486 | Cable laying | 70% | 0.1168% |  | 4765 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 4765 | 1 | 0.1168% | Week 1 | Week 4 | موط به آمادگی ترچ ها |  |  | 4765 | 0.1168% | ok | 0% | 0%
[6 empty] | 6 | Unit - SWS | Electrical | Control Cable |  | FA-25160487 |  |  | FA-25160487 | Cable arrangements and fixing | 5% | 0.008344% |  | 4765 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Control Cable |  | FA-25160488 |  |  | FA-25160488 | Cable Marking | 5% | 0.008344% |  | 4765 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Control Cable |  | FA-25160489 |  |  | FA-25160489 | Continuity & Megger Test | 5% | 0.008344% |  | 4765 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Control Cable |  | FA-25160490 |  |  | FA-25160490 | QC | 5% | 0.008344% |  | 4765 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160491 |  |  | FA-25160491 | Lighting Cable | 23.16% | 0.1257% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Cable |  | FA-25160492 |  |  | FA-25160492 | Handling | 10% | 0.01257% |  | 3590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Cable | 50210 | FA-25160493 |  |  | FA-25160493 | Cable laying | 70% | 0.08801% |  | 3590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Cable |  | FA-25160494 |  |  | FA-25160494 | Cable arrangements and fixing | 5% | 0.006286% |  | 3590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Cable |  | FA-25160495 |  |  | FA-25160495 | Cable Marking | 5% | 0.006286% |  | 3590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Cable |  | FA-25160496 |  |  | FA-25160496 | Continuity & Megger Test | 5% | 0.006286% |  | 3590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Lighting Cable |  | FA-25160497 |  |  | FA-25160497 | QC | 5% | 0.006286% |  | 3590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160498 |  |  | FA-25160498 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 4.138% | 0.05107% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160499 |  |  | FA-25160499 | Cable Gland & Termination | 100% | 0.05107% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Cable Gland & Termination |  | FA-25160500 |  |  | FA-25160500 | Handling | 10% | 0.005107% |  | 165 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Cable Gland & Termination | 50220 | FA-25160501 |  |  | FA-25160501 | Gland Installation | 60% | 0.03064% |  | 165 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Cable Gland & Termination | 50230 | FA-25160502 |  |  | FA-25160502 | Termination | 25% | 0.01277% |  | 165 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Cable Gland & Termination |  | FA-25160503 |  |  | FA-25160503 | QC | 5% | 0.002553% |  | 165 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160504 |  |  | FA-25160504 | Grounding/ Earthing System | 4.42% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160505 |  |  | FA-25160505 | Earthing Cable Pulling | 100% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Earthing Cable Pulling |  | FA-25160506 |  |  | FA-25160506 | Handling | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Earthing Cable Pulling | 50250 | FA-25160507 |  |  | FA-25160507 | Cable laying | 75% | 0.04091% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Earthing Cable Pulling |  | FA-25160508 |  |  | FA-25160508 | Cable arrangements and fixing | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Electrical | Earthing Cable Pulling |  | FA-25160509 |  |  | FA-25160509 | QC | 5% | 0.002727% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Electrical |  |  | FA-25160510 |  |  | FA-25160510 | Unit - FLS | 1.789% | 0.6979% |  |  |  |  | 0 | 4.505% | 0% | 4.505% |  | 0.03144% | 0 | [7 empty] | 0.03144%
[11 empty] | FA-25160511 |  |  | FA-25160511 | Cable Tray, ladder, Conduits | 30.46% | 0.2126% |  |  |  |  | 0 | 0% | 0% | 0% |  | 0% | 0 | [7 empty] | 0%
[11 empty] | FA-25160512 |  |  | FA-25160512 | Installation of Primary Tray, ladder | 21.03% | 0.04469% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[11 empty] | FA-25160513 |  |  | FA-25160513 | Handling | 10% | 0.004469% |  | 270 |  | 0 | 0 | 0% | 0% | 0% | 575 |  | 0 | [6 empty] | 575
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160514 |  |  | FA-25160514 | Tray/ Ladder Assembling | 65% | 0.02905% |  | 270 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Primary Tray, ladder |  | FA-25160515 |  |  | FA-25160515 | Fixing & alignment | 10% | 0.004469% |  | 270 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Primary Tray, ladder |  | FA-25160516 |  |  | FA-25160516 | Installation of covers | 10% | 0.004469% |  | 270 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Primary Tray, ladder |  | FA-25160517 |  |  | FA-25160517 | QC | 5% | 0.002235% |  | 270 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160518 |  |  | FA-25160518 | Installation of Secondary Tray | 21.03% | 0.04469% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Secondary Tray |  | FA-25160519 |  |  | FA-25160519 | Handling | 10% | 0.004469% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Secondary Tray | 50001 | FA-25160520 |  |  | FA-25160520 | Tray/ Ladder Assembling | 65% | 0.02905% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Secondary Tray |  | FA-25160521 |  |  | FA-25160521 | Fixing & alignment | 10% | 0.004469% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Secondary Tray |  | FA-25160522 |  |  | FA-25160522 | Installation of covers | 10% | 0.004469% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of Secondary Tray |  | FA-25160523 |  |  | FA-25160523 | QC | 5% | 0.002235% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160524 |  |  | FA-25160524 | Installation of conduits | 57.94% | 0.1232% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of conduits |  | FA-25160525 |  |  | FA-25160525 | Handling | 10% | 0.01232% |  | 516 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of conduits | 50010 | FA-25160526 |  |  | FA-25160526 | Installation of Conduit | 85% | 0.1047% |  | 516 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Installation of conduits |  | FA-25160527 |  |  | FA-25160527 | QC | 5% | 0.006158% |  | 516 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160528 |  |  | FA-25160528 | Supports | 9.01% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160529 |  |  | FA-25160529 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - FLS | Electrical | Supports |  | FA-25160530 |  |  | FA-25160530 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% |  | 0.03144% | 575 | [7 empty] | 0.03144%
[6 empty] | 6 | Unit - FLS | Electrical | Supports | 50020 | FA-25160531 |  |  | FA-25160531 | Fabrication | 20% | 0.01258% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Supports | 50030 | FA-25160532 |  |  | FA-25160532 | Installation | 25% | 0.01572% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Supports |  | FA-25160533 |  |  | FA-25160533 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160534 |  |  | FA-25160534 | EL Transformer/ Panel/ JB | 2.46% | 0.01717% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160535 |  |  | FA-25160535 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 42.16% | 0.007238% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160536 |  |  | FA-25160536 | Handling | 10% | 0.0007238% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160537 |  |  | FA-25160537 | Installation | 85% | 0.006152% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160538 |  |  | FA-25160538 | QC | 5% | 0.0003619% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160539 |  |  | FA-25160539 | Test and Energizing Local Panels Inside Units | 4.685% | 0.0008042% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160540 |  |  | FA-25160540 | Energizing | 90% | 0.0007238% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160541 |  |  | FA-25160541 | Document | 10% | 8.042e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160542 |  |  | FA-25160542 | Local Control Station | 53.15% | 0.009124% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Local Control Station |  | FA-25160543 |  |  | FA-25160543 | Handling | 10% | 0.0009124% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Local Control Station | 50110 | FA-25160544 |  |  | FA-25160544 | Installation | 85% | 0.007755% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Local Control Station |  | FA-25160545 |  |  | FA-25160545 | QC | 5% | 0.0004562% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160546 |  |  | FA-25160546 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Power Junction Box |  | FA-25160547 |  |  | FA-25160547 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Power Junction Box | 50120 | FA-25160548 |  |  | FA-25160548 | Installation | 85% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Power Junction Box |  | FA-25160549 |  |  | FA-25160549 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160550 |  |  | FA-25160550 | Motor Free Run Test | 1.757% | 0.01226% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160551 |  |  | FA-25160551 | Motor Free Run Test | 100% | 0.01226% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Motor Free Run Test | 50130 | FA-25160552 |  |  | FA-25160552 | Motor Free Run | 95% | 0.01165% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Motor Free Run Test |  | FA-25160553 |  |  | FA-25160553 | QC | 5% | 0.0006132% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160554 |  |  | FA-25160554 | Lighting & Small Power System | 16.07% | 0.1121% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160555 |  |  | FA-25160555 | Lighting JB | 10.58% | 0.01186% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting JB |  | FA-25160556 |  |  | FA-25160556 | Handling | 10% | 0.001186% |  | 19 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting JB | 50140 | FA-25160557 |  |  | FA-25160557 | Fixing in place | 85% | 0.01008% |  | 19 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting JB |  | FA-25160558 |  |  | FA-25160558 | QC | 5% | 0.000593% |  | 19 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160559 |  |  | FA-25160559 | Lighting Fixture | 68.79% | 0.07714% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Fixture |  | FA-25160560 |  |  | FA-25160560 | Handling | 10% | 0.007714% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Fixture | 50150 | FA-25160561 |  |  | FA-25160561 | Installation of lighting poles | 20% | 0.01543% |  | 15 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Fixture | 50160 | FA-25160562 |  |  | FA-25160562 | Installation Fixture | 65% | 0.05014% |  | 55 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Fixture |  | FA-25160563 |  |  | FA-25160563 | QC | 5% | 0.003857% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160564 |  |  | FA-25160564 | Lighting Socket | 20.64% | 0.02314% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Socket |  | FA-25160565 |  |  | FA-25160565 | Handling | 10% | 0.002314% |  | 10 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Socket | 50170 | FA-25160566 |  |  | FA-25160566 | Fixing in place | 85% | 0.01967% |  | 10 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Socket |  | FA-25160567 |  |  | FA-25160567 | QC | 5% | 0.001157% |  | 10 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160568 |  |  | FA-25160568 | Electrical Cabling | 30.51% | 0.2129% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160569 |  |  | FA-25160569 | LV Cable | 51.64% | 0.11% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | LV Cable |  | FA-25160570 |  |  | FA-25160570 | Handling | 10% | 0.011% |  | 3140 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | LV Cable | 50190 | FA-25160571 |  |  | FA-25160571 | Cable laying | 70% | 0.07698% |  | 3140 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | LV Cable |  | FA-25160572 |  |  | FA-25160572 | Cable arrangements and fixing | 5% | 0.005498% |  | 3140 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | LV Cable |  | FA-25160573 |  |  | FA-25160573 | Cable Marking | 5% | 0.005498% |  | 3140 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | LV Cable |  | FA-25160574 |  |  | FA-25160574 | Continuity & Megger Test | 5% | 0.005498% |  | 3140 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | LV Cable |  | FA-25160575 |  |  | FA-25160575 | QC | 5% | 0.005498% |  | 3140 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160576 |  |  | FA-25160576 | Control Cable | 40.13% | 0.08545% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Control Cable |  | FA-25160577 |  |  | FA-25160577 | Handling | 10% | 0.008545% |  | 2440 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Control Cable | 50200 | FA-25160578 |  |  | FA-25160578 | Cable laying | 70% | 0.05982% |  | 2440 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Control Cable |  | FA-25160579 |  |  | FA-25160579 | Cable arrangements and fixing | 5% | 0.004273% |  | 2440 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Control Cable |  | FA-25160580 |  |  | FA-25160580 | Cable Marking | 5% | 0.004273% |  | 2440 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Control Cable |  | FA-25160581 |  |  | FA-25160581 | Continuity & Megger Test | 5% | 0.004273% |  | 2440 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Control Cable |  | FA-25160582 |  |  | FA-25160582 | QC | 5% | 0.004273% |  | 2440 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160583 |  |  | FA-25160583 | Lighting Cable | 8.224% | 0.01751% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Cable |  | FA-25160584 |  |  | FA-25160584 | Handling | 10% | 0.001751% |  | 500 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Cable | 50210 | FA-25160585 |  |  | FA-25160585 | Cable laying | 70% | 0.01226% |  | 500 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Cable |  | FA-25160586 |  |  | FA-25160586 | Cable arrangements and fixing | 5% | 0.0008755% |  | 500 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Cable |  | FA-25160587 |  |  | FA-25160587 | Cable Marking | 5% | 0.0008755% |  | 500 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Cable |  | FA-25160588 |  |  | FA-25160588 | Continuity & Megger Test | 5% | 0.0008755% |  | 500 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Lighting Cable |  | FA-25160589 |  |  | FA-25160589 | QC | 5% | 0.0008755% |  | 500 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160590 |  |  | FA-25160590 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 4.524% | 0.03157% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160591 |  |  | FA-25160591 | Cable Gland & Termination | 100% | 0.03157% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Cable Gland & Termination |  | FA-25160592 |  |  | FA-25160592 | Handling | 10% | 0.003157% |  | 102 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Cable Gland & Termination | 50220 | FA-25160593 |  |  | FA-25160593 | Gland Installation | 60% | 0.01894% |  | 102 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Cable Gland & Termination | 50230 | FA-25160594 |  |  | FA-25160594 | Termination | 25% | 0.007892% |  | 102 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Cable Gland & Termination |  | FA-25160595 |  |  | FA-25160595 | QC | 5% | 0.001578% |  | 102 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160596 |  |  | FA-25160596 | Grounding/ Earthing System | 5.211% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160597 |  |  | FA-25160597 | Earthing Cable Pulling | 100% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Earthing Cable Pulling |  | FA-25160598 |  |  | FA-25160598 | Handling | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Earthing Cable Pulling | 50250 | FA-25160599 |  |  | FA-25160599 | Cable laying | 75% | 0.02727% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Earthing Cable Pulling |  | FA-25160600 |  |  | FA-25160600 | Cable arrangements and fixing | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Electrical | Earthing Cable Pulling |  | FA-25160601 |  |  | FA-25160601 | QC | 5% | 0.001818% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Electrical |  |  | FA-25160602 |  |  | FA-25160602 | Unit - GPRS | 1.423% | 0.5551% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160603 |  |  | FA-25160603 | Electrical Cabling | 83.76% | 0.4649% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160604 |  |  | FA-25160604 | LV Cable | 7.532% | 0.03502% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | LV Cable |  | FA-25160605 |  |  | FA-25160605 | Handling | 10% | 0.003502% |  | 1000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | LV Cable | 50190 | FA-25160606 |  |  | FA-25160606 | Cable laying | 70% | 0.02451% |  | 1000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | LV Cable |  | FA-25160607 |  |  | FA-25160607 | Cable arrangements and fixing | 5% | 0.001751% |  | 1000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | LV Cable |  | FA-25160608 |  |  | FA-25160608 | Cable Marking | 5% | 0.001751% |  | 1000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | LV Cable |  | FA-25160609 |  |  | FA-25160609 | Continuity & Megger Test | 5% | 0.001751% |  | 1000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | LV Cable |  | FA-25160610 |  |  | FA-25160610 | QC | 5% | 0.001751% |  | 1000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160611 |  |  | FA-25160611 | Control Cable | 92.47% | 0.4299% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Control Cable |  | FA-25160612 |  |  | FA-25160612 | Handling | 10% | 0.04299% |  | 12276 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Control Cable | 50200 | FA-25160613 |  |  | FA-25160613 | Cable laying | 70% | 0.3009% |  | 12276 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Control Cable |  | FA-25160614 |  |  | FA-25160614 | Cable arrangements and fixing | 5% | 0.0215% |  | 12276 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Control Cable |  | FA-25160615 |  |  | FA-25160615 | Cable Marking | 5% | 0.0215% |  | 12276 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Control Cable |  | FA-25160616 |  |  | FA-25160616 | Continuity & Megger Test | 5% | 0.0215% |  | 12276 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Control Cable |  | FA-25160617 |  |  | FA-25160617 | QC | 5% | 0.0215% |  | 12276 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160618 |  |  | FA-25160618 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 6.412% | 0.03559% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160619 |  |  | FA-25160619 | Cable Gland & Termination | 100% | 0.03559% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Cable Gland & Termination |  | FA-25160620 |  |  | FA-25160620 | Handling | 10% | 0.003559% |  | 115 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Cable Gland & Termination | 50220 | FA-25160621 |  |  | FA-25160621 | Gland Installation | 60% | 0.02136% |  | 115 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Cable Gland & Termination | 50230 | FA-25160622 |  |  | FA-25160622 | Termination | 25% | 0.008898% |  | 115 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Cable Gland & Termination |  | FA-25160623 |  |  | FA-25160623 | QC | 5% | 0.00178% |  | 115 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160624 |  |  | FA-25160624 | Grounding/ Earthing System | 9.827% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160625 |  |  | FA-25160625 | Earthing Cable Pulling | 100% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Earthing Cable Pulling |  | FA-25160626 |  |  | FA-25160626 | Handling | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Earthing Cable Pulling | 50250 | FA-25160627 |  |  | FA-25160627 | Cable laying | 75% | 0.04091% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Earthing Cable Pulling |  | FA-25160628 |  |  | FA-25160628 | Cable arrangements and fixing | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Electrical | Earthing Cable Pulling |  | FA-25160629 |  |  | FA-25160629 | QC | 5% | 0.002727% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Electrical |  |  | FA-25160630 |  |  | FA-25160630 | Substation - S35 | 12.46% | 4.86% |  |  |  |  | 0 | 22.69% | 18.75% | 41.44% |  | 3.944% | 0 | [7 empty] | 3.944%
[6 empty] | 4 |  | Electrical |  |  | FA-25160631 |  |  | FA-25160631 | Cable Tray, ladder, Conduits | 0.3517% | 0.01709% |  |  |  |  | 0 | 0% | 35.59% | 35.59% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160632 |  |  | FA-25160632 | Installation of Cable Tray, ladder, Cover | 58.11% | 0.009932% |  |  |  |  | 0 | 0% | 61.25% | 61.25% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160633 |  |  | FA-25160633 | Handling | 10% | 0.0009932% |  | 30 |  | 30 | 30 | 0% | 100% | 100% |  |  | 30
[6 empty] | 6 | Substation - S35 | Electrical | Installation of Cable Tray, ladder, Cover | 50001 | FA-25160634 |  |  | FA-25160634 | Tray/ Ladder Assembling | 65% | 0.006456% |  | 30 |  | 20.5 | 20.5 | 0% | 68.33% | 68.33% |  |  | 20.5
[6 empty] | 6 | Substation - S35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160635 |  |  | FA-25160635 | Fixing & alignment | 10% | 0.0009932% |  | 30 |  | 20.5 | 20.5 | 0% | 68.33% | 68.33% |  |  | 20.5
[6 empty] | 6 | Substation - S35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160636 |  |  | FA-25160636 | Installation of covers | 10% | 0.0009932% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160637 |  |  | FA-25160637 | QC | 5% | 0.0004966% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160638 |  |  | FA-25160638 | Installation of conduits | 41.89% | 0.007161% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Installation of conduits |  | FA-25160639 |  |  | FA-25160639 | Handling | 10% | 0.0007161% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Installation of conduits | 50010 | FA-25160640 |  |  | FA-25160640 | Installation of Conduit | 85% | 0.006087% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Installation of conduits |  | FA-25160641 |  |  | FA-25160641 | QC | 5% | 0.000358% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160642 |  |  | FA-25160642 | EL Transformer/ Panel/ JB | 50.38% | 2.449% |  |  |  |  | 0 | 44.63% | 33.84% | 78.47% |  | 2.187% | 0 | [7 empty] | 2.187%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160643 |  |  | FA-25160643 | Transformer | 19.18% | 0.4696% |  |  |  |  | 0 | 45.33% | 18.33% | 63.67% |  | 0.3844% | 0 | [7 empty] | 0.3844%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | Transformer |  | FA-25160644 |  |  | FA-25160644 | Handling | 10% | 0.04696% |  | 15 |  | 13 | 13 | 86.67% | 0% | 86.67% | 13 | 0.04522% | 13 | [6 empty] | 13 | 0.04522%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | Transformer | 10008 | FA-25160645 |  |  | FA-25160645 | Installation | 55% | 0.2583% |  | 15 |  | 11 | 11 | 66.67% | 6.667% | 73.33% | 13 | 0.2487% | 11 | [6 empty] | 13 | 0.2487%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | Transformer |  | FA-25160646 |  |  | FA-25160646 | Installation of Accessories | 20% | 0.09393% |  | 15 |  | 11 | 11 | 0% | 73.33% | 73.33% | 13 | 0.09045% | 11 | [6 empty] | 13 | 0.09045%
[6 empty] | 6 | Substation - S35 | Electrical | Transformer |  | FA-25160647 |  |  | FA-25160647 | Oil Filling | 10% | 0.04696% |  | 15 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Transformer |  | FA-25160648 |  |  | FA-25160648 | QC | 5% | 0.02348% |  | 15 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160649 |  |  | FA-25160649 | LV Switchgear | 31.83% | 0.7794% |  |  |  |  | 0 | 25.45% | 69.55% | 95% |  | 0.8227% | 0 | [7 empty] | 0.8227%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | LV Switchgear |  | FA-25160650 |  |  | FA-25160650 | Handling | 10% | 0.07794% |  | 66 |  | 66 | 66 | 100% | 0% | 100% | 66 | 0.08661% | 66 | [6 empty] | 66 | 0.08661%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | LV Switchgear | 50260 | FA-25160651 |  |  | FA-25160651 | Installation | 75% | 0.5846% |  | 66 |  | 66 | 66 | 18.18% | 81.82% | 100% | 66 | 0.6495% | 66 | [6 empty] | 66 | 0.6495%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | LV Switchgear |  | FA-25160652 |  |  | FA-25160652 | Fixing | 10% | 0.07794% |  | 66 |  | 66 | 66 | 18.18% | 81.82% | 100% | 66 | 0.08661% | 66 | [6 empty] | 66 | 0.08661%
[6 empty] | 6 | Substation - S35 | Electrical | LV Switchgear |  | FA-25160653 |  |  | FA-25160653 | QC | 5% | 0.03897% |  | 66 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160654 |  |  | FA-25160654 | MV Switchgear | 28.46% | 0.6968% |  |  |  |  | 0 | 95% | 5% | 100% |  | 0.7742% | 0 | [7 empty] | 0.7742%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | MV Switchgear |  | FA-25160655 |  |  | FA-25160655 | Handling | 10% | 0.06968% |  | 59 |  | 59 | 59 | 100% | 0% | 100% | 59 | 0.07742% | 59 | [6 empty] | 59 | 0.07742%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | MV Switchgear | 50280 | FA-25160656 |  |  | FA-25160656 | Installation | 75% | 0.5226% |  | 59 |  | 59 | 59 | 100% | 0% | 100% | 59 | 0.5806% | 59 | [6 empty] | 59 | 0.5806%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | MV Switchgear |  | FA-25160657 |  |  | FA-25160657 | Fixing | 10% | 0.06968% |  | 59 |  | 59 | 59 | 100% | 0% | 100% | 59 | 0.07742% | 59 | [6 empty] | 59 | 0.07742%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | MV Switchgear |  | FA-25160658 |  |  | FA-25160658 | QC | 5% | 0.03484% |  | 59 |  | 59 | 59 | 0% | 100% | 100% | 59 | 0.03871% | 59 | [6 empty] | 59 | 0.03871%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160659 |  |  | FA-25160659 | UPS,DC charger and Battries | 5.145% | 0.126% |  |  |  |  | 0 | 5% | 42.5% | 47.5% |  | 0.06648% | 0 | [7 empty] | 0.06648%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | UPS,DC charger and Battries |  | FA-25160660 |  |  | FA-25160660 | Handling | 10% | 0.0126% | Set | 4 |  | 2 | 2 | 50% | 0% | 50% | 2 | 0.006998% | 2 | [6 empty] | 2 | 0.006998%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | UPS,DC charger and Battries | 50290 | FA-25160661 |  |  | FA-25160661 | Installation | 75% | 0.09448% | Set | 4 |  | 2 | 2 | 0% | 50% | 50% | 2 | 0.05249% | 2 | [6 empty] | 2 | 0.05249%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | UPS,DC charger and Battries |  | FA-25160662 |  |  | FA-25160662 | Fixing | 10% | 0.0126% | Set | 4 |  | 2 | 2 | 0% | 50% | 50% | 2 | 0.006998% | 2 | [6 empty] | 2 | 0.006998%
[6 empty] | 6 | Substation - S35 | Electrical | UPS,DC charger and Battries |  | FA-25160663 |  |  | FA-25160663 | QC | 5% | 0.006299% | Set | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160664 |  |  | FA-25160664 | Main Lighting Panel | 3.939% | 0.09645% |  |  |  |  | 0 | 10% | 85% | 95% |  | 0.1018% | 0 | [7 empty] | 0.1018%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | Main Lighting Panel |  | FA-25160665 |  |  | FA-25160665 | Handling | 10% | 0.009645% |  | 7 |  | 7 | 7 | 100% | 0% | 100% | 7 | 0.01072% | 7 | [6 empty] | 7 | 0.01072%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | Main Lighting Panel | 800250 | FA-25160666 |  |  | FA-25160666 | Installation | 75% | 0.07234% |  | 7 |  | 7 | 7 | 0% | 100% | 100% | 7 | 0.08037% | 7 | [6 empty] | 7 | 0.08037%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | Main Lighting Panel |  | FA-25160667 |  |  | FA-25160667 | Fixing | 10% | 0.009645% |  | 7 |  | 7 | 7 | 0% | 100% | 100% | 7 | 0.01072% | 7 | [6 empty] | 7 | 0.01072%
[6 empty] | 6 | Substation - S35 | Electrical | Main Lighting Panel |  | FA-25160668 |  |  | FA-25160668 | QC | 5% | 0.004822% |  | 7 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160669 |  |  | FA-25160669 | VFD Panel | 1.447% | 0.03543% |  |  |  |  | 0 | 10% | 85% | 95% |  | 0.0374% | 0 | [7 empty] | 0.0374%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | VFD Panel |  | FA-25160670 |  |  | FA-25160670 | Handling | 10% | 0.003543% |  | 3 |  | 3 | 3 | 100% | 0% | 100% | 3 | 0.003937% | 3 | [6 empty] | 3 | 0.003937%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | VFD Panel | 900280 | FA-25160671 |  |  | FA-25160671 | Installation | 75% | 0.02657% |  | 3 |  | 3 | 3 | 0% | 100% | 100% | 3 | 0.02952% | 3 | [6 empty] | 3 | 0.02952%
|  |  |  | Plan Jan |  | 6 | Substation - S35 | Electrical | VFD Panel |  | FA-25160672 |  |  | FA-25160672 | Fixing | 10% | 0.003543% |  | 3 |  | 3 | 3 | 0% | 100% | 100% | 3 | 0.003937% | 3 | [6 empty] | 3 | 0.003937%
[6 empty] | 6 | Substation - S35 | Electrical | VFD Panel |  | FA-25160673 |  |  | FA-25160673 | QC | 5% | 0.001771% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160674 |  |  | FA-25160674 | Test and Energizing Transformer/ Switchgeers/ MCC, …. | 10% | 0.2449% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Test and Energizing Transformer/ Switchgeers/ MCC, …. |  | FA-25160675 |  |  | FA-25160675 | Energizing | 90% | 0.2204% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Test and Energizing Transformer/ Switchgeers/ MCC, …. |  | FA-25160676 |  |  | FA-25160676 | Document | 10% | 0.02449% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160677 |  |  | FA-25160677 | Diesel Generator | 1.533% | 0.07452% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160678 |  |  | FA-25160678 | Diesel Generator | 100% | 0.07452% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Diesel Generator |  | FA-25160679 |  |  | FA-25160679 | Handling | 10% | 0.007452% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Diesel Generator | 12128 | FA-25160680 |  |  | FA-25160680 | Installation of Generator | 80% | 0.05962% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Diesel Generator |  | FA-25160681 |  |  | FA-25160681 | Cable connections | 5% | 0.003726% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Diesel Generator |  | FA-25160682 |  |  | FA-25160682 | QC | 5% | 0.003726% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160683 |  |  | FA-25160683 | Electrical Cabling | 29.32% | 1.425% |  |  |  |  | 0 | 0.7126% | 5.142% | 5.855% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160684 |  |  | FA-25160684 | MV Cable | 9.63% | 0.1372% |  |  |  |  | 0 | 7.4% | 53.39% | 60.79% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable |  | FA-25160685 |  |  | FA-25160685 | Handling | 10% | 0.01372% |  | 3919 |  | 3000 | 3000 | 74% | 2.552% | 76.55% |  |  | 3000
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable | 50180 | FA-25160686 |  |  | FA-25160686 | Cable laying | 70% | 0.09607% |  | 3919 |  | 2975 | 2975 | 0% | 75.91% | 75.91% |  |  | 2975
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable |  | FA-25160687 |  |  | FA-25160687 | Cable arrangements and fixing | 5% | 0.006862% |  | 3919 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable |  | FA-25160688 |  |  | FA-25160688 | Cable Marking | 5% | 0.006862% |  | 3919 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable |  | FA-25160689 |  |  | FA-25160689 | Continuity & Megger Test | 5% | 0.006862% |  | 3919 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable |  | FA-25160690 |  |  | FA-25160690 | QC | 5% | 0.006862% |  | 3919 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160691 |  |  | FA-25160691 | LV Cable | 23.67% | 0.3373% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | LV Cable |  | FA-25160692 |  |  | FA-25160692 | Handling | 10% | 0.03373% |  | 9632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | LV Cable | 50190 | FA-25160693 |  |  | FA-25160693 | Cable laying | 70% | 0.2361% |  | 9632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | LV Cable |  | FA-25160694 |  |  | FA-25160694 | Cable arrangements and fixing | 5% | 0.01687% |  | 9632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | LV Cable |  | FA-25160695 |  |  | FA-25160695 | Cable Marking | 5% | 0.01687% |  | 9632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | LV Cable |  | FA-25160696 |  |  | FA-25160696 | Continuity & Megger Test | 5% | 0.01687% |  | 9632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | LV Cable |  | FA-25160697 |  |  | FA-25160697 | QC | 5% | 0.01687% |  | 9632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160698 |  |  | FA-25160698 | Control Cable | 66.7% | 0.9506% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Control Cable |  | FA-25160699 |  |  | FA-25160699 | Handling | 10% | 0.09506% |  | 27143 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Control Cable | 50200 | FA-25160700 |  |  | FA-25160700 | Cable laying | 70% | 0.6654% |  | 27143 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Control Cable |  | FA-25160701 |  |  | FA-25160701 | Cable arrangements and fixing | 5% | 0.04753% |  | 27143 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Control Cable |  | FA-25160702 |  |  | FA-25160702 | Cable Marking | 5% | 0.04753% |  | 27143 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Control Cable |  | FA-25160703 |  |  | FA-25160703 | Continuity & Megger Test | 5% | 0.04753% |  | 27143 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Control Cable |  | FA-25160704 |  |  | FA-25160704 | QC | 5% | 0.04753% |  | 27143 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160705 |  |  | FA-25160705 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 15.04% | 0.731% |  |  |  |  | 0 | 0% | 0.4319% | 0.4319% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160706 |  |  | FA-25160706 | Cable Gland & Termination | 35.36% | 0.2584% |  |  |  |  | 0 | 0% | 1.222% | 1.222% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Cable Gland & Termination |  | FA-25160707 |  |  | FA-25160707 | Handling | 10% | 0.02584% |  | 835 |  | 102 | 102 | 0% | 12.22% | 12.22% |  |  | 102
[6 empty] | 6 | Substation - S35 | Electrical | Cable Gland & Termination | 50220 | FA-25160708 |  |  | FA-25160708 | Gland Installation | 60% | 0.1551% |  | 835 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Cable Gland & Termination | 50230 | FA-25160709 |  |  | FA-25160709 | Termination | 25% | 0.06461% |  | 835 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Cable Gland & Termination |  | FA-25160710 |  |  | FA-25160710 | QC | 5% | 0.01292% |  | 835 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160711 |  |  | FA-25160711 | MV Cable Termination kit | 64.64% | 0.4725% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable Termination kit |  | FA-25160712 |  |  | FA-25160712 | Handling | 10% | 0.04725% |  | 94 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable Termination kit | 50240 | FA-25160713 |  |  | FA-25160713 | Termination Kit | 85% | 0.4016% |  | 94 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | MV Cable Termination kit |  | FA-25160714 |  |  | FA-25160714 | QC | 5% | 0.02363% |  | 94 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160715 |  |  | FA-25160715 | Grounding/ Earthing System | 3.367% | 0.1636% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160716 |  |  | FA-25160716 | Earthing Cable Pulling | 100% | 0.1636% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Earthing Cable Pulling |  | FA-25160717 |  |  | FA-25160717 | Handling | 10% | 0.01636% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Earthing Cable Pulling | 50250 | FA-25160718 |  |  | FA-25160718 | Cable laying | 75% | 0.1227% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Earthing Cable Pulling |  | FA-25160719 |  |  | FA-25160719 | Cable arrangements and fixing | 10% | 0.01636% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S35 | Electrical | Earthing Cable Pulling |  | FA-25160720 |  |  | FA-25160720 | QC | 5% | 0.008182% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Electrical |  |  | FA-25160721 |  |  | FA-25160721 | Unit - C35 | 1.387% | 0.5413% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160722 |  |  | FA-25160722 | Cable Tray, ladder, Conduits | 19.67% | 0.1065% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160723 |  |  | FA-25160723 | Installation of Cable Tray, ladder, Cover | 93.28% | 0.09932% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160724 |  |  | FA-25160724 | Handling | 10% | 0.009932% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of Cable Tray, ladder, Cover | 50001 | FA-25160725 |  |  | FA-25160725 | Tray/ Ladder Assembling | 65% | 0.06456% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160726 |  |  | FA-25160726 | Fixing & alignment | 10% | 0.009932% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160727 |  |  | FA-25160727 | Installation of covers | 10% | 0.009932% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160728 |  |  | FA-25160728 | QC | 5% | 0.004966% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160729 |  |  | FA-25160729 | Installation of conduits | 6.725% | 0.007161% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of conduits |  | FA-25160730 |  |  | FA-25160730 | Handling | 10% | 0.0007161% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of conduits | 50010 | FA-25160731 |  |  | FA-25160731 | Installation of Conduit | 85% | 0.006087% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Installation of conduits |  | FA-25160732 |  |  | FA-25160732 | QC | 5% | 0.000358% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160733 |  |  | FA-25160733 | EL Transformer/ Panel/ JB | 48.45% | 0.2622% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160734 |  |  | FA-25160734 | Transformer | 11.94% | 0.03131% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Transformer |  | FA-25160735 |  |  | FA-25160735 | Handling | 10% | 0.003131% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Transformer | 10008 | FA-25160736 |  |  | FA-25160736 | Installation | 55% | 0.01722% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Transformer |  | FA-25160737 |  |  | FA-25160737 | Installation of Accessories | 20% | 0.006262% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Transformer |  | FA-25160738 |  |  | FA-25160738 | Oil Filling | 10% | 0.003131% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Transformer |  | FA-25160739 |  |  | FA-25160739 | QC | 5% | 0.001565% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160740 |  |  | FA-25160740 | LV Switchgear | 54.04% | 0.1417% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Switchgear |  | FA-25160741 |  |  | FA-25160741 | Handling | 10% | 0.01417% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Switchgear | 50260 | FA-25160742 |  |  | FA-25160742 | Installation | 75% | 0.1063% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Switchgear |  | FA-25160743 |  |  | FA-25160743 | Fixing | 10% | 0.01417% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Switchgear |  | FA-25160744 |  |  | FA-25160744 | QC | 5% | 0.007086% |  | 12 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160745 |  |  | FA-25160745 | UPS,DC charger and Battries | 24.02% | 0.06299% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | UPS,DC charger and Battries |  | FA-25160746 |  |  | FA-25160746 | Handling | 10% | 0.006299% | set | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | UPS,DC charger and Battries | 50290 | FA-25160747 |  |  | FA-25160747 | Installation | 75% | 0.04724% | set | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | UPS,DC charger and Battries |  | FA-25160748 |  |  | FA-25160748 | Fixing | 10% | 0.006299% | set | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | UPS,DC charger and Battries |  | FA-25160749 |  |  | FA-25160749 | QC | 5% | 0.003149% | set | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160750 |  |  | FA-25160750 | Test and Energizing Transformer/ Switchgeers/ MCC, …. | 10% | 0.02622% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Test and Energizing Transformer/ Switchgeers/ MCC, …. |  | FA-25160751 |  |  | FA-25160751 | Energizing | 90% | 0.0236% | set |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Test and Energizing Transformer/ Switchgeers/ MCC, …. |  | FA-25160752 |  |  | FA-25160752 | Document | 10% | 0.002622% | set |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160753 |  |  | FA-25160753 | Electrical Cabling | 13.88% | 0.07512% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160754 |  |  | FA-25160754 | LV Cable | 20.98% | 0.01576% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Cable |  | FA-25160755 |  |  | FA-25160755 | Handling | 10% | 0.001576% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Cable | 50190 | FA-25160756 |  |  | FA-25160756 | Cable laying | 70% | 0.01103% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Cable |  | FA-25160757 |  |  | FA-25160757 | Cable arrangements and fixing | 5% | 0.000788% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Cable |  | FA-25160758 |  |  | FA-25160758 | Cable Marking | 5% | 0.000788% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Cable |  | FA-25160759 |  |  | FA-25160759 | Continuity & Megger Test | 5% | 0.000788% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | LV Cable |  | FA-25160760 |  |  | FA-25160760 | QC | 5% | 0.000788% |  | 450 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160761 |  |  | FA-25160761 | Control Cable | 79.02% | 0.05936% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Control Cable |  | FA-25160762 |  |  | FA-25160762 | Handling | 10% | 0.005936% |  | 1695 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Control Cable | 50200 | FA-25160763 |  |  | FA-25160763 | Cable laying | 70% | 0.04155% |  | 1695 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Control Cable |  | FA-25160764 |  |  | FA-25160764 | Cable arrangements and fixing | 5% | 0.002968% |  | 1695 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Control Cable |  | FA-25160765 |  |  | FA-25160765 | Cable Marking | 5% | 0.002968% |  | 1695 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Control Cable |  | FA-25160766 |  |  | FA-25160766 | Continuity & Megger Test | 5% | 0.002968% |  | 1695 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Control Cable |  | FA-25160767 |  |  | FA-25160767 | QC | 5% | 0.002968% |  | 1695 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160768 |  |  | FA-25160768 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 1.201% | 0.006499% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160769 |  |  | FA-25160769 | Cable Gland & Termination | 100% | 0.006499% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Cable Gland & Termination |  | FA-25160770 |  |  | FA-25160770 | Handling | 10% | 0.0006499% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Cable Gland & Termination | 50220 | FA-25160771 |  |  | FA-25160771 | Gland Installation | 60% | 0.0039% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Cable Gland & Termination | 50230 | FA-25160772 |  |  | FA-25160772 | Termination | 25% | 0.001625% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Cable Gland & Termination |  | FA-25160773 |  |  | FA-25160773 | QC | 5% | 0.000325% |  | 1 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160774 |  |  | FA-25160774 | Grounding/ Earthing System | 16.8% | 0.09091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160775 |  |  | FA-25160775 | Earthing Cable Pulling | 100% | 0.09091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Earthing Cable Pulling |  | FA-25160776 |  |  | FA-25160776 | Handling | 10% | 0.009091% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Earthing Cable Pulling | 50250 | FA-25160777 |  |  | FA-25160777 | Cable laying | 75% | 0.06819% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Earthing Cable Pulling |  | FA-25160778 |  |  | FA-25160778 | Cable arrangements and fixing | 10% | 0.009091% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Electrical | Earthing Cable Pulling |  | FA-25160779 |  |  | FA-25160779 | QC | 5% | 0.004546% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 3 |  | Electrical |  |  | FA-25160780 |  |  | FA-25160780 | Unit - INT | 10% | 3.902% |  |  |  |  | 0 | 13.64% | 11.58% | 25.22% |  |  | 0 |  |  | 0.7576% | [6 empty] | 0.7576%
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160781 |  |  | FA-25160781 | Cable Tray, ladder, Conduits | 30.22% | 1.179% |  |  |  |  | 0 | 0% | 1.965% | 1.965% |  |  | 0 |  |  | 0.1597% | [6 empty] | 0.1597%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160782 |  |  | FA-25160782 | Installation of Primary Tray, ladder | 36.52% | 0.4307% |  |  |  |  | 0 | 0% | 5.38% | 5.38% |  |  | 0 |  |  | 0.1597% | [6 empty] | 0.1597%
Plan | 0.00023175 | 8.907e-06% | 3.836e-09% |  | Plan Feb | 6 | Unit - INT | Electrical | Installation of Primary Tray, ladder |  | FA-25160783 |  |  | FA-25160783 | Handling | 10% | 0.04307% |  | 2602 |  | 1400 | 1400 | 0% | 53.8% | 53.8% |  |  | 1400 | 1400 | 0.53805 | 0.02317% | Week 1 | Week 4 |  |  |  | 1400 | 0.02317% | ok | 0% | 0%
Plan | 0.0011836 | 4.549e-05% | 1.274e-07% |  | Plan Feb | 6 | Unit - INT | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160784 |  |  | FA-25160784 | Tray/ Ladder Assembling | 65% | 0.28% |  | 2602 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 1100 | 0.42275 | 0.1184% | Week 1 | Week 4 |  |  |  | 1100 | 0.1184% | ok | 0% | 0%
Plan | 0.00018209 | 6.998e-06% | 3.014e-09% |  | Plan Feb | 6 | Unit - INT | Electrical | Installation of Primary Tray, ladder |  | FA-25160785 |  |  | FA-25160785 | Fixing & alignment | 10% | 0.04307% |  | 2602 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 1100 | 0.42275 | 0.01821% | Week 1 | Week 4 |  |  |  | 1100 | 0.01821% | ok | 0% | 0%
[6 empty] | 6 | Unit - INT | Electrical | Installation of Primary Tray, ladder |  | FA-25160786 |  |  | FA-25160786 | Installation of covers | 10% | 0.04307% |  | 2602 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of Primary Tray, ladder |  | FA-25160787 |  |  | FA-25160787 | QC | 5% | 0.02154% |  | 2602 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160788 |  |  | FA-25160788 | Installation of Secondary Tray | 36.52% | 0.4307% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of Secondary Tray |  | FA-25160789 |  |  | FA-25160789 | Handling | 10% | 0.04307% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of Secondary Tray | 50001 | FA-25160790 |  |  | FA-25160790 | Tray/ Ladder Assembling | 65% | 0.28% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of Secondary Tray |  | FA-25160791 |  |  | FA-25160791 | Fixing & alignment | 10% | 0.04307% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of Secondary Tray |  | FA-25160792 |  |  | FA-25160792 | Installation of covers | 10% | 0.04307% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of Secondary Tray |  | FA-25160793 |  |  | FA-25160793 | QC | 5% | 0.02154% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160794 |  |  | FA-25160794 | Installation of conduits | 26.96% | 0.3179% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of conduits |  | FA-25160795 |  |  | FA-25160795 | Handling | 10% | 0.03179% |  | 1332 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of conduits | 50010 | FA-25160796 |  |  | FA-25160796 | Installation of Conduit | 85% | 0.2702% |  | 1332 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Installation of conduits |  | FA-25160797 |  |  | FA-25160797 | QC | 5% | 0.0159% |  | 1332 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160798 |  |  | FA-25160798 | Supports | 1.611% | 0.06288% |  |  |  |  | 0 | 52.08% | 2.078% | 54.16% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160799 |  |  | FA-25160799 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 52.08% | 2.078% | 54.16% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - INT | Electrical | Supports |  | FA-25160800 |  |  | FA-25160800 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% | 575 | 0.03144% | 575 | [6 empty] | 575 | 0.03144%
[6 empty] | 6 | Unit - INT | Electrical | Supports | 50020 | FA-25160801 |  |  | FA-25160801 | Fabrication | 20% | 0.01258% |  | 575 |  | 53.1717 | 53.1717 | 4.63% | 4.617% | 9.247% |  |  | 53.1717
[6 empty] | 6 | Unit - INT | Electrical | Supports | 50030 | FA-25160802 |  |  | FA-25160802 | Installation | 25% | 0.01572% |  | 575 |  | 53.1717 | 53.1717 | 4.63% | 4.617% | 9.247% |  |  | 53.1717
[6 empty] | 6 | Unit - INT | Electrical | Supports |  | FA-25160803 |  |  | FA-25160803 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160804 |  |  | FA-25160804 | EL Transformer/ Panel/ JB | 0.5152% | 0.02011% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160805 |  |  | FA-25160805 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 90% | 0.01809% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160806 |  |  | FA-25160806 | Handling | 10% | 0.001809% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160807 |  |  | FA-25160807 | Installation | 85% | 0.01538% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160808 |  |  | FA-25160808 | QC | 5% | 0.0009047% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160809 |  |  | FA-25160809 | Test and Energizing Local Panels Inside Units | 10% | 0.002011% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160810 |  |  | FA-25160810 | Energizing | 90% | 0.001809% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160811 |  |  | FA-25160811 | Document | 10% | 0.0002011% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160812 |  |  | FA-25160812 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Power Junction Box |  | FA-25160813 |  |  | FA-25160813 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Power Junction Box | 50120 | FA-25160814 |  |  | FA-25160814 | Installation | 85% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Power Junction Box |  | FA-25160815 |  |  | FA-25160815 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160816 |  |  | FA-25160816 | Lighting & Small Power System | 45.78% | 1.786% |  |  |  |  | 0 | 25.05% | 20.99% | 46.04% |  | 0.7821% | 0 |  |  | 0.5599% |  |  |  |  | 0.7821% |  | 0.5599%
[6 empty] | 5 |  | Electrical |  |  | FA-25160817 |  |  | FA-25160817 | Lighting JB | 0.8386% | 0.01498% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting JB |  | FA-25160818 |  |  | FA-25160818 | Handling | 10% | 0.001498% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting JB | 50140 | FA-25160819 |  |  | FA-25160819 | Fixing in place | 85% | 0.01273% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting JB |  | FA-25160820 |  |  | FA-25160820 | QC | 5% | 0.0007491% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160821 |  |  | FA-25160821 | Lighting Fixture | 13.52% | 0.2414% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting Fixture |  | FA-25160822 |  |  | FA-25160822 | Handling | 10% | 0.02414% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting Fixture | 50150 | FA-25160823 |  |  | FA-25160823 | Installation of lighting poles | 20% | 0.04829% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting Fixture | 50160 | FA-25160824 |  |  | FA-25160824 | Installation Fixture | 65% | 0.1569% |  | 208 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting Fixture |  | FA-25160825 |  |  | FA-25160825 | QC | 5% | 0.01207% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160826 |  |  | FA-25160826 | Street Lighting | 85.65% | 1.53% |  |  |  |  | 0 | 29.25% | 24.5% | 53.75% |  | 0.7821% | 0 |  |  | 0.5599% |  |  |  |  | 0.7821% |  | 0.5599%
Plan | 0.00053819 | 0.0002704% | 4.138e-07% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Street Lighting |  | FA-25160827 |  |  | FA-25160827 | Handling | 10% | 0.153% |  | 199 |  | 153 | 153 | 43.72% | 33.17% | 76.88% | 100 | 0.07688% | 153 | 70 | 0.35176 | 0.05382% | Week 1 | Week 4 |  | 100 | 0.07688% | 70 | 0.05382% | ok | 50.25% | 0.07688%
Plan | 0.0014249 | 0.001088% | 3.328e-06% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Street Lighting | 90001 | FA-25160828 |  |  | FA-25160828 | Installation of lighting poles | 20% | 0.306% |  | 131 |  | 70 | 70 | 36.64% | 16.79% | 53.44% | 70 | 0.1635% | 70 | 61 | 0.46565 | 0.1425% | Week 1 | Week 4 |  | 70 | 0.1635% | 61 | 0.1425% | ok | 53.44% | 0.1635%
Plan | 0.0021527 | 0.001082% | 6.62e-06% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Street Lighting | 90015 | FA-25160829 |  |  | FA-25160829 | Installation Fixture | 40% | 0.612% |  | 199 |  | 110 | 110 | 28.14% | 27.14% | 55.28% | 100 | 0.3075% | 110 | 70 | 0.35176 | 0.2153% | Week 1 | Week 4 |  | 100 | 0.3075% | 70 | 0.2153% | ok | 50.25% | 0.3075%
Plan | 0.0014831 | 0.001009% | 3.859e-06% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Street Lighting | 90030 | FA-25160830 |  |  | FA-25160830 | Installation JB | 25% | 0.3825% |  | 147 |  | 78 | 78 | 25.17% | 27.89% | 53.06% | 90 | 0.2342% | 78 | 57 | 0.38776 | 0.1483% | Week 1 | Week 4 |  | 90 | 0.2342% | 57 | 0.1483% | ok | 61.22% | 0.2342%
[6 empty] | 6 | Unit - INT | Electrical | Street Lighting |  | FA-25160831 |  |  | FA-25160831 | QC | 5% | 0.0765% |  | 199 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160832 |  |  | FA-25160832 | Electrical Heat Tracing | 4.882% | 0.1905% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160833 |  |  | FA-25160833 | Electrical Heat Tracing Cabling | 100% | 0.1905% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Heat Tracing Cabling |  | FA-25160834 |  |  | FA-25160834 | Handling | 10% | 0.01905% |  | 1292 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Heat Tracing Cabling | 80001 | FA-25160835 |  |  | FA-25160835 | Cable laying | 45% | 0.08574% |  | 1292 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Heat Tracing Cabling |  | FA-25160836 |  |  | FA-25160836 | Cable arrangements and fixing | 10% | 0.01905% |  | 1292 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Heat Tracing Cabling | 80010 | FA-25160837 |  |  | FA-25160837 | Gland Installation | 20% | 0.03811% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Heat Tracing Cabling | 80020 | FA-25160838 |  |  | FA-25160838 | Termination | 10% | 0.01905% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Electrical Heat Tracing Cabling |  | FA-25160839 |  |  | FA-25160839 | QC | 5% | 0.009526% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160840 |  |  | FA-25160840 | Electrical Cabling | 14.01% | 0.5469% |  |  |  |  | 0 | 4.213% | 2.685% | 6.898% |  | 0.02977% | 0 |  |  | 0.02802% |  |  |  |  | 0.02977% |  | 0.02802%
[6 empty] | 5 |  | Electrical |  |  | FA-25160841 |  |  | FA-25160841 | LV Cable | 25.68% | 0.1404% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | LV Cable |  | FA-25160842 |  |  | FA-25160842 | Handling | 10% | 0.01404% |  | 4010 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | LV Cable | 50190 | FA-25160843 |  |  | FA-25160843 | Cable laying | 70% | 0.0983% |  | 4010 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | LV Cable |  | FA-25160844 |  |  | FA-25160844 | Cable arrangements and fixing | 5% | 0.007022% |  | 4010 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | LV Cable |  | FA-25160845 |  |  | FA-25160845 | Cable Marking | 5% | 0.007022% |  | 4010 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | LV Cable |  | FA-25160846 |  |  | FA-25160846 | Continuity & Megger Test | 5% | 0.007022% |  | 4010 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | LV Cable |  | FA-25160847 |  |  | FA-25160847 | QC | 5% | 0.007022% |  | 4010 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160848 |  |  | FA-25160848 | Lighting Cable | 74.32% | 0.4064% |  |  |  |  | 0 | 5.669% | 3.612% | 9.282% |  | 0.02977% | 0 |  |  | 0.02802% |  |  |  |  | 0.02977% |  | 0.02802%
Plan | 3.5021e-05 | 3.018e-07% | 1.226e-10% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Lighting Cable |  | FA-25160849 |  |  | FA-25160849 | Handling | 10% | 0.04064% |  | 11605 |  | 2000 | 2000 | 9.642% | 7.592% | 17.23% | 1000 | 0.003502% | 2000 | 1000 | 0.08617 | 0.003502% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 1000 | 0.003502% | 1000 | 0.003502% | ok | 8.617% | 0.003502%
Plan | 0.00024515 | 2.112e-06% | 6.01e-09% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Lighting Cable | 50210 | FA-25160850 |  |  | FA-25160850 | Cable laying | 70% | 0.2845% |  | 11605 |  | 1169.5 | 1169.5 | 6.273% | 3.804% | 10.08% | 1000 | 0.02451% | 1169.5 | 1000 | 0.08617 | 0.02451% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 1000 | 0.02451% | 1000 | 0.02451% | ok | 8.617% | 0.02451%
|  |  |  | Plan Jan |  | 6 | Unit - INT | Electrical | Lighting Cable |  | FA-25160851 |  |  | FA-25160851 | Cable arrangements and fixing | 5% | 0.02032% |  | 11605 |  | 1169.5 | 1169.5 | 6.273% | 3.804% | 10.08% | 1000 | 0.001751% | 1169.5 | [6 empty] | 1000 | 0.001751%
[6 empty] | 6 | Unit - INT | Electrical | Lighting Cable |  | FA-25160852 |  |  | FA-25160852 | Cable Marking | 5% | 0.02032% |  | 11605 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting Cable |  | FA-25160853 |  |  | FA-25160853 | Continuity & Megger Test | 5% | 0.02032% |  | 11605 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Lighting Cable |  | FA-25160854 |  |  | FA-25160854 | QC | 5% | 0.02032% |  | 11605 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160855 |  |  | FA-25160855 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 2.046% | 0.07985% |  |  |  |  | 0 | 36.2% | 47.44% | 83.64% |  | 0.05942% | 0 |  |  | 0.009997% |  |  |  |  | 0.05942% |  | 0.009997%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160856 |  |  | FA-25160856 | Cable Gland & Termination | 100% | 0.07985% |  |  |  |  | 0 | 36.2% | 47.44% | 83.64% |  | 0.05942% | 0 |  |  | 0.009997% |  |  |  |  | 0.05942% |  | 0.009997%
|  |  |  | Plan Jan |  | 6 | Unit - INT | Electrical | Cable Gland & Termination |  | FA-25160857 |  |  | FA-25160857 | Handling | 10% | 0.007985% |  | 258 |  | 220 | 220 | 85.27% | 0% | 85.27% | 220 | 0.006809% | 220 | [6 empty] | 220 | 0.006809%
Plan | 7.0566e-05 | 2.735e-05% | 1.31e-08% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Cable Gland & Termination | 50220 | FA-25160858 |  |  | FA-25160858 | Gland Installation | 60% | 0.04791% |  | 258 |  | 228 | 228 | 32.56% | 55.81% | 88.37% | 200 | 0.03714% | 228 | 38 | 0.14729 | 0.007057% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 200 | 0.03714% | 38 | 0.007057% | ok | 77.52% | 0.03714%
Plan | 2.9402e-05 | 1.14e-05% | 2.275e-09% | Plan Jan | Plan Feb | 6 | Unit - INT | Electrical | Cable Gland & Termination | 50230 | FA-25160859 |  |  | FA-25160859 | Termination | 25% | 0.01996% |  | 258 |  | 228 | 228 | 32.56% | 55.81% | 88.37% | 200 | 0.01547% | 228 | 38 | 0.14729 | 0.00294% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 200 | 0.01547% | 38 | 0.00294% | ok | 77.52% | 0.01547%
[6 empty] | 6 | Unit - INT | Electrical | Cable Gland & Termination |  | FA-25160860 |  |  | FA-25160860 | QC | 5% | 0.003993% |  | 258 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160861 |  |  | FA-25160861 | Grounding/ Earthing System | 0.9319% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160862 |  |  | FA-25160862 | Earthing Cable Pulling | 100% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Earthing Cable Pulling |  | FA-25160863 |  |  | FA-25160863 | Handling | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Earthing Cable Pulling | 50250 | FA-25160864 |  |  | FA-25160864 | Cable laying | 75% | 0.02727% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Earthing Cable Pulling |  | FA-25160865 |  |  | FA-25160865 | Cable arrangements and fixing | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Electrical | Earthing Cable Pulling |  | FA-25160866 |  |  | FA-25160866 | QC | 5% | 0.001818% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 3 |  | Electrical |  |  | FA-25160867 |  |  | FA-25160867 | Unit - TNK | 18.43% | 7.189% |  |  |  |  | 0 | 1.749% | 3.668% | 5.417% |  |  | 0 |  |  | 0.5449% | [6 empty] | 0.5449%
[6 empty] | 4 |  | Electrical |  |  | FA-25160868 |  |  | FA-25160868 | Cable Tray, ladder, Conduits | 26.69% | 1.919% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160869 |  |  | FA-25160869 | Installation of Primary Tray, ladder | 19.51% | 0.3744% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Primary Tray, ladder |  | FA-25160870 |  |  | FA-25160870 | Handling | 10% | 0.03744% |  | 2262 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Primary Tray, ladder | 50001 | FA-25160871 |  |  | FA-25160871 | Tray/ Ladder Assembling | 65% | 0.2434% |  | 2262 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Primary Tray, ladder |  | FA-25160872 |  |  | FA-25160872 | Fixing & alignment | 10% | 0.03744% |  | 2262 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Primary Tray, ladder |  | FA-25160873 |  |  | FA-25160873 | Installation of covers | 10% | 0.03744% |  | 2262 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Primary Tray, ladder |  | FA-25160874 |  |  | FA-25160874 | QC | 5% | 0.01872% |  | 2262 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160875 |  |  | FA-25160875 | Installation of Secondary Tray | 19.51% | 0.3744% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Secondary Tray |  | FA-25160876 |  |  | FA-25160876 | Handling | 10% | 0.03744% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Secondary Tray | 50001 | FA-25160877 |  |  | FA-25160877 | Tray/ Ladder Assembling | 65% | 0.2434% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Secondary Tray |  | FA-25160878 |  |  | FA-25160878 | Fixing & alignment | 10% | 0.03744% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Secondary Tray |  | FA-25160879 |  |  | FA-25160879 | Installation of covers | 10% | 0.03744% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of Secondary Tray |  | FA-25160880 |  |  | FA-25160880 | QC | 5% | 0.01872% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160881 |  |  | FA-25160881 | Installation of conduits | 60.97% | 1.17% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of conduits |  | FA-25160882 |  |  | FA-25160882 | Handling | 10% | 0.117% |  | 4902 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of conduits | 50010 | FA-25160883 |  |  | FA-25160883 | Installation of Conduit | 85% | 0.9945% |  | 4902 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Installation of conduits |  | FA-25160884 |  |  | FA-25160884 | QC | 5% | 0.0585% |  | 4902 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Electrical |  |  | FA-25160885 |  |  | FA-25160885 | Supports | 3.498% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 | [7 empty] | 0.1258%
|  |  |  | Plan Jan |  | 5 |  | Electrical |  |  | FA-25160886 |  |  | FA-25160886 | Supports | 100% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 | [7 empty] | 0.1258%
|  |  |  | Plan Jan |  | 6 | Unit - TNK | Electrical | Supports |  | FA-25160887 |  |  | FA-25160887 | Material Supply & Handling | 50% | 0.1258% |  | 2300 |  | 2300 | 2300 | 100% | 0% | 100% | 2300 | 0.1258% | 2300 | [6 empty] | 2300 | 0.1258%
[6 empty] | 6 | Unit - TNK | Electrical | Supports | 50020 | FA-25160888 |  |  | FA-25160888 | Fabrication | 20% | 0.0503% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Supports | 50030 | FA-25160889 |  |  | FA-25160889 | Installation | 25% | 0.06288% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Supports |  | FA-25160890 |  |  | FA-25160890 | QC | 5% | 0.01258% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160891 |  |  | FA-25160891 | EL Transformer/ Panel/ JB | 2.507% | 0.1802% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160892 |  |  | FA-25160892 | Electrical Panel( Lighting, Heat Tracing, Local , …) | 42.16% | 0.076% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160893 |  |  | FA-25160893 | Handling | 10% | 0.0076% |  | 21 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) | 50100 | FA-25160894 |  |  | FA-25160894 | Installation | 85% | 0.0646% |  | 21 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Panel( Lighting, Heat Tracing, Local , …) |  | FA-25160895 |  |  | FA-25160895 | QC | 5% | 0.0038% |  | 21 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160896 |  |  | FA-25160896 | Test and Energizing Local Panels Inside Units | 4.685% | 0.008444% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160897 |  |  | FA-25160897 | Energizing | 90% | 0.0076% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Test and Energizing Local Panels Inside Units |  | FA-25160898 |  |  | FA-25160898 | Document | 10% | 0.0008444% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160899 |  |  | FA-25160899 | Local Control Station | 53.15% | 0.0958% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Local Control Station |  | FA-25160900 |  |  | FA-25160900 | Handling | 10% | 0.00958% |  | 42 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Local Control Station | 50110 | FA-25160901 |  |  | FA-25160901 | Installation | 85% | 0.08143% |  | 42 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Local Control Station |  | FA-25160902 |  |  | FA-25160902 | QC | 5% | 0.00479% |  | 42 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160903 |  |  | FA-25160903 | Power Junction Box | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Power Junction Box |  | FA-25160904 |  |  | FA-25160904 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Power Junction Box | 50120 | FA-25160905 |  |  | FA-25160905 | Installation | 85% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Power Junction Box |  | FA-25160906 |  |  | FA-25160906 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160907 |  |  | FA-25160907 | Motor Free Run Test | 2.047% | 0.1472% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160908 |  |  | FA-25160908 | Motor Free Run Test | 100% | 0.1472% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Motor Free Run Test | 50130 | FA-25160909 |  |  | FA-25160909 | Motor Free Run | 95% | 0.1398% |  | 48 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Motor Free Run Test |  | FA-25160910 |  |  | FA-25160910 | QC | 5% | 0.007359% |  | 48 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160911 |  |  | FA-25160911 | Lighting & Small Power System | 27.26% | 1.96% |  |  |  |  | 0 | 0% | 11.47% | 11.47% |  | 0.5571% | 0 |  |  | 0.4271% |  |  |  |  | 0.5571% |  | 0.4271%
[6 empty] | 5 |  | Electrical |  |  | FA-25160912 |  |  | FA-25160912 | Lighting JB | 5.256% | 0.103% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting JB |  | FA-25160913 |  |  | FA-25160913 | Handling | 10% | 0.0103% |  | 159 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting JB | 50140 | FA-25160914 |  |  | FA-25160914 | Fixing in place | 85% | 0.08755% |  | 159 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting JB |  | FA-25160915 |  |  | FA-25160915 | QC | 5% | 0.00515% |  | 159 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160916 |  |  | FA-25160916 | Lighting Fixture | 39.03% | 0.7649% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Fixture |  | FA-25160917 |  |  | FA-25160917 | Handling | 10% | 0.07649% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Fixture | 50150 | FA-25160918 |  |  | FA-25160918 | Installation of lighting poles | 20% | 0.153% |  | 356 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Fixture | 50160 | FA-25160919 |  |  | FA-25160919 | Installation Fixture | 65% | 0.4972% |  | 387 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Fixture |  | FA-25160920 |  |  | FA-25160920 | QC | 5% | 0.03824% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160921 |  |  | FA-25160921 | Lighting Socket | 2.834% | 0.05554% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Socket |  | FA-25160922 |  |  | FA-25160922 | Handling | 10% | 0.005554% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Socket | 50170 | FA-25160923 |  |  | FA-25160923 | Fixing in place | 85% | 0.04721% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Socket |  | FA-25160924 |  |  | FA-25160924 | QC | 5% | 0.002777% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160925 |  |  | FA-25160925 | Street Lighting | 52.87% | 1.036% |  |  |  |  | 0 | 0% | 21.7% | 21.7% |  | 0.5571% | 0 |  |  | 0.4271% |  |  |  |  | 0.5571% |  | 0.4271%
Plan | 0.00044963 | 0.0001414% | 1.465e-07% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Street Lighting |  | FA-25160926 |  |  | FA-25160926 | Handling | 10% | 0.1036% |  | 318 |  | 318 | 318 | 0% | 100% | 100% | 180 | 0.05865% | 318 | 138 | 0.43396 | 0.04496% | Week 1 | Week 4 |  | 180 | 0.05865% | 138 | 0.04496% | ok | 56.6% | 0.05865%
Plan | 0.00089925 | 0.001697% | 3.516e-06% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Street Lighting | 90001 | FA-25160927 |  |  | FA-25160927 | Installation of lighting poles | 20% | 0.2072% |  | 53 |  | 11 | 11 | 0% | 20.75% | 20.75% | 30 | 0.1173% | 11 | 23 | 0.43396 | 0.08993% | Week 1 | Week 4 |  | 30 | 0.1173% | 23 | 0.08993% | ok | 56.6% | 0.1173%
Plan | 0.0017985 | 0.0005656% | 2.344e-06% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Street Lighting | 90015 | FA-25160928 |  |  | FA-25160928 | Installation Fixture | 40% | 0.4144% |  | 318 |  | 0 | 0 | 0% | 0% | 0% | 180 | 0.2346% | 0 | 138 | 0.43396 | 0.1799% | Week 1 | Week 4 |  | 180 | 0.2346% | 138 | 0.1799% | ok | 56.6% | 0.2346%
Plan | 0.0011241 | 0.00106% | 2.747e-06% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Street Lighting | 90030 | FA-25160929 |  |  | FA-25160929 | Installation JB | 25% | 0.259% |  | 106 |  | 32 | 32 | 0% | 30.19% | 30.19% | 60 | 0.1466% | 32 | 46 | 0.43396 | 0.1124% | Week 1 | Week 4 |  | 60 | 0.1466% | 46 | 0.1124% | ok | 56.6% | 0.1466%
[6 empty] | 6 | Unit - TNK | Electrical | Street Lighting |  | FA-25160930 |  |  | FA-25160930 | QC | 5% | 0.0518% |  | 53 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160931 |  |  | FA-25160931 | Electrical Heat Tracing | 1.772% | 0.1274% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160932 |  |  | FA-25160932 | Electrical Heat Tracing Cabling | 100% | 0.1274% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Heat Tracing Cabling |  | FA-25160933 |  |  | FA-25160933 | Handling | 10% | 0.01274% |  | 864 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Heat Tracing Cabling | 80001 | FA-25160934 |  |  | FA-25160934 | Cable laying | 45% | 0.05733% |  | 864 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Heat Tracing Cabling |  | FA-25160935 |  |  | FA-25160935 | Cable arrangements and fixing | 10% | 0.01274% |  | 864 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Heat Tracing Cabling | 80010 | FA-25160936 |  |  | FA-25160936 | Gland Installation | 20% | 0.02548% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Heat Tracing Cabling | 80020 | FA-25160937 |  |  | FA-25160937 | Termination | 10% | 0.01274% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Electrical Heat Tracing Cabling |  | FA-25160938 |  |  | FA-25160938 | QC | 5% | 0.006371% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160939 |  |  | FA-25160939 | Electrical Cabling | 30.22% | 2.173% |  |  |  |  | 0 | 0% | 0.7608% | 0.7608% |  | 0.02977% | 0 |  |  | 0.02802% |  |  |  |  | 0.02977% |  | 0.02802%
[6 empty] | 5 |  | Electrical |  |  | FA-25160940 |  |  | FA-25160940 | MV Cable | 3.913% | 0.08503% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable |  | FA-25160941 |  |  | FA-25160941 | Handling | 10% | 0.008503% |  | 2428 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable | 50180 | FA-25160942 |  |  | FA-25160942 | Cable laying | 70% | 0.05952% |  | 2428 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable |  | FA-25160943 |  |  | FA-25160943 | Cable arrangements and fixing | 5% | 0.004252% |  | 2428 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable | 50180 | FA-25160944 |  |  | FA-25160944 | Cable Marking | 5% | 0.004252% |  | 2428 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable |  | FA-25160945 |  |  | FA-25160945 | Continuity & Megger Test | 5% | 0.004252% |  | 2428 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable |  | FA-25160946 |  |  | FA-25160946 | QC | 5% | 0.004252% |  | 2428 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160947 |  |  | FA-25160947 | LV Cable | 45.75% | 0.994% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | LV Cable |  | FA-25160948 |  |  | FA-25160948 | Handling | 10% | 0.0994% |  | 28383 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | LV Cable | 50190 | FA-25160949 |  |  | FA-25160949 | Cable laying | 70% | 0.6958% |  | 28383 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | LV Cable |  | FA-25160950 |  |  | FA-25160950 | Cable arrangements and fixing | 5% | 0.0497% |  | 28383 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | LV Cable | 50190 | FA-25160951 |  |  | FA-25160951 | Cable Marking | 5% | 0.0497% |  | 28383 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | LV Cable |  | FA-25160952 |  |  | FA-25160952 | Continuity & Megger Test | 5% | 0.0497% |  | 28383 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | LV Cable |  | FA-25160953 |  |  | FA-25160953 | QC | 5% | 0.0497% |  | 28383 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160954 |  |  | FA-25160954 | Control Cable | 25.95% | 0.5639% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Control Cable |  | FA-25160955 |  |  | FA-25160955 | Handling | 10% | 0.05639% |  | 16103 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Control Cable | 50200 | FA-25160956 |  |  | FA-25160956 | Cable laying | 70% | 0.3948% |  | 16103 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Control Cable |  | FA-25160957 |  |  | FA-25160957 | Cable arrangements and fixing | 5% | 0.0282% |  | 16103 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Control Cable | 50200 | FA-25160958 |  |  | FA-25160958 | Cable Marking | 5% | 0.0282% |  | 16103 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Control Cable |  | FA-25160959 |  |  | FA-25160959 | Continuity & Megger Test | 5% | 0.0282% |  | 16103 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Control Cable |  | FA-25160960 |  |  | FA-25160960 | QC | 5% | 0.0282% |  | 16103 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160961 |  |  | FA-25160961 | Lighting Cable | 24.39% | 0.5299% |  |  |  |  | 0 | 0% | 3.12% | 3.12% |  | 0.02977% | 0 |  |  | 0.02802% |  |  |  |  | 0.02977% |  | 0.02802%
Plan | 3.5021e-05 | 2.315e-07% | 1.226e-10% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Lighting Cable |  | FA-25160962 |  |  | FA-25160962 | Handling | 10% | 0.05299% |  | 15130 |  | 1300 | 1300 | 0% | 8.592% | 8.592% | 1000 | 0.003502% | 1300 | 1000 | 0.066094 | 0.003502% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 1000 | 0.003502% | 1000 | 0.003502% | ok | 6.609% | 0.003502%
Plan | 0.00024515 | 1.62e-06% | 6.01e-09% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Lighting Cable | 50210 | FA-25160963 |  |  | FA-25160963 | Cable laying | 70% | 0.3709% |  | 15130 |  | 456 | 456 | 0% | 3.014% | 3.014% | 1000 | 0.02451% | 456 | 1000 | 0.066094 | 0.02451% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 1000 | 0.02451% | 1000 | 0.02451% | ok | 6.609% | 0.02451%
|  |  |  | Plan Jan |  | 6 | Unit - TNK | Electrical | Lighting Cable |  | FA-25160964 |  |  | FA-25160964 | Cable arrangements and fixing | 5% | 0.02649% |  | 15130 |  | 456 | 456 | 0% | 3.014% | 3.014% | 1000 | 0.001751% | 456 | [6 empty] | 1000 | 0.001751%
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Cable | 50210 | FA-25160965 |  |  | FA-25160965 | Cable Marking | 5% | 0.02649% |  | 15130 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Cable |  | FA-25160966 |  |  | FA-25160966 | Continuity & Megger Test | 5% | 0.02649% |  | 15130 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Lighting Cable |  | FA-25160967 |  |  | FA-25160967 | QC | 5% | 0.02649% |  | 15130 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Electrical |  |  | FA-25160968 |  |  | FA-25160968 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 4.991% | 0.3588% |  |  |  |  | 0 | 0% | 6.228% | 6.228% |  | 0.1411% | 0 |  |  | 0.08969% |  |  |  |  | 0.1411% |  | 0.08969%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Electrical |  |  | FA-25160969 |  |  | FA-25160969 | Cable Gland & Termination | 74.78% | 0.2683% |  |  |  |  | 0 | 0% | 8.328% | 8.328% |  | 0.1411% | 0 |  |  | 0.08969% |  |  |  |  | 0.1411% |  | 0.08969%
|  |  |  | Plan Jan |  | 6 | Unit - TNK | Electrical | Cable Gland & Termination |  | FA-25160970 |  |  | FA-25160970 | Handling | 10% | 0.02683% |  | 867 |  | 450 | 450 | 0% | 51.9% | 51.9% | 480 | 0.01486% | 450 | [6 empty] | 480 | 0.01486%
Plan | 0.00059795 | 6.897e-05% | 1.11e-07% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Cable Gland & Termination | 50220 | FA-25160971 |  |  | FA-25160971 | Gland Installation | 60% | 0.161% |  | 867 |  | 32 | 32 | 0% | 3.691% | 3.691% | 480 | 0.08914% | 32 | 322 | 0.3714 | 0.0598% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 480 | 0.08914% | 322 | 0.0598% | ok | 55.36% | 0.08914%
Plan | 0.00024915 | 2.874e-05% | 1.928e-08% | Plan Jan | Plan Feb | 6 | Unit - TNK | Electrical | Cable Gland & Termination | 50230 | FA-25160972 |  |  | FA-25160972 | Termination | 25% | 0.06708% |  | 867 |  | 32 | 32 | 0% | 3.691% | 3.691% | 480 | 0.03714% | 32 | 322 | 0.3714 | 0.02491% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون | 480 | 0.03714% | 322 | 0.02491% | ok | 55.36% | 0.03714%
Plan | 4.9829e-05 | 5.747e-06% | 7.711e-10% |  | Plan Feb | 6 | Unit - TNK | Electrical | Cable Gland & Termination |  | FA-25160973 |  |  | FA-25160973 | QC | 5% | 0.01342% |  | 867 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 322 | 0.3714 | 0.004983% | Week 1 | Week 4 | منوط به تهیه کابل بدون Armor و فنداسیون |  |  | 322 | 0.004983% | ok | 0% | 0%
[6 empty] | 5 |  | Electrical |  |  | FA-25160974 |  |  | FA-25160974 | MV Cable Termination kit | 25.22% | 0.09048% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable Termination kit |  | FA-25160975 |  |  | FA-25160975 | Handling | 10% | 0.009048% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable Termination kit | 50240 | FA-25160976 |  |  | FA-25160976 | Termination Kit | 85% | 0.07691% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | MV Cable Termination kit |  | FA-25160977 |  |  | FA-25160977 | QC | 5% | 0.004524% |  | 18 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25160978 |  |  | FA-25160978 | Grounding/ Earthing System | 1.012% | 0.07273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160979 |  |  | FA-25160979 | Earthing Cable Pulling | 100% | 0.07273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Earthing Cable Pulling |  | FA-25160980 |  |  | FA-25160980 | Handling | 10% | 0.007273% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Earthing Cable Pulling | 50250 | FA-25160981 |  |  | FA-25160981 | Cable laying | 75% | 0.05455% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Earthing Cable Pulling |  | FA-25160982 |  |  | FA-25160982 | Cable arrangements and fixing | 10% | 0.007273% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Electrical | Earthing Cable Pulling |  | FA-25160983 |  |  | FA-25160983 | QC | 5% | 0.003637% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 3 |  | Electrical |  |  | FA-25160984 |  |  | FA-25160984 | Substation - S55 | 5.49% | 2.142% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.7628% | [6 empty] | 0.7628%
[6 empty] | 4 |  | Electrical |  |  | FA-25160985 |  |  | FA-25160985 | Cable Tray, ladder, Conduits | 0.532% | 0.0114% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160986 |  |  | FA-25160986 | Installation of Cable Tray, ladder, Cover | 58.11% | 0.006621% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160987 |  |  | FA-25160987 | Handling | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of Cable Tray, ladder, Cover | 50001 | FA-25160988 |  |  | FA-25160988 | Tray/ Ladder Assembling | 65% | 0.004304% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160989 |  |  | FA-25160989 | Fixing & alignment | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160990 |  |  | FA-25160990 | Installation of covers | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of Cable Tray, ladder, Cover |  | FA-25160991 |  |  | FA-25160991 | QC | 5% | 0.0003311% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25160992 |  |  | FA-25160992 | Installation of conduits | 41.89% | 0.004774% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of conduits |  | FA-25160993 |  |  | FA-25160993 | Handling | 10% | 0.0004774% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of conduits | 50010 | FA-25160994 |  |  | FA-25160994 | Installation of Conduit | 85% | 0.004058% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Installation of conduits |  | FA-25160995 |  |  | FA-25160995 | QC | 5% | 0.0002387% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Electrical |  |  | FA-25160996 |  |  | FA-25160996 | EL Transformer/ Panel/ JB | 46.84% | 1.003% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.7628% | [6 empty] | 0.7628%
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25160997 |  |  | FA-25160997 | Transformer | 9.362% | 0.09393% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.06105% | [6 empty] | 0.06105%
Plan | 9.3926e-05 | 0.003131% | 2.941e-07% |  | Plan Feb | 6 | Substation - S55 | Electrical | Transformer |  | FA-25160998 |  |  | FA-25160998 | Handling | 10% | 0.009393% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 3 | 1 | 0.009393% | Week 3 | Week 4 |  |  |  | 3 | 0.009393% | ok | 0% | 0%
Plan | 0.00051659 | 0.01722% | 8.896e-06% |  | Plan Feb | 6 | Substation - S55 | Electrical | Transformer | 10008 | FA-25160999 |  |  | FA-25160999 | Installation | 55% | 0.05166% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 3 | 1 | 0.05166% | Week 3 | Week 4 |  |  |  | 3 | 0.05166% | ok | 0% | 0%
[6 empty] | 6 | Substation - S55 | Electrical | Transformer |  | FA-25161000 |  |  | FA-25161000 | Installation of Accessories | 20% | 0.01879% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Transformer |  | FA-25161001 |  |  | FA-25161001 | Oil Filling | 10% | 0.009393% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Transformer |  | FA-25161002 |  |  | FA-25161002 | QC | 5% | 0.004696% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25161003 |  |  | FA-25161003 | LV Switchgear | 32.96% | 0.3307% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.3141% | [6 empty] | 0.3141%
Plan | 0.00033067 | 0.001181% | 3.905e-07% |  | Plan Feb | 6 | Substation - S55 | Electrical | LV Switchgear |  | FA-25161004 |  |  | FA-25161004 | Handling | 10% | 0.03307% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 28 | 1 | 0.03307% | Week 3 | Week 4 |  |  |  | 28 | 0.03307% | ok | 0% | 0%
Plan | 0.0024801 | 0.008857% | 2.197e-05% |  | Plan Feb | 6 | Substation - S55 | Electrical | LV Switchgear | 50260 | FA-25161005 |  |  | FA-25161005 | Installation | 75% | 0.248% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 28 | 1 | 0.248% | Week 3 | Week 4 |  |  |  | 28 | 0.248% | ok | 0% | 0%
Plan | 0.00033067 | 0.001181% | 3.905e-07% |  | Plan Feb | 6 | Substation - S55 | Electrical | LV Switchgear |  | FA-25161006 |  |  | FA-25161006 | Fixing | 10% | 0.03307% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 28 | 1 | 0.03307% | Week 3 | Week 4 |  |  |  | 28 | 0.03307% | ok | 0% | 0%
[6 empty] | 6 | Substation - S55 | Electrical | LV Switchgear |  | FA-25161007 |  |  | FA-25161007 | QC | 5% | 0.01653% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25161008 |  |  | FA-25161008 | MV Switchgear | 28.25% | 0.2834% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2693% | [6 empty] | 0.2693%
Plan | 0.00028344 | 0.001181% | 3.347e-07% |  | Plan Feb | 6 | Substation - S55 | Electrical | MV Switchgear |  | FA-25161009 |  |  | FA-25161009 | Handling | 10% | 0.02834% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 24 | 1 | 0.02834% | Week 3 | Week 4 |  |  |  | 24 | 0.02834% | ok | 0% | 0%
Plan | 0.0021258 | 0.008857% | 1.883e-05% |  | Plan Feb | 6 | Substation - S55 | Electrical | MV Switchgear | 50280 | FA-25161010 |  |  | FA-25161010 | Installation | 75% | 0.2126% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 24 | 1 | 0.2126% | Week 3 | Week 4 |  |  |  | 24 | 0.2126% | ok | 0% | 0%
Plan | 0.00028344 | 0.001181% | 3.347e-07% |  | Plan Feb | 6 | Substation - S55 | Electrical | MV Switchgear |  | FA-25161011 |  |  | FA-25161011 | Fixing | 10% | 0.02834% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 24 | 1 | 0.02834% | Week 3 | Week 4 |  |  |  | 24 | 0.02834% | ok | 0% | 0%
[6 empty] | 6 | Substation - S55 | Electrical | MV Switchgear |  | FA-25161012 |  |  | FA-25161012 | QC | 5% | 0.01417% |  | 24 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25161013 |  |  | FA-25161013 | UPS,DC charger and Battries | 12.56% | 0.126% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.05984% | [6 empty] | 0.05984%
Plan | 6.2986e-05 | 0.001575% | 1.984e-07% |  | Plan Feb | 6 | Substation - S55 | Electrical | UPS,DC charger and Battries |  | FA-25161014 |  |  | FA-25161014 | Handling | 10% | 0.0126% | Set | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2 | 0.5 | 0.006299% | Week 3 | Week 4 |  |  |  | 2 | 0.006299% | ok | 0% | 0%
Plan | 0.00047239 | 0.01181% | 1.116e-05% |  | Plan Feb | 6 | Substation - S55 | Electrical | UPS,DC charger and Battries | 50290 | FA-25161015 |  |  | FA-25161015 | Installation | 75% | 0.09448% | Set | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2 | 0.5 | 0.04724% | Week 3 | Week 4 |  |  |  | 2 | 0.04724% | ok | 0% | 0%
Plan | 6.2986e-05 | 0.001575% | 1.984e-07% |  | Plan Feb | 6 | Substation - S55 | Electrical | UPS,DC charger and Battries |  | FA-25161016 |  |  | FA-25161016 | Fixing | 10% | 0.0126% | Set | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2 | 0.5 | 0.006299% | Week 3 | Week 4 |  |  |  | 2 | 0.006299% | ok | 0% | 0%
[6 empty] | 6 | Substation - S55 | Electrical | UPS,DC charger and Battries |  | FA-25161017 |  |  | FA-25161017 | QC | 5% | 0.006299% | Set | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Electrical |  |  | FA-25161018 |  |  | FA-25161018 | Main Lighting Panel | 6.867% | 0.06889% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.05856% | [6 empty] | 0.05856%
Plan | 6.889e-05 | 0.001378% | 9.492e-08% |  | Plan Feb | 6 | Substation - S55 | Electrical | Main Lighting Panel |  | FA-25161019 |  |  | FA-25161019 | Handling | 10% | 0.006889% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 5 | 1 | 0.006889% | Week 3 | Week 4 |  |  |  | 5 | 0.006889% | ok | 0% | 0%
Plan | 0.00051668 | 0.01033% | 5.339e-06% |  | Plan Feb | 6 | Substation - S55 | Electrical | Main Lighting Panel | 800250 | FA-25161020 |  |  | FA-25161020 | Installation | 75% | 0.05167% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 5 | 1 | 0.05167% | Week 3 | Week 4 |  |  |  | 5 | 0.05167% | ok | 0% | 0%
[6 empty] | 6 | Substation - S55 | Electrical | Main Lighting Panel |  | FA-25161021 |  |  | FA-25161021 | Fixing | 10% | 0.006889% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Main Lighting Panel |  | FA-25161022 |  |  | FA-25161022 | QC | 5% | 0.003445% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161023 |  |  | FA-25161023 | Test and Energizing Transformer/ Switchgeers/ MCC, …. | 10% | 0.1003% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Test and Energizing Transformer/ Switchgeers/ MCC, …. |  | FA-25161024 |  |  | FA-25161024 | Energizing | 90% | 0.09029% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Test and Energizing Transformer/ Switchgeers/ MCC, …. |  | FA-25161025 |  |  | FA-25161025 | Document | 10% | 0.01003% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25161026 |  |  | FA-25161026 | Diesel Generator | 6.958% | 0.149% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161027 |  |  | FA-25161027 | Diesel Generator | 100% | 0.149% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Diesel Generator |  | FA-25161028 |  |  | FA-25161028 | Handling | 10% | 0.0149% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Diesel Generator | 12128 | FA-25161029 |  |  | FA-25161029 | Installation of Generator | 80% | 0.1192% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Diesel Generator |  | FA-25161030 |  |  | FA-25161030 | Cable connections | 5% | 0.007452% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Diesel Generator |  | FA-25161031 |  |  | FA-25161031 | QC | 5% | 0.007452% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25161032 |  |  | FA-25161032 | Electrical Cabling | 31.28% | 0.6699% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161033 |  |  | FA-25161033 | MV Cable | 63.44% | 0.425% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable |  | FA-25161034 |  |  | FA-25161034 | Handling | 10% | 0.0425% |  | 12135 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable | 50180 | FA-25161035 |  |  | FA-25161035 | Cable laying | 70% | 0.2975% |  | 12135 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable |  | FA-25161036 |  |  | FA-25161036 | Cable arrangements and fixing | 5% | 0.02125% |  | 12135 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable |  | FA-25161037 |  |  | FA-25161037 | Cable Marking | 5% | 0.02125% |  | 12135 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable |  | FA-25161038 |  |  | FA-25161038 | Continuity & Megger Test | 5% | 0.02125% |  | 12135 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable |  | FA-25161039 |  |  | FA-25161039 | QC | 5% | 0.02125% |  | 12135 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161040 |  |  | FA-25161040 | LV Cable | 12.72% | 0.08521% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | LV Cable |  | FA-25161041 |  |  | FA-25161041 | Handling | 10% | 0.008521% |  | 2433 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | LV Cable | 50190 | FA-25161042 |  |  | FA-25161042 | Cable laying | 70% | 0.05964% |  | 2433 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | LV Cable |  | FA-25161043 |  |  | FA-25161043 | Cable arrangements and fixing | 5% | 0.00426% |  | 2433 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | LV Cable |  | FA-25161044 |  |  | FA-25161044 | Cable Marking | 5% | 0.00426% |  | 2433 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | LV Cable |  | FA-25161045 |  |  | FA-25161045 | Continuity & Megger Test | 5% | 0.00426% |  | 2433 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | LV Cable |  | FA-25161046 |  |  | FA-25161046 | QC | 5% | 0.00426% |  | 2433 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161047 |  |  | FA-25161047 | Control Cable | 23.84% | 0.1597% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Control Cable |  | FA-25161048 |  |  | FA-25161048 | Handling | 10% | 0.01597% |  | 4561 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Control Cable | 50200 | FA-25161049 |  |  | FA-25161049 | Cable laying | 70% | 0.1118% |  | 4561 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Control Cable |  | FA-25161050 |  |  | FA-25161050 | Cable arrangements and fixing | 5% | 0.007987% |  | 4561 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Control Cable |  | FA-25161051 |  |  | FA-25161051 | Cable Marking | 5% | 0.007987% |  | 4561 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Control Cable |  | FA-25161052 |  |  | FA-25161052 | Continuity & Megger Test | 5% | 0.007987% |  | 4561 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Control Cable |  | FA-25161053 |  |  | FA-25161053 | QC | 5% | 0.007987% |  | 4561 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25161054 |  |  | FA-25161054 | Electrical Cable Gland/ Termination/ MV Cable Termination kit | 9.302% | 0.1992% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161055 |  |  | FA-25161055 | Cable Gland & Termination | 29.36% | 0.0585% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Cable Gland & Termination |  | FA-25161056 |  |  | FA-25161056 | Handling | 10% | 0.00585% |  | 189 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Cable Gland & Termination | 50220 | FA-25161057 |  |  | FA-25161057 | Gland Installation | 60% | 0.0351% |  | 189 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Cable Gland & Termination | 50230 | FA-25161058 |  |  | FA-25161058 | Termination | 25% | 0.01462% |  | 189 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Cable Gland & Termination |  | FA-25161059 |  |  | FA-25161059 | QC | 5% | 0.002925% |  | 189 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161060 |  |  | FA-25161060 | MV Cable Termination kit | 70.64% | 0.1408% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable Termination kit |  | FA-25161061 |  |  | FA-25161061 | Handling | 10% | 0.01408% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable Termination kit | 50240 | FA-25161062 |  |  | FA-25161062 | Termination Kit | 85% | 0.1196% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | MV Cable Termination kit |  | FA-25161063 |  |  | FA-25161063 | QC | 5% | 0.007038% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Electrical |  |  | FA-25161064 |  |  | FA-25161064 | Grounding/ Earthing System | 5.093% | 0.1091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Electrical |  |  | FA-25161065 |  |  | FA-25161065 | Earthing Cable Pulling | 100% | 0.1091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Earthing Cable Pulling |  | FA-25161066 |  |  | FA-25161066 | Handling | 10% | 0.01091% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Earthing Cable Pulling | 50250 | FA-25161067 |  |  | FA-25161067 | Cable laying | 75% | 0.08182% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Earthing Cable Pulling |  | FA-25161068 |  |  | FA-25161068 | Cable arrangements and fixing | 10% | 0.01091% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Substation - S55 | Electrical | Earthing Cable Pulling |  | FA-25161069 |  |  | FA-25161069 | QC | 5% | 0.005455% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Electrical |  |  | FA-25161070 |  |  | FA-25161070 | Unit - WWT | 5% | 1.951% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - WWT | Electrical |  |  | FA-25161071 |  |  | FA-25161071 | Unit - WWT | 100% | 1.951% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Electrical |  |  | FA-25161072 |  |  | FA-25161072 | Contingency Reserve | 5% | 1.951% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Contingency Reserve | Electrical |  |  | FA-25161073 |  |  | FA-25161073 | Contingency Reserve | 100% | 1.951% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 2 |  | Instrument |  |  | FA-25161074 |  |  | FA-25161074 | Instrument | 42.48% | 42.48% |  |  |  |  | 0 | 1.903% | 0.309% | 2.212% |  | 0.8745% | 0 |  |  | 3.378% |  |  |  |  | 0.8745% |  | 3.371%
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Instrument |  |  | FA-25161075 |  |  | FA-25161075 | Unit - CDU | 20.36% | 8.647% |  |  |  |  | 0 | 1.454% | 0% | 1.454% |  | 0.1258% | 0 |  |  | 1.726% |  |  |  |  | 0.1258% |  | 1.726%
Plan |  |  |  |  | Plan Feb | 4 |  | Instrument |  |  | FA-25161076 |  |  | FA-25161076 | Cable Tray, ladder, Conduits | 12.39% | 1.071% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2814% | [6 empty] | 0.2814%
Plan |  |  |  |  | Plan Feb | 5 |  | Instrument |  |  | FA-25161077 |  |  | FA-25161077 | Installation of Primary Tray, ladder | 46.36% | 0.4966% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2814% | [6 empty] | 0.2814%
Plan | 0.00033107 | 1.104e-05% | 5.48e-09% |  | Plan Feb | 6 | Unit - CDU | Instrument | Installation of Primary Tray, ladder |  | FA-25161078 |  |  | FA-25161078 | Handling | 10% | 0.04966% |  | 3000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2000 | 0.66667 | 0.03311% | Week 1 | Week 4 |  |  |  | 2000 | 0.03311% | ok | 0% | 0%
Plan | 0.002152 | 7.173e-05% | 2.315e-07% |  | Plan Feb | 6 | Unit - CDU | Instrument | Installation of Primary Tray, ladder | 40001 | FA-25161079 |  |  | FA-25161079 | Tray/ Ladder Assembling | 65% | 0.3228% |  | 3000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2000 | 0.66667 | 0.2152% | Week 1 | Week 4 |  |  |  | 2000 | 0.2152% | ok | 0% | 0%
Plan | 0.00033107 | 1.104e-05% | 5.48e-09% |  | Plan Feb | 6 | Unit - CDU | Instrument | Installation of Primary Tray, ladder |  | FA-25161080 |  |  | FA-25161080 | Fixing & alignment | 10% | 0.04966% |  | 3000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2000 | 0.66667 | 0.03311% | Week 1 | Week 4 |  |  |  | 2000 | 0.03311% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Instrument | Installation of Primary Tray, ladder |  | FA-25161081 |  |  | FA-25161081 | Installation of covers | 10% | 0.04966% |  | 3000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Installation of Primary Tray, ladder |  | FA-25161082 |  |  | FA-25161082 | QC | 5% | 0.02483% |  | 3000 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161083 |  |  | FA-25161083 | Installation of Secondary Tray | 46.36% | 0.4966% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Installation of Secondary Tray |  | FA-25161084 |  |  | FA-25161084 | Handling | 10% | 0.04966% |  |  |  | 153 | 153 | 0% | 0% | 0% |  |  | 153
[6 empty] | 6 | Unit - CDU | Instrument | Installation of Secondary Tray | 40001 | FA-25161085 |  |  | FA-25161085 | Tray/ Ladder Assembling | 65% | 0.3228% |  |  |  | 153 | 153 | 0% | 0% | 0% |  |  | 153
[6 empty] | 6 | Unit - CDU | Instrument | Installation of Secondary Tray |  | FA-25161086 |  |  | FA-25161086 | Fixing & alignment | 10% | 0.04966% |  |  |  | 153 | 153 | 0% | 0% | 0% |  |  | 153
[6 empty] | 6 | Unit - CDU | Instrument | Installation of Secondary Tray |  | FA-25161087 |  |  | FA-25161087 | Installation of covers | 10% | 0.04966% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Installation of Secondary Tray |  | FA-25161088 |  |  | FA-25161088 | QC | 5% | 0.02483% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161089 |  |  | FA-25161089 | Installation of conduits | 7.286% | 0.07805% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Installation of conduits |  | FA-25161090 |  |  | FA-25161090 | Handling | 10% | 0.007805% |  | 327 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Installation of conduits | 40010 | FA-25161091 |  |  | FA-25161091 | Installation of Conduit | 85% | 0.06634% |  | 327 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Installation of conduits |  | FA-25161092 |  |  | FA-25161092 | QC | 5% | 0.003903% |  | 327 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Instrument |  |  | FA-25161093 |  |  | FA-25161093 | Supports | 2.909% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 |  |  | 0.07381% |  |  |  |  | 0.1258% |  | 0.07381%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Instrument |  |  | FA-25161094 |  |  | FA-25161094 | Supports | 100% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 |  |  | 0.07381% |  |  |  |  | 0.1258% |  | 0.07381%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Instrument | Supports |  | FA-25161095 |  |  | FA-25161095 | Material Supply & Handling | 50% | 0.1258% |  | 2300 |  | 2300 | 2300 | 100% | 0% | 100% | 2300 | 0.1258% | 2300 | [6 empty] | 2300 | 0.1258%
Plan | 0.00032805 | 1.426e-05% | 7.174e-09% |  | Plan Feb | 6 | Unit - CDU | Instrument | Supports | 40020 | FA-25161096 |  |  | FA-25161096 | Fabrication | 20% | 0.0503% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 1500 | 0.65217 | 0.0328% | Week 1 | Week 4 |  |  |  | 1500 | 0.0328% | ok | 0% | 0%
Plan | 0.00041006 | 1.783e-05% | 1.121e-08% |  | Plan Feb | 6 | Unit - CDU | Instrument | Supports | 40030 | FA-25161097 |  |  | FA-25161097 | Installation | 25% | 0.06288% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 1500 | 0.65217 | 0.04101% | Week 1 | Week 4 |  |  |  | 1500 | 0.04101% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Instrument | Supports |  | FA-25161098 |  |  | FA-25161098 | QC | 5% | 0.01258% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161099 |  |  | FA-25161099 | Calibration ( Device & Valve ) | 2.018% | 0.1745% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161100 |  |  | FA-25161100 | Calibration ( Device & Valve ) | 100% | 0.1745% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Calibration ( Device & Valve ) |  | FA-25161101 |  |  | FA-25161101 | Handling | 10% | 0.01745% |  | 628 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161102 |  |  | FA-25161102 | Calibration and restoring | 90% | 0.157% |  | 628 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Instrument |  |  | FA-25161103 |  |  | FA-25161103 | Instrument Equipment | 28.8% | 2.49% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2299% | [6 empty] | 0.2299%
[6 empty] | 5 |  | Instrument |  |  | FA-25161104 |  |  | FA-25161104 | FIELD INSTRUMENTS | 72.09% | 1.795% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | FIELD INSTRUMENTS |  | FA-25161105 |  |  | FA-25161105 | Handling | 10% | 0.1795% |  | 459 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161106 |  |  | FA-25161106 | Installation | 85% | 1.526% |  | 459 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | FIELD INSTRUMENTS |  | FA-25161107 |  |  | FA-25161107 | QC | 5% | 0.08975% |  | 459 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161108 |  |  | FA-25161108 | F&G DETECTORS | 18.15% | 0.4519% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | F&G DETECTORS |  | FA-25161109 |  |  | FA-25161109 | Handling | 10% | 0.04519% |  | 170 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | F&G DETECTORS | 40060 | FA-25161110 |  |  | FA-25161110 | Installation | 85% | 0.3841% |  | 170 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | F&G DETECTORS |  | FA-25161111 |  |  | FA-25161111 | QC | 5% | 0.02259% |  | 170 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Instrument |  |  | FA-25161112 |  |  | FA-25161112 | Junction Box | 9.719% | 0.242% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2299% | [6 empty] | 0.2299%
Plan | 0.000242 | 0.0003361% | 8.134e-08% |  | Plan Feb | 6 | Unit - CDU | Instrument | Junction Box |  | FA-25161113 |  |  | FA-25161113 | Handling | 10% | 0.0242% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 72 | 1 | 0.0242% | Week 1 | Week 4 |  |  |  | 72 | 0.0242% | ok | 0% | 0%
Plan | 0.002057 | 0.002857% | 5.877e-06% |  | Plan Feb | 6 | Unit - CDU | Instrument | Junction Box | 40075 | FA-25161114 |  |  | FA-25161114 | Installation | 85% | 0.2057% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 72 | 1 | 0.2057% | Week 1 | Week 4 |  |  |  | 72 | 0.2057% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Instrument | Junction Box |  | FA-25161115 |  |  | FA-25161115 | QC | 5% | 0.0121% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161116 |  |  | FA-25161116 | Analyzer | 0.04322% | 0.001076% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Analyzer |  | FA-25161117 |  |  | FA-25161117 | Handling | 10% | 0.0001076% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Analyzer |  | FA-25161118 |  |  | FA-25161118 | Installation | 85% | 0.0009147% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Analyzer |  | FA-25161119 |  |  | FA-25161119 | QC | 5% | 5.38e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Instrument |  |  | FA-25161120 |  |  | FA-25161120 | Instrument Cabling | 33.23% | 2.874% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 1.141% | [6 empty] | 1.141%
Plan |  |  |  |  | Plan Feb | 5 |  | Instrument |  |  | FA-25161121 |  |  | FA-25161121 | Main Cabling | 100% | 2.874% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 1.141% | [6 empty] | 1.141%
Plan | 0.0014263 | 2.832e-06% | 8.138e-09% |  | Plan Feb | 6 | Unit - CDU | Instrument | Main Cabling |  | FA-25161122 |  |  | FA-25161122 | Handling | 10% | 0.2874% |  | 50369 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 25000 | 0.49634 | 0.1426% | Week 1 | Week 4 |  |  |  | 25000 | 0.1426% | ok | 0% | 0%
Plan | 0.0099843 | 1.982e-05% | 3.987e-07% |  | Plan Feb | 6 | Unit - CDU | Instrument | Main Cabling | 40090 | FA-25161123 |  |  | FA-25161123 | Cable laying | 70% | 2.012% |  | 50369 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 25000 | 0.49634 | 0.9984% | Week 1 | Week 4 | موط به آمادگی ترچ ها |  |  | 25000 | 0.9984% | ok | 0% | 0%
[6 empty] | 6 | Unit - CDU | Instrument | Main Cabling |  | FA-25161124 |  |  | FA-25161124 | Cable arrangements and fixing | 5% | 0.1437% |  | 50369 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Main Cabling |  | FA-25161125 |  |  | FA-25161125 | Cable Marking | 5% | 0.1437% |  | 50369 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Main Cabling |  | FA-25161126 |  |  | FA-25161126 | Continuity & Megger Test | 5% | 0.1437% |  | 50369 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Main Cabling |  | FA-25161127 |  |  | FA-25161127 | QC | 5% | 0.1437% |  | 50369 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161128 |  |  | FA-25161128 | Secondary Cabling | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Secondary Cabling |  | FA-25161129 |  |  | FA-25161129 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Secondary Cabling | 40500 | FA-25161130 |  |  | FA-25161130 | Cable laying | 70% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Secondary Cabling |  | FA-25161131 |  |  | FA-25161131 | Cable arrangements and fixing | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Secondary Cabling |  | FA-25161132 |  |  | FA-25161132 | Cable Marking | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Secondary Cabling |  | FA-25161133 |  |  | FA-25161133 | Continuity & Megger Test | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Secondary Cabling |  | FA-25161134 |  |  | FA-25161134 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161135 |  |  | FA-25161135 | Instrument Cable Gland | 2.072% | 0.1791% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161136 |  |  | FA-25161136 | Instrument Cable Gland | 100% | 0.1791% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Instrument Cable Gland |  | FA-25161137 |  |  | FA-25161137 | Handling | 10% | 0.01791% |  | 1168 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Instrument Cable Gland | 40520 | FA-25161138 |  |  | FA-25161138 | Gland Installation | 60% | 0.1075% |  | 1168 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Instrument Cable Gland | 40530 | FA-25161139 |  |  | FA-25161139 | Termination | 25% | 0.04479% |  | 1168 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Instrument Cable Gland |  | FA-25161140 |  |  | FA-25161140 | QC | 5% | 0.008957% |  | 1168 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161141 |  |  | FA-25161141 | Loop Test ( Hot) | 4.876% | 0.4217% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161142 |  |  | FA-25161142 | Loop Test ( Hot) | 100% | 0.4217% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Loop Test ( Hot) | 40540 | FA-25161143 |  |  | FA-25161143 | Loop Test | 100% | 0.4217% |  | 674 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161144 |  |  | FA-25161144 | Air Pipe and Tubing | 12.02% | 1.04% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161145 |  |  | FA-25161145 | Air Pipe and Tubing | 100% | 1.04% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Air Pipe and Tubing |  | FA-25161146 |  |  | FA-25161146 | Handling | 10% | 0.104% |  | 3337 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Air Pipe and Tubing | 40550 | FA-25161147 |  |  | FA-25161147 | Tubing and connections | 85% | 0.8836% |  | 3337 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Air Pipe and Tubing |  | FA-25161148 |  |  | FA-25161148 | QC | 5% | 0.05198% |  | 3337 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161149 |  |  | FA-25161149 | Grounding/ Earthing System | 1.682% | 0.1455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161150 |  |  | FA-25161150 | Earthing Cable Pulling | 100% | 0.1455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Earthing Cable Pulling |  | FA-25161151 |  |  | FA-25161151 | Handling | 10% | 0.01455% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Earthing Cable Pulling | 40585 | FA-25161152 |  |  | FA-25161152 | Cable laying | 75% | 0.1091% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Earthing Cable Pulling |  | FA-25161153 |  |  | FA-25161153 | Cable arrangements and fixing | 10% | 0.01455% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Instrument | Earthing Cable Pulling |  | FA-25161154 |  |  | FA-25161154 | QC | 5% | 0.007273% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Instrument |  |  | FA-25161155 |  |  | FA-25161155 | Unit - LPG/LPT | 18.65% | 7.922% |  |  |  |  | 0 | 1.19% | 1.169% | 2.359% |  | 0.09431% | 0 |  |  | 1.423% |  |  |  |  | 0.09431% |  | 1.423%
Plan |  |  |  |  | Plan Feb | 4 |  | Instrument |  |  | FA-25161156 |  |  | FA-25161156 | Cable Tray, ladder, Conduits | 16.02% | 1.269% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2814% | [6 empty] | 0.2814%
Plan |  |  |  |  | Plan Feb | 5 |  | Instrument |  |  | FA-25161157 |  |  | FA-25161157 | Installation of Primary Tray, ladder | 38.97% | 0.4946% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2814% | [6 empty] | 0.2814%
Plan | 0.00033107 | 1.108e-05% | 5.48e-09% |  | Plan Feb | 6 | Unit - LPG/LPT | Instrument | Installation of Primary Tray, ladder |  | FA-25161158 |  |  | FA-25161158 | Handling | 10% | 0.04946% |  | 2988 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2000 | 0.66934 | 0.03311% | Week 1 | Week 4 |  |  |  | 2000 | 0.03311% | ok | 0% | 0%
Plan | 0.002152 | 7.202e-05% | 2.315e-07% |  | Plan Feb | 6 | Unit - LPG/LPT | Instrument | Installation of Primary Tray, ladder | 40001 | FA-25161159 |  |  | FA-25161159 | Tray/ Ladder Assembling | 65% | 0.3215% |  | 2988 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2000 | 0.66934 | 0.2152% | Week 1 | Week 4 |  |  |  | 2000 | 0.2152% | ok | 0% | 0%
Plan | 0.00033107 | 1.108e-05% | 5.48e-09% |  | Plan Feb | 6 | Unit - LPG/LPT | Instrument | Installation of Primary Tray, ladder |  | FA-25161160 |  |  | FA-25161160 | Fixing & alignment | 10% | 0.04946% |  | 2988 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 2000 | 0.66934 | 0.03311% | Week 1 | Week 4 |  |  |  | 2000 | 0.03311% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of Primary Tray, ladder |  | FA-25161161 |  |  | FA-25161161 | Installation of covers | 10% | 0.04946% |  | 2988 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of Primary Tray, ladder |  | FA-25161162 |  |  | FA-25161162 | QC | 5% | 0.02473% |  | 2988 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161163 |  |  | FA-25161163 | Installation of Secondary Tray | 38.97% | 0.4946% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of Secondary Tray |  | FA-25161164 |  |  | FA-25161164 | Handling | 10% | 0.04946% |  |  |  | 140 | 140 | 0% | 0% | 0% |  |  | 140
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of Secondary Tray | 40001 | FA-25161165 |  |  | FA-25161165 | Tray/ Ladder Assembling | 65% | 0.3215% |  |  |  | 140 | 140 | 0% | 0% | 0% |  |  | 140
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of Secondary Tray |  | FA-25161166 |  |  | FA-25161166 | Fixing & alignment | 10% | 0.04946% |  |  |  | 140 | 140 | 0% | 0% | 0% |  |  | 140
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of Secondary Tray |  | FA-25161167 |  |  | FA-25161167 | Installation of covers | 10% | 0.04946% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of Secondary Tray |  | FA-25161168 |  |  | FA-25161168 | QC | 5% | 0.02473% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161169 |  |  | FA-25161169 | Installation of conduits | 22.06% | 0.28% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of conduits |  | FA-25161170 |  |  | FA-25161170 | Handling | 10% | 0.028% |  | 1173 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of conduits | 40010 | FA-25161171 |  |  | FA-25161171 | Installation of Conduit | 85% | 0.238% |  | 1173 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Installation of conduits |  | FA-25161172 |  |  | FA-25161172 | QC | 5% | 0.014% |  | 1173 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161173 |  |  | FA-25161173 | Supports | 2.381% | 0.1886% |  |  |  |  | 0 | 50% | 49.08% | 99.08% |  | 0.09431% | 0 | [7 empty] | 0.09431%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161174 |  |  | FA-25161174 | Supports | 100% | 0.1886% |  |  |  |  | 0 | 50% | 49.08% | 99.08% |  | 0.09431% | 0 | [7 empty] | 0.09431%
|  |  |  | Plan Jan |  | 6 | Unit - LPG/LPT | Instrument | Supports |  | FA-25161175 |  |  | FA-25161175 | Material Supply & Handling | 50% | 0.09431% |  | 1725 |  | 1725 | 1725 | 100% | 0% | 100% | 1725 | 0.09431% | 1725 | [6 empty] | 1725 | 0.09431%
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Supports | 40020 | FA-25161176 |  |  | FA-25161176 | Fabrication | 20% | 0.03773% |  | 1725 |  | 1881.478 | 1881.478 | 0% | 109.1% | 109.1% |  |  | 1881.478
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Supports | 40030 | FA-25161177 |  |  | FA-25161177 | Installation | 25% | 0.04716% |  | 1725 |  | 1881.478 | 1881.478 | 0% | 109.1% | 109.1% |  |  | 1881.478
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Supports |  | FA-25161178 |  |  | FA-25161178 | QC | 5% | 0.009431% |  | 1725 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161179 |  |  | FA-25161179 | Calibration ( Device & Valve ) | 2.778% | 0.2201% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161180 |  |  | FA-25161180 | Calibration ( Device & Valve ) | 100% | 0.2201% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Calibration ( Device & Valve ) |  | FA-25161181 |  |  | FA-25161181 | Handling | 10% | 0.02201% |  | 632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161182 |  |  | FA-25161182 | Calibration and restoring | 90% | 0.1981% |  | 632 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Instrument |  |  | FA-25161183 |  |  | FA-25161183 | Instrument Equipment | 28.32% | 2.244% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2746% | [6 empty] | 0.2746%
[6 empty] | 5 |  | Instrument |  |  | FA-25161184 |  |  | FA-25161184 | FIELD INSTRUMENTS | 72.74% | 1.632% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | FIELD INSTRUMENTS |  | FA-25161185 |  |  | FA-25161185 | Handling | 10% | 0.1632% |  | 460 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161186 |  |  | FA-25161186 | Installation | 85% | 1.387% |  | 460 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | FIELD INSTRUMENTS |  | FA-25161187 |  |  | FA-25161187 | QC | 5% | 0.08161% |  | 460 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161188 |  |  | FA-25161188 | F&G DETECTORS | 14.33% | 0.3216% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | F&G DETECTORS |  | FA-25161189 |  |  | FA-25161189 | Handling | 10% | 0.03216% |  | 131 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | F&G DETECTORS | 40060 | FA-25161190 |  |  | FA-25161190 | Installation | 85% | 0.2734% |  | 131 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | F&G DETECTORS |  | FA-25161191 |  |  | FA-25161191 | QC | 5% | 0.01608% |  | 131 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 5 |  | Instrument |  |  | FA-25161192 |  |  | FA-25161192 | Junction Box | 12.88% | 0.2891% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2746% | [6 empty] | 0.2746%
Plan | 0.00028906 | 0.0003361% | 9.716e-08% |  | Plan Feb | 6 | Unit - LPG/LPT | Instrument | Junction Box |  | FA-25161193 |  |  | FA-25161193 | Handling | 10% | 0.02891% |  | 86 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 86 | 1 | 0.02891% | Week 4 | Week 4 |  |  |  | 86 | 0.02891% | ok | 0% | 0%
Plan | 0.002457 | 0.002857% | 7.019e-06% |  | Plan Feb | 6 | Unit - LPG/LPT | Instrument | Junction Box | 40075 | FA-25161194 |  |  | FA-25161194 | Installation | 85% | 0.2457% |  | 86 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 86 | 1 | 0.2457% | Week 4 | Week 4 |  |  |  | 86 | 0.2457% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Junction Box |  | FA-25161195 |  |  | FA-25161195 | QC | 5% | 0.01445% |  | 86 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161196 |  |  | FA-25161196 | Analyzer | 0.04322% | 0.0009697% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Analyzer |  | FA-25161197 |  |  | FA-25161197 | Handling | 10% | 9.697e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Analyzer |  | FA-25161198 |  |  | FA-25161198 | Installation | 85% | 0.0008242% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Analyzer |  | FA-25161199 |  |  | FA-25161199 | QC | 5% | 4.848e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Instrument |  |  | FA-25161200 |  |  | FA-25161200 | Instrument Cabling | 31.43% | 2.49% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.8672% | [6 empty] | 0.8672%
Plan |  |  |  |  | Plan Feb | 5 |  | Instrument |  |  | FA-25161201 |  |  | FA-25161201 | Main Cabling | 100% | 2.49% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.8672% | [6 empty] | 0.8672%
Plan | 0.001084 | 2.483e-06% | 6.185e-09% |  | Plan Feb | 6 | Unit - LPG/LPT | Instrument | Main Cabling |  | FA-25161202 |  |  | FA-25161202 | Handling | 10% | 0.249% |  | 43650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 19000 | 0.43528 | 0.1084% | Week 3 | Week 4 |  |  |  | 19000 | 0.1084% | ok | 0% | 0%
Plan | 0.007588 | 1.738e-05% | 3.03e-07% |  | Plan Feb | 6 | Unit - LPG/LPT | Instrument | Main Cabling | 40090 | FA-25161203 |  |  | FA-25161203 | Cable laying | 70% | 1.743% |  | 43650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 19000 | 0.43528 | 0.7588% | Week 3 | Week 4 | موط به آمادگی ترچ ها |  |  | 19000 | 0.7588% | ok | 0% | 0%
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Main Cabling |  | FA-25161204 |  |  | FA-25161204 | Cable arrangements and fixing | 5% | 0.1245% |  | 43650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Main Cabling |  | FA-25161205 |  |  | FA-25161205 | Cable Marking | 5% | 0.1245% |  | 43650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Main Cabling |  | FA-25161206 |  |  | FA-25161206 | Continuity & Megger Test | 5% | 0.1245% |  | 43650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Main Cabling |  | FA-25161207 |  |  | FA-25161207 | QC | 5% | 0.1245% |  | 43650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161208 |  |  | FA-25161208 | Secondary Cabling | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Secondary Cabling |  | FA-25161209 |  |  | FA-25161209 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Secondary Cabling | 40500 | FA-25161210 |  |  | FA-25161210 | Cable laying | 70% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Secondary Cabling |  | FA-25161211 |  |  | FA-25161211 | Cable arrangements and fixing | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Secondary Cabling |  | FA-25161212 |  |  | FA-25161212 | Cable Marking | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Secondary Cabling |  | FA-25161213 |  |  | FA-25161213 | Continuity & Megger Test | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Secondary Cabling |  | FA-25161214 |  |  | FA-25161214 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161215 |  |  | FA-25161215 | Instrument Cable Gland | 1.959% | 0.1552% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161216 |  |  | FA-25161216 | Instrument Cable Gland | 100% | 0.1552% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Instrument Cable Gland |  | FA-25161217 |  |  | FA-25161217 | Handling | 10% | 0.01552% |  | 1012 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Instrument Cable Gland | 40520 | FA-25161218 |  |  | FA-25161218 | Gland Installation | 60% | 0.09313% |  | 1012 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Instrument Cable Gland | 40530 | FA-25161219 |  |  | FA-25161219 | Termination | 25% | 0.0388% |  | 1012 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Instrument Cable Gland |  | FA-25161220 |  |  | FA-25161220 | QC | 5% | 0.007761% |  | 1012 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161221 |  |  | FA-25161221 | Loop Test ( Hot) | 3.988% | 0.3159% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161222 |  |  | FA-25161222 | Loop Test ( Hot) | 100% | 0.3159% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Loop Test ( Hot) | 40540 | FA-25161223 |  |  | FA-25161223 | Loop Test | 100% | 0.3159% |  | 505 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161224 |  |  | FA-25161224 | Air Pipe and Tubing | 11.51% | 0.9118% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161225 |  |  | FA-25161225 | Air Pipe and Tubing | 100% | 0.9118% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Air Pipe and Tubing |  | FA-25161226 |  |  | FA-25161226 | Handling | 10% | 0.09118% |  | 2927 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Air Pipe and Tubing | 40550 | FA-25161227 |  |  | FA-25161227 | Tubing and connections | 85% | 0.7751% |  | 2927 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Air Pipe and Tubing |  | FA-25161228 |  |  | FA-25161228 | QC | 5% | 0.04559% |  | 2927 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161229 |  |  | FA-25161229 | Grounding/ Earthing System | 1.607% | 0.1273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161230 |  |  | FA-25161230 | Earthing Cable Pulling | 100% | 0.1273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Earthing Cable Pulling |  | FA-25161231 |  |  | FA-25161231 | Handling | 10% | 0.01273% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Earthing Cable Pulling | 40585 | FA-25161232 |  |  | FA-25161232 | Cable laying | 75% | 0.09546% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Earthing Cable Pulling |  | FA-25161233 |  |  | FA-25161233 | Cable arrangements and fixing | 10% | 0.01273% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Instrument | Earthing Cable Pulling |  | FA-25161234 |  |  | FA-25161234 | QC | 5% | 0.006364% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Instrument |  |  | FA-25161235 |  |  | FA-25161235 | Unit - UTILITY | 10.32% | 4.385% |  |  |  |  | 0 | 2.868% | 0% | 2.868% |  | 0.1258% | 0 | [7 empty] | 0.1258%
[6 empty] | 4 |  | Instrument |  |  | FA-25161236 |  |  | FA-25161236 | Cable Tray, ladder, Conduits | 9.626% | 0.4221% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161237 |  |  | FA-25161237 | Installation of Primary Tray, ladder | 41.89% | 0.1768% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Primary Tray, ladder |  | FA-25161238 |  |  | FA-25161238 | Handling | 10% | 0.01768% |  | 1068 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Primary Tray, ladder | 40001 | FA-25161239 |  |  | FA-25161239 | Tray/ Ladder Assembling | 65% | 0.1149% |  | 1068 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Primary Tray, ladder |  | FA-25161240 |  |  | FA-25161240 | Fixing & alignment | 10% | 0.01768% |  | 1068 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Primary Tray, ladder |  | FA-25161241 |  |  | FA-25161241 | Installation of covers | 10% | 0.01768% |  | 1068 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Primary Tray, ladder |  | FA-25161242 |  |  | FA-25161242 | QC | 5% | 0.00884% |  | 1068 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161243 |  |  | FA-25161243 | Installation of Secondary Tray | 41.89% | 0.1768% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Secondary Tray |  | FA-25161244 |  |  | FA-25161244 | Handling | 10% | 0.01768% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Secondary Tray | 40001 | FA-25161245 |  |  | FA-25161245 | Tray/ Ladder Assembling | 65% | 0.1149% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Secondary Tray |  | FA-25161246 |  |  | FA-25161246 | Fixing & alignment | 10% | 0.01768% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Secondary Tray |  | FA-25161247 |  |  | FA-25161247 | Installation of covers | 10% | 0.01768% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of Secondary Tray |  | FA-25161248 |  |  | FA-25161248 | QC | 5% | 0.00884% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161249 |  |  | FA-25161249 | Installation of conduits | 16.23% | 0.0685% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of conduits |  | FA-25161250 |  |  | FA-25161250 | Handling | 10% | 0.00685% |  | 287 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of conduits | 40010 | FA-25161251 |  |  | FA-25161251 | Installation of Conduit | 85% | 0.05823% |  | 287 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Installation of conduits |  | FA-25161252 |  |  | FA-25161252 | QC | 5% | 0.003425% |  | 287 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161253 |  |  | FA-25161253 | Supports | 5.736% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 | [7 empty] | 0.1258%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161254 |  |  | FA-25161254 | Supports | 100% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 | [7 empty] | 0.1258%
|  |  |  | Plan Jan |  | 6 | Unit - UTILITY | Instrument | Supports |  | FA-25161255 |  |  | FA-25161255 | Material Supply & Handling | 50% | 0.1258% |  | 2300 |  | 2300 | 2300 | 100% | 0% | 100% | 2300 | 0.1258% | 2300 | [6 empty] | 2300 | 0.1258%
[6 empty] | 6 | Unit - UTILITY | Instrument | Supports | 40020 | FA-25161256 |  |  | FA-25161256 | Fabrication | 20% | 0.0503% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Supports | 40030 | FA-25161257 |  |  | FA-25161257 | Installation | 25% | 0.06288% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Supports |  | FA-25161258 |  |  | FA-25161258 | QC | 5% | 0.01258% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161259 |  |  | FA-25161259 | Calibration ( Device & Valve ) | 5.539% | 0.2429% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161260 |  |  | FA-25161260 | Calibration ( Device & Valve ) | 100% | 0.2429% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Calibration ( Device & Valve ) |  | FA-25161261 |  |  | FA-25161261 | Handling | 10% | 0.02429% |  | 308 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161262 |  |  | FA-25161262 | Calibration and restoring | 90% | 0.2186% |  | 308 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161263 |  |  | FA-25161263 | Instrument Equipment | 15.31% | 0.6713% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161264 |  |  | FA-25161264 | FIELD INSTRUMENTS | 66.21% | 0.4445% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | FIELD INSTRUMENTS |  | FA-25161265 |  |  | FA-25161265 | Handling | 10% | 0.04445% |  | 29 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161266 |  |  | FA-25161266 | Installation | 85% | 0.3778% |  | 29 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | FIELD INSTRUMENTS |  | FA-25161267 |  |  | FA-25161267 | QC | 5% | 0.02222% |  | 29 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161268 |  |  | FA-25161268 | F&G DETECTORS | 8.711% | 0.05848% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | F&G DETECTORS |  | FA-25161269 |  |  | FA-25161269 | Handling | 10% | 0.005848% |  | 22 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | F&G DETECTORS | 40060 | FA-25161270 |  |  | FA-25161270 | Installation | 85% | 0.04971% |  | 22 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | F&G DETECTORS |  | FA-25161271 |  |  | FA-25161271 | QC | 5% | 0.002924% |  | 22 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161272 |  |  | FA-25161272 | Junction Box | 25.03% | 0.1681% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Junction Box |  | FA-25161273 |  |  | FA-25161273 | Handling | 10% | 0.01681% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Junction Box | 40075 | FA-25161274 |  |  | FA-25161274 | Installation | 85% | 0.1428% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Junction Box |  | FA-25161275 |  |  | FA-25161275 | QC | 5% | 0.008403% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161276 |  |  | FA-25161276 | Analyzer | 0.04322% | 0.0002901% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Analyzer |  | FA-25161277 |  |  | FA-25161277 | Handling | 10% | 2.901e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Analyzer |  | FA-25161278 |  |  | FA-25161278 | Installation | 85% | 0.0002466% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Analyzer |  | FA-25161279 |  |  | FA-25161279 | QC | 5% | 1.451e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161280 |  |  | FA-25161280 | Instrument Cabling | 45.09% | 1.977% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161281 |  |  | FA-25161281 | Main Cabling | 100% | 1.977% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Main Cabling |  | FA-25161282 |  |  | FA-25161282 | Handling | 10% | 0.1977% |  | 34650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Main Cabling | 40090 | FA-25161283 |  |  | FA-25161283 | Cable laying | 70% | 1.384% |  | 34650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Main Cabling |  | FA-25161284 |  |  | FA-25161284 | Cable arrangements and fixing | 5% | 0.09884% |  | 34650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Main Cabling |  | FA-25161285 |  |  | FA-25161285 | Cable Marking | 5% | 0.09884% |  | 34650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Main Cabling |  | FA-25161286 |  |  | FA-25161286 | Continuity & Megger Test | 5% | 0.09884% |  | 34650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Main Cabling |  | FA-25161287 |  |  | FA-25161287 | QC | 5% | 0.09884% |  | 34650 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161288 |  |  | FA-25161288 | Secondary Cabling | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Secondary Cabling |  | FA-25161289 |  |  | FA-25161289 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Secondary Cabling | 40500 | FA-25161290 |  |  | FA-25161290 | Cable laying | 70% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Secondary Cabling |  | FA-25161291 |  |  | FA-25161291 | Cable arrangements and fixing | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Secondary Cabling |  | FA-25161292 |  |  | FA-25161292 | Cable Marking | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Secondary Cabling |  | FA-25161293 |  |  | FA-25161293 | Continuity & Megger Test | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Secondary Cabling |  | FA-25161294 |  |  | FA-25161294 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161295 |  |  | FA-25161295 | Instrument Cable Gland | 2.816% | 0.1235% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161296 |  |  | FA-25161296 | Instrument Cable Gland | 100% | 0.1235% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Instrument Cable Gland |  | FA-25161297 |  |  | FA-25161297 | Handling | 10% | 0.01235% |  | 805 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Instrument Cable Gland | 40520 | FA-25161298 |  |  | FA-25161298 | Gland Installation | 60% | 0.07408% |  | 805 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Instrument Cable Gland | 40530 | FA-25161299 |  |  | FA-25161299 | Termination | 25% | 0.03087% |  | 805 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Instrument Cable Gland |  | FA-25161300 |  |  | FA-25161300 | QC | 5% | 0.006173% |  | 805 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161301 |  |  | FA-25161301 | Loop Test ( Hot) | 4.352% | 0.1908% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161302 |  |  | FA-25161302 | Loop Test ( Hot) | 100% | 0.1908% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Loop Test ( Hot) | 40540 | FA-25161303 |  |  | FA-25161303 | Loop Test | 100% | 0.1908% |  | 305 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161304 |  |  | FA-25161304 | Air Pipe and Tubing | 8.632% | 0.3785% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161305 |  |  | FA-25161305 | Air Pipe and Tubing | 100% | 0.3785% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Air Pipe and Tubing |  | FA-25161306 |  |  | FA-25161306 | Handling | 10% | 0.03785% |  | 1215 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Air Pipe and Tubing | 40550 | FA-25161307 |  |  | FA-25161307 | Tubing and connections | 85% | 0.3217% |  | 1215 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Air Pipe and Tubing |  | FA-25161308 |  |  | FA-25161308 | QC | 5% | 0.01893% |  | 1215 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161309 |  |  | FA-25161309 | Grounding/ Earthing System | 2.903% | 0.1273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161310 |  |  | FA-25161310 | Earthing Cable Pulling | 100% | 0.1273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Earthing Cable Pulling |  | FA-25161311 |  |  | FA-25161311 | Handling | 10% | 0.01273% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Earthing Cable Pulling | 40585 | FA-25161312 |  |  | FA-25161312 | Cable laying | 75% | 0.09546% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Earthing Cable Pulling |  | FA-25161313 |  |  | FA-25161313 | Cable arrangements and fixing | 10% | 0.01273% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Instrument | Earthing Cable Pulling |  | FA-25161314 |  |  | FA-25161314 | QC | 5% | 0.006364% |  | 350 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan | Plan Feb | 3 |  | Instrument |  |  | FA-25161315 |  |  | FA-25161315 | Unit - FWS | 2.645% | 1.124% |  |  |  |  | 0 | 2.798% | 0% | 2.798% |  | 0.03144% | 0 |  |  | 0.007035% |  |  |  |  | 0.03144%
[5 empty] | Plan Feb | 4 |  | Instrument |  |  | FA-25161316 |  |  | FA-25161316 | Cable Tray, ladder, Conduits | 12.79% | 0.1437% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.007035%
[5 empty] | Plan Feb | 5 |  | Instrument |  |  | FA-25161317 |  |  | FA-25161317 | Installation of Primary Tray, ladder | 41.12% | 0.0591% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.007035%
[5 empty] | Plan Feb | 6 | Unit - FWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161318 |  |  | FA-25161318 | Handling | 10% | 0.00591% |  | 357 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 50 | 0.14006 | 0.0008277% | Week 1 | Week 4
[5 empty] | Plan Feb | 6 | Unit - FWS | Instrument | Installation of Primary Tray, ladder | 40001 | FA-25161319 |  |  | FA-25161319 | Tray/ Ladder Assembling | 65% | 0.03841% |  | 357 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 50 | 0.14006 | 0.00538% | Week 1 | Week 4
[5 empty] | Plan Feb | 6 | Unit - FWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161320 |  |  | FA-25161320 | Fixing & alignment | 10% | 0.00591% |  | 357 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 50 | 0.14006 | 0.0008277% | Week 1 | Week 4
[6 empty] | 6 | Unit - FWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161321 |  |  | FA-25161321 | Installation of covers | 10% | 0.00591% |  | 357 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161322 |  |  | FA-25161322 | QC | 5% | 0.002955% |  | 357 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161323 |  |  | FA-25161323 | Installation of Secondary Tray | 41.12% | 0.0591% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of Secondary Tray |  | FA-25161324 |  |  | FA-25161324 | Handling | 10% | 0.00591% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of Secondary Tray | 40001 | FA-25161325 |  |  | FA-25161325 | Tray/ Ladder Assembling | 65% | 0.03841% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of Secondary Tray |  | FA-25161326 |  |  | FA-25161326 | Fixing & alignment | 10% | 0.00591% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of Secondary Tray |  | FA-25161327 |  |  | FA-25161327 | Installation of covers | 10% | 0.00591% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of Secondary Tray |  | FA-25161328 |  |  | FA-25161328 | QC | 5% | 0.002955% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161329 |  |  | FA-25161329 | Installation of conduits | 17.77% | 0.02554% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of conduits |  | FA-25161330 |  |  | FA-25161330 | Handling | 10% | 0.002554% |  | 107 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of conduits | 40010 | FA-25161331 |  |  | FA-25161331 | Installation of Conduit | 85% | 0.02171% |  | 107 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Installation of conduits |  | FA-25161332 |  |  | FA-25161332 | QC | 5% | 0.001277% |  | 107 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161333 |  |  | FA-25161333 | Supports | 5.595% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161334 |  |  | FA-25161334 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - FWS | Instrument | Supports |  | FA-25161335 |  |  | FA-25161335 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% | 575 | 0.03144% | 575 | [6 empty] | 575 | 0.03144%
[6 empty] | 6 | Unit - FWS | Instrument | Supports | 40020 | FA-25161336 |  |  | FA-25161336 | Fabrication | 20% | 0.01258% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Supports | 40030 | FA-25161337 |  |  | FA-25161337 | Installation | 25% | 0.01572% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Supports |  | FA-25161338 |  |  | FA-25161338 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161339 |  |  | FA-25161339 | Calibration ( Device & Valve ) | 7.88% | 0.08855% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161340 |  |  | FA-25161340 | Calibration ( Device & Valve ) | 100% | 0.08855% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Calibration ( Device & Valve ) |  | FA-25161341 |  |  | FA-25161341 | Handling | 10% | 0.008855% |  | 9 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161342 |  |  | FA-25161342 | Calibration and restoring | 90% | 0.0797% |  | 9 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161343 |  |  | FA-25161343 | Instrument Equipment | 7.934% | 0.08915% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161344 |  |  | FA-25161344 | FIELD INSTRUMENTS | 30.42% | 0.02712% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | FIELD INSTRUMENTS |  | FA-25161345 |  |  | FA-25161345 | Handling | 10% | 0.002712% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161346 |  |  | FA-25161346 | Installation | 85% | 0.02306% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | FIELD INSTRUMENTS |  | FA-25161347 |  |  | FA-25161347 | QC | 5% | 0.001356% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161348 |  |  | FA-25161348 | F&G DETECTORS | 50.68% | 0.04519% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | F&G DETECTORS |  | FA-25161349 |  |  | FA-25161349 | Handling | 10% | 0.004519% |  | 17 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | F&G DETECTORS | 40060 | FA-25161350 |  |  | FA-25161350 | Installation | 85% | 0.03841% |  | 17 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | F&G DETECTORS |  | FA-25161351 |  |  | FA-25161351 | QC | 5% | 0.002259% |  | 17 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161352 |  |  | FA-25161352 | Junction Box | 18.85% | 0.01681% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Junction Box |  | FA-25161353 |  |  | FA-25161353 | Handling | 10% | 0.001681% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Junction Box | 40075 | FA-25161354 |  |  | FA-25161354 | Installation | 85% | 0.01428% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Junction Box |  | FA-25161355 |  |  | FA-25161355 | QC | 5% | 0.0008403% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161356 |  |  | FA-25161356 | Analyzer | 0.04322% | 3.853e-05% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Analyzer |  | FA-25161357 |  |  | FA-25161357 | Handling | 10% | 3.853e-06% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Analyzer |  | FA-25161358 |  |  | FA-25161358 | Installation | 85% | 3.275e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Analyzer |  | FA-25161359 |  |  | FA-25161359 | QC | 5% | 1.926e-06% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161360 |  |  | FA-25161360 | Instrument Cabling | 53.95% | 0.6062% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161361 |  |  | FA-25161361 | Main Cabling | 100% | 0.6062% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Main Cabling |  | FA-25161362 |  |  | FA-25161362 | Handling | 10% | 0.06062% |  | 10626 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Main Cabling | 40090 | FA-25161363 |  |  | FA-25161363 | Cable laying | 70% | 0.4244% |  | 10626 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Main Cabling |  | FA-25161364 |  |  | FA-25161364 | Cable arrangements and fixing | 5% | 0.03031% |  | 10626 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Main Cabling |  | FA-25161365 |  |  | FA-25161365 | Cable Marking | 5% | 0.03031% |  | 10626 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Main Cabling |  | FA-25161366 |  |  | FA-25161366 | Continuity & Megger Test | 5% | 0.03031% |  | 10626 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Main Cabling |  | FA-25161367 |  |  | FA-25161367 | QC | 5% | 0.03031% |  | 10626 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161368 |  |  | FA-25161368 | Secondary Cabling | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Secondary Cabling |  | FA-25161369 |  |  | FA-25161369 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Secondary Cabling | 40500 | FA-25161370 |  |  | FA-25161370 | Cable laying | 70% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Secondary Cabling |  | FA-25161371 |  |  | FA-25161371 | Cable arrangements and fixing | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Secondary Cabling |  | FA-25161372 |  |  | FA-25161372 | Cable Marking | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Secondary Cabling |  | FA-25161373 |  |  | FA-25161373 | Continuity & Megger Test | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Secondary Cabling |  | FA-25161374 |  |  | FA-25161374 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161375 |  |  | FA-25161375 | Instrument Cable Gland | 3.385% | 0.03804% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161376 |  |  | FA-25161376 | Instrument Cable Gland | 100% | 0.03804% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Instrument Cable Gland |  | FA-25161377 |  |  | FA-25161377 | Handling | 10% | 0.003804% |  | 248 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Instrument Cable Gland | 40520 | FA-25161378 |  |  | FA-25161378 | Gland Installation | 60% | 0.02282% |  | 248 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Instrument Cable Gland | 40530 | FA-25161379 |  |  | FA-25161379 | Termination | 25% | 0.009509% |  | 248 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Instrument Cable Gland |  | FA-25161380 |  |  | FA-25161380 | QC | 5% | 0.001902% |  | 248 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161381 |  |  | FA-25161381 | Loop Test ( Hot) | 1.614% | 0.01814% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161382 |  |  | FA-25161382 | Loop Test ( Hot) | 100% | 0.01814% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Loop Test ( Hot) | 40540 | FA-25161383 |  |  | FA-25161383 | Loop Test | 100% | 0.01814% |  | 29 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161384 |  |  | FA-25161384 | Air Pipe and Tubing | 1.996% | 0.02243% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161385 |  |  | FA-25161385 | Air Pipe and Tubing | 100% | 0.02243% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Air Pipe and Tubing |  | FA-25161386 |  |  | FA-25161386 | Handling | 10% | 0.002243% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Air Pipe and Tubing | 40550 | FA-25161387 |  |  | FA-25161387 | Tubing and connections | 85% | 0.01907% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Air Pipe and Tubing |  | FA-25161388 |  |  | FA-25161388 | QC | 5% | 0.001122% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161389 |  |  | FA-25161389 | Grounding/ Earthing System | 4.854% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161390 |  |  | FA-25161390 | Earthing Cable Pulling | 100% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Earthing Cable Pulling |  | FA-25161391 |  |  | FA-25161391 | Handling | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Earthing Cable Pulling | 40585 | FA-25161392 |  |  | FA-25161392 | Cable laying | 75% | 0.04091% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Earthing Cable Pulling |  | FA-25161393 |  |  | FA-25161393 | Cable arrangements and fixing | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Instrument | Earthing Cable Pulling |  | FA-25161394 |  |  | FA-25161394 | QC | 5% | 0.002727% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Instrument |  |  | FA-25161395 |  |  | FA-25161395 | Unit - SWS | 5.598% | 2.378% |  |  |  |  | 0 | 1.322% | 0% | 1.322% |  | 0.03144% | 0 | [7 empty] | 0.03144%
[6 empty] | 4 |  | Instrument |  |  | FA-25161396 |  |  | FA-25161396 | Cable Tray, ladder, Conduits | 7.052% | 0.1677% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161397 |  |  | FA-25161397 | Installation of Primary Tray, ladder | 43.24% | 0.0725% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161398 |  |  | FA-25161398 | Handling | 10% | 0.00725% |  | 438 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Primary Tray, ladder | 40001 | FA-25161399 |  |  | FA-25161399 | Tray/ Ladder Assembling | 65% | 0.04713% |  | 438 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161400 |  |  | FA-25161400 | Fixing & alignment | 10% | 0.00725% |  | 438 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161401 |  |  | FA-25161401 | Installation of covers | 10% | 0.00725% |  | 438 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Primary Tray, ladder |  | FA-25161402 |  |  | FA-25161402 | QC | 5% | 0.003625% |  | 438 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161403 |  |  | FA-25161403 | Installation of Secondary Tray | 43.24% | 0.0725% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Secondary Tray |  | FA-25161404 |  |  | FA-25161404 | Handling | 10% | 0.00725% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Secondary Tray | 40001 | FA-25161405 |  |  | FA-25161405 | Tray/ Ladder Assembling | 65% | 0.04713% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Secondary Tray |  | FA-25161406 |  |  | FA-25161406 | Fixing & alignment | 10% | 0.00725% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Secondary Tray |  | FA-25161407 |  |  | FA-25161407 | Installation of covers | 10% | 0.00725% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of Secondary Tray |  | FA-25161408 |  |  | FA-25161408 | QC | 5% | 0.003625% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161409 |  |  | FA-25161409 | Installation of conduits | 13.52% | 0.02268% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of conduits |  | FA-25161410 |  |  | FA-25161410 | Handling | 10% | 0.002268% |  | 95 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of conduits | 40010 | FA-25161411 |  |  | FA-25161411 | Installation of Conduit | 85% | 0.01927% |  | 95 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Installation of conduits |  | FA-25161412 |  |  | FA-25161412 | QC | 5% | 0.001134% |  | 95 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161413 |  |  | FA-25161413 | Supports | 2.644% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161414 |  |  | FA-25161414 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - SWS | Instrument | Supports |  | FA-25161415 |  |  | FA-25161415 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% | 575 | 0.03144% | 575 | [6 empty] | 575 | 0.03144%
[6 empty] | 6 | Unit - SWS | Instrument | Supports | 40020 | FA-25161416 |  |  | FA-25161416 | Fabrication | 20% | 0.01258% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Supports | 40030 | FA-25161417 |  |  | FA-25161417 | Installation | 25% | 0.01572% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Supports |  | FA-25161418 |  |  | FA-25161418 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161419 |  |  | FA-25161419 | Calibration ( Device & Valve ) | 4.683% | 0.1113% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161420 |  |  | FA-25161420 | Calibration ( Device & Valve ) | 100% | 0.1113% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Calibration ( Device & Valve ) |  | FA-25161421 |  |  | FA-25161421 | Handling | 10% | 0.01113% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161422 |  |  | FA-25161422 | Calibration and restoring | 90% | 0.1002% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161423 |  |  | FA-25161423 | Instrument Equipment | 12.96% | 0.3082% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161424 |  |  | FA-25161424 | FIELD INSTRUMENTS | 58.35% | 0.1798% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | FIELD INSTRUMENTS |  | FA-25161425 |  |  | FA-25161425 | Handling | 10% | 0.01798% |  | 125 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161426 |  |  | FA-25161426 | Installation | 85% | 0.1528% |  | 125 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | FIELD INSTRUMENTS |  | FA-25161427 |  |  | FA-25161427 | QC | 5% | 0.008991% |  | 125 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161428 |  |  | FA-25161428 | F&G DETECTORS | 24.15% | 0.07443% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | F&G DETECTORS |  | FA-25161429 |  |  | FA-25161429 | Handling | 10% | 0.007443% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | F&G DETECTORS | 40060 | FA-25161430 |  |  | FA-25161430 | Installation | 85% | 0.06326% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | F&G DETECTORS |  | FA-25161431 |  |  | FA-25161431 | QC | 5% | 0.003721% |  | 28 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161432 |  |  | FA-25161432 | Junction Box | 17.45% | 0.05378% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Junction Box |  | FA-25161433 |  |  | FA-25161433 | Handling | 10% | 0.005378% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Junction Box | 40075 | FA-25161434 |  |  | FA-25161434 | Installation | 85% | 0.04571% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Junction Box |  | FA-25161435 |  |  | FA-25161435 | QC | 5% | 0.002689% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161436 |  |  | FA-25161436 | Analyzer | 0.04322% | 0.0001332% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Analyzer |  | FA-25161437 |  |  | FA-25161437 | Handling | 10% | 1.332e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Analyzer |  | FA-25161438 |  |  | FA-25161438 | Installation | 85% | 0.0001132% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Analyzer |  | FA-25161439 |  |  | FA-25161439 | QC | 5% | 6.659e-06% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161440 |  |  | FA-25161440 | Instrument Cabling | 59.62% | 1.418% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161441 |  |  | FA-25161441 | Main Cabling | 100% | 1.418% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Main Cabling |  | FA-25161442 |  |  | FA-25161442 | Handling | 10% | 0.1418% |  | 24850 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Main Cabling | 40090 | FA-25161443 |  |  | FA-25161443 | Cable laying | 70% | 0.9924% |  | 24850 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Main Cabling |  | FA-25161444 |  |  | FA-25161444 | Cable arrangements and fixing | 5% | 0.07089% |  | 24850 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Main Cabling |  | FA-25161445 |  |  | FA-25161445 | Cable Marking | 5% | 0.07089% |  | 24850 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Main Cabling |  | FA-25161446 |  |  | FA-25161446 | Continuity & Megger Test | 5% | 0.07089% |  | 24850 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Main Cabling |  | FA-25161447 |  |  | FA-25161447 | QC | 5% | 0.07089% |  | 24850 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161448 |  |  | FA-25161448 | Secondary Cabling | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Secondary Cabling |  | FA-25161449 |  |  | FA-25161449 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Secondary Cabling | 40500 | FA-25161450 |  |  | FA-25161450 | Cable laying | 70% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Secondary Cabling |  | FA-25161451 |  |  | FA-25161451 | Cable arrangements and fixing | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Secondary Cabling |  | FA-25161452 |  |  | FA-25161452 | Cable Marking | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Secondary Cabling |  | FA-25161453 |  |  | FA-25161453 | Continuity & Megger Test | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Secondary Cabling |  | FA-25161454 |  |  | FA-25161454 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161455 |  |  | FA-25161455 | Instrument Cable Gland | 3.709% | 0.08819% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161456 |  |  | FA-25161456 | Instrument Cable Gland | 100% | 0.08819% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Instrument Cable Gland |  | FA-25161457 |  |  | FA-25161457 | Handling | 10% | 0.008819% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Instrument Cable Gland | 40520 | FA-25161458 |  |  | FA-25161458 | Gland Installation | 60% | 0.05291% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Instrument Cable Gland | 40530 | FA-25161459 |  |  | FA-25161459 | Termination | 25% | 0.02205% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Instrument Cable Gland |  | FA-25161460 |  |  | FA-25161460 | QC | 5% | 0.00441% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161461 |  |  | FA-25161461 | Loop Test ( Hot) | 3.131% | 0.07445% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161462 |  |  | FA-25161462 | Loop Test ( Hot) | 100% | 0.07445% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Loop Test ( Hot) | 40540 | FA-25161463 |  |  | FA-25161463 | Loop Test | 100% | 0.07445% |  | 119 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161464 |  |  | FA-25161464 | Air Pipe and Tubing | 3.904% | 0.09284% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161465 |  |  | FA-25161465 | Air Pipe and Tubing | 100% | 0.09284% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Air Pipe and Tubing |  | FA-25161466 |  |  | FA-25161466 | Handling | 10% | 0.009284% |  | 298 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Air Pipe and Tubing | 40550 | FA-25161467 |  |  | FA-25161467 | Tubing and connections | 85% | 0.07891% |  | 298 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Air Pipe and Tubing |  | FA-25161468 |  |  | FA-25161468 | QC | 5% | 0.004642% |  | 298 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161469 |  |  | FA-25161469 | Grounding/ Earthing System | 2.294% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161470 |  |  | FA-25161470 | Earthing Cable Pulling | 100% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Earthing Cable Pulling |  | FA-25161471 |  |  | FA-25161471 | Handling | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Earthing Cable Pulling | 40585 | FA-25161472 |  |  | FA-25161472 | Cable laying | 75% | 0.04091% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Earthing Cable Pulling |  | FA-25161473 |  |  | FA-25161473 | Cable arrangements and fixing | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Instrument | Earthing Cable Pulling |  | FA-25161474 |  |  | FA-25161474 | QC | 5% | 0.002727% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Instrument |  |  | FA-25161475 |  |  | FA-25161475 | Unit - FLS | 1.88% | 0.7987% |  |  |  |  | 0 | 3.936% | 0% | 3.936% |  | 0.03144% | 0 | [7 empty] | 0.03144%
[6 empty] | 4 |  | Instrument |  |  | FA-25161476 |  |  | FA-25161476 | Cable Tray, ladder, Conduits | 19% | 0.1518% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161477 |  |  | FA-25161477 | Installation of Primary Tray, ladder | 34.9% | 0.05297% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Primary Tray, ladder |  | FA-25161478 |  |  | FA-25161478 | Handling | 10% | 0.005297% |  | 120 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Primary Tray, ladder | 40001 | FA-25161479 |  |  | FA-25161479 | Tray/ Ladder Assembling | 65% | 0.03443% |  | 120 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Primary Tray, ladder |  | FA-25161480 |  |  | FA-25161480 | Fixing & alignment | 10% | 0.005297% |  | 120 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Primary Tray, ladder |  | FA-25161481 |  |  | FA-25161481 | Installation of covers | 10% | 0.005297% |  | 120 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Primary Tray, ladder |  | FA-25161482 |  |  | FA-25161482 | QC | 5% | 0.002649% |  | 120 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161483 |  |  | FA-25161483 | Installation of Secondary Tray | 34.9% | 0.05297% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Secondary Tray |  | FA-25161484 |  |  | FA-25161484 | Handling | 10% | 0.005297% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Secondary Tray | 40001 | FA-25161485 |  |  | FA-25161485 | Tray/ Ladder Assembling | 65% | 0.03443% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Secondary Tray |  | FA-25161486 |  |  | FA-25161486 | Fixing & alignment | 10% | 0.005297% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Secondary Tray |  | FA-25161487 |  |  | FA-25161487 | Installation of covers | 10% | 0.005297% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of Secondary Tray |  | FA-25161488 |  |  | FA-25161488 | QC | 5% | 0.002649% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161489 |  |  | FA-25161489 | Installation of conduits | 30.2% | 0.04583% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of conduits |  | FA-25161490 |  |  | FA-25161490 | Handling | 10% | 0.004583% |  | 192 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of conduits | 40010 | FA-25161491 |  |  | FA-25161491 | Installation of Conduit | 85% | 0.03895% |  | 192 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Installation of conduits |  | FA-25161492 |  |  | FA-25161492 | QC | 5% | 0.002291% |  | 192 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161493 |  |  | FA-25161493 | Supports | 7.872% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161494 |  |  | FA-25161494 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - FLS | Instrument | Supports |  | FA-25161495 |  |  | FA-25161495 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% | 575 | 0.03144% | 575 | [6 empty] | 575 | 0.03144%
[6 empty] | 6 | Unit - FLS | Instrument | Supports | 40020 | FA-25161496 |  |  | FA-25161496 | Fabrication | 20% | 0.01258% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Supports | 40030 | FA-25161497 |  |  | FA-25161497 | Installation | 25% | 0.01572% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Supports |  | FA-25161498 |  |  | FA-25161498 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161499 |  |  | FA-25161499 | Calibration ( Device & Valve ) | 11.53% | 0.09206% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161500 |  |  | FA-25161500 | Calibration ( Device & Valve ) | 100% | 0.09206% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Calibration ( Device & Valve ) |  | FA-25161501 |  |  | FA-25161501 | Handling | 10% | 0.009206% |  | 56 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161502 |  |  | FA-25161502 | Calibration and restoring | 90% | 0.08285% |  | 56 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161503 |  |  | FA-25161503 | Instrument Equipment | 31.1% | 0.2484% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161504 |  |  | FA-25161504 | FIELD INSTRUMENTS | 69.66% | 0.1731% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | FIELD INSTRUMENTS |  | FA-25161505 |  |  | FA-25161505 | Handling | 10% | 0.01731% |  | 51 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161506 |  |  | FA-25161506 | Installation | 85% | 0.1471% |  | 51 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | FIELD INSTRUMENTS |  | FA-25161507 |  |  | FA-25161507 | QC | 5% | 0.008653% |  | 51 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161508 |  |  | FA-25161508 | F&G DETECTORS | 23.54% | 0.05848% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | F&G DETECTORS |  | FA-25161509 |  |  | FA-25161509 | Handling | 10% | 0.005848% |  | 22 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | F&G DETECTORS | 40060 | FA-25161510 |  |  | FA-25161510 | Installation | 85% | 0.04971% |  | 22 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | F&G DETECTORS |  | FA-25161511 |  |  | FA-25161511 | QC | 5% | 0.002924% |  | 22 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161512 |  |  | FA-25161512 | Junction Box | 6.764% | 0.01681% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Junction Box |  | FA-25161513 |  |  | FA-25161513 | Handling | 10% | 0.001681% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Junction Box | 40075 | FA-25161514 |  |  | FA-25161514 | Installation | 85% | 0.01428% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Junction Box |  | FA-25161515 |  |  | FA-25161515 | QC | 5% | 0.0008403% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161516 |  |  | FA-25161516 | Analyzer | 0.04322% | 0.0001074% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Analyzer |  | FA-25161517 |  |  | FA-25161517 | Handling | 10% | 1.074e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Analyzer |  | FA-25161518 |  |  | FA-25161518 | Installation | 85% | 9.126e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Analyzer |  | FA-25161519 |  |  | FA-25161519 | QC | 5% | 5.368e-06% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161520 |  |  | FA-25161520 | Instrument Cabling | 15.86% | 0.1267% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161521 |  |  | FA-25161521 | Main Cabling | 100% | 0.1267% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Main Cabling |  | FA-25161522 |  |  | FA-25161522 | Handling | 10% | 0.01267% |  | 2220 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Main Cabling | 40090 | FA-25161523 |  |  | FA-25161523 | Cable laying | 70% | 0.08866% |  | 2220 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Main Cabling |  | FA-25161524 |  |  | FA-25161524 | Cable arrangements and fixing | 5% | 0.006333% |  | 2220 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Main Cabling |  | FA-25161525 |  |  | FA-25161525 | Cable Marking | 5% | 0.006333% |  | 2220 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Main Cabling |  | FA-25161526 |  |  | FA-25161526 | Continuity & Megger Test | 5% | 0.006333% |  | 2220 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Main Cabling |  | FA-25161527 |  |  | FA-25161527 | QC | 5% | 0.006333% |  | 2220 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161528 |  |  | FA-25161528 | Secondary Cabling | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Secondary Cabling |  | FA-25161529 |  |  | FA-25161529 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Secondary Cabling | 40500 | FA-25161530 |  |  | FA-25161530 | Cable laying | 70% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Secondary Cabling |  | FA-25161531 |  |  | FA-25161531 | Cable arrangements and fixing | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Secondary Cabling |  | FA-25161532 |  |  | FA-25161532 | Cable Marking | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Secondary Cabling |  | FA-25161533 |  |  | FA-25161533 | Continuity & Megger Test | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Secondary Cabling |  | FA-25161534 |  |  | FA-25161534 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161535 |  |  | FA-25161535 | Instrument Cable Gland | 1.018% | 0.008129% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161536 |  |  | FA-25161536 | Instrument Cable Gland | 100% | 0.008129% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Instrument Cable Gland |  | FA-25161537 |  |  | FA-25161537 | Handling | 10% | 0.0008129% |  | 53 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Instrument Cable Gland | 40520 | FA-25161538 |  |  | FA-25161538 | Gland Installation | 60% | 0.004877% |  | 53 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Instrument Cable Gland | 40530 | FA-25161539 |  |  | FA-25161539 | Termination | 25% | 0.002032% |  | 53 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Instrument Cable Gland |  | FA-25161540 |  |  | FA-25161540 | QC | 5% | 0.0004064% |  | 53 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161541 |  |  | FA-25161541 | Loop Test ( Hot) | 4.778% | 0.03816% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161542 |  |  | FA-25161542 | Loop Test ( Hot) | 100% | 0.03816% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Loop Test ( Hot) | 40540 | FA-25161543 |  |  | FA-25161543 | Loop Test | 100% | 0.03816% |  | 61 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161544 |  |  | FA-25161544 | Air Pipe and Tubing | 4.29% | 0.03427% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161545 |  |  | FA-25161545 | Air Pipe and Tubing | 100% | 0.03427% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Air Pipe and Tubing |  | FA-25161546 |  |  | FA-25161546 | Handling | 10% | 0.003427% |  | 110 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Air Pipe and Tubing | 40550 | FA-25161547 |  |  | FA-25161547 | Tubing and connections | 85% | 0.02913% |  | 110 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Air Pipe and Tubing |  | FA-25161548 |  |  | FA-25161548 | QC | 5% | 0.001713% |  | 110 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161549 |  |  | FA-25161549 | Grounding/ Earthing System | 4.553% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161550 |  |  | FA-25161550 | Earthing Cable Pulling | 100% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Earthing Cable Pulling |  | FA-25161551 |  |  | FA-25161551 | Handling | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Earthing Cable Pulling | 40585 | FA-25161552 |  |  | FA-25161552 | Cable laying | 75% | 0.02727% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Earthing Cable Pulling |  | FA-25161553 |  |  | FA-25161553 | Cable arrangements and fixing | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FLS | Instrument | Earthing Cable Pulling |  | FA-25161554 |  |  | FA-25161554 | QC | 5% | 0.001818% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Instrument |  |  | FA-25161555 |  |  | FA-25161555 | Unit - GPRS | 0.4937% | 0.2097% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161556 |  |  | FA-25161556 | Calibration ( Device & Valve ) | 41.81% | 0.08767% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161557 |  |  | FA-25161557 | Calibration ( Device & Valve ) | 100% | 0.08767% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Calibration ( Device & Valve ) |  | FA-25161558 |  |  | FA-25161558 | Handling | 10% | 0.008767% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161559 |  |  | FA-25161559 | Calibration and restoring | 90% | 0.07891% |  | 5 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161560 |  |  | FA-25161560 | Instrument Equipment | 32.18% | 0.06748% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161561 |  |  | FA-25161561 | FIELD INSTRUMENTS | 25.12% | 0.01695% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | FIELD INSTRUMENTS |  | FA-25161562 |  |  | FA-25161562 | Handling | 10% | 0.001695% |  | 86 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161563 |  |  | FA-25161563 | Installation | 85% | 0.01441% |  | 86 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | FIELD INSTRUMENTS |  | FA-25161564 |  |  | FA-25161564 | QC | 5% | 0.0008474% |  | 86 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161565 |  |  | FA-25161565 | F&G DETECTORS | 74.84% | 0.0505% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | F&G DETECTORS |  | FA-25161566 |  |  | FA-25161566 | Handling | 10% | 0.00505% |  | 19 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | F&G DETECTORS | 40060 | FA-25161567 |  |  | FA-25161567 | Installation | 85% | 0.04293% |  | 19 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | F&G DETECTORS |  | FA-25161568 |  |  | FA-25161568 | QC | 5% | 0.002525% |  | 19 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161569 |  |  | FA-25161569 | Analyzer | 0.04322% | 2.916e-05% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Analyzer |  | FA-25161570 |  |  | FA-25161570 | Handling | 10% | 2.916e-06% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Analyzer |  | FA-25161571 |  |  | FA-25161571 | Installation | 85% | 2.479e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Analyzer |  | FA-25161572 |  |  | FA-25161572 | QC | 5% | 1.458e-06% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161573 |  |  | FA-25161573 | Grounding/ Earthing System | 26.01% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161574 |  |  | FA-25161574 | Earthing Cable Pulling | 100% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Earthing Cable Pulling |  | FA-25161575 |  |  | FA-25161575 | Handling | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Earthing Cable Pulling | 40585 | FA-25161576 |  |  | FA-25161576 | Cable laying | 75% | 0.04091% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Earthing Cable Pulling |  | FA-25161577 |  |  | FA-25161577 | Cable arrangements and fixing | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - GPRS | Instrument | Earthing Cable Pulling |  | FA-25161578 |  |  | FA-25161578 | QC | 5% | 0.002727% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Instrument |  |  | FA-25161579 |  |  | FA-25161579 | ITR - ITR35 | 3.238% | 1.375% |  |  |  |  | 0 | 15.33% | 2.811% | 18.14% |  | 0.2772% | 0 | [7 empty] | 0.2772%
[6 empty] | 4 |  | Instrument |  |  | FA-25161580 |  |  | FA-25161580 | Cable Tray, ladder, Conduits | 0.4814% | 0.006621% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161581 |  |  | FA-25161581 | Installation of Cable Tray, ladder, Cover | 100% | 0.006621% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161582 |  |  | FA-25161582 | Handling | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Installation of Cable Tray, ladder, Cover | 40001 | FA-25161583 |  |  | FA-25161583 | Tray/ Ladder Assembling | 65% | 0.004304% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161584 |  |  | FA-25161584 | Fixing & alignment | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161585 |  |  | FA-25161585 | Installation of covers | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161586 |  |  | FA-25161586 | QC | 5% | 0.0003311% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161587 |  |  | FA-25161587 | Calibration ( Device & Valve ) | 0.255% | 0.003507% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161588 |  |  | FA-25161588 | Calibration ( Device & Valve ) | 100% | 0.003507% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Calibration ( Device & Valve ) |  | FA-25161589 |  |  | FA-25161589 | Handling | 10% | 0.0003507% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161590 |  |  | FA-25161590 | Calibration and restoring | 90% | 0.003156% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161591 |  |  | FA-25161591 | Instrument Equipment | 0.9874% | 0.01358% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161592 |  |  | FA-25161592 | FIELD INSTRUMENTS | 100% | 0.01358% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | FIELD INSTRUMENTS |  | FA-25161593 |  |  | FA-25161593 | Handling | 10% | 0.001358% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161594 |  |  | FA-25161594 | Installation | 85% | 0.01154% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | FIELD INSTRUMENTS |  | FA-25161595 |  |  | FA-25161595 | QC | 5% | 0.0006791% |  | 4 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161596 |  |  | FA-25161596 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 49.32% | 0.6784% |  |  |  |  | 0 | 31.08% | 5.699% | 36.77% |  | 0.2772% | 0 | [7 empty] | 0.2772%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161597 |  |  | FA-25161597 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 100% | 0.6784% |  |  |  |  | 0 | 31.08% | 5.699% | 36.77% |  | 0.2772% | 0 | [7 empty] | 0.2772%
|  |  |  | Plan Jan |  | 6 | ITR - ITR35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) |  | FA-25161598 |  |  | FA-25161598 | Handling | 10% | 0.06784% |  | 93 |  | 36 | 36 | 36.56% | 2.151% | 38.71% | 40 | 0.02918% | 36 | [6 empty] | 40 | 0.02918%
|  |  |  | Plan Jan |  | 6 | ITR - ITR35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 40085 | FA-25161599 |  |  | FA-25161599 | Installation | 75% | 0.5088% |  | 93 |  | 36 | 36 | 36.56% | 2.151% | 38.71% | 40 | 0.2188% | 36 | [6 empty] | 40 | 0.2188%
|  |  |  | Plan Jan |  | 6 | ITR - ITR35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 40085 | FA-25161600 |  |  | FA-25161600 | Fixing | 10% | 0.06784% |  | 93 |  | 36 | 36 | 0% | 38.71% | 38.71% | 40 | 0.02918% | 36 | [6 empty] | 40 | 0.02918%
[6 empty] | 6 | ITR - ITR35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) |  | FA-25161601 |  |  | FA-25161601 | QC | 5% | 0.03392% |  | 93 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161602 |  |  | FA-25161602 | Instrument Cabling | 38.56% | 0.5303% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161603 |  |  | FA-25161603 | Internal Cabling | 100% | 0.5303% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Internal Cabling |  | FA-25161604 |  |  | FA-25161604 | Handling | 10% | 0.05303% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Internal Cabling | 40510 | FA-25161605 |  |  | FA-25161605 | Cable laying | 70% | 0.3712% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Internal Cabling |  | FA-25161606 |  |  | FA-25161606 | Cable arrangements and fixing | 5% | 0.02652% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Internal Cabling |  | FA-25161607 |  |  | FA-25161607 | Cable Marking | 5% | 0.02652% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Internal Cabling |  | FA-25161608 |  |  | FA-25161608 | Continuity & Megger Test | 5% | 0.02652% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Internal Cabling |  | FA-25161609 |  |  | FA-25161609 | QC | 5% | 0.02652% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161610 |  |  | FA-25161610 | Instrument Cable Gland | 2.464% | 0.0339% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161611 |  |  | FA-25161611 | Instrument Cable Gland | 100% | 0.0339% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Instrument Cable Gland |  | FA-25161612 |  |  | FA-25161612 | Handling | 10% | 0.00339% |  | 221 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Instrument Cable Gland | 40520 | FA-25161613 |  |  | FA-25161613 | Gland Installation | 60% | 0.02034% |  | 221 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Instrument Cable Gland | 40530 | FA-25161614 |  |  | FA-25161614 | Termination | 25% | 0.008474% |  | 221 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Instrument Cable Gland |  | FA-25161615 |  |  | FA-25161615 | QC | 5% | 0.001695% |  | 221 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161616 |  |  | FA-25161616 | Grounding/ Earthing System | 7.932% | 0.1091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161617 |  |  | FA-25161617 | Earthing Cable Pulling | 100% | 0.1091% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Earthing Cable Pulling |  | FA-25161618 |  |  | FA-25161618 | Handling | 10% | 0.01091% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Earthing Cable Pulling | 40585 | FA-25161619 |  |  | FA-25161619 | Cable laying | 75% | 0.08182% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Earthing Cable Pulling |  | FA-25161620 |  |  | FA-25161620 | Cable arrangements and fixing | 10% | 0.01091% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR35 | Instrument | Earthing Cable Pulling |  | FA-25161621 |  |  | FA-25161621 | QC | 5% | 0.005455% |  | 300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Instrument |  |  | FA-25161622 |  |  | FA-25161622 | Unit - C35 | 2.333% | 0.9911% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161623 |  |  | FA-25161623 | Cable Tray, ladder, Conduits | 14.08% | 0.1396% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161624 |  |  | FA-25161624 | Installation of Primary Tray, ladder | 47.44% | 0.06621% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161625 |  |  | FA-25161625 | Handling | 10% | 0.006621% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover | 40001 | FA-25161626 |  |  | FA-25161626 | Tray/ Ladder Assembling | 65% | 0.04304% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161627 |  |  | FA-25161627 | Fixing & alignment | 10% | 0.006621% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161628 |  |  | FA-25161628 | Installation of covers | 10% | 0.006621% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161629 |  |  | FA-25161629 | QC | 5% | 0.003311% |  | 400 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161630 |  |  | FA-25161630 | Installation of Secondary Tray | 47.44% | 0.06621% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161631 |  |  | FA-25161631 | Handling | 10% | 0.006621% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover | 40001 | FA-25161632 |  |  | FA-25161632 | Tray/ Ladder Assembling | 65% | 0.04304% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161633 |  |  | FA-25161633 | Fixing & alignment | 10% | 0.006621% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161634 |  |  | FA-25161634 | Installation of covers | 10% | 0.006621% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161635 |  |  | FA-25161635 | QC | 5% | 0.003311% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161636 |  |  | FA-25161636 | Installation of conduits | 5.13% | 0.007161% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of conduits |  | FA-25161637 |  |  | FA-25161637 | Handling | 10% | 0.0007161% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of conduits | 40010 | FA-25161638 |  |  | FA-25161638 | Installation of Conduit | 85% | 0.006087% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Installation of conduits |  | FA-25161639 |  |  | FA-25161639 | QC | 5% | 0.000358% |  | 30 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161640 |  |  | FA-25161640 | Calibration ( Device & Valve ) | 1.415% | 0.01403% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161641 |  |  | FA-25161641 | Calibration ( Device & Valve ) | 100% | 0.01403% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Calibration ( Device & Valve ) |  | FA-25161642 |  |  | FA-25161642 | Handling | 10% | 0.001403% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161643 |  |  | FA-25161643 | Calibration and restoring | 90% | 0.01263% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161644 |  |  | FA-25161644 | Instrument Equipment | 5.481% | 0.05433% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161645 |  |  | FA-25161645 | FIELD INSTRUMENTS | 100% | 0.05433% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | FIELD INSTRUMENTS |  | FA-25161646 |  |  | FA-25161646 | Handling | 10% | 0.005433% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161647 |  |  | FA-25161647 | Installation | 85% | 0.04618% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | FIELD INSTRUMENTS |  | FA-25161648 |  |  | FA-25161648 | QC | 5% | 0.002716% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161649 |  |  | FA-25161649 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 52.99% | 0.5252% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161650 |  |  | FA-25161650 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 100% | 0.5252% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) |  | FA-25161651 |  |  | FA-25161651 | Handling | 10% | 0.05252% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 40085 | FA-25161652 |  |  | FA-25161652 | Installation | 75% | 0.3939% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 40085 | FA-25161653 |  |  | FA-25161653 | Fixing | 10% | 0.05252% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) |  | FA-25161654 |  |  | FA-25161654 | QC | 5% | 0.02626% |  | 72 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161655 |  |  | FA-25161655 | Instrument Cabling | 19.28% | 0.1911% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161656 |  |  | FA-25161656 | Internal Cabling | 100% | 0.1911% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Internal Cabling |  | FA-25161657 |  |  | FA-25161657 | Handling | 10% | 0.01911% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Internal Cabling | 40510 | FA-25161658 |  |  | FA-25161658 | Cable laying | 70% | 0.1338% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Internal Cabling |  | FA-25161659 |  |  | FA-25161659 | Cable arrangements and fixing | 5% | 0.009556% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Internal Cabling |  | FA-25161660 |  |  | FA-25161660 | Cable Marking | 5% | 0.009556% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Internal Cabling |  | FA-25161661 |  |  | FA-25161661 | Continuity & Megger Test | 5% | 0.009556% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Internal Cabling |  | FA-25161662 |  |  | FA-25161662 | QC | 5% | 0.009556% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161663 |  |  | FA-25161663 | Instrument Cable Gland | 1.238% | 0.01227% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161664 |  |  | FA-25161664 | Instrument Cable Gland | 100% | 0.01227% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Cable Gland |  | FA-25161665 |  |  | FA-25161665 | Handling | 10% | 0.001227% |  | 80 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Cable Gland | 40520 | FA-25161666 |  |  | FA-25161666 | Gland Installation | 60% | 0.007362% |  | 80 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Cable Gland | 40530 | FA-25161667 |  |  | FA-25161667 | Termination | 25% | 0.003067% |  | 80 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Instrument Cable Gland |  | FA-25161668 |  |  | FA-25161668 | QC | 5% | 0.0006135% |  | 80 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161669 |  |  | FA-25161669 | Grounding/ Earthing System | 5.504% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161670 |  |  | FA-25161670 | Earthing Cable Pulling | 100% | 0.05455% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Earthing Cable Pulling |  | FA-25161671 |  |  | FA-25161671 | Handling | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Earthing Cable Pulling | 40585 | FA-25161672 |  |  | FA-25161672 | Cable laying | 75% | 0.04091% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Earthing Cable Pulling |  | FA-25161673 |  |  | FA-25161673 | Cable arrangements and fixing | 10% | 0.005455% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - C35 | Instrument | Earthing Cable Pulling |  | FA-25161674 |  |  | FA-25161674 | QC | 5% | 0.002727% |  | 150 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Instrument |  |  | FA-25161675 |  |  | FA-25161675 | Unit - INT | 0.3511% | 0.1491% |  |  |  |  | 0 | 21.08% | 0% | 21.08% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161676 |  |  | FA-25161676 | Supports | 42.16% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161677 |  |  | FA-25161677 | Supports | 100% | 0.06288% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.03144% | 0 | [7 empty] | 0.03144%
|  |  |  | Plan Jan |  | 6 | Unit - INT | Instrument | Supports |  | FA-25161678 |  |  | FA-25161678 | Material Supply & Handling | 50% | 0.03144% |  | 575 |  | 575 | 575 | 100% | 0% | 100% | 575 | 0.03144% | 575 | [6 empty] | 575 | 0.03144%
[6 empty] | 6 | Unit - INT | Instrument | Supports | 40020 | FA-25161679 |  |  | FA-25161679 | Fabrication | 20% | 0.01258% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Supports | 40030 | FA-25161680 |  |  | FA-25161680 | Installation | 25% | 0.01572% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Supports |  | FA-25161681 |  |  | FA-25161681 | QC | 5% | 0.003144% |  | 575 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161682 |  |  | FA-25161682 | Instrument Equipment | 26.74% | 0.03987% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161683 |  |  | FA-25161683 | F&G DETECTORS | 99.96% | 0.03985% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | F&G DETECTORS |  | FA-25161684 |  |  | FA-25161684 | Handling | 10% | 0.003985% |  | 15 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | F&G DETECTORS | 40060 | FA-25161685 |  |  | FA-25161685 | Installation | 85% | 0.03388% |  | 15 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | F&G DETECTORS |  | FA-25161686 |  |  | FA-25161686 | QC | 5% | 0.001993% |  | 15 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161687 |  |  | FA-25161687 | Analyzer | 0.04322% | 1.723e-05% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Analyzer |  | FA-25161688 |  |  | FA-25161688 | Handling | 10% | 1.723e-06% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Analyzer |  | FA-25161689 |  |  | FA-25161689 | Installation | 85% | 1.465e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Analyzer |  | FA-25161690 |  |  | FA-25161690 | QC | 5% | 8.615e-07% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161691 |  |  | FA-25161691 | Loop Test ( Hot) | 6.712% | 0.01001% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161692 |  |  | FA-25161692 | Loop Test ( Hot) | 100% | 0.01001% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Loop Test ( Hot) | 40540 | FA-25161693 |  |  | FA-25161693 | Loop Test | 100% | 0.01001% |  | 16 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161694 |  |  | FA-25161694 | Grounding/ Earthing System | 24.39% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161695 |  |  | FA-25161695 | Earthing Cable Pulling | 100% | 0.03637% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Earthing Cable Pulling |  | FA-25161696 |  |  | FA-25161696 | Handling | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Earthing Cable Pulling | 40585 | FA-25161697 |  |  | FA-25161697 | Cable laying | 75% | 0.02727% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Earthing Cable Pulling |  | FA-25161698 |  |  | FA-25161698 | Cable arrangements and fixing | 10% | 0.003637% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Instrument | Earthing Cable Pulling |  | FA-25161699 |  |  | FA-25161699 | QC | 5% | 0.001818% |  | 100 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 3 |  | Instrument |  |  | FA-25161700 |  |  | FA-25161700 | Unit - TNK | 23.08% | 9.803% |  |  |  |  | 0 | 1.283% | 0% | 1.283% |  | 0.1258% | 0 | [7 empty] | 0.1258%
[6 empty] | 4 |  | Instrument |  |  | FA-25161701 |  |  | FA-25161701 | Cable Tray, ladder, Conduits | 13.99% | 1.372% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161702 |  |  | FA-25161702 | Installation of Primary Tray, ladder | 33.09% | 0.4539% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Primary Tray, ladder |  | FA-25161703 |  |  | FA-25161703 | Handling | 10% | 0.04539% |  | 2742 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Primary Tray, ladder | 40001 | FA-25161704 |  |  | FA-25161704 | Tray/ Ladder Assembling | 65% | 0.295% |  | 2742 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Primary Tray, ladder |  | FA-25161705 |  |  | FA-25161705 | Fixing & alignment | 10% | 0.04539% |  | 2742 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Primary Tray, ladder |  | FA-25161706 |  |  | FA-25161706 | Installation of covers | 10% | 0.04539% |  | 2742 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Primary Tray, ladder |  | FA-25161707 |  |  | FA-25161707 | QC | 5% | 0.02269% |  | 2742 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161708 |  |  | FA-25161708 | Installation of Secondary Tray | 33.09% | 0.4539% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Secondary Tray |  | FA-25161709 |  |  | FA-25161709 | Handling | 10% | 0.04539% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Secondary Tray | 40001 | FA-25161710 |  |  | FA-25161710 | Tray/ Ladder Assembling | 65% | 0.295% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Secondary Tray |  | FA-25161711 |  |  | FA-25161711 | Fixing & alignment | 10% | 0.04539% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Secondary Tray |  | FA-25161712 |  |  | FA-25161712 | Installation of covers | 10% | 0.04539% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of Secondary Tray |  | FA-25161713 |  |  | FA-25161713 | QC | 5% | 0.02269% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161714 |  |  | FA-25161714 | Installation of conduits | 33.82% | 0.464% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of conduits |  | FA-25161715 |  |  | FA-25161715 | Handling | 10% | 0.0464% |  | 1944 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of conduits | 40010 | FA-25161716 |  |  | FA-25161716 | Installation of Conduit | 85% | 0.3944% |  | 1944 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Installation of conduits |  | FA-25161717 |  |  | FA-25161717 | QC | 5% | 0.0232% |  | 1944 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 4 |  | Instrument |  |  | FA-25161718 |  |  | FA-25161718 | Supports | 2.566% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 | [7 empty] | 0.1258%
|  |  |  | Plan Jan |  | 5 |  | Instrument |  |  | FA-25161719 |  |  | FA-25161719 | Supports | 100% | 0.2515% |  |  |  |  | 0 | 50% | 0% | 50% |  | 0.1258% | 0 | [7 empty] | 0.1258%
|  |  |  | Plan Jan |  | 6 | Unit - TNK | Instrument | Supports |  | FA-25161720 |  |  | FA-25161720 | Material Supply & Handling | 50% | 0.1258% |  | 2300 |  | 2300 | 2300 | 100% | 0% | 100% | 2300 | 0.1258% | 2300 | [6 empty] | 2300 | 0.1258%
[6 empty] | 6 | Unit - TNK | Instrument | Supports | 40020 | FA-25161721 |  |  | FA-25161721 | Fabrication | 20% | 0.0503% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Supports | 40030 | FA-25161722 |  |  | FA-25161722 | Installation | 25% | 0.06288% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Supports |  | FA-25161723 |  |  | FA-25161723 | QC | 5% | 0.01258% |  | 2300 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161724 |  |  | FA-25161724 | Calibration ( Device & Valve ) | 1.923% | 0.1885% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161725 |  |  | FA-25161725 | Calibration ( Device & Valve ) | 100% | 0.1885% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Calibration ( Device & Valve ) |  | FA-25161726 |  |  | FA-25161726 | Handling | 10% | 0.01885% |  | 653 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161727 |  |  | FA-25161727 | Calibration and restoring | 90% | 0.1697% |  | 653 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161728 |  |  | FA-25161728 | Instrument Equipment | 31.46% | 3.084% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161729 |  |  | FA-25161729 | FIELD INSTRUMENTS | 59.19% | 1.825% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | FIELD INSTRUMENTS |  | FA-25161730 |  |  | FA-25161730 | Handling | 10% | 0.1825% |  | 275 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161731 |  |  | FA-25161731 | Installation | 85% | 1.552% |  | 275 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | FIELD INSTRUMENTS |  | FA-25161732 |  |  | FA-25161732 | QC | 5% | 0.09127% |  | 275 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161733 |  |  | FA-25161733 | F&G DETECTORS | 31.29% | 0.9649% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | F&G DETECTORS |  | FA-25161734 |  |  | FA-25161734 | Handling | 10% | 0.09649% |  | 363 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | F&G DETECTORS | 40060 | FA-25161735 |  |  | FA-25161735 | Installation | 85% | 0.8201% |  | 363 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | F&G DETECTORS |  | FA-25161736 |  |  | FA-25161736 | QC | 5% | 0.04824% |  | 363 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161737 |  |  | FA-25161737 | Junction Box | 9.482% | 0.2924% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Junction Box |  | FA-25161738 |  |  | FA-25161738 | Handling | 10% | 0.02924% |  | 87 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Junction Box | 40075 | FA-25161739 |  |  | FA-25161739 | Installation | 85% | 0.2486% |  | 87 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Junction Box |  | FA-25161740 |  |  | FA-25161740 | QC | 5% | 0.01462% |  | 87 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161741 |  |  | FA-25161741 | Analyzer | 0.04322% | 0.001333% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Analyzer |  | FA-25161742 |  |  | FA-25161742 | Handling | 10% | 0.0001333% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Analyzer |  | FA-25161743 |  |  | FA-25161743 | Installation | 85% | 0.001133% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Analyzer |  | FA-25161744 |  |  | FA-25161744 | QC | 5% | 6.664e-05% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161745 |  |  | FA-25161745 | Instrument Cabling | 40.12% | 3.933% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161746 |  |  | FA-25161746 | Main Cabling | 100% | 3.933% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Main Cabling |  | FA-25161747 |  |  | FA-25161747 | Handling | 10% | 0.3933% |  | 68940 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Main Cabling | 40090 | FA-25161748 |  |  | FA-25161748 | Cable laying | 70% | 2.753% |  | 68940 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Main Cabling |  | FA-25161749 |  |  | FA-25161749 | Cable arrangements and fixing | 5% | 0.1967% |  | 68940 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Main Cabling |  | FA-25161750 |  |  | FA-25161750 | Cable Marking | 5% | 0.1967% |  | 68940 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Main Cabling |  | FA-25161751 |  |  | FA-25161751 | Continuity & Megger Test | 5% | 0.1967% |  | 68940 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Main Cabling |  | FA-25161752 |  |  | FA-25161752 | QC | 5% | 0.1967% |  | 68940 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161753 |  |  | FA-25161753 | Secondary Cabling | 0% | 0% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Secondary Cabling |  | FA-25161754 |  |  | FA-25161754 | Handling | 10% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Secondary Cabling | 40500 | FA-25161755 |  |  | FA-25161755 | Cable laying | 70% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Secondary Cabling |  | FA-25161756 |  |  | FA-25161756 | Cable arrangements and fixing | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Secondary Cabling |  | FA-25161757 |  |  | FA-25161757 | Cable Marking | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Secondary Cabling |  | FA-25161758 |  |  | FA-25161758 | Continuity & Megger Test | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Secondary Cabling |  | FA-25161759 |  |  | FA-25161759 | QC | 5% | 0% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161760 |  |  | FA-25161760 | Instrument Cable Gland | 2.488% | 0.2439% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161761 |  |  | FA-25161761 | Instrument Cable Gland | 100% | 0.2439% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Instrument Cable Gland |  | FA-25161762 |  |  | FA-25161762 | Handling | 10% | 0.02439% |  | 1590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Instrument Cable Gland | 40520 | FA-25161763 |  |  | FA-25161763 | Gland Installation | 60% | 0.1463% |  | 1590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Instrument Cable Gland | 40530 | FA-25161764 |  |  | FA-25161764 | Termination | 25% | 0.06097% |  | 1590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Instrument Cable Gland |  | FA-25161765 |  |  | FA-25161765 | QC | 5% | 0.01219% |  | 1590 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161766 |  |  | FA-25161766 | Loop Test ( Hot) | 4.046% | 0.3966% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161767 |  |  | FA-25161767 | Loop Test ( Hot) | 100% | 0.3966% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Loop Test ( Hot) | 40540 | FA-25161768 |  |  | FA-25161768 | Loop Test | 100% | 0.3966% |  | 634 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161769 |  |  | FA-25161769 | Air Pipe and Tubing | 2.657% | 0.2604% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161770 |  |  | FA-25161770 | Air Pipe and Tubing | 100% | 0.2604% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Air Pipe and Tubing |  | FA-25161771 |  |  | FA-25161771 | Handling | 10% | 0.02604% |  | 836 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Air Pipe and Tubing | 40550 | FA-25161772 |  |  | FA-25161772 | Tubing and connections | 85% | 0.2214% |  | 836 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Air Pipe and Tubing |  | FA-25161773 |  |  | FA-25161773 | QC | 5% | 0.01302% |  | 836 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161774 |  |  | FA-25161774 | Grounding/ Earthing System | 0.742% | 0.07273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161775 |  |  | FA-25161775 | Earthing Cable Pulling | 100% | 0.07273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Earthing Cable Pulling |  | FA-25161776 |  |  | FA-25161776 | Handling | 10% | 0.007273% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Earthing Cable Pulling | 40585 | FA-25161777 |  |  | FA-25161777 | Cable laying | 75% | 0.05455% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Earthing Cable Pulling |  | FA-25161778 |  |  | FA-25161778 | Cable arrangements and fixing | 10% | 0.007273% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Instrument | Earthing Cable Pulling |  | FA-25161779 |  |  | FA-25161779 | QC | 5% | 0.003637% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 3 |  | Instrument |  |  | FA-25161780 |  |  | FA-25161780 | ITR - ITR55 | 1.053% | 0.4474% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2218% | [6 empty] | 0.2218%
[6 empty] | 4 |  | Instrument |  |  | FA-25161781 |  |  | FA-25161781 | Cable Tray, ladder, Conduits | 1.48% | 0.006621% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161782 |  |  | FA-25161782 | Installation of Cable Tray, ladder, Cover | 100% | 0.006621% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161783 |  |  | FA-25161783 | Handling | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Installation of Cable Tray, ladder, Cover | 40001 | FA-25161784 |  |  | FA-25161784 | Tray/ Ladder Assembling | 65% | 0.004304% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161785 |  |  | FA-25161785 | Fixing & alignment | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161786 |  |  | FA-25161786 | Installation of covers | 10% | 0.0006621% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Installation of Cable Tray, ladder, Cover |  | FA-25161787 |  |  | FA-25161787 | QC | 5% | 0.0003311% |  | 20 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161788 |  |  | FA-25161788 | Calibration ( Device & Valve ) | 0.5879% | 0.00263% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161789 |  |  | FA-25161789 | Calibration ( Device & Valve ) | 100% | 0.00263% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Calibration ( Device & Valve ) |  | FA-25161790 |  |  | FA-25161790 | Handling | 10% | 0.000263% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Calibration ( Device & Valve ) | 40040 | FA-25161791 |  |  | FA-25161791 | Calibration and restoring | 90% | 0.002367% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161792 |  |  | FA-25161792 | Instrument Equipment | 2.277% | 0.01019% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161793 |  |  | FA-25161793 | FIELD INSTRUMENTS | 100% | 0.01019% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | FIELD INSTRUMENTS |  | FA-25161794 |  |  | FA-25161794 | Handling | 10% | 0.001019% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | FIELD INSTRUMENTS | 40050 | FA-25161795 |  |  | FA-25161795 | Installation | 85% | 0.008658% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | FIELD INSTRUMENTS |  | FA-25161796 |  |  | FA-25161796 | QC | 5% | 0.0005093% |  | 3 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  |  | Plan Feb | 4 |  | Instrument |  |  | FA-25161797 |  |  | FA-25161797 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 52.18% | 0.2334% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2218% | [6 empty] | 0.2218%
Plan |  |  |  |  | Plan Feb | 5 |  | Instrument |  |  | FA-25161798 |  |  | FA-25161798 | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 100% | 0.2334% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0 |  |  | 0.2218% | [6 empty] | 0.2218%
Plan | 0.00023344 | 0.0007295% | 1.703e-07% |  | Plan Feb | 6 | ITR - ITR55 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) |  | FA-25161799 |  |  | FA-25161799 | Handling | 10% | 0.02334% |  | 32 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 32 | 1 | 0.02334% | Week 3 | Week 4 | منوط به تهیه پنل ها |  |  | 32 | 0.02334% | ok | 0% | 0%
Plan | 0.0017508 | 0.005471% | 9.579e-06% |  | Plan Feb | 6 | ITR - ITR55 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 40085 | FA-25161800 |  |  | FA-25161800 | Installation | 75% | 0.1751% |  | 32 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 32 | 1 | 0.1751% | Week 3 | Week 4 | منوط به تهیه پنل ها |  |  | 32 | 0.1751% | ok | 0% | 0%
Plan | 0.00023344 | 0.0007295% | 1.703e-07% |  | Plan Feb | 6 | ITR - ITR55 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) | 40085 | FA-25161801 |  |  | FA-25161801 | Fixing | 10% | 0.02334% |  | 32 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 32 | 1 | 0.02334% | Week 3 | Week 4 | منوط به تهیه پنل ها |  |  | 32 | 0.02334% | ok | 0% | 0%
[6 empty] | 6 | ITR - ITR55 | Instrument | Instrument Panel (DCS/ESD/F&G/TGS/PLC , ….) |  | FA-25161802 |  |  | FA-25161802 | QC | 5% | 0.01167% |  | 32 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161803 |  |  | FA-25161803 | Instrument Cabling | 25.51% | 0.1141% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161804 |  |  | FA-25161804 | Internal Cabling | 100% | 0.1141% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Internal Cabling |  | FA-25161805 |  |  | FA-25161805 | Handling | 10% | 0.01141% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Internal Cabling | 40510 | FA-25161806 |  |  | FA-25161806 | Cable laying | 70% | 0.07987% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Internal Cabling |  | FA-25161807 |  |  | FA-25161807 | Cable arrangements and fixing | 5% | 0.005705% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Internal Cabling |  | FA-25161808 |  |  | FA-25161808 | Cable Marking | 5% | 0.005705% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Internal Cabling |  | FA-25161809 |  |  | FA-25161809 | Continuity & Megger Test | 5% | 0.005705% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Internal Cabling |  | FA-25161810 |  |  | FA-25161810 | QC | 5% | 0.005705% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161811 |  |  | FA-25161811 | Instrument Cable Gland | 1.714% | 0.007669% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161812 |  |  | FA-25161812 | Instrument Cable Gland | 100% | 0.007669% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Instrument Cable Gland |  | FA-25161813 |  |  | FA-25161813 | Handling | 10% | 0.0007669% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Instrument Cable Gland | 40520 | FA-25161814 |  |  | FA-25161814 | Gland Installation | 60% | 0.004601% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Instrument Cable Gland | 40530 | FA-25161815 |  |  | FA-25161815 | Termination | 25% | 0.001917% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Instrument Cable Gland |  | FA-25161816 |  |  | FA-25161816 | QC | 5% | 0.0003834% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Instrument |  |  | FA-25161817 |  |  | FA-25161817 | Grounding/ Earthing System | 16.26% | 0.07273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Instrument |  |  | FA-25161818 |  |  | FA-25161818 | Earthing Cable Pulling | 100% | 0.07273% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Earthing Cable Pulling |  | FA-25161819 |  |  | FA-25161819 | Handling | 10% | 0.007273% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Earthing Cable Pulling | 40585 | FA-25161820 |  |  | FA-25161820 | Cable laying | 75% | 0.05455% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Earthing Cable Pulling |  | FA-25161821 |  |  | FA-25161821 | Cable arrangements and fixing | 10% | 0.007273% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | ITR - ITR55 | Instrument | Earthing Cable Pulling |  | FA-25161822 |  |  | FA-25161822 | QC | 5% | 0.003637% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Instrument |  |  | FA-25161823 |  |  | FA-25161823 | Unit - WWT | 5% | 2.124% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - WWT | Instrument |  |  | FA-25161824 |  |  | FA-25161824 | Unit - WWT | 100% | 2.124% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Instrument |  |  | FA-25161825 |  |  | FA-25161825 | Contingency Reserve | 5% | 2.124% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Contingency Reserve | Instrument |  |  | FA-25161826 |  |  | FA-25161826 | Contingency Reserve | 100% | 2.124% |  | 200 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 2 |  | Telecom |  |  | FA-25161827 |  |  | FA-25161827 | Telecom | 8.045% | 8.045% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Telecom |  |  | FA-25161828 |  |  | FA-25161828 | All Unit | 95% | 7.643% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161829 |  |  | FA-25161829 | Cable Tray, ladder, Conduits | 9.195% | 0.7028% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161830 |  |  | FA-25161830 | Installation of Primary Tray, ladder | 23.88% | 0.1678% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Primary Tray, ladder |  | FA-25161831 |  |  | FA-25161831 | Handling | 10% | 0.01678% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Primary Tray, ladder | 80050 | FA-25161832 |  |  | FA-25161832 | Tray/ Ladder Assembling | 65% | 0.1091% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Primary Tray, ladder |  | FA-25161833 |  |  | FA-25161833 | Fixing & alignment | 10% | 0.01678% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Primary Tray, ladder |  | FA-25161834 |  |  | FA-25161834 | Installation of covers | 10% | 0.01678% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Primary Tray, ladder |  | FA-25161835 |  |  | FA-25161835 | QC | 5% | 0.008392% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161836 |  |  | FA-25161836 | Installation of Secondary Tray | 23.88% | 0.1678% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Secondary Tray |  | FA-25161837 |  |  | FA-25161837 | Handling | 10% | 0.01678% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Secondary Tray | 80050 | FA-25161838 |  |  | FA-25161838 | Tray/ Ladder Assembling | 65% | 0.1091% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Secondary Tray |  | FA-25161839 |  |  | FA-25161839 | Fixing & alignment | 10% | 0.01678% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Secondary Tray |  | FA-25161840 |  |  | FA-25161840 | Installation of covers | 10% | 0.01678% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of Secondary Tray |  | FA-25161841 |  |  | FA-25161841 | QC | 5% | 0.008392% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161842 |  |  | FA-25161842 | Installation of conduits | 52.24% | 0.3671% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of conduits |  | FA-25161843 |  |  | FA-25161843 | Handling | 10% | 0.03671% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of conduits | 80060 | FA-25161844 |  |  | FA-25161844 | Installation of Conduit | 85% | 0.312% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Installation of conduits |  | FA-25161845 |  |  | FA-25161845 | QC | 5% | 0.01836% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161846 |  |  | FA-25161846 | Supports | 1.737% | 0.1327% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161847 |  |  | FA-25161847 | Supports | 100% | 0.1327% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Supports |  | FA-25161848 |  |  | FA-25161848 | Material Supply & Handling | 50% | 0.06637% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Supports | 80070 | FA-25161849 |  |  | FA-25161849 | Fabrication | 20% | 0.02655% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Supports | 80080 | FA-25161850 |  |  | FA-25161850 | Installation | 25% | 0.03318% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Supports |  | FA-25161851 |  |  | FA-25161851 | QC | 5% | 0.006637% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161852 |  |  | FA-25161852 | Communication Cabling | 36% | 2.751% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161853 |  |  | FA-25161853 | Communication Cabling | 100% | 2.751% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Communication Cabling |  | FA-25161854 |  |  | FA-25161854 | Handling | 10% | 0.2751% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Communication Cabling | 80090 | FA-25161855 |  |  | FA-25161855 | Cable laying | 70% | 1.926% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Communication Cabling |  | FA-25161856 |  |  | FA-25161856 | Cable arrangements and fixing | 5% | 0.1376% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Communication Cabling |  | FA-25161857 |  |  | FA-25161857 | Cable Marking | 5% | 0.1376% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Communication Cabling |  | FA-25161858 |  |  | FA-25161858 | QC | 10% | 0.2751% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161859 |  |  | FA-25161859 | Telecom Cable Gland | 12% | 0.917% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161860 |  |  | FA-25161860 | Telecom Cable Gland | 100% | 0.917% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telecom Cable Gland |  | FA-25161861 |  |  | FA-25161861 | Handling | 10% | 0.0917% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telecom Cable Gland | 80100 | FA-25161862 |  |  | FA-25161862 | Gland Installation | 60% | 0.5502% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telecom Cable Gland | 80110 | FA-25161863 |  |  | FA-25161863 | Termination | 25% | 0.2293% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telecom Cable Gland |  | FA-25161864 |  |  | FA-25161864 | QC | 5% | 0.04585% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161865 |  |  | FA-25161865 | CCTV system | 8.706% | 0.6654% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161866 |  |  | FA-25161866 | CCTV Device | 82.82% | 0.5511% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Device |  | FA-25161867 |  |  | FA-25161867 | Handling | 10% | 0.05511% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Device | 80120 | FA-25161868 |  |  | FA-25161868 | Pole For CCT | 15% | 0.08267% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Device | 80130 | FA-25161869 |  |  | FA-25161869 | Device Installation | 70% | 0.3858% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Device |  | FA-25161870 |  |  | FA-25161870 | QC | 5% | 0.02756% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161871 |  |  | FA-25161871 | CCTV Junction Box | 7.158% | 0.04763% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Junction Box |  | FA-25161872 |  |  | FA-25161872 | Handling | 10% | 0.004763% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Junction Box | 80140 | FA-25161873 |  |  | FA-25161873 | Installation | 85% | 0.04048% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Junction Box |  | FA-25161874 |  |  | FA-25161874 | QC | 5% | 0.002381% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161875 |  |  | FA-25161875 | CCTV Panel | 7.158% | 0.04763% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Panel |  | FA-25161876 |  |  | FA-25161876 | Handling | 10% | 0.004763% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Panel | 80150 | FA-25161877 |  |  | FA-25161877 | Installation | 85% | 0.04049% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Panel |  | FA-25161878 |  |  | FA-25161878 | QC | 5% | 0.002381% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161879 |  |  | FA-25161879 | CCTV Workstation | 2.863% | 0.01905% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Workstation |  | FA-25161880 |  |  | FA-25161880 | Handling | 10% | 0.001905% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Workstation | 80160 | FA-25161881 |  |  | FA-25161881 | Keyboard | 25% | 0.004763% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Workstation | 80170 | FA-25161882 |  |  | FA-25161882 | Monitor | 60% | 0.01143% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | CCTV Workstation |  | FA-25161883 |  |  | FA-25161883 | QC | 5% | 0.0009526% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161884 |  |  | FA-25161884 | Telephone and Fire Telephone system | 19.05% | 1.456% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161885 |  |  | FA-25161885 | Telephone and Fire Telephone Device | 65.49% | 0.9536% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Device |  | FA-25161886 |  |  | FA-25161886 | Handling | 10% | 0.09536% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Device | 80180 | FA-25161887 |  |  | FA-25161887 | Pedestal Pole | 15% | 0.143% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Device | 80190 | FA-25161888 |  |  | FA-25161888 | Device Installation | 70% | 0.6675% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Device |  | FA-25161889 |  |  | FA-25161889 | QC | 5% | 0.04768% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161890 |  |  | FA-25161890 | Telephone and Fire Telephone Junction Box | 14.39% | 0.2096% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Junction Box |  | FA-25161891 |  |  | FA-25161891 | Handling | 10% | 0.02096% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Junction Box | 80200 | FA-25161892 |  |  | FA-25161892 | Installation | 85% | 0.1781% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Junction Box |  | FA-25161893 |  |  | FA-25161893 | QC | 5% | 0.01048% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161894 |  |  | FA-25161894 | Telephone and Fire Telephone Panel | 20.12% | 0.2929% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Panel |  | FA-25161895 |  |  | FA-25161895 | Handling | 10% | 0.02929% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Panel | 80210 | FA-25161896 |  |  | FA-25161896 | Installation | 85% | 0.249% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Telephone and Fire Telephone Panel |  | FA-25161897 |  |  | FA-25161897 | QC | 5% | 0.01465% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161898 |  |  | FA-25161898 | Radio system | 1.122% | 0.08573% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161899 |  |  | FA-25161899 | Radio system | 100% | 0.08573% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Radio system |  | FA-25161900 |  |  | FA-25161900 | Handling | 10% | 0.008573% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Radio system | 80215 | FA-25161901 |  |  | FA-25161901 | Installation Main Panels | 85% | 0.07287% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Radio system |  | FA-25161902 |  |  | FA-25161902 | QC | 5% | 0.004287% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161903 |  |  | FA-25161903 | PA/GA system | 10.73% | 0.8197% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161904 |  |  | FA-25161904 | PA/GA Device | 76.06% | 0.6235% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Device |  | FA-25161905 |  |  | FA-25161905 | Handling | 10% | 0.06235% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Device | 80220 | FA-25161906 |  |  | FA-25161906 | HDG Pole | 15% | 0.09352% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Device | 80228 | FA-25161907 |  |  | FA-25161907 | Device Installation | 70% | 0.4364% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Device |  | FA-25161908 |  |  | FA-25161908 | QC | 5% | 0.03117% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161909 |  |  | FA-25161909 | PA/GA Junction Box | 14.18% | 0.1162% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Junction Box |  | FA-25161910 |  |  | FA-25161910 | Handling | 10% | 0.01162% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Junction Box | 80225 | FA-25161911 |  |  | FA-25161911 | Installation | 85% | 0.09879% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Junction Box |  | FA-25161912 |  |  | FA-25161912 | QC | 5% | 0.005811% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161913 |  |  | FA-25161913 | PA/GA Panel | 9.762% | 0.08002% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Panel |  | FA-25161914 |  |  | FA-25161914 | Handling | 10% | 0.008002% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Panel | 80230 | FA-25161915 |  |  | FA-25161915 | Installation | 85% | 0.06802% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | PA/GA Panel |  | FA-25161916 |  |  | FA-25161916 | QC | 5% | 0.004001% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Telecom |  |  | FA-25161917 |  |  | FA-25161917 | Grounding/ Earthing System | 1.467% | 0.1121% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Telecom |  |  | FA-25161918 |  |  | FA-25161918 | Earthing Cable Pulling | 100% | 0.1121% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Earthing Cable Pulling |  | FA-25161919 |  |  | FA-25161919 | Handling | 10% | 0.01121% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Earthing Cable Pulling | 80235 | FA-25161920 |  |  | FA-25161920 | Cable laying | 75% | 0.0841% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Earthing Cable Pulling |  | FA-25161921 |  |  | FA-25161921 | Cable arrangements and fixing | 10% | 0.01121% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | All Unit | Telecom | Earthing Cable Pulling |  | FA-25161922 |  |  | FA-25161922 | QC | 5% | 0.005606% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Telecom |  |  | FA-25161923 |  |  | FA-25161923 | Contingency Reserve | 5% | 0.4022% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Contingency Reserve | Telecom |  |  | FA-25161924 |  |  | FA-25161924 | Contingency Reserve | 100% | 0.4022% |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 2 |  | Civil |  |  | FA-25161925 |  |  | FA-25161925 | General Work ( Civil Activity ) | 4.962% | 4.962% |  |  |  |  | 0 | 0.7677% | 0.08416% | 0.8519% |  | 0.27% | 0 |  |  | 0.2485% |  |  |  |  | 0.27% |  | 0.2485%
|  |  |  | Plan Jan |  | 3 |  | Civil |  |  | FA-25161926 |  |  | FA-25161926 | Unit - CDU | 2.302% | 0.1142% |  |  |  |  | 0 | 9.411% | 3.656% | 13.07% |  | 0.0215% | 0 | [7 empty] | 0.0215%
|  |  |  | Plan Jan |  | 4 |  | Civil |  |  | FA-25161927 |  |  | FA-25161927 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1142% |  |  |  |  | 0 | 9.411% | 3.656% | 13.07% |  | 0.0215% | 0 | [7 empty] | 0.0215%
|  |  |  | Plan Jan |  | 5 |  | Civil | Civil Work( Excavation, sand fill, backfill ,…. |  | FA-25161928 |  |  | FA-25161928 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1142% |  |  |  |  | 0 | 9.411% | 3.656% | 13.07% |  | 0.0215% | 0 | [7 empty] | 0.0215%
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90050 | FA-25161929 |  |  | FA-25161929 | Material Handling (Soil) | 10% | 0.01142% |  | 246 |  | 100 | 100 | 20.33% | 20.33% | 40.65% | 100 | 0.004643% | 100 | [6 empty] | 100 | 0.004643%
[6 empty] | 6 | Unit - CDU | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90060 | FA-25161930 |  |  | FA-25161930 | Excavation | 25% | 0.02855% |  | 83 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90065 | FA-25161931 |  |  | FA-25161931 | Preparation and execution of tile brick | 18.2% | 0.02079% |  | 154 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - CDU | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90070 | FA-25161932 |  |  | FA-25161932 | Prepare and installation of cable route marker | 2.3% | 0.002627% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
|  |  |  | Plan Jan |  | 6 | Unit - CDU | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90075 | FA-25161933 |  |  | FA-25161933 | Sand preparation and sand filling cable trench | 36.3% | 0.04146% |  | 246 |  | 61 | 61 | 20.33% | 4.472% | 24.8% | 100 | 0.01685% | 61 | [6 empty] | 100 | 0.01685%
[6 empty] | 6 | Unit - CDU | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90080 | FA-25161934 |  |  | FA-25161934 | Backfill | 8.2% | 0.009366% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Civil |  |  | FA-25161935 |  |  | FA-25161935 | Unit - LPG/LPT | 2.37% | 0.1176% |  |  |  |  | 0 | 1.06% | 0% | 1.06% |  |  | 0
[6 empty] | 4 |  | Civil |  |  | FA-25161936 |  |  | FA-25161936 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1176% |  |  |  |  | 0 | 1.06% | 0% | 1.06% |  |  | 0
[6 empty] | 5 |  | Civil |  |  | FA-25161937 |  |  | FA-25161937 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1176% |  |  |  |  | 0 | 1.06% | 0% | 1.06% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90050 | FA-25161938 |  |  | FA-25161938 | Material Handling (Soil) | 10% | 0.01176% |  | 262 |  | 6 | 6 | 2.29% | 0% | 2.29% |  |  | 6
[6 empty] | 6 | Unit - LPG/LPT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90060 | FA-25161939 |  |  | FA-25161939 | Excavation | 25% | 0.0294% |  | 77 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90065 | FA-25161940 |  |  | FA-25161940 | Preparation and execution of tile brick | 18.2% | 0.0214% |  | 164 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90070 | FA-25161941 |  |  | FA-25161941 | Prepare and installation of cable route marker | 2.3% | 0.002705% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - LPG/LPT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90075 | FA-25161942 |  |  | FA-25161942 | Sand preparation and sand filling cable trench | 36.3% | 0.04269% |  | 262 |  | 6 | 6 | 2.29% | 0% | 2.29% |  |  | 6
[6 empty] | 6 | Unit - LPG/LPT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90080 | FA-25161943 |  |  | FA-25161943 | Backfill | 8.2% | 0.009643% |  | 46 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Civil |  |  | FA-25161944 |  |  | FA-25161944 | Unit - UTILITY | 3.63% | 0.1801% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Civil |  |  | FA-25161945 |  |  | FA-25161945 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1801% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Civil |  |  | FA-25161946 |  |  | FA-25161946 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1801% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90050 | FA-25161947 |  |  | FA-25161947 | Material Handling (Soil) | 10% | 0.01801% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90060 | FA-25161948 |  |  | FA-25161948 | Excavation | 25% | 0.04502% |  | 279 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90065 | FA-25161949 |  |  | FA-25161949 | Preparation and execution of tile brick | 18.2% | 0.03278% |  | 156 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90070 | FA-25161950 |  |  | FA-25161950 | Prepare and installation of cable route marker | 2.3% | 0.004142% |  | 8 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90075 | FA-25161951 |  |  | FA-25161951 | Sand preparation and sand filling cable trench | 36.3% | 0.06538% |  | 250 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - UTILITY | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90080 | FA-25161952 |  |  | FA-25161952 | Backfill | 8.2% | 0.01477% |  | 168 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Civil |  |  | FA-25161953 |  |  | FA-25161953 | Unit - FWS | 0.9472% | 0.047% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Civil |  |  | FA-25161954 |  |  | FA-25161954 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.047% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Civil |  |  | FA-25161955 |  |  | FA-25161955 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.047% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90060 | FA-25161956 |  |  | FA-25161956 | Excavation | 75% | 0.03525% |  | 143 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - FWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90080 | FA-25161957 |  |  | FA-25161957 | Backfill | 25% | 0.01175% |  | 85 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Civil |  |  | FA-25161958 |  |  | FA-25161958 | Unit - SWS | 1.166% | 0.05783% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Civil |  |  | FA-25161959 |  |  | FA-25161959 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.05783% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Civil |  |  | FA-25161960 |  |  | FA-25161960 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.05783% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90050 | FA-25161961 |  |  | FA-25161961 | Material Handling (Soil) | 10% | 0.005783% |  | 81 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90060 | FA-25161962 |  |  | FA-25161962 | Excavation | 25% | 0.01446% |  | 90 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90065 | FA-25161963 |  |  | FA-25161963 | Preparation and execution of tile brick | 18.2% | 0.01053% |  | 50 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90070 | FA-25161964 |  |  | FA-25161964 | Prepare and installation of cable route marker | 2.3% | 0.00133% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90075 | FA-25161965 |  |  | FA-25161965 | Sand preparation and sand filling cable trench | 36.3% | 0.02099% |  | 81 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - SWS | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90080 | FA-25161966 |  |  | FA-25161966 | Backfill | 8.2% | 0.004742% |  | 54 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan |  |  |  | Plan Jan | Plan Feb | 3 |  | Civil |  |  | FA-25161967 |  |  | FA-25161967 | Unit - INT | 76.58% | 3.799% |  |  |  |  | 0 | 0.6868% | 0% | 0.6868% |  | 0.2485% | 0 |  |  | 0.2485% |  |  |  |  | 0.2485% |  | 0.2485%
Plan |  |  |  | Plan Jan | Plan Feb | 4 |  | Civil |  |  | FA-25161968 |  |  | FA-25161968 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 3.799% |  |  |  |  | 0 | 0.6868% | 0% | 0.6868% |  | 0.2485% | 0 |  |  | 0.2485% |  |  |  |  | 0.2485% |  | 0.2485%
Plan |  |  |  | Plan Jan | Plan Feb | 5 |  | Civil |  |  | FA-25161969 |  |  | FA-25161969 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 3.799% |  |  |  |  | 0 | 0.6868% | 0% | 0.6868% |  | 0.2485% | 0 |  |  | 0.2485% |  |  |  |  | 0.2485% |  | 0.2485%
Plan | 0.00053679 | 7.584e-06% | 2.881e-08% | Plan Jan | Plan Feb | 6 | Unit - INT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90050 | FA-25161970 |  |  | FA-25161970 | Material Handling (Soil) | 10% | 0.3799% |  | 7078 |  | 105 | 105 | 1.483% | 0% | 1.483% | 1000 | 0.05368% | 105 | 1000 | 0.14128 | 0.05368% | Week 1 | Week 4 |  | 1000 | 0.05368% | 1000 | 0.05368% | ok | 14.13% | 0.05368%
[6 empty] | 6 | Unit - INT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90060 | FA-25161971 |  |  | FA-25161971 | Excavation | 25% | 0.9498% |  | 3963 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90065 | FA-25161972 |  |  | FA-25161972 | Preparation and execution of tile brick | 18.2% | 0.6915% |  | 4424 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - INT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90070 | FA-25161973 |  |  | FA-25161973 | Prepare and installation of cable route marker | 2.3% | 0.08739% |  | 222 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
Plan | 0.0019485 | 2.753e-05% | 3.797e-07% | Plan Jan | Plan Feb | 6 | Unit - INT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90075 | FA-25161974 |  |  | FA-25161974 | Sand preparation and sand filling cable trench | 36.3% | 1.379% |  | 7078 |  | 105 | 105 | 1.483% | 0% | 1.483% | 1000 | 0.1949% | 105 | 1000 | 0.14128 | 0.1949% | Week 1 | Week 4 |  | 1000 | 0.1949% | 1000 | 0.1949% | ok | 14.13% | 0.1949%
[6 empty] | 6 | Unit - INT | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90080 | FA-25161975 |  |  | FA-25161975 | Backfill | 8.2% | 0.3116% |  | 2378 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Civil |  |  | FA-25161976 |  |  | FA-25161976 | Unit - TNK | 3.008% | 0.1492% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 4 |  | Civil |  |  | FA-25161977 |  |  | FA-25161977 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1492% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 5 |  | Civil |  |  | FA-25161978 |  |  | FA-25161978 | Civil Work( Excavation, sand fill, backfill ,…. | 100% | 0.1492% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90050 | FA-25161979 |  |  | FA-25161979 | Material Handling (Soil) | 10% | 0.01492% |  | 83 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90060 | FA-25161980 |  |  | FA-25161980 | Excavation | 25% | 0.03731% |  | 365 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90065 | FA-25161981 |  |  | FA-25161981 | Preparation and execution of tile brick | 18.2% | 0.02716% |  | 52 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90070 | FA-25161982 |  |  | FA-25161982 | Prepare and installation of cable route marker | 2.3% | 0.003432% |  | 2 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90075 | FA-25161983 |  |  | FA-25161983 | Sand preparation and sand filling cable trench | 36.3% | 0.05417% |  | 83 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - TNK | Civil | Civil Work( Excavation, sand fill, backfill ,…. | 90080 | FA-25161984 |  |  | FA-25161984 | Backfill | 8.2% | 0.01224% |  | 219 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Civil |  |  | FA-25161985 |  |  | FA-25161985 | Unit - WWT | 5% | 0.2481% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Unit - WWT | Civil |  |  | FA-25161986 |  |  | FA-25161986 | Unit - WWT | 100% | 0.2481% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 3 |  | Civil |  |  | FA-25161987 |  |  | FA-25161987 | Contingency Reserve | 5% | 0.2481% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | Contingency Reserve | Civil |  |  | FA-25161988 |  |  | FA-25161988 | Contingency Reserve | 100% | 0.2481% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 2 |  | Demobilization |  |  | FA-25161989 |  |  | FA-25161989 | Demobilization | 0.5% | 0.5% |  |  |  |  | 0 | 0% | 0% | 0% |  |  | 0
[6 empty] | 6 | General | Demobilization | Demobilization |  | FA-25161990 |  |  | FA-25161990 | Demobilization | 100% | 0.5% |  | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  | 0